## Sequence
Wave | ID | Activity | Discipline | Status | Needs (direct) | External inputs | Data owned | Deliverables | Feeds (direct) | Downstream activities | Downstream deliverables | Note
1 | PRJ-01 | Design basis (BOD) | Project | Issued (FEED) |  | Owner capacity, crude slate, product specs, turndown Site, climate and utility conditions Codes, standards and owner specifications |  | CFU-000-PR-BOD-001 | LAY-01, PIP-01, PRC-01, PRJ-02 | 44 | 103 | Every other activity reads the basis; a change here re-opens the whole package.
2 | PRJ-02 | Crude assay characterisation | Process | Issued, provisional | PRJ-01: crude slate, design and check crudes | Full laboratory assay (TBP, gravity, sulphur, salts, metals, acidity) |  |  | PRC-00, PRC-01 | 43 | 103 | Uses a published Arab Light assay with pseudo-components, not a lab assay.
3 | PRC-00 | Rigorous simulation and model calibration | Process | Not started | PRJ-02: lab assay pseudo-components | Simulator licence (HYSYS / Petro-SIM / Pro-II) Licensor or owner operating data |  |  | PRC-01 | 42 | 103 | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
4 | PRC-01 | Heat and material balance | Process | Issued, provisional | PRJ-01: capacity, product specs, utility conditions PRJ-02: pseudo-components PRC-00: calibrated cut points and efficiencies |  | streams.json, process_results.json | CFU-000-PR-HMB-001 | ICS-01, ICS-04, LAY-01, MEC-01, PIP-01, PRC-02, PRC-03, PRC-04, PRC-05, PRC-06, PRC-07 | 41 | 102
5 | PRC-02 | Process equipment sizing | Process | Issued (FEED) | PRC-01: flows, duties, column vapour/liquid loads |  | equipment.json | CFU-000-ME-LST-001 | CST-01, ELE-01, ELE-02, ICS-01, ICS-03, ICS-04, ICS-05, LAY-01, LAY-02, MEC-01, MEC-02, PRC-03, PRC-04, PRC-06, PRC-07, PRC-08 | 38 | 99 | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
5 | PRC-05 | Block flow diagram | Process | Issued (FEED) | PRC-01: unit yields |  |  | CFU-000-PR-BFD-001 | PRJ-03 | 2 | 3
5 | PIP-01 | Piping material classes | Piping | Issued (FEED) | PRJ-01: codes, corrosion basis PRC-01: design T/P, sulphur and acid corrosion |  |  | CFU-000-PI-SPC-001 | PIP-04, PRC-08 | 20 | 50 | Defined in CONVENTIONS.md; summary issued with the P&IDs.
6 | PRC-03 | Relief load and PSV sizing (unit) | Process | Issued (FEED) | PRC-01: relief compositions and rates PRC-02: design pressures, wetted areas |  | psv.json |  | ICS-03, MEC-01, MEC-02, PIP-02, PRC-07, PRC-08, SAF-01, SAF-02 | 28 | 69
6 | PRC-04 | Control loops and SIF definition | Process | Issued (FEED) | PRC-01: operating points PRC-02: equipment and instrument ranges |  | control_loops.json |  | ELE-02, ICS-01, ICS-02, ICS-03, ICS-04, ICS-05, PRC-06, PRC-08, SAF-01 | 24 | 69
6 | LAY-01 | Plot plan and equipment layout | Layout | Issued (FEED) | PRC-02: equipment list and footprints PRC-01: hazard inventory, heater duties PRJ-01: site, spacing standards |  | layout.json | CFU-000-PL-PLT-001 | CIV-01, ELE-02, ELE-04, ICS-05, LAY-02, PIP-02, PRC-08, SAF-04 | 23 | 58
6 | ELE-01 | Electrical load list | Electrical | Issued (FEED) | PRC-02: motor ratings, absorbed power |  |  | CFU-000-EL-LDL-001 | ELE-03, ELE-04 | 7 | 10
7 | PRC-06 | Process flow diagrams | Process | Issued (FEED) | PRC-01: stream table PRC-02: equipment data PRC-04: principal control loops |  |  | CFU-000-PR-PFD-ALL, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006 | PRC-08 | 20 | 50
7 | PRC-07 | Process design report | Process | Issued (FEED) | PRC-01: H&MB PRC-02: sizing results PRC-03: relief summary |  |  | CFU-000-PR-RPT-001 | PRJ-03 | 2 | 3
7 | SAF-02 | Global flare load study | Safety | Not started | PRC-03: unit relief loads | Refinery flare network model, other units' loads |  |  | PRJ-04 | 1 | 0 | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
7 | MEC-01 | Mechanical design calculations | Mechanical | Issued (FEED) | PRC-02: design P/T, dimensions, internals PRC-01: nozzle flows PRC-03: PSV set points |  | mech.json | CFU-000-ME-CAL-001 | CIV-01, CST-01, MEC-02, MEC-03, PIP-02, PIP-03 | 15 | 37
7 | LAY-02 | Sections and 3D layout model | Layout | Issued (FEED) | LAY-01: equipment positions, structures PRC-02: equipment heights |  |  | CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003 | LAY-03, PRJ-03 | 3 | 3
7 | ICS-01 | Control philosophy and schemes | I&C | Issued (FEED) | PRC-04: loops and SIFs PRC-01: operating points PRC-02: equipment |  |  | CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-RPT-001, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-200-IC-CSD-005 | PRJ-03 | 2 | 3
7 | ELE-02 | Hazardous area classification | Electrical | Issued (FEED) | LAY-01: release-source positions PRC-02: fluids and conditions PRC-04: analysers and vents |  |  | CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003 | ELE-04, SAF-04 | 5 | 4
7 | ELE-03 | Electrical sizing, single-line diagrams | Electrical | Issued (FEED) | ELE-01: loads and demand |  | electrical.json | CFU-000-EL-CAL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004 | ELE-04, ELE-05, ICS-07 | 6 | 5
8 | PRC-08 | P&IDs, line list, instrument index | Process | Issued (FEED) | PRC-02: equipment and design conditions PRC-03: PSV tags and sizes PRC-04: control loops and SIFs PRC-06: PFD topology PIP-01: piping classes LAY-01: fire and gas detector locations |  | lines.json, instruments.json | CFU-000-IC-IDX-001, CFU-000-PI-LL-001, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016 | ICS-04, ICS-05, PIP-02, SAF-01, SAF-03 | 19 | 30 | Line list and instrument index feed piping, I&C and electrical; P&ID revisions ripple widely.
8 | MEC-02 | Equipment datasheets | Mechanical | Issued (FEED) | MEC-01: thicknesses, weights, nozzles PRC-02: process data PRC-03: PSV data |  |  | CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007 | PRJ-03, VEN-01 | 7 | 3
8 | MEC-03 | Equipment GA drawings | Mechanical | Issued (FEED) | MEC-01: geometry, nozzle schedule |  |  | CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-200-ME-GA-004, CFU-200-ME-GA-006 | PRJ-03 | 2 | 3
8 | ELE-04 | Cable schedule | Electrical | Issued (FEED) | ELE-01: loads ELE-03: feeders LAY-01: routes ELE-02: zone ratings |  |  | CFU-000-EL-CBL-001 | CST-02, PRJ-03 | 3 | 3
8 | CST-01 | Class 4 cost estimate | Cost | Issued (FEED) | PRC-02: equipment list MEC-01: shell weights |  |  | CFU-000-PM-EST-001 | CST-02, PRJ-03 | 3 | 3
9 | SAF-01 | Preliminary HAZOP | Safety | Issued (FEED) | PRC-08: P&IDs PRC-04: SIFs PRC-03: relief devices |  |  | CFU-000-PR-RPT-002 | ICS-02, PRJ-03, SAF-03, SAF-04 | 7 | 5
9 | VEN-01 | Vendor enquiries and vendor data | Mechanical | Not started | MEC-02: datasheets for enquiry | Vendor quotations and certified data (heaters, desalters, packing, pumps, ejectors, air coolers) |  |  | CST-02, ELE-05, ICS-08, PIP-05 | 5 | 0 | Vendor data revises weights, nozzles, motor ratings and I/O; plan for one full update cycle.
9 | PIP-02 | Piping routing and 3D model | Piping | Issued (FEED) | PRC-08: line list, in-line instruments LAY-01: nozzle positions, pipe rack PRC-03: PSV inlet/outlet MEC-01: nozzle sizes, weights |  | routing.json | CFU-000-PI-3DM-002 | LAY-03, PIP-03, PIP-04 | 8 | 19
9 | ICS-04 | Control valve sizing | I&C | Issued (FEED) | PRC-01: flows, densities PRC-02: pump curves PRC-04: valve tags PRC-08: line sizes |  |  | CFU-000-IC-CAL-001 | PRJ-03 | 2 | 3
9 | ICS-05 | I/O list | I&C | Issued (FEED) | PRC-08: instrument index PRC-04: loops and SIFs PRC-02: motor drivers LAY-01: junction-box zones |  | io_list.json | CFU-000-IC-IOL-001 | ICS-06, ICS-07 | 4 | 8
10 | SAF-04 | Siting study, QRA, F&G mapping | Safety | Not started | LAY-01: plot plan SAF-01: major hazards ELE-02: release sources | Occupied building list, meteorology |  |  | PRJ-04 | 1 | 0 | API 752/753 siting, QRA, fire and gas mapping and fireproofing; may move buildings or equipment.
10 | PIP-03 | Pipe stress and supports (screening) | Piping | Issued, provisional | PIP-02: routed geometry MEC-01: nozzle allowables |  |  | CFU-000-PI-RPT-001 | CIV-01, PIP-05, PRJ-03 | 6 | 3 | Screening only; CAESAR II analysis is PIP-05.
10 | PIP-04 | Isometrics and piping MTO | Piping | Issued (FEED) | PIP-02: routed geometry PIP-01: piping classes |  |  | CFU-000-PI-ISO-000, CFU-000-PI-MTO-001, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-200-PI-ISO-001 | CST-02, PRJ-03 | 3 | 3
10 | ICS-02 | SIF list and SIL determination (LOPA) | I&C | Issued, provisional | PRC-04: SIF definitions SAF-01: hazard scenarios |  |  | CFU-000-IC-RPT-002 | ICS-03, ICS-08, SAF-03 | 5 | 4 | LOPA frequencies are FEED judgements pending SAF-03.
10 | ICS-06 | Loop diagrams | I&C | Issued (FEED) | ICS-05: terminations, cabinets |  |  | CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL | PRJ-03 | 2 | 3
10 | ICS-07 | ICS architecture | I&C | Issued (FEED) | ICS-05: I/O counts ELE-03: UPS feeds |  |  | CFU-000-IC-BLK-001 | PRJ-03 | 2 | 3
10 | ELE-05 | Power system studies and protection | Electrical | Not started | ELE-03: SLD VEN-01: motor and transformer data | Utility short-circuit data ETAP or equivalent |  |  | PRJ-04 | 1 | 0 | Load flow, short circuit, motor starting, arc flash, relay coordination.
11 | SAF-03 | Formal HAZOP and LOPA workshop | Safety | Not started | PRC-08: IFD P&IDs SAF-01: preliminary findings ICS-02: draft SIL targets | Multidisciplinary team incl. owner operations |  |  | ICS-08, PRJ-04 | 2 | 0
11 | PIP-05 | Detailed pipe stress (CAESAR II) | Piping | Not started | PIP-03: critical line list VEN-01: certified nozzle allowables | CAESAR II or equivalent |  |  | PRJ-04 | 1 | 0 | Includes nozzle-load agreement with equipment vendors.
11 | CIV-01 | Geotechnical, civil and structural design | Civil | Not started | LAY-01: plot plan MEC-01: operating and test weights PIP-03: support loads | Geotechnical survey Topographic survey |  |  | CST-02, LAY-03 | 3 | 0 | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
11 | ICS-03 | Cause and effect matrix | I&C | Issued (FEED) | PRC-04: SIFs PRC-03: relief devices PRC-02: equipment ICS-02: SIL targets |  |  | CFU-000-IC-CE-001 | PRJ-03 | 2 | 3
12 | PRJ-03 | Document register and portal | Project | Issued (FEED) | CST-01: estimate SAF-01: HAZOP PIP-04: isometrics ICS-06: loop diagrams ICS-07: architecture ELE-04: cables MEC-03: GAs LAY-02: 3D model PRC-05: BFD PRC-07: process report ICS-01: control philosophy ICS-03: C&E ICS-04: CV sizing MEC-02: datasheets PIP-03: stress study |  |  | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001 | PRJ-04 | 1 | 0
12 | LAY-03 | 3D model reviews and constructability | Layout | Not started | PIP-02: routed model LAY-02: layout model CIV-01: structures | Owner operations and maintenance reviewers |  |  | PRJ-04 | 1 | 0 | 30/60/90 % model reviews.
12 | ICS-08 | SIL verification and SRS | I&C | Not started | ICS-02: SIL targets SAF-03: validated LOPA VEN-01: device failure data |  |  |  | PRJ-04 | 1 | 0 | PFDavg calculations and the safety requirements specification (IEC 61511).
12 | CST-02 | Class 3 cost estimate | Cost | Not started | CST-01: estimate structure VEN-01: budget quotes PIP-04: piping MTO ELE-04: cable quantities CIV-01: civil quantities |  |  |  | PRJ-04 | 1 | 0
13 | PRJ-04 | PE review, seal and IFC issue | Project | Not started | PRJ-03: complete document set SAF-03: closed HAZOP actions ICS-08: SIL verification PIP-05: stress sign-off ELE-05: studies CST-02: Class 3 estimate LAY-03: model review SAF-04: siting study SAF-02: flare study | Licensed Professional Engineer in responsible charge |  |  |  | 0 | 0 | Nothing in this package is sealed; this is the gate before any use for construction.

## Links
From | To | Type | What flows / what is revised
PRJ-01 | LAY-01 | input | site, spacing standards
PRJ-01 | PIP-01 | input | codes, corrosion basis
PRJ-01 | PRC-01 | input | capacity, product specs, utility conditions
PRJ-01 | PRJ-02 | input | crude slate, design and check crudes
PRJ-02 | PRC-00 | input | lab assay pseudo-components
PRJ-02 | PRC-01 | input | pseudo-components
PRC-00 | PRC-01 | input | calibrated cut points and efficiencies
PRC-01 | ICS-01 | input | operating points
PRC-01 | ICS-04 | input | flows, densities
PRC-01 | LAY-01 | input | hazard inventory, heater duties
PRC-01 | MEC-01 | input | nozzle flows
PRC-01 | PIP-01 | input | design T/P, sulphur and acid corrosion
PRC-01 | PRC-02 | input | flows, duties, column vapour/liquid loads
PRC-01 | PRC-03 | input | relief compositions and rates
PRC-01 | PRC-04 | input | operating points
PRC-01 | PRC-05 | input | unit yields
PRC-01 | PRC-06 | input | stream table
PRC-01 | PRC-07 | input | H&MB
PIP-01 | PIP-04 | input | piping classes
PIP-01 | PRC-08 | input | piping classes
PRC-02 | CST-01 | input | equipment list
PRC-02 | ELE-01 | input | motor ratings, absorbed power
PRC-02 | ELE-02 | input | fluids and conditions
PRC-02 | ICS-01 | input | equipment
PRC-02 | ICS-03 | input | equipment
PRC-02 | ICS-04 | input | pump curves
PRC-02 | ICS-05 | input | motor drivers
PRC-02 | LAY-01 | input | equipment list and footprints
PRC-02 | LAY-02 | input | equipment heights
PRC-02 | MEC-01 | input | design P/T, dimensions, internals
PRC-02 | MEC-02 | input | process data
PRC-02 | PRC-03 | input | design pressures, wetted areas
PRC-02 | PRC-04 | input | equipment and instrument ranges
PRC-02 | PRC-06 | input | equipment data
PRC-02 | PRC-07 | input | sizing results
PRC-02 | PRC-08 | input | equipment and design conditions
PRC-05 | PRJ-03 | input | BFD
ELE-01 | ELE-03 | input | loads and demand
ELE-01 | ELE-04 | input | loads
LAY-01 | CIV-01 | input | plot plan
LAY-01 | ELE-02 | input | release-source positions
LAY-01 | ELE-04 | input | routes
LAY-01 | ICS-05 | input | junction-box zones
LAY-01 | LAY-02 | input | equipment positions, structures
LAY-01 | PIP-02 | input | nozzle positions, pipe rack
LAY-01 | PRC-08 | input | fire and gas detector locations
LAY-01 | SAF-04 | input | plot plan
PRC-03 | ICS-03 | input | relief devices
PRC-03 | MEC-01 | input | PSV set points
PRC-03 | MEC-02 | input | PSV data
PRC-03 | PIP-02 | input | PSV inlet/outlet
PRC-03 | PRC-07 | input | relief summary
PRC-03 | PRC-08 | input | PSV tags and sizes
PRC-03 | SAF-01 | input | relief devices
PRC-03 | SAF-02 | input | unit relief loads
PRC-04 | ELE-02 | input | analysers and vents
PRC-04 | ICS-01 | input | loops and SIFs
PRC-04 | ICS-02 | input | SIF definitions
PRC-04 | ICS-03 | input | SIFs
PRC-04 | ICS-04 | input | valve tags
PRC-04 | ICS-05 | input | loops and SIFs
PRC-04 | PRC-06 | input | principal control loops
PRC-04 | PRC-08 | input | control loops and SIFs
PRC-04 | SAF-01 | input | SIFs
ELE-02 | ELE-04 | input | zone ratings
ELE-02 | SAF-04 | input | release sources
ELE-03 | ELE-04 | input | feeders
ELE-03 | ELE-05 | input | SLD
ELE-03 | ICS-07 | input | UPS feeds
ICS-01 | PRJ-03 | input | control philosophy
LAY-02 | LAY-03 | input | layout model
LAY-02 | PRJ-03 | input | 3D model
MEC-01 | CIV-01 | input | operating and test weights
MEC-01 | CST-01 | input | shell weights
MEC-01 | MEC-02 | input | thicknesses, weights, nozzles
MEC-01 | MEC-03 | input | geometry, nozzle schedule
MEC-01 | PIP-02 | input | nozzle sizes, weights
MEC-01 | PIP-03 | input | nozzle allowables
PRC-06 | PRC-08 | input | PFD topology
PRC-07 | PRJ-03 | input | process report
SAF-02 | PRJ-04 | input | flare study
CST-01 | CST-02 | input | estimate structure
CST-01 | PRJ-03 | input | estimate
ELE-04 | CST-02 | input | cable quantities
ELE-04 | PRJ-03 | input | cables
MEC-02 | PRJ-03 | input | datasheets
MEC-02 | VEN-01 | input | datasheets for enquiry
MEC-03 | PRJ-03 | input | GAs
PRC-08 | ICS-04 | input | line sizes
PRC-08 | ICS-05 | input | instrument index
PRC-08 | PIP-02 | input | line list, in-line instruments
PRC-08 | SAF-01 | input | P&IDs
PRC-08 | SAF-03 | input | IFD P&IDs
ICS-04 | PRJ-03 | input | CV sizing
ICS-05 | ICS-06 | input | terminations, cabinets
ICS-05 | ICS-07 | input | I/O counts
PIP-02 | LAY-03 | input | routed model
PIP-02 | PIP-03 | input | routed geometry
PIP-02 | PIP-04 | input | routed geometry
SAF-01 | ICS-02 | input | hazard scenarios
SAF-01 | PRJ-03 | input | HAZOP
SAF-01 | SAF-03 | input | preliminary findings
SAF-01 | SAF-04 | input | major hazards
VEN-01 | CST-02 | input | budget quotes
VEN-01 | ELE-05 | input | motor and transformer data
VEN-01 | ICS-08 | input | device failure data
VEN-01 | PIP-05 | input | certified nozzle allowables
ELE-05 | PRJ-04 | input | studies
ICS-02 | ICS-03 | input | SIL targets
ICS-02 | ICS-08 | input | SIL targets
ICS-02 | SAF-03 | input | draft SIL targets
ICS-06 | PRJ-03 | input | loop diagrams
ICS-07 | PRJ-03 | input | architecture
PIP-03 | CIV-01 | input | support loads
PIP-03 | PIP-05 | input | critical line list
PIP-03 | PRJ-03 | input | stress study
PIP-04 | CST-02 | input | piping MTO
PIP-04 | PRJ-03 | input | isometrics
SAF-04 | PRJ-04 | input | siting study
CIV-01 | CST-02 | input | civil quantities
CIV-01 | LAY-03 | input | structures
ICS-03 | PRJ-03 | input | C&E
PIP-05 | PRJ-04 | input | stress sign-off
SAF-03 | ICS-08 | input | validated LOPA
SAF-03 | PRJ-04 | input | closed HAZOP actions
CST-02 | PRJ-04 | input | Class 3 estimate
ICS-08 | PRJ-04 | input | SIL verification
LAY-03 | PRJ-04 | input | model review
PRJ-03 | PRJ-04 | input | complete document set
MEC-01 | PRC-02 | iteration | mechanical holds re-rate sizing (C-201 bed-1 diameter, heater box length)
MEC-01 | LAY-01 | iteration | calculated dimensions and weights update footprints and spacing
PIP-02 | PRC-02 | iteration | routed lengths update pump and line hydraulics
PIP-02 | LAY-01 | iteration | rack width and clashes move equipment
ICS-04 | PRC-08 | iteration | control valve sizes and reducers shown on the P&IDs
SAF-01 | PRC-08 | iteration | HAZOP recommendations revise the P&IDs
ELE-04 | ELE-03 | iteration | actual cable impedances re-run the motor-starting voltage-dip check
ICS-07 | ELE-01 | iteration | ICS cabinet and UPS loads added to the load list
SAF-02 | PRC-03 | iteration | flare back-pressure changes PSV type and size
SAF-03 | PRC-08 | iteration | formal HAZOP actions revise the P&IDs
SAF-04 | LAY-01 | iteration | siting study moves occupied buildings and equipment
VEN-01 | MEC-01 | iteration | certified vendor dimensions, weights and nozzles
VEN-01 | LAY-01 | iteration | vendor package footprints
VEN-01 | ELE-01 | iteration | certified motor ratings
VEN-01 | ICS-05 | iteration | vendor package I/O

## DSM
Reads from -> | PRJ-01 | PRJ-02 | PRC-00 | PRC-01 | PRC-02 | PRC-05 | PIP-01 | PRC-03 | PRC-04 | LAY-01 | ELE-01 | PRC-06 | PRC-07 | SAF-02 | MEC-01 | LAY-02 | ICS-01 | ELE-02 | ELE-03 | PRC-08 | MEC-02 | MEC-03 | ELE-04 | CST-01 | SAF-01 | VEN-01 | PIP-02 | ICS-04 | ICS-05 | SAF-04 | PIP-03 | PIP-04 | ICS-02 | ICS-06 | ICS-07 | ELE-05 | SAF-03 | PIP-05 | CIV-01 | ICS-03 | PRJ-03 | LAY-03 | ICS-08 | CST-02 | PRJ-04
PRJ-01 Design basis (BO | ·
PRJ-02 Crude assay char | X | ·
PRC-00 Rigorous simulat |  | X | ·
PRC-01 Heat and materia | X | X | X | ·
PRC-02 Process equipmen |  |  |  | X | · | [9 empty] | F | [11 empty] | F
PRC-05 Block flow diagr |  |  |  | X |  | ·
PIP-01 Piping material | X |  |  | X |  |  | ·
PRC-03 Relief load and |  |  |  | X | X |  |  | · | [5 empty] | F
PRC-04 Control loops an |  |  |  | X | X |  |  |  | ·
LAY-01 Plot plan and eq | X |  |  | X | X |  |  |  |  | · |  |  |  |  | F | [10 empty] | F | F |  |  | F
ELE-01 Electrical load |  |  |  |  | X | [5 empty] | · | [14 empty] | F | [8 empty] | F
PRC-06 Process flow dia |  |  |  | X | X |  |  |  | X |  |  | ·
PRC-07 Process design r |  |  |  | X | X |  |  | X |  |  |  |  | ·
SAF-02 Global flare loa | [7 empty] | X | [5 empty] | ·
MEC-01 Mechanical desig |  |  |  | X | X |  |  | X | [6 empty] | · | [10 empty] | F
LAY-02 Sections and 3D |  |  |  |  | X |  |  |  |  | X | [5 empty] | ·
ICS-01 Control philosop |  |  |  | X | X |  |  |  | X | [7 empty] | ·
ELE-02 Hazardous area c |  |  |  |  | X |  |  |  | X | X | [7 empty] | ·
ELE-03 Electrical sizin | [10 empty] | X | [7 empty] | · |  |  |  | F
PRC-08 P&IDs, line list |  |  |  |  | X |  | X | X | X | X |  | X | [7 empty] | · |  |  |  |  | F |  |  | F | [8 empty] | F
MEC-02 Equipment datash |  |  |  |  | X |  |  | X | [6 empty] | X | [5 empty] | ·
MEC-03 Equipment GA dra | [14 empty] | X | [6 empty] | ·
ELE-04 Cable schedule | [9 empty] | X | X | [6 empty] | X | X |  |  |  | ·
CST-01 Class 4 cost est |  |  |  |  | X | [9 empty] | X | [8 empty] | ·
SAF-01 Preliminary HAZO | [7 empty] | X | X | [10 empty] | X |  |  |  |  | ·
VEN-01 Vendor enquiries | [20 empty] | X |  |  |  |  | ·
PIP-02 Piping routing a | [7 empty] | X |  | X |  |  |  |  | X |  |  |  |  | X | [6 empty] | ·
ICS-04 Control valve si |  |  |  | X | X |  |  |  | X | [10 empty] | X | [7 empty] | ·
ICS-05 I/O list |  |  |  |  | X |  |  |  | X | X | [9 empty] | X | [5 empty] | F |  |  | ·
SAF-04 Siting study, QR | [9 empty] | X | [7 empty] | X | [6 empty] | X |  |  |  |  | ·
PIP-03 Pipe stress and | [14 empty] | X | [11 empty] | X |  |  |  | ·
PIP-04 Isometrics and p | [6 empty] | X | [19 empty] | X |  |  |  |  | ·
ICS-02 SIF list and SIL | [8 empty] | X | [15 empty] | X | [7 empty] | ·
ICS-06 Loop diagrams | [28 empty] | X |  |  |  |  | ·
ICS-07 ICS architecture | [18 empty] | X | [9 empty] | X | [5 empty] | ·
ELE-05 Power system stu | [18 empty] | X | [6 empty] | X | [9 empty] | ·
SAF-03 Formal HAZOP and | [19 empty] | X |  |  |  |  | X | [7 empty] | X |  |  |  | ·
PIP-05 Detailed pipe st | [25 empty] | X |  |  |  |  | X | [6 empty] | ·
CIV-01 Geotechnical, ci | [9 empty] | X |  |  |  |  | X | [15 empty] | X | [7 empty] | ·
ICS-03 Cause and effect |  |  |  |  | X |  |  | X | X | [23 empty] | X | [6 empty] | ·
PRJ-03 Document registe | [5 empty] | X | [6 empty] | X |  |  | X | X |  |  |  | X | X | X | X | X |  |  | X |  |  | X | X |  | X | X |  |  |  |  | X | ·
LAY-03 3D model reviews | [15 empty] | X | [10 empty] | X | [11 empty] | X |  |  | ·
ICS-08 SIL verification | [25 empty] | X | [6 empty] | X |  |  |  | X | [5 empty] | ·
CST-02 Class 3 cost est | [22 empty] | X | X |  | X | [5 empty] | X | [6 empty] | X |  |  |  |  | ·
PRJ-04 PE review, seal | [13 empty] | X | [15 empty] | X | [5 empty] | X | X | X |  |  | X | X | X | X | ·
Row reads from column. X = input (below diagonal), F = iteration loop (above diagonal).

## Change impact
If this changes | Activity | Re-check activities (all downstream) | Deliverables to revise
PRJ-01 | Design basis (BOD) | PRJ-02, PRC-00, PRC-01, PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, SAF-02, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-ME-LST-001, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PI-SPC-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-BFD-001, CFU-000-PR-BOD-001, CFU-000-PR-HMB-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRJ-02 | Crude assay characterisation | PRC-00, PRC-01, PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, SAF-02, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-ME-LST-001, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PI-SPC-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-BFD-001, CFU-000-PR-HMB-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-00 | Rigorous simulation and model calibration | PRC-01, PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, SAF-02, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-ME-LST-001, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PI-SPC-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-BFD-001, CFU-000-PR-HMB-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-01 | Heat and material balance | PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, SAF-02, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-ME-LST-001, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PI-SPC-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-BFD-001, CFU-000-PR-HMB-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-02 | Process equipment sizing | PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, SAF-02, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-ME-LST-001, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-03 | Relief load and PSV sizing (unit) | PRC-07, SAF-02, MEC-01, PRC-08, MEC-02, MEC-03, CST-01, SAF-01, VEN-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ELE-05, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-002, CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-001, CFU-000-PR-RPT-002, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-04 | Control loops and SIF definition | PRC-06, ICS-01, ELE-02, PRC-08, ELE-04, SAF-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-001, CFU-000-IC-RPT-002, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-002, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-IC-CSD-005, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
LAY-01 | Plot plan and equipment layout | LAY-02, ELE-02, PRC-08, ELE-04, SAF-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-002, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PL-PLT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-002, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-PI-ISO-001, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-06 | Process flow diagrams | PRC-08, SAF-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-002, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-PFD-ALL, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-002, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PFD-001, CFU-100-PR-PFD-002, CFU-100-PR-PFD-003, CFU-100-PR-PFD-004, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-PI-ISO-001, CFU-200-PR-PFD-005, CFU-200-PR-PFD-006, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PIP-01 | Piping material classes | PRC-08, SAF-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-002, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PI-SPC-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-002, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-PI-ISO-001, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
PRC-08 | P&IDs, line list, instrument index | SAF-01, PIP-02, ICS-04, ICS-05, SAF-04, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, SAF-03, PIP-05, CIV-01, ICS-03, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-IC-CAL-001, CFU-000-IC-CE-001, CFU-000-IC-IDX-001, CFU-000-IC-IOL-001, CFU-000-IC-RPT-002, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-LL-001, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-PID-000, CFU-000-PR-PID-ALL, CFU-000-PR-RPT-002, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-100-PR-PID-001, CFU-100-PR-PID-002, CFU-100-PR-PID-003, CFU-100-PR-PID-004, CFU-100-PR-PID-005, CFU-100-PR-PID-006, CFU-100-PR-PID-007, CFU-100-PR-PID-008, CFU-100-PR-PID-009, CFU-100-PR-PID-010, CFU-100-PR-PID-011, CFU-200-PI-ISO-001, CFU-200-PR-PID-012, CFU-200-PR-PID-013, CFU-200-PR-PID-014, CFU-200-PR-PID-015, CFU-900-PR-PID-016
MEC-01 | Mechanical design calculations | MEC-02, MEC-03, CST-01, VEN-01, PIP-02, PIP-03, PIP-04, ELE-05, PIP-05, CIV-01, PRJ-03, LAY-03, ICS-08, CST-02, PRJ-04 | CFU-000-ME-CAL-001, CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-200-ME-GA-004, CFU-200-ME-GA-006, CFU-200-PI-ISO-001
PIP-02 | Piping routing and 3D model | PIP-03, PIP-04, PIP-05, CIV-01, PRJ-03, LAY-03, CST-02, PRJ-04 | CFU-000-PI-3DM-002, CFU-000-PI-ISO-000, CFU-000-PI-MTO-001, CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-200-PI-ISO-001
SAF-01 | Preliminary HAZOP | SAF-04, ICS-02, SAF-03, ICS-03, PRJ-03, ICS-08, PRJ-04 | CFU-000-IC-CE-001, CFU-000-IC-RPT-002, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-RPT-002
MEC-02 | Equipment datasheets | VEN-01, ELE-05, PIP-05, PRJ-03, ICS-08, CST-02, PRJ-04 | CFU-000-ME-DS-000, CFU-000-ME-DS-001, CFU-000-ME-DS-002, CFU-000-ME-DS-003, CFU-000-ME-DS-004, CFU-000-ME-DS-005, CFU-000-ME-DS-006, CFU-000-ME-DS-007, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ELE-01 | Electrical load list | ELE-03, ELE-04, ICS-07, ELE-05, PRJ-03, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-LDL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
PIP-03 | Pipe stress and supports (screening) | PIP-05, CIV-01, PRJ-03, LAY-03, CST-02, PRJ-04 | CFU-000-PI-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ELE-03 | Electrical sizing, single-line diagrams | ELE-04, ICS-07, ELE-05, PRJ-03, CST-02, PRJ-04 | CFU-000-EL-CAL-001, CFU-000-EL-CBL-001, CFU-000-EL-SLD-001, CFU-000-EL-SLD-002, CFU-000-EL-SLD-003, CFU-000-EL-SLD-004, CFU-000-IC-BLK-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
VEN-01 | Vendor enquiries and vendor data | ELE-05, PIP-05, ICS-08, CST-02, PRJ-04
ICS-02 | SIF list and SIL determination (LOPA) | SAF-03, ICS-03, PRJ-03, ICS-08, PRJ-04 | CFU-000-IC-CE-001, CFU-000-IC-RPT-002, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ELE-02 | Hazardous area classification | ELE-04, SAF-04, PRJ-03, CST-02, PRJ-04 | CFU-000-EL-CBL-001, CFU-000-EL-HAC-001, CFU-000-EL-HAC-002, CFU-000-EL-HAC-003, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ICS-05 | I/O list | ICS-06, ICS-07, PRJ-03, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-IC-IOL-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL
LAY-02 | Sections and 3D layout model | PRJ-03, LAY-03, PRJ-04 | CFU-000-PL-3DM-001, CFU-000-PL-ELV-001, CFU-000-PL-ELV-002, CFU-000-PL-ELV-003, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
PIP-04 | Isometrics and piping MTO | PRJ-03, CST-02, PRJ-04 | CFU-000-PI-ISO-000, CFU-000-PI-MTO-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-PI-ISO-001, CFU-100-PI-ISO-002, CFU-100-PI-ISO-003, CFU-100-PI-ISO-004, CFU-100-PI-ISO-005, CFU-100-PI-ISO-006, CFU-100-PI-ISO-007, CFU-100-PI-ISO-008, CFU-100-PI-ISO-009, CFU-100-PI-ISO-010, CFU-100-PI-ISO-011, CFU-100-PI-ISO-012, CFU-200-PI-ISO-001
CIV-01 | Geotechnical, civil and structural design | LAY-03, CST-02, PRJ-04
ELE-04 | Cable schedule | PRJ-03, CST-02, PRJ-04 | CFU-000-EL-CBL-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
CST-01 | Class 4 cost estimate | PRJ-03, CST-02, PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-EST-001, CFU-000-PM-REG-001
PRC-05 | Block flow diagram | PRJ-03, PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-BFD-001
PRC-07 | Process design report | PRJ-03, PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-000-PR-RPT-001
SAF-03 | Formal HAZOP and LOPA workshop | ICS-08, PRJ-04
MEC-03 | Equipment GA drawings | PRJ-03, PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-ME-GA-001, CFU-100-ME-GA-002, CFU-100-ME-GA-003, CFU-100-ME-GA-005, CFU-100-ME-GA-007, CFU-100-ME-GA-008, CFU-200-ME-GA-004, CFU-200-ME-GA-006
ICS-01 | Control philosophy and schemes | PRJ-03, PRJ-04 | CFU-000-IC-CSD-006, CFU-000-IC-CSD-ALL, CFU-000-IC-RPT-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-IC-CSD-001, CFU-100-IC-CSD-002, CFU-100-IC-CSD-003, CFU-100-IC-CSD-004, CFU-200-IC-CSD-005
ICS-03 | Cause and effect matrix | PRJ-03, PRJ-04 | CFU-000-IC-CE-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ICS-04 | Control valve sizing | PRJ-03, PRJ-04 | CFU-000-IC-CAL-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
ICS-06 | Loop diagrams | PRJ-03, PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001, CFU-100-IC-LD-001, CFU-100-IC-LD-002, CFU-100-IC-LD-003, CFU-100-IC-LD-ALL
ICS-07 | ICS architecture | PRJ-03, PRJ-04 | CFU-000-IC-BLK-001, CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
SAF-02 | Global flare load study | PRJ-04
SAF-04 | Siting study, QRA, F&G mapping | PRJ-04
LAY-03 | 3D model reviews and constructability | PRJ-04
PIP-05 | Detailed pipe stress (CAESAR II) | PRJ-04
ICS-08 | SIL verification and SRS | PRJ-04
ELE-05 | Power system studies and protection | PRJ-04
CST-02 | Class 3 cost estimate | PRJ-04
PRJ-03 | Document register and portal | PRJ-04 | CFU-000-PM-DEP-001, CFU-000-PM-DEP-002, CFU-000-PM-REG-001
PRJ-04 | PE review, seal and IFC issue

## To do
Order | ID | Activity | Status | Ready to start? | Waiting on | Then re-check | Note
1 | PRJ-02 | Crude assay characterisation | Issued, provisional | yes |  | PRC-01, PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, PIP-02, ICS-04, ICS-05, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ICS-03, PRJ-03 | Uses a published Arab Light assay with pseudo-components, not a lab assay.
2 | PRC-00 | Rigorous simulation and model calibration | Not started | yes |  | PRC-01, PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, PIP-02, ICS-04, ICS-05, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ICS-03, PRJ-03 | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
3 | PRC-01 | Heat and material balance | Issued, provisional | no | PRC-00 | PRC-02, PRC-05, PIP-01, PRC-03, PRC-04, LAY-01, ELE-01, PRC-06, PRC-07, MEC-01, LAY-02, ICS-01, ELE-02, ELE-03, PRC-08, MEC-02, MEC-03, ELE-04, CST-01, SAF-01, PIP-02, ICS-04, ICS-05, PIP-03, PIP-04, ICS-02, ICS-06, ICS-07, ICS-03, PRJ-03
4 | SAF-02 | Global flare load study | Not started | yes |  |  | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
5 | VEN-01 | Vendor enquiries and vendor data | Not started | yes |  |  | Vendor data revises weights, nozzles, motor ratings and I/O; plan for one full update cycle.
6 | SAF-04 | Siting study, QRA, F&G mapping | Not started | yes |  |  | API 752/753 siting, QRA, fire and gas mapping and fireproofing; may move buildings or equipment.
7 | PIP-03 | Pipe stress and supports (screening) | Issued, provisional | yes |  | PRJ-03 | Screening only; CAESAR II analysis is PIP-05.
8 | ICS-02 | SIF list and SIL determination (LOPA) | Issued, provisional | yes |  | ICS-03, PRJ-03 | LOPA frequencies are FEED judgements pending SAF-03.
9 | ELE-05 | Power system studies and protection | Not started | no | VEN-01 |  | Load flow, short circuit, motor starting, arc flash, relay coordination.
10 | SAF-03 | Formal HAZOP and LOPA workshop | Not started | yes
11 | PIP-05 | Detailed pipe stress (CAESAR II) | Not started | no | VEN-01 |  | Includes nozzle-load agreement with equipment vendors.
12 | CIV-01 | Geotechnical, civil and structural design | Not started | yes |  |  | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
13 | LAY-03 | 3D model reviews and constructability | Not started | no | CIV-01 |  | 30/60/90 % model reviews.
14 | ICS-08 | SIL verification and SRS | Not started | no | SAF-03, VEN-01 |  | PFDavg calculations and the safety requirements specification (IEC 61511).
15 | CST-02 | Class 3 cost estimate | Not started | no | VEN-01, CIV-01
16 | PRJ-04 | PE review, seal and IFC issue | Not started | no | SAF-03, ICS-08, PIP-05, ELE-05, CST-02, LAY-03, SAF-04, SAF-02 |  | Nothing in this package is sealed; this is the gate before any use for construction.

## Code check
Module | Activity | Reads | Owner | Result
cfu/drawing/bfd.py | PRC-05 | process_results.json | PRC-01 | upstream
cfu/drawing/bfd.py | PRC-05 | streams.json | PRC-01 | upstream
cfu/elec/__init__.py | ELE-04 | layout.json | LAY-01 | upstream
cfu/elec/hac.py | ELE-02 | control_loops.json | PRC-04 | upstream
cfu/elec/hac.py | ELE-02 | equipment.json | PRC-02 | upstream
cfu/elec/hac.py | ELE-02 | layout.json | LAY-01 | upstream
cfu/elec/loads.py | ELE-01 | equipment.json | PRC-02 | upstream
cfu/ic/arch.py | ICS-07 | electrical.json | ELE-03 | upstream
cfu/ic/arch.py | ICS-07 | io_list.json | ICS-05 | upstream
cfu/ic/ce.py | ICS-03 | control_loops.json | PRC-04 | upstream
cfu/ic/ce.py | ICS-03 | equipment.json | PRC-02 | upstream
cfu/ic/ce.py | ICS-03 | process_results.json | PRC-01 | upstream
cfu/ic/ce.py | ICS-03 | psv.json | PRC-03 | upstream
cfu/ic/csd.py | ICS-01 | control_loops.json | PRC-04 | upstream
cfu/ic/csd.py | ICS-01 | process_results.json | PRC-01 | upstream
cfu/ic/csd.py | ICS-01 | streams.json | PRC-01 | upstream
cfu/ic/cvsizing.py | ICS-04 | equipment.json | PRC-02 | upstream
cfu/ic/cvsizing.py | ICS-04 | process_results.json | PRC-01 | upstream
cfu/ic/cvsizing.py | ICS-04 | streams.json | PRC-01 | upstream
cfu/ic/iolist.py | ICS-05 | control_loops.json | PRC-04 | upstream
cfu/ic/iolist.py | ICS-05 | equipment.json | PRC-02 | upstream
cfu/ic/iolist.py | ICS-05 | instruments.json | PRC-08 | upstream
cfu/ic/iolist.py | ICS-05 | layout.json | LAY-01 | upstream
cfu/ic/loops_ld.py | ICS-06 | io_list.json | ICS-05 | upstream
cfu/ic/report.py | ICS-01 | control_loops.json | PRC-04 | upstream
cfu/ic/report.py | ICS-01 | equipment.json | PRC-02 | upstream
cfu/ic/report.py | ICS-01 | process_results.json | PRC-01 | upstream
cfu/ic/report.py | ICS-01 | streams.json | PRC-01 | upstream
cfu/layout/elevations.py | LAY-02 | equipment.json | PRC-02 | upstream
cfu/layout/model.py | LAY-01 | equipment.json | PRC-02 | upstream
cfu/layout/model.py | LAY-01 | process_results.json | PRC-01 | upstream
cfu/mech/geometry.py | MEC-01 | process_results.json | PRC-01 | upstream
cfu/mech/geometry.py | MEC-01 | psv.json | PRC-03 | upstream
cfu/mech/geometry.py | MEC-01 | streams.json | PRC-01 | upstream
cfu/mech/pumps.py | MEC-01 | equipment.json | PRC-02 | upstream
cfu/pid/pfd.py | PRC-06 | control_loops.json | PRC-04 | upstream
cfu/pid/pfd.py | PRC-06 | equipment.json | PRC-02 | upstream
cfu/pid/pfd.py | PRC-06 | process_results.json | PRC-01 | upstream
cfu/pid/pfd.py | PRC-06 | streams.json | PRC-01 | upstream
cfu/pid/pid.py | PRC-08 | layout.json | LAY-01 | upstream
cfu/pid/pid_data.py | PRC-08 | control_loops.json | PRC-04 | upstream
cfu/pid/pid_data.py | PRC-08 | equipment.json | PRC-02 | upstream
cfu/pid/pid_data.py | PRC-08 | process_results.json | PRC-01 | upstream
cfu/pid/pid_data.py | PRC-08 | psv.json | PRC-03 | upstream
cfu/pid/pid_data.py | PRC-08 | streams.json | PRC-01 | upstream
cfu/piping/auto.py | PIP-02 | psv.json | PRC-03 | upstream
cfu/piping/router.py | PIP-02 | instruments.json | PRC-08 | upstream
cfu/piping/router.py | PIP-02 | layout.json | LAY-01 | upstream
cfu/piping/router.py | PIP-02 | lines.json | PRC-08 | upstream
cfu/piping/stress.py | PIP-03 | mech.json | MEC-01 | upstream
cfu/reports.py | PRC-07 | process_results.json | PRC-01 | upstream
cfu/reports.py | PRC-07 | streams.json | PRC-01 | upstream
cfu/wrapup/estimate.py | CST-01 | equipment.json | PRC-02 | upstream
cfu/wrapup/estimate.py | CST-01 | mech.json | MEC-01 | upstream
cfu/wrapup/portal.py | PRJ-03 | electrical.json | ELE-03 | upstream
cfu/wrapup/portal.py | PRJ-03 | equipment.json | PRC-02 | upstream
cfu/wrapup/portal.py | PRJ-03 | instruments.json | PRC-08 | upstream
cfu/wrapup/portal.py | PRJ-03 | io_list.json | ICS-05 | upstream
cfu/wrapup/portal.py | PRJ-03 | lines.json | PRC-08 | upstream
cfu/wrapup/portal.py | PRJ-03 | process_results.json | PRC-01 | upstream
cfu/wrapup/portal.py | PRJ-03 | routing.json | PIP-02 | upstream
cfu/wrapup/portal.py | PRJ-03 | streams.json | PRC-01 | upstream