## Matrix
ID | Activity | Discipline | Status | FEL1 | FEL2 | FEL3 | DD | Achieved | Note
FEL-01 | Business case, capacity and product slate | Project | Assumed by the design basis | 3 | 4 | 4 | 4 | 4 | Taken as given in this package: the BOD states capacity, crude and products.
PRJ-01 | Design basis (BOD) | Project | Issued | 2 | 3 | 4 | 4 | 4 | Every other activity reads the basis; a change here re-opens the whole package.
PRJ-03 | Document register and portal | Project | Issued | 1 | 2 | 3 | 4 | 3
PRJ-05 | Execution plan and contracting strategy | Project | Not started | 1 | 2 | 4 | 4 | 0
SEL-04 | Permitting and environmental basis | Project | Not started | 0 | 2 | 3 | 4 | 0
PRJ-04 | PE review, seal and IFC issue | Project | Not started | 0 | 0 | 0 | 4 | 0 | Nothing in this package is sealed; this is the gate before any use for construction.
FEL-02 | Configuration options and screening | Process | Assumed by the design basis | 4 | 4 | 4 | 4 | 4 | Taken as given: a conventional CDU/VDU configuration was assumed, no options were screened.
PRC-01 | Heat and material balance | Process | Issued, provisional | 1 | 2 | 3 | 4 | 2
PRC-02 | Process equipment sizing | Process | Issued | 1 | 2 | 3 | 4 | 3 | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
PRC-05 | Block flow diagram | Process | Issued | 1 | 3 | 4 | 4 | 4
PRC-06 | Process flow diagrams | Process | Issued | 1 | 2 | 3 | 4 | 3
PRJ-02 | Crude assay characterisation | Process | Issued, provisional | 1 | 2 | 4 | 4 | 2 | Uses a published Arab Light assay with pseudo-components, not a lab assay.
PRC-00 | Rigorous simulation and model calibration | Process | Not started | 0 | 1 | 4 | 4 | 0 | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
PRC-03 | Relief load and PSV sizing (unit) | Process | Issued | 0 | 1 | 3 | 4 | 3
PRC-04 | Control loops and SIF definition | Process | Issued | 0 | 1 | 3 | 4 | 3
PRC-07 | Process design report | Process | Issued | 0 | 1 | 4 | 4 | 4
PRC-08 | P&IDs, line list, instrument index | Process | Issued | 0 | 1 | 3 | 4 | 3 | Line list and instrument index feed piping, I&C and electrical; P&ID revisions ripple widely.
SEL-01 | Alternatives evaluation and select decision | Process | Assumed by the design basis | 0 | 4 | 4 | 4 | 4 | Taken as given: the package develops a single case.
SEL-02 | Technology and licensor selection | Process | Assumed by the design basis | 0 | 4 | 4 | 4 | 4 | Taken as given: open-art distillation, no licensor.
SEL-03 | Utility and offsite basis | Process | Issued, provisional | 0 | 2 | 3 | 4 | 2 | The BOD gives battery-limit utility conditions only; no utility or offsite balances.
SAF-02 | Global flare load study | Safety | Not started | 0 | 1 | 3 | 4 | 0 | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
SAF-01 | Preliminary HAZOP | Safety | Issued | 0 | 0 | 4 | 4 | 4
SAF-04 | Siting study, QRA, F&G mapping | Safety | Not started | 0 | 0 | 4 | 4 | 0 | API 752/753 siting, QRA, fire and gas mapping and fireproofing; may move buildings or equipment.
SAF-03 | Formal HAZOP and LOPA workshop | Safety | Not started | 0 | 0 | 0 | 4 | 0
MEC-01 | Mechanical design calculations | Mechanical | Issued | 0 | 1 | 3 | 4 | 3
MEC-02 | Equipment datasheets | Mechanical | Issued | 0 | 1 | 3 | 4 | 3
MEC-03 | Equipment GA drawings | Mechanical | Issued | 0 | 0 | 2 | 4 | 2
VEN-01 | Vendor enquiries and vendor data | Mechanical | Not started | 0 | 0 | 2 | 4 | 0 | Vendor data revises weights, nozzles, motor ratings and I/O; plan for one full update cycle.
PRO-01 | Requisitions and technical bid evaluations | Procurement | Not started | 0 | 0 | 3 | 4 | 0 | Long-lead items (heaters, columns, compressors, large pumps) are requisitioned in FEL 3.
FEL-03 | Site screening and selection | Layout | Assumed by the design basis | 2 | 4 | 4 | 4 | 4 | Taken as given: generic US Gulf Coast site in the BOD.
LAY-01 | Plot plan and equipment layout | Layout | Issued | 1 | 2 | 3 | 4 | 3
LAY-02 | Sections and 3D layout model | Layout | Issued | 0 | 1 | 3 | 4 | 3
LAY-03 | 3D model reviews and constructability | Layout | Not started | 0 | 0 | 2 | 4 | 0 | 30/60/90 % model reviews.
PIP-01 | Piping material classes | Piping | Issued | 0 | 1 | 3 | 4 | 3 | Defined in CONVENTIONS.md; summary issued with the P&IDs.
PIP-02 | Piping routing and 3D model | Piping | Issued | 0 | 0 | 2 | 4 | 2
PIP-03 | Pipe stress and supports (screening) | Piping | Issued, provisional | 0 | 0 | 2 | 4 | 1 | Screening only; CAESAR II analysis is PIP-05.
PIP-04 | Isometrics and piping MTO | Piping | Issued | 0 | 0 | 2 | 4 | 2
PIP-05 | Detailed pipe stress (CAESAR II) | Piping | Not started | 0 | 0 | 1 | 4 | 0 | Includes nozzle-load agreement with equipment vendors.
CIV-01 | Geotechnical, civil and structural design | Civil | Not started | 0 | 1 | 2 | 4 | 0 | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
CIV-02 | Foundation and structural steel detailing | Civil | Not started | 0 | 0 | 0 | 4 | 0
ICS-01 | Control philosophy and schemes | I&C | Issued | 0 | 1 | 3 | 4 | 3
ICS-07 | ICS architecture | I&C | Issued | 0 | 1 | 3 | 4 | 3
ICS-02 | SIF list and SIL determination (LOPA) | I&C | Issued, provisional | 0 | 0 | 2 | 4 | 1 | LOPA frequencies are FEED judgements pending SAF-03.
ICS-03 | Cause and effect matrix | I&C | Issued | 0 | 0 | 2 | 4 | 2
ICS-04 | Control valve sizing | I&C | Issued | 0 | 0 | 2 | 4 | 2
ICS-05 | I/O list | I&C | Issued | 0 | 0 | 2 | 4 | 2
ICS-06 | Loop diagrams | I&C | Issued | 0 | 0 | 1 | 4 | 1
ICS-08 | SIL verification and SRS | I&C | Not started | 0 | 0 | 0 | 4 | 0 | PFDavg calculations and the safety requirements specification (IEC 61511).
ICS-09 | Instrument installation design | I&C | Not started | 0 | 0 | 0 | 4 | 0 | Location plans, hook-ups, JB and cabinet wiring.
ELE-01 | Electrical load list | Electrical | Issued | 0 | 1 | 3 | 4 | 3
ELE-03 | Electrical sizing, single-line diagrams | Electrical | Issued | 0 | 1 | 3 | 4 | 3
ELE-02 | Hazardous area classification | Electrical | Issued | 0 | 0 | 3 | 4 | 3
ELE-04 | Cable schedule | Electrical | Issued | 0 | 0 | 2 | 4 | 2
ELE-05 | Power system studies and protection | Electrical | Not started | 0 | 0 | 1 | 4 | 0 | Load flow, short circuit, motor starting, arc flash, relay coordination.
ELE-06 | Electrical layouts | Electrical | Not started | 0 | 0 | 0 | 4 | 0 | Raceway, grounding, lighting and substation layouts.
CON-01 | Constructability, modularisation and path of construction | Construction | Not started | 0 | 1 | 3 | 4 | 0
CON-02 | Work packaging and system boundaries | Construction | Not started | 0 | 0 | 1 | 4 | 0 | Engineering and construction work packages, test packs, commissioning systems.
FEL-04 | Class 5 estimate and economics | Cost | Assumed by the design basis | 4 | 4 | 4 | 4 | 4 | Superseded in this package by the Class 4 estimate (CST-01).
CST-01 | Class 4 cost estimate | Cost | Issued | 0 | 4 | 4 | 4 | 4
CST-02 | Class 3 cost estimate | Cost | Not started | 0 | 0 | 4 | 4 | 0
CST-03 | Control estimate | Cost | Not started | 0 | 0 | 0 | 4 | 0
Levels: 0 Not started; 1 Concept; 2 Preliminary; 3 Defined; 4 Final

## Gates
Gate | ID | Activity | Target | Achieved | Met | Note
FEL1 | FEL-01 | Business case, capacity and product slate | 3 Defined | 4 Final | assumed | Taken as given in this package: the BOD states capacity, crude and products.
FEL1 | PRJ-01 | Design basis (BOD) | 2 Preliminary | 4 Final | yes | Every other activity reads the basis; a change here re-opens the whole package.
FEL1 | PRJ-03 | Document register and portal | 1 Concept | 3 Defined | yes
FEL1 | PRJ-05 | Execution plan and contracting strategy | 1 Concept | 0 Not started | no
FEL1 | FEL-02 | Configuration options and screening | 4 Final | 4 Final | assumed | Taken as given: a conventional CDU/VDU configuration was assumed, no options were screened.
FEL1 | PRC-01 | Heat and material balance | 1 Concept | 2 Preliminary | yes
FEL1 | PRC-02 | Process equipment sizing | 1 Concept | 3 Defined | yes | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
FEL1 | PRC-05 | Block flow diagram | 1 Concept | 4 Final | yes
FEL1 | PRC-06 | Process flow diagrams | 1 Concept | 3 Defined | yes
FEL1 | PRJ-02 | Crude assay characterisation | 1 Concept | 2 Preliminary | yes | Uses a published Arab Light assay with pseudo-components, not a lab assay.
FEL1 | FEL-03 | Site screening and selection | 2 Preliminary | 4 Final | assumed | Taken as given: generic US Gulf Coast site in the BOD.
FEL1 | LAY-01 | Plot plan and equipment layout | 1 Concept | 3 Defined | yes
FEL1 | FEL-04 | Class 5 estimate and economics | 4 Final | 4 Final | assumed | Superseded in this package by the Class 4 estimate (CST-01).
FEL2 | FEL-01 | Business case, capacity and product slate | 4 Final | 4 Final | assumed | Taken as given in this package: the BOD states capacity, crude and products.
FEL2 | PRJ-01 | Design basis (BOD) | 3 Defined | 4 Final | yes | Every other activity reads the basis; a change here re-opens the whole package.
FEL2 | PRJ-03 | Document register and portal | 2 Preliminary | 3 Defined | yes
FEL2 | PRJ-05 | Execution plan and contracting strategy | 2 Preliminary | 0 Not started | no
FEL2 | SEL-04 | Permitting and environmental basis | 2 Preliminary | 0 Not started | no
FEL2 | FEL-02 | Configuration options and screening | 4 Final | 4 Final | assumed | Taken as given: a conventional CDU/VDU configuration was assumed, no options were screened.
FEL2 | PRC-01 | Heat and material balance | 2 Preliminary | 2 Preliminary | yes
FEL2 | PRC-02 | Process equipment sizing | 2 Preliminary | 3 Defined | yes | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
FEL2 | PRC-05 | Block flow diagram | 3 Defined | 4 Final | yes
FEL2 | PRC-06 | Process flow diagrams | 2 Preliminary | 3 Defined | yes
FEL2 | PRJ-02 | Crude assay characterisation | 2 Preliminary | 2 Preliminary | yes | Uses a published Arab Light assay with pseudo-components, not a lab assay.
FEL2 | PRC-00 | Rigorous simulation and model calibration | 1 Concept | 0 Not started | no | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
FEL2 | PRC-03 | Relief load and PSV sizing (unit) | 1 Concept | 3 Defined | yes
FEL2 | PRC-04 | Control loops and SIF definition | 1 Concept | 3 Defined | yes
FEL2 | PRC-07 | Process design report | 1 Concept | 4 Final | yes
FEL2 | PRC-08 | P&IDs, line list, instrument index | 1 Concept | 3 Defined | yes | Line list and instrument index feed piping, I&C and electrical; P&ID revisions ripple widely.
FEL2 | SEL-01 | Alternatives evaluation and select decision | 4 Final | 4 Final | assumed | Taken as given: the package develops a single case.
FEL2 | SEL-02 | Technology and licensor selection | 4 Final | 4 Final | assumed | Taken as given: open-art distillation, no licensor.
FEL2 | SEL-03 | Utility and offsite basis | 2 Preliminary | 2 Preliminary | yes | The BOD gives battery-limit utility conditions only; no utility or offsite balances.
FEL2 | SAF-02 | Global flare load study | 1 Concept | 0 Not started | no | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
FEL2 | MEC-01 | Mechanical design calculations | 1 Concept | 3 Defined | yes
FEL2 | MEC-02 | Equipment datasheets | 1 Concept | 3 Defined | yes
FEL2 | FEL-03 | Site screening and selection | 4 Final | 4 Final | assumed | Taken as given: generic US Gulf Coast site in the BOD.
FEL2 | LAY-01 | Plot plan and equipment layout | 2 Preliminary | 3 Defined | yes
FEL2 | LAY-02 | Sections and 3D layout model | 1 Concept | 3 Defined | yes
FEL2 | PIP-01 | Piping material classes | 1 Concept | 3 Defined | yes | Defined in CONVENTIONS.md; summary issued with the P&IDs.
FEL2 | CIV-01 | Geotechnical, civil and structural design | 1 Concept | 0 Not started | no | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
FEL2 | ICS-01 | Control philosophy and schemes | 1 Concept | 3 Defined | yes
FEL2 | ICS-07 | ICS architecture | 1 Concept | 3 Defined | yes
FEL2 | ELE-01 | Electrical load list | 1 Concept | 3 Defined | yes
FEL2 | ELE-03 | Electrical sizing, single-line diagrams | 1 Concept | 3 Defined | yes
FEL2 | CON-01 | Constructability, modularisation and path of construction | 1 Concept | 0 Not started | no
FEL2 | FEL-04 | Class 5 estimate and economics | 4 Final | 4 Final | assumed | Superseded in this package by the Class 4 estimate (CST-01).
FEL2 | CST-01 | Class 4 cost estimate | 4 Final | 4 Final | yes
FEL3 | FEL-01 | Business case, capacity and product slate | 4 Final | 4 Final | assumed | Taken as given in this package: the BOD states capacity, crude and products.
FEL3 | PRJ-01 | Design basis (BOD) | 4 Final | 4 Final | yes | Every other activity reads the basis; a change here re-opens the whole package.
FEL3 | PRJ-03 | Document register and portal | 3 Defined | 3 Defined | yes
FEL3 | PRJ-05 | Execution plan and contracting strategy | 4 Final | 0 Not started | no
FEL3 | SEL-04 | Permitting and environmental basis | 3 Defined | 0 Not started | no
FEL3 | FEL-02 | Configuration options and screening | 4 Final | 4 Final | assumed | Taken as given: a conventional CDU/VDU configuration was assumed, no options were screened.
FEL3 | PRC-01 | Heat and material balance | 3 Defined | 2 Preliminary | no
FEL3 | PRC-02 | Process equipment sizing | 3 Defined | 3 Defined | yes | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
FEL3 | PRC-05 | Block flow diagram | 4 Final | 4 Final | yes
FEL3 | PRC-06 | Process flow diagrams | 3 Defined | 3 Defined | yes
FEL3 | PRJ-02 | Crude assay characterisation | 4 Final | 2 Preliminary | no | Uses a published Arab Light assay with pseudo-components, not a lab assay.
FEL3 | PRC-00 | Rigorous simulation and model calibration | 4 Final | 0 Not started | no | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
FEL3 | PRC-03 | Relief load and PSV sizing (unit) | 3 Defined | 3 Defined | yes
FEL3 | PRC-04 | Control loops and SIF definition | 3 Defined | 3 Defined | yes
FEL3 | PRC-07 | Process design report | 4 Final | 4 Final | yes
FEL3 | PRC-08 | P&IDs, line list, instrument index | 3 Defined | 3 Defined | yes | Line list and instrument index feed piping, I&C and electrical; P&ID revisions ripple widely.
FEL3 | SEL-01 | Alternatives evaluation and select decision | 4 Final | 4 Final | assumed | Taken as given: the package develops a single case.
FEL3 | SEL-02 | Technology and licensor selection | 4 Final | 4 Final | assumed | Taken as given: open-art distillation, no licensor.
FEL3 | SEL-03 | Utility and offsite basis | 3 Defined | 2 Preliminary | no | The BOD gives battery-limit utility conditions only; no utility or offsite balances.
FEL3 | SAF-02 | Global flare load study | 3 Defined | 0 Not started | no | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
FEL3 | SAF-01 | Preliminary HAZOP | 4 Final | 4 Final | yes
FEL3 | SAF-04 | Siting study, QRA, F&G mapping | 4 Final | 0 Not started | no | API 752/753 siting, QRA, fire and gas mapping and fireproofing; may move buildings or equipment.
FEL3 | MEC-01 | Mechanical design calculations | 3 Defined | 3 Defined | yes
FEL3 | MEC-02 | Equipment datasheets | 3 Defined | 3 Defined | yes
FEL3 | MEC-03 | Equipment GA drawings | 2 Preliminary | 2 Preliminary | yes
FEL3 | VEN-01 | Vendor enquiries and vendor data | 2 Preliminary | 0 Not started | no | Vendor data revises weights, nozzles, motor ratings and I/O; plan for one full update cycle.
FEL3 | PRO-01 | Requisitions and technical bid evaluations | 3 Defined | 0 Not started | no | Long-lead items (heaters, columns, compressors, large pumps) are requisitioned in FEL 3.
FEL3 | FEL-03 | Site screening and selection | 4 Final | 4 Final | assumed | Taken as given: generic US Gulf Coast site in the BOD.
FEL3 | LAY-01 | Plot plan and equipment layout | 3 Defined | 3 Defined | yes
FEL3 | LAY-02 | Sections and 3D layout model | 3 Defined | 3 Defined | yes
FEL3 | LAY-03 | 3D model reviews and constructability | 2 Preliminary | 0 Not started | no | 30/60/90 % model reviews.
FEL3 | PIP-01 | Piping material classes | 3 Defined | 3 Defined | yes | Defined in CONVENTIONS.md; summary issued with the P&IDs.
FEL3 | PIP-02 | Piping routing and 3D model | 2 Preliminary | 2 Preliminary | yes
FEL3 | PIP-03 | Pipe stress and supports (screening) | 2 Preliminary | 1 Concept | no | Screening only; CAESAR II analysis is PIP-05.
FEL3 | PIP-04 | Isometrics and piping MTO | 2 Preliminary | 2 Preliminary | yes
FEL3 | PIP-05 | Detailed pipe stress (CAESAR II) | 1 Concept | 0 Not started | no | Includes nozzle-load agreement with equipment vendors.
FEL3 | CIV-01 | Geotechnical, civil and structural design | 2 Preliminary | 0 Not started | no | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
FEL3 | ICS-01 | Control philosophy and schemes | 3 Defined | 3 Defined | yes
FEL3 | ICS-07 | ICS architecture | 3 Defined | 3 Defined | yes
FEL3 | ICS-02 | SIF list and SIL determination (LOPA) | 2 Preliminary | 1 Concept | no | LOPA frequencies are FEED judgements pending SAF-03.
FEL3 | ICS-03 | Cause and effect matrix | 2 Preliminary | 2 Preliminary | yes
FEL3 | ICS-04 | Control valve sizing | 2 Preliminary | 2 Preliminary | yes
FEL3 | ICS-05 | I/O list | 2 Preliminary | 2 Preliminary | yes
FEL3 | ICS-06 | Loop diagrams | 1 Concept | 1 Concept | yes
FEL3 | ELE-01 | Electrical load list | 3 Defined | 3 Defined | yes
FEL3 | ELE-03 | Electrical sizing, single-line diagrams | 3 Defined | 3 Defined | yes
FEL3 | ELE-02 | Hazardous area classification | 3 Defined | 3 Defined | yes
FEL3 | ELE-04 | Cable schedule | 2 Preliminary | 2 Preliminary | yes
FEL3 | ELE-05 | Power system studies and protection | 1 Concept | 0 Not started | no | Load flow, short circuit, motor starting, arc flash, relay coordination.
FEL3 | CON-01 | Constructability, modularisation and path of construction | 3 Defined | 0 Not started | no
FEL3 | CON-02 | Work packaging and system boundaries | 1 Concept | 0 Not started | no | Engineering and construction work packages, test packs, commissioning systems.
FEL3 | FEL-04 | Class 5 estimate and economics | 4 Final | 4 Final | assumed | Superseded in this package by the Class 4 estimate (CST-01).
FEL3 | CST-01 | Class 4 cost estimate | 4 Final | 4 Final | yes
FEL3 | CST-02 | Class 3 cost estimate | 4 Final | 0 Not started | no
DD | FEL-01 | Business case, capacity and product slate | 4 Final | 4 Final | assumed | Taken as given in this package: the BOD states capacity, crude and products.
DD | PRJ-01 | Design basis (BOD) | 4 Final | 4 Final | yes | Every other activity reads the basis; a change here re-opens the whole package.
DD | PRJ-03 | Document register and portal | 4 Final | 3 Defined | no
DD | PRJ-05 | Execution plan and contracting strategy | 4 Final | 0 Not started | no
DD | SEL-04 | Permitting and environmental basis | 4 Final | 0 Not started | no
DD | PRJ-04 | PE review, seal and IFC issue | 4 Final | 0 Not started | no | Nothing in this package is sealed; this is the gate before any use for construction.
DD | FEL-02 | Configuration options and screening | 4 Final | 4 Final | assumed | Taken as given: a conventional CDU/VDU configuration was assumed, no options were screened.
DD | PRC-01 | Heat and material balance | 4 Final | 2 Preliminary | no
DD | PRC-02 | Process equipment sizing | 4 Final | 3 Defined | no | Equipment list is the hub: mechanical, layout, electrical, I&C and cost all read it.
DD | PRC-05 | Block flow diagram | 4 Final | 4 Final | yes
DD | PRC-06 | Process flow diagrams | 4 Final | 3 Defined | no
DD | PRJ-02 | Crude assay characterisation | 4 Final | 2 Preliminary | no | Uses a published Arab Light assay with pseudo-components, not a lab assay.
DD | PRC-00 | Rigorous simulation and model calibration | 4 Final | 0 Not started | no | Replaces the ideal-VLE shortcut model; expect 5-10 C changes in draw temperatures.
DD | PRC-03 | Relief load and PSV sizing (unit) | 4 Final | 3 Defined | no
DD | PRC-04 | Control loops and SIF definition | 4 Final | 3 Defined | no
DD | PRC-07 | Process design report | 4 Final | 4 Final | yes
DD | PRC-08 | P&IDs, line list, instrument index | 4 Final | 3 Defined | no | Line list and instrument index feed piping, I&C and electrical; P&ID revisions ripple widely.
DD | SEL-01 | Alternatives evaluation and select decision | 4 Final | 4 Final | assumed | Taken as given: the package develops a single case.
DD | SEL-02 | Technology and licensor selection | 4 Final | 4 Final | assumed | Taken as given: open-art distillation, no licensor.
DD | SEL-03 | Utility and offsite basis | 4 Final | 2 Preliminary | no | The BOD gives battery-limit utility conditions only; no utility or offsite balances.
DD | SAF-02 | Global flare load study | 4 Final | 0 Not started | no | Governing case (C-101 reflux failure, about 220 t/h) needs power and cooling-water failure cases.
DD | SAF-01 | Preliminary HAZOP | 4 Final | 4 Final | yes
DD | SAF-04 | Siting study, QRA, F&G mapping | 4 Final | 0 Not started | no | API 752/753 siting, QRA, fire and gas mapping and fireproofing; may move buildings or equipment.
DD | SAF-03 | Formal HAZOP and LOPA workshop | 4 Final | 0 Not started | no
DD | MEC-01 | Mechanical design calculations | 4 Final | 3 Defined | no
DD | MEC-02 | Equipment datasheets | 4 Final | 3 Defined | no
DD | MEC-03 | Equipment GA drawings | 4 Final | 2 Preliminary | no
DD | VEN-01 | Vendor enquiries and vendor data | 4 Final | 0 Not started | no | Vendor data revises weights, nozzles, motor ratings and I/O; plan for one full update cycle.
DD | PRO-01 | Requisitions and technical bid evaluations | 4 Final | 0 Not started | no | Long-lead items (heaters, columns, compressors, large pumps) are requisitioned in FEL 3.
DD | FEL-03 | Site screening and selection | 4 Final | 4 Final | assumed | Taken as given: generic US Gulf Coast site in the BOD.
DD | LAY-01 | Plot plan and equipment layout | 4 Final | 3 Defined | no
DD | LAY-02 | Sections and 3D layout model | 4 Final | 3 Defined | no
DD | LAY-03 | 3D model reviews and constructability | 4 Final | 0 Not started | no | 30/60/90 % model reviews.
DD | PIP-01 | Piping material classes | 4 Final | 3 Defined | no | Defined in CONVENTIONS.md; summary issued with the P&IDs.
DD | PIP-02 | Piping routing and 3D model | 4 Final | 2 Preliminary | no
DD | PIP-03 | Pipe stress and supports (screening) | 4 Final | 1 Concept | no | Screening only; CAESAR II analysis is PIP-05.
DD | PIP-04 | Isometrics and piping MTO | 4 Final | 2 Preliminary | no
DD | PIP-05 | Detailed pipe stress (CAESAR II) | 4 Final | 0 Not started | no | Includes nozzle-load agreement with equipment vendors.
DD | CIV-01 | Geotechnical, civil and structural design | 4 Final | 0 Not started | no | No civil deliverables in this package: foundations, pipe rack and structures are still to do.
DD | CIV-02 | Foundation and structural steel detailing | 4 Final | 0 Not started | no
DD | ICS-01 | Control philosophy and schemes | 4 Final | 3 Defined | no
DD | ICS-07 | ICS architecture | 4 Final | 3 Defined | no
DD | ICS-02 | SIF list and SIL determination (LOPA) | 4 Final | 1 Concept | no | LOPA frequencies are FEED judgements pending SAF-03.
DD | ICS-03 | Cause and effect matrix | 4 Final | 2 Preliminary | no
DD | ICS-04 | Control valve sizing | 4 Final | 2 Preliminary | no
DD | ICS-05 | I/O list | 4 Final | 2 Preliminary | no
DD | ICS-06 | Loop diagrams | 4 Final | 1 Concept | no
DD | ICS-08 | SIL verification and SRS | 4 Final | 0 Not started | no | PFDavg calculations and the safety requirements specification (IEC 61511).
DD | ICS-09 | Instrument installation design | 4 Final | 0 Not started | no | Location plans, hook-ups, JB and cabinet wiring.
DD | ELE-01 | Electrical load list | 4 Final | 3 Defined | no
DD | ELE-03 | Electrical sizing, single-line diagrams | 4 Final | 3 Defined | no
DD | ELE-02 | Hazardous area classification | 4 Final | 3 Defined | no
DD | ELE-04 | Cable schedule | 4 Final | 2 Preliminary | no
DD | ELE-05 | Power system studies and protection | 4 Final | 0 Not started | no | Load flow, short circuit, motor starting, arc flash, relay coordination.
DD | ELE-06 | Electrical layouts | 4 Final | 0 Not started | no | Raceway, grounding, lighting and substation layouts.
DD | CON-01 | Constructability, modularisation and path of construction | 4 Final | 0 Not started | no
DD | CON-02 | Work packaging and system boundaries | 4 Final | 0 Not started | no | Engineering and construction work packages, test packs, commissioning systems.
DD | FEL-04 | Class 5 estimate and economics | 4 Final | 4 Final | assumed | Superseded in this package by the Class 4 estimate (CST-01).
DD | CST-01 | Class 4 cost estimate | 4 Final | 4 Final | yes
DD | CST-02 | Class 3 cost estimate | 4 Final | 0 Not started | no
DD | CST-03 | Control estimate | 4 Final | 0 Not started | no

## Steps
Phase | Order | ID | Activity | To level | State today | Needs | Waiting on
FEL1 | 1 | FEL-01 | Business case, capacity and product slate | 1 Concept | done
FEL1 | 1 | PRJ-03 | Document register and portal | 1 Concept | done
FEL1 | 2 | FEL-01 | Business case, capacity and product slate | 2 Preliminary | done
FEL1 | 2 | FEL-03 | Site screening and selection | 1 Concept | done | FEL-01 at 1
FEL1 | 2 | PRJ-01 | Design basis (BOD) | 1 Concept | done | FEL-01 at 1
FEL1 | 2 | PRJ-05 | Execution plan and contracting strategy | 1 Concept | ready | FEL-01 at 1
FEL1 | 3 | FEL-01 | Business case, capacity and product slate | 3 Defined | done
FEL1 | 3 | FEL-02 | Configuration options and screening | 1 Concept | done | FEL-01 at 1, PRJ-01 at 1
FEL1 | 3 | FEL-03 | Site screening and selection | 2 Preliminary | done | FEL-01 at 2
FEL1 | 3 | PRJ-01 | Design basis (BOD) | 2 Preliminary | done | FEL-01 at 2
FEL1 | 3 | PRJ-02 | Crude assay characterisation | 1 Concept | done | PRJ-01 at 1
FEL1 | 4 | FEL-02 | Configuration options and screening | 2 Preliminary | done | FEL-01 at 2, PRJ-01 at 2
FEL1 | 4 | PRC-01 | Heat and material balance | 1 Concept | done | PRJ-01 at 1, PRJ-02 at 1
FEL1 | 5 | FEL-02 | Configuration options and screening | 3 Defined | done | FEL-01 at 2, PRJ-01 at 2
FEL1 | 5 | PRC-02 | Process equipment sizing | 1 Concept | done | PRC-01 at 1
FEL1 | 5 | PRC-05 | Block flow diagram | 1 Concept | done | PRC-01 at 1
FEL1 | 6 | FEL-02 | Configuration options and screening | 4 Final | done | FEL-01 at 2, PRJ-01 at 2
FEL1 | 6 | LAY-01 | Plot plan and equipment layout | 1 Concept | done | PRC-02 at 1, PRC-01 at 1, PRJ-01 at 1, FEL-03 at 1
FEL1 | 6 | PRC-06 | Process flow diagrams | 1 Concept | done | PRC-01 at 1, PRC-02 at 1
FEL1 | 7 | FEL-04 | Class 5 estimate and economics | 1 Concept | done | FEL-01 at 1, FEL-02 at 1, PRC-02 at 1, LAY-01 at 1
FEL1 | 8 | FEL-04 | Class 5 estimate and economics | 2 Preliminary | done | FEL-01 at 1, FEL-02 at 1, PRC-02 at 1, LAY-01 at 1
FEL1 | 9 | FEL-04 | Class 5 estimate and economics | 3 Defined | done | FEL-01 at 1, FEL-02 at 1, PRC-02 at 1, LAY-01 at 1
FEL1 | 10 | FEL-04 | Class 5 estimate and economics | 4 Final | done | FEL-01 at 1, FEL-02 at 1, PRC-02 at 1, LAY-01 at 1
FEL2 | 2 | PRJ-03 | Document register and portal | 2 Preliminary | done
FEL2 | 4 | FEL-01 | Business case, capacity and product slate | 4 Final | done
FEL2 | 4 | FEL-03 | Site screening and selection | 3 Defined | done | FEL-01 at 2
FEL2 | 4 | PRC-00 | Rigorous simulation and model calibration | 1 Concept | ready | PRJ-02 at 1
FEL2 | 4 | PRJ-01 | Design basis (BOD) | 3 Defined | done | FEL-01 at 3
FEL2 | 4 | PRJ-02 | Crude assay characterisation | 2 Preliminary | done | PRJ-01 at 2
FEL2 | 4 | SEL-02 | Technology and licensor selection | 1 Concept | done | FEL-02 at 1
FEL2 | 5 | FEL-03 | Site screening and selection | 4 Final | done | FEL-01 at 2
FEL2 | 5 | PIP-01 | Piping material classes | 1 Concept | done | PRJ-01 at 1, PRC-01 at 1
FEL2 | 5 | PRC-01 | Heat and material balance | 2 Preliminary | done | PRJ-01 at 2, PRJ-02 at 2, PRC-00 at 1 | PRC-00 at 1
FEL2 | 5 | SEL-01 | Alternatives evaluation and select decision | 1 Concept | done | FEL-02 at 1, SEL-02 at 1, PRC-01 at 1, FEL-03 at 1
FEL2 | 5 | SEL-02 | Technology and licensor selection | 2 Preliminary | done | FEL-02 at 2
FEL2 | 5 | SEL-03 | Utility and offsite basis | 1 Concept | done | PRJ-01 at 1, PRC-01 at 1
FEL2 | 6 | ELE-01 | Electrical load list | 1 Concept | done | PRC-02 at 1
FEL2 | 6 | PRC-02 | Process equipment sizing | 2 Preliminary | done | PRC-01 at 2
FEL2 | 6 | PRC-03 | Relief load and PSV sizing (unit) | 1 Concept | done | PRC-01 at 1, PRC-02 at 1
FEL2 | 6 | PRC-04 | Control loops and SIF definition | 1 Concept | done | PRC-01 at 1, PRC-02 at 1
FEL2 | 6 | PRC-05 | Block flow diagram | 2 Preliminary | done | PRC-01 at 2
FEL2 | 6 | SEL-01 | Alternatives evaluation and select decision | 2 Preliminary | done | FEL-02 at 2, SEL-02 at 2, PRC-01 at 2, FEL-03 at 2
FEL2 | 6 | SEL-02 | Technology and licensor selection | 3 Defined | done | FEL-02 at 2
FEL2 | 6 | SEL-03 | Utility and offsite basis | 2 Preliminary | done | PRJ-01 at 2, PRC-01 at 2
FEL2 | 7 | ELE-03 | Electrical sizing, single-line diagrams | 1 Concept | done | ELE-01 at 1
FEL2 | 7 | ICS-01 | Control philosophy and schemes | 1 Concept | done | PRC-04 at 1, PRC-01 at 1, PRC-02 at 1
FEL2 | 7 | LAY-01 | Plot plan and equipment layout | 2 Preliminary | done | PRC-02 at 2, PRC-01 at 2, PRJ-01 at 2, FEL-03 at 2
FEL2 | 7 | LAY-02 | Sections and 3D layout model | 1 Concept | done | LAY-01 at 1, PRC-02 at 1
FEL2 | 7 | MEC-01 | Mechanical design calculations | 1 Concept | done | PRC-02 at 1, PRC-01 at 1, PRC-03 at 1
FEL2 | 7 | PRC-05 | Block flow diagram | 3 Defined | done | PRC-01 at 2
FEL2 | 7 | PRC-06 | Process flow diagrams | 2 Preliminary | done | PRC-01 at 2, PRC-02 at 2, PRC-04 at 1
FEL2 | 7 | PRC-07 | Process design report | 1 Concept | done | PRC-01 at 1, PRC-02 at 1, PRC-03 at 1
FEL2 | 7 | PRC-08 | P&IDs, line list, instrument index | 1 Concept | done | PRC-02 at 1, PRC-03 at 1, PRC-04 at 1, PRC-06 at 1, PIP-01 at 1, LAY-01 at 1
FEL2 | 7 | PRJ-05 | Execution plan and contracting strategy | 2 Preliminary | blocked | FEL-01 at 2, SEL-01 at 2 | PRJ-05 at 1
FEL2 | 7 | SAF-02 | Global flare load study | 1 Concept | ready | PRC-03 at 1
FEL2 | 7 | SEL-01 | Alternatives evaluation and select decision | 3 Defined | done | FEL-02 at 2, SEL-02 at 2, PRC-01 at 2, FEL-03 at 2
FEL2 | 7 | SEL-02 | Technology and licensor selection | 4 Final | done | FEL-02 at 2
FEL2 | 7 | SEL-04 | Permitting and environmental basis | 1 Concept | ready | PRC-01 at 1, LAY-01 at 1
FEL2 | 8 | CIV-01 | Geotechnical, civil and structural design | 1 Concept | ready | LAY-01 at 1, MEC-01 at 1
FEL2 | 8 | CON-01 | Constructability, modularisation and path of construction | 1 Concept | blocked | LAY-01 at 1, LAY-02 at 1, PRJ-05 at 1 | PRJ-05 at 1
FEL2 | 8 | CST-01 | Class 4 cost estimate | 1 Concept | done | PRC-02 at 1, MEC-01 at 1, SEL-01 at 1
FEL2 | 8 | ICS-07 | ICS architecture | 1 Concept | done | ELE-03 at 1
FEL2 | 8 | MEC-02 | Equipment datasheets | 1 Concept | done | MEC-01 at 1, PRC-02 at 1, PRC-03 at 1
FEL2 | 8 | SEL-01 | Alternatives evaluation and select decision | 4 Final | done | FEL-02 at 2, SEL-02 at 2, PRC-01 at 2, FEL-03 at 2
FEL2 | 8 | SEL-04 | Permitting and environmental basis | 2 Preliminary | blocked | PRC-01 at 2, LAY-01 at 2 | SEL-04 at 1
FEL2 | 9 | CST-01 | Class 4 cost estimate | 2 Preliminary | done | PRC-02 at 2, MEC-01 at 2, SEL-01 at 2
FEL2 | 10 | CST-01 | Class 4 cost estimate | 3 Defined | done | PRC-02 at 2, MEC-01 at 2, SEL-01 at 2
FEL2 | 11 | CST-01 | Class 4 cost estimate | 4 Final | done | PRC-02 at 2, MEC-01 at 1, SEL-01 at 2
FEL3 | 3 | PRJ-03 | Document register and portal | 3 Defined | done
FEL3 | 5 | PRC-00 | Rigorous simulation and model calibration | 2 Preliminary | blocked | PRJ-02 at 2 | PRC-00 at 1
FEL3 | 5 | PRJ-01 | Design basis (BOD) | 4 Final | done | FEL-01 at 4
FEL3 | 5 | PRJ-02 | Crude assay characterisation | 3 Defined | ready | PRJ-01 at 3
FEL3 | 6 | PIP-01 | Piping material classes | 2 Preliminary | done | PRJ-01 at 2, PRC-01 at 2
FEL3 | 6 | PRC-00 | Rigorous simulation and model calibration | 3 Defined | blocked | PRJ-02 at 3 | PRJ-02 at 3, PRC-00 at 2
FEL3 | 6 | PRJ-02 | Crude assay characterisation | 4 Final | blocked | PRJ-01 at 4 | PRJ-02 at 3
FEL3 | 7 | ELE-01 | Electrical load list | 2 Preliminary | done | PRC-02 at 2
FEL3 | 7 | ELE-02 | Hazardous area classification | 1 Concept | done | LAY-01 at 1, PRC-02 at 1, PRC-04 at 1
FEL3 | 7 | PRC-00 | Rigorous simulation and model calibration | 4 Final | blocked | PRJ-02 at 4 | PRJ-02 at 4, PRC-00 at 3
FEL3 | 7 | PRC-03 | Relief load and PSV sizing (unit) | 2 Preliminary | done | PRC-01 at 2, PRC-02 at 2
FEL3 | 7 | PRC-04 | Control loops and SIF definition | 2 Preliminary | done | PRC-01 at 2, PRC-02 at 2
FEL3 | 8 | ELE-02 | Hazardous area classification | 2 Preliminary | done | LAY-01 at 2, PRC-02 at 2, PRC-04 at 2
FEL3 | 8 | ELE-03 | Electrical sizing, single-line diagrams | 2 Preliminary | done | ELE-01 at 2
FEL3 | 8 | ELE-04 | Cable schedule | 1 Concept | done | ELE-01 at 1, ELE-03 at 1, LAY-01 at 1, ELE-02 at 1
FEL3 | 8 | ICS-01 | Control philosophy and schemes | 2 Preliminary | done | PRC-04 at 2, PRC-01 at 2, PRC-02 at 2
FEL3 | 8 | ICS-04 | Control valve sizing | 1 Concept | done | PRC-01 at 1, PRC-02 at 1, PRC-04 at 1, PRC-08 at 1
FEL3 | 8 | ICS-05 | I/O list | 1 Concept | done | PRC-08 at 1, PRC-04 at 1, PRC-02 at 1, LAY-01 at 1
FEL3 | 8 | LAY-02 | Sections and 3D layout model | 2 Preliminary | done | LAY-01 at 2, PRC-02 at 2
FEL3 | 8 | MEC-01 | Mechanical design calculations | 2 Preliminary | done | PRC-02 at 2, PRC-01 at 2, PRC-03 at 2
FEL3 | 8 | MEC-03 | Equipment GA drawings | 1 Concept | done | MEC-01 at 1
FEL3 | 8 | PIP-02 | Piping routing and 3D model | 1 Concept | done | PRC-08 at 1, LAY-01 at 1, PRC-03 at 1, MEC-01 at 1
FEL3 | 8 | PRC-01 | Heat and material balance | 3 Defined | blocked | PRJ-01 at 3, PRJ-02 at 3, PRC-00 at 3, SEL-01 at 3 | PRJ-02 at 3, PRC-00 at 3
FEL3 | 8 | PRC-05 | Block flow diagram | 4 Final | done | PRC-01 at 2
FEL3 | 8 | PRC-07 | Process design report | 2 Preliminary | done | PRC-01 at 2, PRC-02 at 2, PRC-03 at 2
FEL3 | 8 | PRC-08 | P&IDs, line list, instrument index | 2 Preliminary | done | PRC-02 at 2, PRC-03 at 2, PRC-04 at 2, PRC-06 at 2, PIP-01 at 2, LAY-01 at 2
FEL3 | 8 | PRJ-05 | Execution plan and contracting strategy | 3 Defined | blocked | FEL-01 at 3, SEL-01 at 3 | PRJ-05 at 2
FEL3 | 8 | SAF-01 | Preliminary HAZOP | 1 Concept | done | PRC-08 at 1, PRC-04 at 1, PRC-03 at 1
FEL3 | 8 | SAF-02 | Global flare load study | 2 Preliminary | blocked | PRC-03 at 2 | SAF-02 at 1
FEL3 | 9 | CON-01 | Constructability, modularisation and path of construction | 2 Preliminary | blocked | LAY-01 at 2, LAY-02 at 2, PRJ-05 at 2 | PRJ-05 at 2, CON-01 at 1
FEL3 | 9 | ELE-04 | Cable schedule | 2 Preliminary | done | ELE-01 at 2, ELE-03 at 2, LAY-01 at 2, ELE-02 at 2
FEL3 | 9 | ICS-02 | SIF list and SIL determination (LOPA) | 1 Concept | done | PRC-04 at 1, SAF-01 at 1
FEL3 | 9 | ICS-04 | Control valve sizing | 2 Preliminary | done | PRC-01 at 2, PRC-02 at 2, PRC-04 at 2, PRC-08 at 2
FEL3 | 9 | ICS-05 | I/O list | 2 Preliminary | done | PRC-08 at 2, PRC-04 at 2, PRC-02 at 2, LAY-01 at 2
FEL3 | 9 | ICS-06 | Loop diagrams | 1 Concept | done | ICS-05 at 1
FEL3 | 9 | LAY-03 | 3D model reviews and constructability | 1 Concept | blocked | PIP-02 at 1, LAY-02 at 1, CIV-01 at 1 | CIV-01 at 1
FEL3 | 9 | MEC-02 | Equipment datasheets | 2 Preliminary | done | MEC-01 at 2, PRC-02 at 2, PRC-03 at 2
FEL3 | 9 | MEC-03 | Equipment GA drawings | 2 Preliminary | done | MEC-01 at 2
FEL3 | 9 | PIP-01 | Piping material classes | 3 Defined | done | PRJ-01 at 3, PRC-01 at 3 | PRC-01 at 3
FEL3 | 9 | PIP-02 | Piping routing and 3D model | 2 Preliminary | done | PRC-08 at 2, LAY-01 at 2, PRC-03 at 2, MEC-01 at 2
FEL3 | 9 | PIP-03 | Pipe stress and supports (screening) | 1 Concept | done | PIP-02 at 1, MEC-01 at 1
FEL3 | 9 | PIP-04 | Isometrics and piping MTO | 1 Concept | done | PIP-02 at 1, PIP-01 at 1
FEL3 | 9 | PRC-02 | Process equipment sizing | 3 Defined | done | PRC-01 at 3, MEC-01 at 2 | PRC-01 at 3
FEL3 | 9 | PRJ-05 | Execution plan and contracting strategy | 4 Final | blocked | FEL-01 at 4, SEL-01 at 4 | PRJ-05 at 3
FEL3 | 9 | PRO-01 | Requisitions and technical bid evaluations | 1 Concept | blocked | MEC-02 at 1, PRJ-05 at 1 | PRJ-05 at 1
FEL3 | 9 | SAF-01 | Preliminary HAZOP | 2 Preliminary | done | PRC-08 at 2, PRC-04 at 2, PRC-03 at 2
FEL3 | 9 | SAF-04 | Siting study, QRA, F&G mapping | 1 Concept | ready | LAY-01 at 1, SAF-01 at 1, ELE-02 at 1
FEL3 | 9 | SEL-03 | Utility and offsite basis | 3 Defined | blocked | PRJ-01 at 3, PRC-01 at 3 | PRC-01 at 3
FEL3 | 10 | CON-02 | Work packaging and system boundaries | 1 Concept | blocked | CON-01 at 1, PRC-08 at 1, PIP-04 at 1 | CON-01 at 1
FEL3 | 10 | ELE-01 | Electrical load list | 3 Defined | done | PRC-02 at 3
FEL3 | 10 | ICS-02 | SIF list and SIL determination (LOPA) | 2 Preliminary | ready | PRC-04 at 2, SAF-01 at 2
FEL3 | 10 | ICS-03 | Cause and effect matrix | 1 Concept | done | PRC-04 at 1, PRC-03 at 1, PRC-02 at 1, ICS-02 at 1
FEL3 | 10 | ICS-07 | ICS architecture | 2 Preliminary | done | ICS-05 at 2, ELE-03 at 2
FEL3 | 10 | PIP-03 | Pipe stress and supports (screening) | 2 Preliminary | ready | PIP-02 at 2, MEC-01 at 2
FEL3 | 10 | PIP-04 | Isometrics and piping MTO | 2 Preliminary | done | PIP-02 at 2, PIP-01 at 2
FEL3 | 10 | PRC-03 | Relief load and PSV sizing (unit) | 3 Defined | done | PRC-01 at 3, PRC-02 at 3 | PRC-01 at 3
FEL3 | 10 | PRC-04 | Control loops and SIF definition | 3 Defined | done | PRC-01 at 3, PRC-02 at 3 | PRC-01 at 3
FEL3 | 10 | PRO-01 | Requisitions and technical bid evaluations | 2 Preliminary | blocked | MEC-02 at 2, PRJ-05 at 2 | PRJ-05 at 2, PRO-01 at 1
FEL3 | 10 | SAF-01 | Preliminary HAZOP | 3 Defined | done | PRC-08 at 2, PRC-04 at 2, PRC-03 at 2
FEL3 | 10 | SAF-04 | Siting study, QRA, F&G mapping | 2 Preliminary | blocked | LAY-01 at 2, SAF-01 at 2, ELE-02 at 2 | SAF-04 at 1
FEL3 | 10 | VEN-01 | Vendor enquiries and vendor data | 1 Concept | blocked | MEC-02 at 1, PRO-01 at 1 | PRO-01 at 1
FEL3 | 11 | CIV-01 | Geotechnical, civil and structural design | 2 Preliminary | blocked | LAY-01 at 2, MEC-01 at 2, PIP-03 at 2 | PIP-03 at 2, CIV-01 at 1
FEL3 | 11 | CST-02 | Class 3 cost estimate | 1 Concept | blocked | CST-01 at 1, VEN-01 at 1, PIP-04 at 1, ELE-04 at 1, CIV-01 at 1 | VEN-01 at 1, CIV-01 at 1
FEL3 | 11 | ELE-03 | Electrical sizing, single-line diagrams | 3 Defined | done | ELE-01 at 3
FEL3 | 11 | ELE-05 | Power system studies and protection | 1 Concept | blocked | ELE-03 at 1, VEN-01 at 1 | VEN-01 at 1
FEL3 | 11 | ICS-01 | Control philosophy and schemes | 3 Defined | done | PRC-04 at 3, PRC-01 at 3, PRC-02 at 3 | PRC-01 at 3
FEL3 | 11 | ICS-03 | Cause and effect matrix | 2 Preliminary | done | PRC-04 at 2, PRC-03 at 2, PRC-02 at 2, ICS-02 at 2 | ICS-02 at 2
FEL3 | 11 | MEC-01 | Mechanical design calculations | 3 Defined | done | PRC-02 at 3, PRC-01 at 3, PRC-03 at 3 | PRC-01 at 3
FEL3 | 11 | PIP-05 | Detailed pipe stress (CAESAR II) | 1 Concept | blocked | PIP-03 at 1, VEN-01 at 1 | VEN-01 at 1
FEL3 | 11 | PRC-06 | Process flow diagrams | 3 Defined | done | PRC-01 at 3, PRC-02 at 3, PRC-04 at 3 | PRC-01 at 3
FEL3 | 11 | PRC-07 | Process design report | 3 Defined | done | PRC-01 at 3, PRC-02 at 3, PRC-03 at 3 | PRC-01 at 3
FEL3 | 11 | SAF-01 | Preliminary HAZOP | 4 Final | done | PRC-08 at 2, PRC-04 at 2, PRC-03 at 2
FEL3 | 11 | SAF-02 | Global flare load study | 3 Defined | blocked | PRC-03 at 3 | SAF-02 at 2
FEL3 | 11 | SAF-04 | Siting study, QRA, F&G mapping | 3 Defined | blocked | LAY-01 at 2, SAF-01 at 2, ELE-02 at 2 | SAF-04 at 2
FEL3 | 11 | VEN-01 | Vendor enquiries and vendor data | 2 Preliminary | blocked | MEC-02 at 2, PRO-01 at 2 | PRO-01 at 2, VEN-01 at 1
FEL3 | 12 | CST-02 | Class 3 cost estimate | 2 Preliminary | blocked | CST-01 at 2, VEN-01 at 2, PIP-04 at 2, ELE-04 at 2, CIV-01 at 2 | VEN-01 at 2, CIV-01 at 2, CST-02 at 1
FEL3 | 12 | ICS-07 | ICS architecture | 3 Defined | done | ICS-05 at 2, ELE-03 at 3
FEL3 | 12 | LAY-03 | 3D model reviews and constructability | 2 Preliminary | blocked | PIP-02 at 2, LAY-02 at 2, CIV-01 at 2 | CIV-01 at 2, LAY-03 at 1
FEL3 | 12 | MEC-02 | Equipment datasheets | 3 Defined | done | MEC-01 at 3, PRC-02 at 3, PRC-03 at 3
FEL3 | 12 | PRC-07 | Process design report | 4 Final | done | PRC-01 at 3, PRC-02 at 3, PRC-03 at 3 | PRC-01 at 3
FEL3 | 12 | SAF-04 | Siting study, QRA, F&G mapping | 4 Final | blocked | LAY-01 at 2, SAF-01 at 2, ELE-02 at 2 | SAF-04 at 3
FEL3 | 13 | CST-02 | Class 3 cost estimate | 3 Defined | blocked | CST-01 at 2, VEN-01 at 2, PIP-04 at 2, ELE-04 at 2, CIV-01 at 2 | VEN-01 at 2, CIV-01 at 2, CST-02 at 2
FEL3 | 13 | LAY-01 | Plot plan and equipment layout | 3 Defined | done | PRC-02 at 3, PRC-01 at 3, PRJ-01 at 3, FEL-03 at 3, MEC-01 at 2, SAF-04 at 4 | PRC-01 at 3, SAF-04 at 4
FEL3 | 13 | PRO-01 | Requisitions and technical bid evaluations | 3 Defined | blocked | MEC-02 at 3, PRJ-05 at 3 | PRJ-05 at 3, PRO-01 at 2
FEL3 | 14 | CST-02 | Class 3 cost estimate | 4 Final | blocked | CST-01 at 2, VEN-01 at 2, PIP-04 at 2, ELE-04 at 2, CIV-01 at 2 | VEN-01 at 2, CIV-01 at 2, CST-02 at 3
FEL3 | 14 | ELE-02 | Hazardous area classification | 3 Defined | done | LAY-01 at 3, PRC-02 at 3, PRC-04 at 3
FEL3 | 14 | LAY-02 | Sections and 3D layout model | 3 Defined | done | LAY-01 at 3, PRC-02 at 3
FEL3 | 14 | PRC-08 | P&IDs, line list, instrument index | 3 Defined | done | PRC-02 at 3, PRC-03 at 3, PRC-04 at 3, PRC-06 at 3, PIP-01 at 3, LAY-01 at 3, SAF-01 at 4
FEL3 | 14 | SEL-04 | Permitting and environmental basis | 3 Defined | blocked | PRC-01 at 3, LAY-01 at 3 | PRC-01 at 3, SEL-04 at 2
FEL3 | 15 | CON-01 | Constructability, modularisation and path of construction | 3 Defined | blocked | LAY-01 at 3, LAY-02 at 3, PRJ-05 at 3 | PRJ-05 at 3, CON-01 at 2
DD | 9 | ELE-06 | Electrical layouts | 1 Concept | ready | ELE-04 at 1, LAY-02 at 1, PIP-02 at 1
DD | 9 | PRC-01 | Heat and material balance | 4 Final | blocked | PRJ-01 at 4, PRJ-02 at 4, PRC-00 at 4, SEL-01 at 4 | PRJ-02 at 4, PRC-00 at 4, PRC-01 at 3
DD | 10 | ELE-06 | Electrical layouts | 2 Preliminary | blocked | ELE-04 at 2, LAY-02 at 2, PIP-02 at 2 | ELE-06 at 1
DD | 10 | ICS-06 | Loop diagrams | 2 Preliminary | ready | ICS-05 at 2
DD | 10 | PIP-01 | Piping material classes | 4 Final | blocked | PRJ-01 at 4, PRC-01 at 4 | PRC-01 at 4
DD | 10 | SAF-03 | Formal HAZOP and LOPA workshop | 1 Concept | ready | PRC-08 at 1, SAF-01 at 1, ICS-02 at 1
DD | 10 | SEL-03 | Utility and offsite basis | 4 Final | blocked | PRJ-01 at 4, PRC-01 at 4 | PRC-01 at 4, SEL-03 at 3
DD | 11 | CON-02 | Work packaging and system boundaries | 2 Preliminary | blocked | CON-01 at 2, PRC-08 at 2, PIP-04 at 2 | CON-01 at 2, CON-02 at 1
DD | 11 | ICS-02 | SIF list and SIL determination (LOPA) | 3 Defined | blocked | PRC-04 at 3, SAF-01 at 3 | ICS-02 at 2
DD | 11 | ICS-08 | SIL verification and SRS | 1 Concept | blocked | ICS-02 at 1, SAF-03 at 1, VEN-01 at 1 | SAF-03 at 1, VEN-01 at 1
DD | 11 | ICS-09 | Instrument installation design | 1 Concept | blocked | ICS-05 at 1, PIP-02 at 1, VEN-01 at 1 | VEN-01 at 1
DD | 11 | SAF-03 | Formal HAZOP and LOPA workshop | 2 Preliminary | blocked | PRC-08 at 2, SAF-01 at 2, ICS-02 at 2 | ICS-02 at 2, SAF-03 at 1
DD | 12 | CIV-02 | Foundation and structural steel detailing | 1 Concept | blocked | CIV-01 at 1, VEN-01 at 1, PIP-05 at 1 | CIV-01 at 1, VEN-01 at 1, PIP-05 at 1
DD | 12 | CST-03 | Control estimate | 1 Concept | blocked | CST-02 at 1, PRO-01 at 1, PIP-04 at 1, CIV-01 at 1 | CST-02 at 1, PRO-01 at 1, CIV-01 at 1
DD | 12 | ELE-05 | Power system studies and protection | 2 Preliminary | blocked | ELE-03 at 2, VEN-01 at 2 | VEN-01 at 2, ELE-05 at 1
DD | 12 | ICS-03 | Cause and effect matrix | 3 Defined | blocked | PRC-04 at 3, PRC-03 at 3, PRC-02 at 3, ICS-02 at 3 | ICS-02 at 3
DD | 12 | ICS-08 | SIL verification and SRS | 2 Preliminary | blocked | ICS-02 at 2, SAF-03 at 2, VEN-01 at 2 | ICS-02 at 2, SAF-03 at 2, VEN-01 at 2, ICS-08 at 1
DD | 12 | ICS-09 | Instrument installation design | 2 Preliminary | blocked | ICS-05 at 2, PIP-02 at 2, VEN-01 at 2 | VEN-01 at 2, ICS-09 at 1
DD | 12 | MEC-03 | Equipment GA drawings | 3 Defined | ready | MEC-01 at 3
DD | 12 | PIP-05 | Detailed pipe stress (CAESAR II) | 2 Preliminary | blocked | PIP-03 at 2, VEN-01 at 2 | PIP-03 at 2, VEN-01 at 2, PIP-05 at 1
DD | 13 | CIV-02 | Foundation and structural steel detailing | 2 Preliminary | blocked | CIV-01 at 2, VEN-01 at 2, PIP-05 at 2 | CIV-01 at 2, VEN-01 at 2, PIP-05 at 2, CIV-02 at 1
DD | 13 | CST-03 | Control estimate | 2 Preliminary | blocked | CST-02 at 2, PRO-01 at 2, PIP-04 at 2, CIV-01 at 2 | CST-02 at 2, PRO-01 at 2, CIV-01 at 2, CST-03 at 1
DD | 13 | PRJ-04 | PE review, seal and IFC issue | 1 Concept | blocked | PRJ-03 at 1, SAF-03 at 1, ICS-08 at 1, PIP-05 at 1, ELE-05 at 1, CST-02 at 1, LAY-03 at 1, SAF-04 at 1, SAF-02 at 1, CIV-02 at 1, ICS-09 at 1, ELE-06 at 1, CON-02 at 1, PRO-01 at 1 | SAF-03 at 1, ICS-08 at 1, PIP-05 at 1, ELE-05 at 1, CST-02 at 1, LAY-03 at 1, SAF-04 at 1, SAF-02 at 1, CIV-02 at 1, ICS-09 at 1, ELE-06 at 1, CON-02 at 1, PRO-01 at 1
DD | 14 | PRJ-04 | PE review, seal and IFC issue | 2 Preliminary | blocked | PRJ-03 at 2, SAF-03 at 2, ICS-08 at 2, PIP-05 at 2, ELE-05 at 2, CST-02 at 2, LAY-03 at 2, SAF-04 at 2, SAF-02 at 2, CIV-02 at 2, ICS-09 at 2, ELE-06 at 2, CON-02 at 2, PRO-01 at 2 | SAF-03 at 2, ICS-08 at 2, PIP-05 at 2, ELE-05 at 2, CST-02 at 2, LAY-03 at 2, SAF-04 at 2, SAF-02 at 2, CIV-02 at 2, ICS-09 at 2, ELE-06 at 2, CON-02 at 2, PRO-01 at 2, PRJ-04 at 1
DD | 14 | VEN-01 | Vendor enquiries and vendor data | 3 Defined | blocked | MEC-02 at 3, PRO-01 at 3 | PRO-01 at 3, VEN-01 at 2
DD | 15 | ELE-04 | Cable schedule | 3 Defined | ready | ELE-01 at 3, ELE-03 at 3, LAY-01 at 3, ELE-02 at 3
DD | 15 | ELE-05 | Power system studies and protection | 3 Defined | blocked | ELE-03 at 3, VEN-01 at 3 | VEN-01 at 3, ELE-05 at 2
DD | 15 | ICS-04 | Control valve sizing | 3 Defined | blocked | PRC-01 at 3, PRC-02 at 3, PRC-04 at 3, PRC-08 at 3 | PRC-01 at 3
DD | 15 | ICS-05 | I/O list | 3 Defined | ready | PRC-08 at 3, PRC-04 at 3, PRC-02 at 3, LAY-01 at 3
DD | 15 | PIP-02 | Piping routing and 3D model | 3 Defined | ready | PRC-08 at 3, LAY-01 at 3, PRC-03 at 3, MEC-01 at 3
DD | 15 | SAF-03 | Formal HAZOP and LOPA workshop | 3 Defined | blocked | PRC-08 at 3, SAF-01 at 3, ICS-02 at 3 | ICS-02 at 3, SAF-03 at 2
DD | 15 | VEN-01 | Vendor enquiries and vendor data | 4 Final | blocked | MEC-02 at 3, PRO-01 at 3 | PRO-01 at 3, VEN-01 at 3
DD | 16 | ELE-06 | Electrical layouts | 3 Defined | blocked | ELE-04 at 3, LAY-02 at 3, PIP-02 at 3 | ELE-04 at 3, PIP-02 at 3, ELE-06 at 2
DD | 16 | ICS-06 | Loop diagrams | 3 Defined | blocked | ICS-05 at 3 | ICS-05 at 3, ICS-06 at 2
DD | 16 | ICS-08 | SIL verification and SRS | 3 Defined | blocked | ICS-02 at 3, SAF-03 at 3, VEN-01 at 3 | ICS-02 at 3, SAF-03 at 3, VEN-01 at 3, ICS-08 at 2
DD | 16 | ICS-09 | Instrument installation design | 3 Defined | blocked | ICS-05 at 3, PIP-02 at 3, VEN-01 at 3 | ICS-05 at 3, PIP-02 at 3, VEN-01 at 3, ICS-09 at 2
DD | 16 | PIP-03 | Pipe stress and supports (screening) | 3 Defined | blocked | PIP-02 at 3, MEC-01 at 3 | PIP-02 at 3, PIP-03 at 2
DD | 16 | PIP-04 | Isometrics and piping MTO | 3 Defined | blocked | PIP-02 at 3, PIP-01 at 3 | PIP-02 at 3
DD | 16 | PRC-02 | Process equipment sizing | 4 Final | blocked | PRC-01 at 4, MEC-01 at 2, PIP-02 at 3 | PRC-01 at 4, PIP-02 at 3
DD | 16 | SAF-03 | Formal HAZOP and LOPA workshop | 4 Final | blocked | PRC-08 at 3, SAF-01 at 3, ICS-02 at 3 | ICS-02 at 3, SAF-03 at 3
DD | 17 | CIV-01 | Geotechnical, civil and structural design | 3 Defined | blocked | LAY-01 at 3, MEC-01 at 3, PIP-03 at 3 | PIP-03 at 3, CIV-01 at 2
DD | 17 | CON-02 | Work packaging and system boundaries | 3 Defined | blocked | CON-01 at 3, PRC-08 at 3, PIP-04 at 3 | CON-01 at 3, PIP-04 at 3, CON-02 at 2
DD | 17 | ELE-01 | Electrical load list | 4 Final | blocked | PRC-02 at 4, ICS-07 at 3, VEN-01 at 4 | PRC-02 at 4, VEN-01 at 4
DD | 17 | LAY-01 | Plot plan and equipment layout | 4 Final | blocked | PRC-02 at 4, PRC-01 at 4, PRJ-01 at 4, FEL-03 at 4, MEC-01 at 2, PIP-02 at 3, SAF-04 at 4, VEN-01 at 4 | PRC-02 at 4, PRC-01 at 4, PIP-02 at 3, SAF-04 at 4, VEN-01 at 4
DD | 17 | PIP-05 | Detailed pipe stress (CAESAR II) | 3 Defined | blocked | PIP-03 at 3, VEN-01 at 3 | PIP-03 at 3, VEN-01 at 3, PIP-05 at 2
DD | 17 | PRC-03 | Relief load and PSV sizing (unit) | 4 Final | blocked | PRC-01 at 4, PRC-02 at 4, SAF-02 at 3 | PRC-01 at 4, PRC-02 at 4, SAF-02 at 3
DD | 17 | PRC-04 | Control loops and SIF definition | 4 Final | blocked | PRC-01 at 4, PRC-02 at 4 | PRC-01 at 4, PRC-02 at 4
DD | 18 | CIV-02 | Foundation and structural steel detailing | 3 Defined | blocked | CIV-01 at 3, VEN-01 at 3, PIP-05 at 3 | CIV-01 at 3, VEN-01 at 3, PIP-05 at 3, CIV-02 at 2
DD | 18 | CST-03 | Control estimate | 3 Defined | blocked | CST-02 at 3, PRO-01 at 3, PIP-04 at 3, CIV-01 at 3 | CST-02 at 3, PRO-01 at 3, PIP-04 at 3, CIV-01 at 3, CST-03 at 2
DD | 18 | ELE-02 | Hazardous area classification | 4 Final | blocked | LAY-01 at 4, PRC-02 at 4, PRC-04 at 4 | LAY-01 at 4, PRC-02 at 4, PRC-04 at 4
DD | 18 | ELE-03 | Electrical sizing, single-line diagrams | 4 Final | blocked | ELE-01 at 4, ELE-04 at 3 | ELE-01 at 4, ELE-04 at 3
DD | 18 | ICS-01 | Control philosophy and schemes | 4 Final | blocked | PRC-04 at 4, PRC-01 at 4, PRC-02 at 4 | PRC-04 at 4, PRC-01 at 4, PRC-02 at 4
DD | 18 | ICS-02 | SIF list and SIL determination (LOPA) | 4 Final | blocked | PRC-04 at 4, SAF-01 at 4 | PRC-04 at 4, ICS-02 at 3
DD | 18 | LAY-02 | Sections and 3D layout model | 4 Final | blocked | LAY-01 at 4, PRC-02 at 4 | LAY-01 at 4, PRC-02 at 4
DD | 18 | LAY-03 | 3D model reviews and constructability | 3 Defined | blocked | PIP-02 at 3, LAY-02 at 3, CIV-01 at 3 | PIP-02 at 3, CIV-01 at 3, LAY-03 at 2
DD | 18 | MEC-01 | Mechanical design calculations | 4 Final | blocked | PRC-02 at 4, PRC-01 at 4, PRC-03 at 4, VEN-01 at 4 | PRC-02 at 4, PRC-01 at 4, PRC-03 at 4, VEN-01 at 4
DD | 18 | PRC-06 | Process flow diagrams | 4 Final | blocked | PRC-01 at 4, PRC-02 at 4, PRC-04 at 4 | PRC-01 at 4, PRC-02 at 4, PRC-04 at 4
DD | 18 | SAF-02 | Global flare load study | 4 Final | blocked | PRC-03 at 4 | PRC-03 at 4, SAF-02 at 3
DD | 18 | SEL-04 | Permitting and environmental basis | 4 Final | blocked | PRC-01 at 4, LAY-01 at 4 | PRC-01 at 4, LAY-01 at 4, SEL-04 at 3
DD | 19 | CON-01 | Constructability, modularisation and path of construction | 4 Final | blocked | LAY-01 at 4, LAY-02 at 4, PRJ-05 at 4 | LAY-01 at 4, LAY-02 at 4, PRJ-05 at 4, CON-01 at 3
DD | 19 | CST-03 | Control estimate | 4 Final | blocked | CST-02 at 3, PRO-01 at 3, PIP-04 at 3, CIV-01 at 3 | CST-02 at 3, PRO-01 at 3, PIP-04 at 3, CIV-01 at 3, CST-03 at 3
DD | 19 | ELE-04 | Cable schedule | 4 Final | blocked | ELE-01 at 4, ELE-03 at 4, LAY-01 at 4, ELE-02 at 4 | ELE-01 at 4, ELE-03 at 4, LAY-01 at 4, ELE-02 at 4, ELE-04 at 3
DD | 19 | ELE-05 | Power system studies and protection | 4 Final | blocked | ELE-03 at 4, VEN-01 at 4 | ELE-03 at 4, VEN-01 at 4, ELE-05 at 3
DD | 19 | ICS-03 | Cause and effect matrix | 4 Final | blocked | PRC-04 at 4, PRC-03 at 4, PRC-02 at 4, ICS-02 at 4 | PRC-04 at 4, PRC-03 at 4, PRC-02 at 4, ICS-02 at 4, ICS-03 at 3
DD | 19 | ICS-08 | SIL verification and SRS | 4 Final | blocked | ICS-02 at 4, SAF-03 at 4, VEN-01 at 4 | ICS-02 at 4, SAF-03 at 4, VEN-01 at 4, ICS-08 at 3
DD | 19 | MEC-02 | Equipment datasheets | 4 Final | blocked | MEC-01 at 4, PRC-02 at 4, PRC-03 at 4 | MEC-01 at 4, PRC-02 at 4, PRC-03 at 4
DD | 19 | MEC-03 | Equipment GA drawings | 4 Final | blocked | MEC-01 at 4 | MEC-01 at 4, MEC-03 at 3
DD | 19 | PRC-08 | P&IDs, line list, instrument index | 4 Final | blocked | PRC-02 at 4, PRC-03 at 4, PRC-04 at 4, PRC-06 at 4, PIP-01 at 4, LAY-01 at 4, ICS-04 at 3, SAF-01 at 4, SAF-03 at 4 | PRC-02 at 4, PRC-03 at 4, PRC-04 at 4, PRC-06 at 4, PIP-01 at 4, LAY-01 at 4, ICS-04 at 3, SAF-03 at 4
DD | 19 | PRJ-04 | PE review, seal and IFC issue | 3 Defined | blocked | PRJ-03 at 3, SAF-03 at 3, ICS-08 at 3, PIP-05 at 3, ELE-05 at 3, CST-02 at 3, LAY-03 at 3, SAF-04 at 3, SAF-02 at 3, CIV-02 at 3, ICS-09 at 3, ELE-06 at 3, CON-02 at 3, PRO-01 at 3 | SAF-03 at 3, ICS-08 at 3, PIP-05 at 3, ELE-05 at 3, CST-02 at 3, LAY-03 at 3, SAF-04 at 3, SAF-02 at 3, CIV-02 at 3, ICS-09 at 3, ELE-06 at 3, CON-02 at 3, PRO-01 at 3, PRJ-04 at 2
DD | 20 | ICS-04 | Control valve sizing | 4 Final | blocked | PRC-01 at 4, PRC-02 at 4, PRC-04 at 4, PRC-08 at 4 | PRC-01 at 4, PRC-02 at 4, PRC-04 at 4, PRC-08 at 4, ICS-04 at 3
DD | 20 | ICS-05 | I/O list | 4 Final | blocked | PRC-08 at 4, PRC-04 at 4, PRC-02 at 4, LAY-01 at 4, VEN-01 at 4 | PRC-08 at 4, PRC-04 at 4, PRC-02 at 4, LAY-01 at 4, VEN-01 at 4, ICS-05 at 3
DD | 20 | PIP-02 | Piping routing and 3D model | 4 Final | blocked | PRC-08 at 4, LAY-01 at 4, PRC-03 at 4, MEC-01 at 4 | PRC-08 at 4, LAY-01 at 4, PRC-03 at 4, MEC-01 at 4, PIP-02 at 3
DD | 20 | PRO-01 | Requisitions and technical bid evaluations | 4 Final | blocked | MEC-02 at 4, PRJ-05 at 4 | MEC-02 at 4, PRJ-05 at 4, PRO-01 at 3
DD | 21 | ELE-06 | Electrical layouts | 4 Final | blocked | ELE-04 at 4, LAY-02 at 4, PIP-02 at 4 | ELE-04 at 4, LAY-02 at 4, PIP-02 at 4, ELE-06 at 3
DD | 21 | ICS-06 | Loop diagrams | 4 Final | blocked | ICS-05 at 4 | ICS-05 at 4, ICS-06 at 3
DD | 21 | ICS-07 | ICS architecture | 4 Final | blocked | ICS-05 at 4, ELE-03 at 4 | ICS-05 at 4, ELE-03 at 4
DD | 21 | ICS-09 | Instrument installation design | 4 Final | blocked | ICS-05 at 4, PIP-02 at 4, VEN-01 at 4 | ICS-05 at 4, PIP-02 at 4, VEN-01 at 4, ICS-09 at 3
DD | 21 | PIP-03 | Pipe stress and supports (screening) | 4 Final | blocked | PIP-02 at 4, MEC-01 at 4 | PIP-02 at 4, MEC-01 at 4, PIP-03 at 3
DD | 21 | PIP-04 | Isometrics and piping MTO | 4 Final | blocked | PIP-02 at 4, PIP-01 at 4 | PIP-02 at 4, PIP-01 at 4, PIP-04 at 3
DD | 22 | CIV-01 | Geotechnical, civil and structural design | 4 Final | blocked | LAY-01 at 4, MEC-01 at 4, PIP-03 at 4 | LAY-01 at 4, MEC-01 at 4, PIP-03 at 4, CIV-01 at 3
DD | 22 | CON-02 | Work packaging and system boundaries | 4 Final | blocked | CON-01 at 4, PRC-08 at 4, PIP-04 at 4 | CON-01 at 4, PRC-08 at 4, PIP-04 at 4, CON-02 at 3
DD | 22 | PIP-05 | Detailed pipe stress (CAESAR II) | 4 Final | blocked | PIP-03 at 4, VEN-01 at 4 | PIP-03 at 4, VEN-01 at 4, PIP-05 at 3
DD | 22 | PRJ-03 | Document register and portal | 4 Final | blocked | CST-01 at 4, SAF-01 at 4, PIP-04 at 4, ICS-06 at 4, ICS-07 at 4, ELE-04 at 4, MEC-03 at 4, LAY-02 at 4, PRC-05 at 4, PRC-07 at 4, ICS-01 at 4, ICS-03 at 4, ICS-04 at 4, MEC-02 at 4, PIP-03 at 4 | PIP-04 at 4, ICS-06 at 4, ICS-07 at 4, ELE-04 at 4, MEC-03 at 4, LAY-02 at 4, ICS-01 at 4, ICS-03 at 4, ICS-04 at 4, MEC-02 at 4, PIP-03 at 4
DD | 23 | CIV-02 | Foundation and structural steel detailing | 4 Final | blocked | CIV-01 at 4, VEN-01 at 4, PIP-05 at 4 | CIV-01 at 4, VEN-01 at 4, PIP-05 at 4, CIV-02 at 3
DD | 23 | LAY-03 | 3D model reviews and constructability | 4 Final | blocked | PIP-02 at 4, LAY-02 at 4, CIV-01 at 4 | PIP-02 at 4, LAY-02 at 4, CIV-01 at 4, LAY-03 at 3
DD | 24 | PRJ-04 | PE review, seal and IFC issue | 4 Final | blocked | PRJ-03 at 4, SAF-03 at 4, ICS-08 at 4, PIP-05 at 4, ELE-05 at 4, CST-02 at 4, LAY-03 at 4, SAF-04 at 4, SAF-02 at 4, CIV-02 at 4, ICS-09 at 4, ELE-06 at 4, CON-02 at 4, PRO-01 at 4 | PRJ-03 at 4, SAF-03 at 4, ICS-08 at 4, PIP-05 at 4, ELE-05 at 4, CST-02 at 4, LAY-03 at 4, SAF-04 at 4, SAF-02 at 4, CIV-02 at 4, ICS-09 at 4, ELE-06 at 4, CON-02 at 4, PRO-01 at 4, PRJ-04 at 3

## Link maturity
From | To | Type | What flows | To at 1 | To at 2 | To at 3 | To at 4
PRJ-01 | PRJ-02 | input | crude slate, design and check crudes | 1 | 2 | 3 | 4
PRJ-02 | PRC-00 | input | lab assay pseudo-components | 1 | 2 | 3 | 4
PRJ-01 | PRC-01 | input | capacity, product specs, utility conditions | 1 | 2 | 3 | 4
PRJ-02 | PRC-01 | input | pseudo-components | 1 | 2 | 3 | 4
PRC-00 | PRC-01 | input | calibrated cut points and efficiencies | 0 | 1 | 3 | 4
PRC-01 | PRC-02 | input | flows, duties, column vapour/liquid loads | 1 | 2 | 3 | 4
PRC-01 | PRC-03 | input | relief compositions and rates | 1 | 2 | 3 | 4
PRC-02 | PRC-03 | input | design pressures, wetted areas | 1 | 2 | 3 | 4
PRC-01 | PRC-04 | input | operating points | 1 | 2 | 3 | 4
PRC-02 | PRC-04 | input | equipment and instrument ranges | 1 | 2 | 3 | 4
PRC-01 | PRC-05 | input | unit yields | 1 | 2 | 2 | 2
PRC-01 | PRC-06 | input | stream table | 1 | 2 | 3 | 4
PRC-02 | PRC-06 | input | equipment data | 1 | 2 | 3 | 4
PRC-04 | PRC-06 | input | principal control loops | 0 | 1 | 3 | 4
PRC-01 | PRC-07 | input | H&MB | 1 | 2 | 3 | 3
PRC-02 | PRC-07 | input | sizing results | 1 | 2 | 3 | 3
PRC-03 | PRC-07 | input | relief summary | 1 | 2 | 3 | 3
PRJ-01 | PIP-01 | input | codes, corrosion basis | 1 | 2 | 3 | 4
PRC-01 | PIP-01 | input | design T/P, sulphur and acid corrosion | 1 | 2 | 3 | 4
PRC-02 | PRC-08 | input | equipment and design conditions | 1 | 2 | 3 | 4
PRC-03 | PRC-08 | input | PSV tags and sizes | 1 | 2 | 3 | 4
PRC-04 | PRC-08 | input | control loops and SIFs | 1 | 2 | 3 | 4
PRC-06 | PRC-08 | input | PFD topology | 1 | 2 | 3 | 4
PIP-01 | PRC-08 | input | piping classes | 1 | 2 | 3 | 4
LAY-01 | PRC-08 | input | fire and gas detector locations | 1 | 2 | 3 | 4
PRC-08 | SAF-01 | input | P&IDs | 1 | 2 | 2 | 2
PRC-04 | SAF-01 | input | SIFs | 1 | 2 | 2 | 2
PRC-03 | SAF-01 | input | relief devices | 1 | 2 | 2 | 2
PRC-03 | SAF-02 | input | unit relief loads | 1 | 2 | 3 | 4
PRC-08 | SAF-03 | input | IFD P&IDs | 1 | 2 | 3 | 3
SAF-01 | SAF-03 | input | preliminary findings | 1 | 2 | 3 | 3
ICS-02 | SAF-03 | input | draft SIL targets | 1 | 2 | 3 | 3
LAY-01 | SAF-04 | input | plot plan | 1 | 2 | 2 | 2
SAF-01 | SAF-04 | input | major hazards | 1 | 2 | 2 | 2
ELE-02 | SAF-04 | input | release sources | 1 | 2 | 2 | 2
PRC-02 | MEC-01 | input | design P/T, dimensions, internals | 1 | 2 | 3 | 4
PRC-01 | MEC-01 | input | nozzle flows | 1 | 2 | 3 | 4
PRC-03 | MEC-01 | input | PSV set points | 1 | 2 | 3 | 4
MEC-01 | MEC-02 | input | thicknesses, weights, nozzles | 1 | 2 | 3 | 4
PRC-02 | MEC-02 | input | process data | 1 | 2 | 3 | 4
PRC-03 | MEC-02 | input | PSV data | 1 | 2 | 3 | 4
MEC-01 | MEC-03 | input | geometry, nozzle schedule | 1 | 2 | 3 | 4
MEC-02 | VEN-01 | input | datasheets for enquiry | 1 | 2 | 3 | 3
PRC-02 | LAY-01 | input | equipment list and footprints | 1 | 2 | 3 | 4
PRC-01 | LAY-01 | input | hazard inventory, heater duties | 1 | 2 | 3 | 4
PRJ-01 | LAY-01 | input | site, spacing standards | 1 | 2 | 3 | 4
LAY-01 | LAY-02 | input | equipment positions, structures | 1 | 2 | 3 | 4
PRC-02 | LAY-02 | input | equipment heights | 1 | 2 | 3 | 4
PIP-02 | LAY-03 | input | routed model | 1 | 2 | 3 | 4
LAY-02 | LAY-03 | input | layout model | 1 | 2 | 3 | 4
CIV-01 | LAY-03 | input | structures | 1 | 2 | 3 | 4
PRC-08 | PIP-02 | input | line list, in-line instruments | 1 | 2 | 3 | 4
LAY-01 | PIP-02 | input | nozzle positions, pipe rack | 1 | 2 | 3 | 4
PRC-03 | PIP-02 | input | PSV inlet/outlet | 1 | 2 | 3 | 4
MEC-01 | PIP-02 | input | nozzle sizes, weights | 1 | 2 | 3 | 4
PIP-02 | PIP-03 | input | routed geometry | 1 | 2 | 3 | 4
MEC-01 | PIP-03 | input | nozzle allowables | 1 | 2 | 3 | 4
PIP-02 | PIP-04 | input | routed geometry | 1 | 2 | 3 | 4
PIP-01 | PIP-04 | input | piping classes | 1 | 2 | 3 | 4
PIP-03 | PIP-05 | input | critical line list | 1 | 2 | 3 | 4
VEN-01 | PIP-05 | input | certified nozzle allowables | 1 | 2 | 3 | 4
LAY-01 | CIV-01 | input | plot plan | 1 | 2 | 3 | 4
MEC-01 | CIV-01 | input | operating and test weights | 1 | 2 | 3 | 4
PIP-03 | CIV-01 | input | support loads | 0 | 2 | 3 | 4
PRC-04 | ICS-01 | input | loops and SIFs | 1 | 2 | 3 | 4
PRC-01 | ICS-01 | input | operating points | 1 | 2 | 3 | 4
PRC-02 | ICS-01 | input | equipment | 1 | 2 | 3 | 4
PRC-04 | ICS-02 | input | SIF definitions | 1 | 2 | 3 | 4
SAF-01 | ICS-02 | input | hazard scenarios | 1 | 2 | 3 | 4
PRC-04 | ICS-03 | input | SIFs | 1 | 2 | 3 | 4
PRC-03 | ICS-03 | input | relief devices | 1 | 2 | 3 | 4
PRC-02 | ICS-03 | input | equipment | 1 | 2 | 3 | 4
ICS-02 | ICS-03 | input | SIL targets | 1 | 2 | 3 | 4
PRC-01 | ICS-04 | input | flows, densities | 1 | 2 | 3 | 4
PRC-02 | ICS-04 | input | pump curves | 1 | 2 | 3 | 4
PRC-04 | ICS-04 | input | valve tags | 1 | 2 | 3 | 4
PRC-08 | ICS-04 | input | line sizes | 1 | 2 | 3 | 4
PRC-08 | ICS-05 | input | instrument index | 1 | 2 | 3 | 4
PRC-04 | ICS-05 | input | loops and SIFs | 1 | 2 | 3 | 4
PRC-02 | ICS-05 | input | motor drivers | 1 | 2 | 3 | 4
LAY-01 | ICS-05 | input | junction-box zones | 1 | 2 | 3 | 4
ICS-05 | ICS-06 | input | terminations, cabinets | 1 | 2 | 3 | 4
ICS-05 | ICS-07 | input | I/O counts | 0 | 2 | 2 | 4
ELE-03 | ICS-07 | input | UPS feeds | 1 | 2 | 3 | 4
ICS-02 | ICS-08 | input | SIL targets | 1 | 2 | 3 | 4
SAF-03 | ICS-08 | input | validated LOPA | 1 | 2 | 3 | 4
VEN-01 | ICS-08 | input | device failure data | 1 | 2 | 3 | 4
PRC-02 | ELE-01 | input | motor ratings, absorbed power | 1 | 2 | 3 | 4
LAY-01 | ELE-02 | input | release-source positions | 1 | 2 | 3 | 4
PRC-02 | ELE-02 | input | fluids and conditions | 1 | 2 | 3 | 4
PRC-04 | ELE-02 | input | analysers and vents | 1 | 2 | 3 | 4
ELE-01 | ELE-03 | input | loads and demand | 1 | 2 | 3 | 4
ELE-01 | ELE-04 | input | loads | 1 | 2 | 3 | 4
ELE-03 | ELE-04 | input | feeders | 1 | 2 | 3 | 4
LAY-01 | ELE-04 | input | routes | 1 | 2 | 3 | 4
ELE-02 | ELE-04 | input | zone ratings | 1 | 2 | 3 | 4
ELE-03 | ELE-05 | input | SLD | 1 | 2 | 3 | 4
VEN-01 | ELE-05 | input | motor and transformer data | 1 | 2 | 3 | 4
PRC-02 | CST-01 | input | equipment list | 1 | 2 | 2 | 2
MEC-01 | CST-01 | input | shell weights | 1 | 2 | 2 | 1
CST-01 | CST-02 | input | estimate structure | 1 | 2 | 2 | 2
VEN-01 | CST-02 | input | budget quotes | 1 | 2 | 2 | 2
PIP-04 | CST-02 | input | piping MTO | 1 | 2 | 2 | 2
ELE-04 | CST-02 | input | cable quantities | 1 | 2 | 2 | 2
CIV-01 | CST-02 | input | civil quantities | 1 | 2 | 2 | 2
CST-01 | PRJ-03 | input | estimate | 0 | 0 | 0 | 4
SAF-01 | PRJ-03 | input | HAZOP | 0 | 0 | 0 | 4
PIP-04 | PRJ-03 | input | isometrics | 0 | 0 | 0 | 4
ICS-06 | PRJ-03 | input | loop diagrams | 0 | 0 | 0 | 4
ICS-07 | PRJ-03 | input | architecture | 0 | 0 | 0 | 4
ELE-04 | PRJ-03 | input | cables | 0 | 0 | 0 | 4
MEC-03 | PRJ-03 | input | GAs | 0 | 0 | 0 | 4
LAY-02 | PRJ-03 | input | 3D model | 0 | 0 | 0 | 4
PRC-05 | PRJ-03 | input | BFD | 0 | 0 | 0 | 4
PRC-07 | PRJ-03 | input | process report | 0 | 0 | 0 | 4
ICS-01 | PRJ-03 | input | control philosophy | 0 | 0 | 0 | 4
ICS-03 | PRJ-03 | input | C&E | 0 | 0 | 0 | 4
ICS-04 | PRJ-03 | input | CV sizing | 0 | 0 | 0 | 4
MEC-02 | PRJ-03 | input | datasheets | 0 | 0 | 0 | 4
PIP-03 | PRJ-03 | input | stress study | 0 | 0 | 0 | 4
PRJ-03 | PRJ-04 | input | complete document set | 1 | 2 | 3 | 4
SAF-03 | PRJ-04 | input | closed HAZOP actions | 1 | 2 | 3 | 4
ICS-08 | PRJ-04 | input | SIL verification | 1 | 2 | 3 | 4
PIP-05 | PRJ-04 | input | stress sign-off | 1 | 2 | 3 | 4
ELE-05 | PRJ-04 | input | studies | 1 | 2 | 3 | 4
CST-02 | PRJ-04 | input | Class 3 estimate | 1 | 2 | 3 | 4
LAY-03 | PRJ-04 | input | model review | 1 | 2 | 3 | 4
SAF-04 | PRJ-04 | input | siting study | 1 | 2 | 3 | 4
SAF-02 | PRJ-04 | input | flare study | 1 | 2 | 3 | 4
FEL-01 | FEL-02 | input | capacity, products | 1 | 2 | 2 | 2
PRJ-01 | FEL-02 | input | design basis | 1 | 2 | 2 | 2
FEL-01 | FEL-03 | input | location constraints | 1 | 2 | 2 | 2
FEL-01 | FEL-04 | input | capacity, margins | 1 | 1 | 1 | 1
FEL-02 | FEL-04 | input | options | 1 | 1 | 1 | 1
PRC-02 | FEL-04 | input | major equipment list | 1 | 1 | 1 | 1
LAY-01 | FEL-04 | input | outline plot area | 1 | 1 | 1 | 1
FEL-02 | SEL-02 | input | screened options | 1 | 2 | 2 | 2
FEL-02 | SEL-01 | input | options | 1 | 2 | 2 | 2
SEL-02 | SEL-01 | input | selected technology | 1 | 2 | 2 | 2
PRC-01 | SEL-01 | input | case balances | 1 | 2 | 2 | 2
FEL-03 | SEL-01 | input | selected site | 1 | 2 | 2 | 2
PRJ-01 | SEL-03 | input | utility conditions | 1 | 2 | 3 | 4
PRC-01 | SEL-03 | input | utility demands | 1 | 2 | 3 | 4
PRC-01 | SEL-04 | input | emissions and effluents | 1 | 2 | 3 | 4
LAY-01 | SEL-04 | input | site layout | 1 | 2 | 3 | 4
FEL-01 | PRJ-05 | input | schedule driver | 1 | 2 | 3 | 4
SEL-01 | PRJ-05 | input | selected scope | 0 | 2 | 3 | 4
LAY-01 | CON-01 | input | plot plan | 1 | 2 | 3 | 4
LAY-02 | CON-01 | input | layout model | 1 | 2 | 3 | 4
PRJ-05 | CON-01 | input | execution strategy | 1 | 2 | 3 | 4
MEC-02 | PRO-01 | input | datasheets | 1 | 2 | 3 | 4
PRJ-05 | PRO-01 | input | contracting strategy | 1 | 2 | 3 | 4
CON-01 | CON-02 | input | path of construction | 1 | 2 | 3 | 4
PRC-08 | CON-02 | input | P&IDs | 1 | 2 | 3 | 4
PIP-04 | CON-02 | input | isometrics | 1 | 2 | 3 | 4
CIV-01 | CIV-02 | input | civil and structural design | 1 | 2 | 3 | 4
VEN-01 | CIV-02 | input | certified loads and anchor bolts | 1 | 2 | 3 | 4
PIP-05 | CIV-02 | input | support loads | 1 | 2 | 3 | 4
ICS-05 | ICS-09 | input | I/O list | 1 | 2 | 3 | 4
PIP-02 | ICS-09 | input | instrument positions | 1 | 2 | 3 | 4
VEN-01 | ICS-09 | input | vendor instruments | 1 | 2 | 3 | 4
ELE-04 | ELE-06 | input | cable schedule | 1 | 2 | 3 | 4
LAY-02 | ELE-06 | input | layout model | 1 | 2 | 3 | 4
PIP-02 | ELE-06 | input | piping model | 1 | 2 | 3 | 4
CST-02 | CST-03 | input | Class 3 estimate | 1 | 2 | 3 | 3
PRO-01 | CST-03 | input | awarded prices | 1 | 2 | 3 | 3
PIP-04 | CST-03 | input | piping MTO | 1 | 2 | 3 | 3
CIV-01 | CST-03 | input | civil quantities | 1 | 2 | 3 | 3
FEL-01 | PRJ-01 | input | business case | 1 | 2 | 3 | 4
FEL-03 | LAY-01 | input | selected site | 1 | 2 | 3 | 4
SEL-01 | PRC-01 | input | selected configuration | 0 | 0 | 3 | 4
SEL-01 | CST-01 | input | selected scope | 1 | 2 | 2 | 2
PRO-01 | VEN-01 | input | purchase orders | 1 | 2 | 3 | 3
CIV-02 | PRJ-04 | input | foundation and steel drawings | 1 | 2 | 3 | 4
ICS-09 | PRJ-04 | input | installation drawings | 1 | 2 | 3 | 4
ELE-06 | PRJ-04 | input | electrical layouts | 1 | 2 | 3 | 4
CON-02 | PRJ-04 | input | work packages | 1 | 2 | 3 | 4
PRO-01 | PRJ-04 | input | purchase orders | 1 | 2 | 3 | 4
MEC-01 | PRC-02 | loop | mechanical holds re-rate sizing (C-201 bed-1 diameter, heater box length) |  |  | 2
MEC-01 | LAY-01 | loop | calculated dimensions and weights update footprints and spacing |  |  | 2
PIP-02 | PRC-02 | loop | routed lengths update pump and line hydraulics |  |  |  | 3
PIP-02 | LAY-01 | loop | rack width and clashes move equipment |  |  |  | 3
ICS-04 | PRC-08 | loop | control valve sizes and reducers shown on the P&IDs |  |  |  | 3
SAF-01 | PRC-08 | loop | HAZOP recommendations revise the P&IDs |  |  | 4
ELE-04 | ELE-03 | loop | actual cable impedances re-run the motor-starting voltage-dip check |  |  |  | 3
ICS-07 | ELE-01 | loop | ICS cabinet and UPS loads added to the load list |  |  |  | 3
SAF-02 | PRC-03 | loop | flare back-pressure changes PSV type and size |  |  |  | 3
SAF-03 | PRC-08 | loop | formal HAZOP actions revise the P&IDs |  |  |  | 4
SAF-04 | LAY-01 | loop | siting study moves occupied buildings and equipment |  |  | 4
VEN-01 | MEC-01 | loop | certified vendor dimensions, weights and nozzles |  |  |  | 4
VEN-01 | LAY-01 | loop | vendor package footprints |  |  |  | 4
VEN-01 | ELE-01 | loop | certified motor ratings |  |  |  | 4
VEN-01 | ICS-05 | loop | vendor package I/O |  |  |  | 4
Cells give the level of 'From' needed for 'To' to reach each level (0 = not needed).

## Consistency
Issue
none: every gate target is supported by its inputs at the same gate