## Exchanges
Item | Information | Form | From discipline | From task | From system | To discipline | To task | To system | What is used | Method today | Level needed | Phases
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | nameplate capacity and budget envelope | review | 1 | FEL1
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | capacity and start-up date | manual | 2 | FEL2, FEL3
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROC | PROC-T010 Prepare process design basis | Excel / Word | nameplate capacity and project objective | review | 2 | FEL1, FEL2, FEL3
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | candidate configurations, capacity and budget constraints | meeting | 1 | FEL1, FEL2
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | economic hurdle rate and evaluation basis | meeting | 2 | FEL2
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | project objective, nameplate capacity, target start-up date, budget envelope and gate approvals for the phase plan | review | 2 | FEL1, FEL2, FEL3, DD
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | capacity, budget envelope, economic hurdle and start-up date | manual | 1 | FEL1
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | capacity and project objective | review | 1 | FEL1, FEL2
OWNR-I010 | Business case | decision | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | annual throughput and operating basis | review | 2 | FEL2, FEL3, DD
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | product slate driving column and tank count | review | 1 | FEL1
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | product slate and specifications | manual | 2 | FEL2, FEL3
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROC | PROC-T010 Prepare process design basis | Excel / Word | product slate, rates and product quality specifications | review | 2 | FEL1, FEL2, FEL3
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | product slate and destinations defining project scope | review | 2 | FEL1, FEL2, FEL3, DD
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | product slate defining unit scope | manual | 1 | FEL1
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | product slate | review | 1 | FEL1, FEL2
OWNR-I020 | Product slate and specifications | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | product specifications | manual | 2 | FEL2, FEL3
OWNR-I030 | Crude assays and feed cases | data | OWNR | OWNR-T020 Supply crude assays and feed cases | Excel / Word | PROC | PROC-T020 Characterise feed and set up assay in simulation | HYSYS | TBP/distillation curves, API, sulfur, metals, TAN per assay; design, check and turndown crude cases with rates | manual | 3 | FEL1, FEL2, FEL3
OWNR-I030 | Crude assays and feed cases | data | OWNR | OWNR-T020 Supply crude assays and feed cases | Excel / Word | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | crude sulfur content and assay data for H2S/mercaptan potential | manual | 2 | FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | historic soil data, climatic and seismic data, survey control and site access rules per candidate site | manual | 1 | FEL1
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | climatic design data, seismic zone, survey control and coordinate system | manual | 2 | FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T030 Specify and manage the topographic survey | Excel / Word | existing survey control and benchmarks | manual | 2 | FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | site access rules, climatic data, soil history, working-hour restrictions | manual | 2 | FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | site access rules and benchmarks | manual | 2 | FEL2, FEL3, DD
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | survey control points and benchmarks | manual | 4 | CON
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | site boundary, survey benchmarks, prevailing wind and site access rules | manual | 1 | FEL1
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | climatic design data and seismic zone | manual | 2 | FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROC | PROC-T010 Prepare process design basis | Excel / Word | climatic design data and site elevation | manual | 2 | FEL1, FEL2, FEL3
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | candidate site location and access rules | review | 2 | FEL1, FEL2
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | candidate site data, climatic data and access rules | review | 1 | FEL1
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | climatic design data (wind, temperature, humidity) | manual | 1 | FEL2
OWNR-I040 | Site conditions data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | site meteorology | review | 2 | FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | existing facilities, underground and utilities on or next to each candidate site | manual | 1 | FEL1
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T030 Specify and manage the topographic survey | Excel / Word | as-built drawings of existing underground services and facilities | manual | 2 | FEL2, FEL3
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CIVL | CIVL-T090 Design site preparation and earthworks | Excel / Word | existing facilities within the plot to demolish or relocate | review | 2 | FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | existing utility capacity available for start-up | meeting | 2 | FEL3
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | COMM | COMM-T120 Plan temporary commissioning facilities | Excel / Word | existing N2, steam and water availability | manual | 3 | DD, CON
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | existing facility constraints: as-built interconnecting piping, utilities and electrical supply near the plot | manual | 2 | FEL2, FEL3
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | existing underground services and available area outside battery limits | manual | 2 | FEL2, FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | existing electrical supply capacity, existing service points and agreements | meeting | 1 | FEL1, FEL2, FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | existing fire water system capacity | meeting | 2 | FEL2, FEL3
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | existing fire water capacity | review | 2 | FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | existing site networks and telecom standards for connection | meeting | 2 | FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | existing facility layout, existing interconnecting piping and utility tie points | manual | 1 | FEL1
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | existing facility as-built drawings and line data | file | 3 | FEL3, DD, CON
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | existing units, utilities, flare, tankage and interconnecting tie points | review | 1 | FEL1, FEL2
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | available capacity and conditions of existing steam, CW, air, N2, fuel gas and flare systems | review | 2 | FEL2, FEL3
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | existing unit operating data for calibration (brownfield) | manual | 3 | FEL2, FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | existing line process conditions | review | 3 | FEL3, DD
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | PROJ | PROJ-T190 Run interface management | Excel / Word | existing facility data and available utility capacity at interfaces | meeting | 3 | FEL3, DD, CON
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | existing permits, emission caps and netting history, existing source baseline | review | 2 | FEL1, FEL2
OWNR-I050 | Existing facility and utility data | document | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | existing source baseline | review | 2 | FEL2, FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | owner civil/structural standards and order of precedence | manual | 2 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | security and fencing standards | review | 2 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | owner building standards | review | 2 | FEL2, FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | owner check sheet standards and witness points | review | 3 | DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | owner electrical standards, preferred vendors, NFPA 70E program, spare philosophy | review | 3 | FEL1, FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | owner area classification practice (Division vs Zone) | review | 3 | FEL2, FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | owner electrical standards and approved vendor list | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T140 Specify power transformers | Excel / Word | owner electrical standards and approved vendor list | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | owner electrical standards and approved vendor list | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | owner electrical standards and approved vendor list | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | owner electrical standards and approved vendor list | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | ELEC | ELEC-T260 Perform arc flash study | ETAP | owner NFPA 70E program and labeling standard | review | 3 | DD, COM
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | owner fire protection and insurer standards | meeting | 2 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | DCS/SIS platform preference, integration with existing control room, operator interface standards; approved system vendors and owner automation standards | review | 1 | FEL1, FEL2
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | owner instrument standards, order of precedence, approved vendor list; spares philosophy for specifications | review | 2 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | existing site networks and telecom standards for connection | meeting | 2 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | preferred standards and vendors for equipment type selection | review | 1 | FEL1
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | owner engineering standards and approved vendor list | review | 3 | FEL2
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | owner engineering standards and order of precedence | review | 3 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | owner layout and spacing standards | manual | 1 | FEL1
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | owner piping and layout standards, order of precedence | review | 2 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | owner piping material standards and approved vendors | review | 2 | FEL2, FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | owner welding, NDE, painting and insulation standards | review | 2 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PIPE | PIPE-T250 Design pipe supports | S3D | owner standard pipe support catalogue and standards | manual | 3 | DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PROC | PROC-T010 Prepare process design basis | Excel / Word | owner process engineering standards | review | 3 | FEL1, FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PROC | PROC-T200 Develop P&IDs (process content) | SPID | P&ID legend and drafting standards | review | 3 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | owner standards, order of precedence and procedures the execution plan must reference | manual | 3 | FEL1, FEL2, FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | owner document numbering standard and revision conventions | manual | 3 | FEL1, FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | owner SHE standards and order of precedence | review | 2 | FEL2, FEL3
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | approved vendor list by commodity and excluded vendors | manual | 4 | FEL3, DD
OWNR-I060 | Owner standards and approved vendor list | document | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | VEND | VEND-T180 Compile the MDR / data book | Document Locator | owner data book index and format standard | manual | 4 | CON, COM
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | design life, winterisation and environmental limits | manual | 2 | FEL2, FEL3
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | design life, on-stream factor, sparing and reliability expectations | review | 3 | FEL1, FEL2, FEL3
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | design life, sparing, design margins, winterisation | review | 3 | FEL2
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | design life, units, winterisation and site design margins | manual | 2 | FEL2, FEL3
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | PROC | PROC-T010 Prepare process design basis | Excel / Word | on-stream factor, turndown; sparing philosophy, design margins, utility conditions, winterisation | review | 3 | FEL1, FEL2, FEL3
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | environmental limits | review | 2 | FEL2, FEL3
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | design margins | review | 3 | FEL3, DD
OWNR-I070 | Owner design basis requirements | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | environmental limits | review | 2 | FEL2, FEL3
OWNR-I080 | Risk tolerance criteria | decision | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | corporate risk matrix and tolerance | review | 1 | FEL1, FEL2
OWNR-I080 | Risk tolerance criteria | decision | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | owner risk matrix for ranking | meeting | 1 | FEL1, FEL2
OWNR-I080 | Risk tolerance criteria | decision | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | risk matrix, individual/societal risk criteria | review | 2 | FEL2, FEL3
OWNR-I080 | Risk tolerance criteria | decision | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | individual and societal risk criteria | review | 3 | FEL3, DD
OWNR-I080 | Risk tolerance criteria | decision | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | LOPA target frequencies and IPL credit rules | review | 3 | FEL3, DD
OWNR-I090 | Gate decision | decision | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | shortlisted options and gate conditions from FEL1 gate | meeting | 2 | FEL2
OWNR-I090 | Gate decision | decision | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | approval to proceed, approved budget (AFE) and conditions on contingency | review | 4 | DD
OWNR-I090 | Gate decision | decision | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | gate criteria, decision, selected option and conditions | meeting | 3 | FEL1, FEL2, FEL3
OWNR-I100 | Permit approvals and conditions | document | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | existing permit limits and conditions (Title V, NPDES) | review | 2 | FEL1, FEL2
OWNR-I100 | Permit approvals and conditions | document | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | issued permit conditions | manual | 4 | CON
OWNR-I110 | Owner comments on deliverables | document | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | owner comments on IFD electrical deliverables | review | 3 | DD
OWNR-I110 | Owner comments on deliverables | document | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | operator graphics standards and owner acceptance comments at FAT | meeting | 3 | DD, CON
OWNR-I110 | Owner comments on deliverables | document | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | PROC | PROC-T110 Prepare heat and material balance | HYSYS | owner approval codes and comments on design and check case list | review | 3 | FEL2, FEL3, DD
OWNR-I110 | Owner comments on deliverables | document | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | owner P&ID comments | review | 3 | DD
OWNR-I110 | Owner comments on deliverables | document | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | owner comments and approval code per document | review | 2 | FEL2, FEL3, DD
OWNR-I120 | Operations and maintenance requirements | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | INST | INST-T230 Verify SIL achievement | Excel / Word | turnaround interval for proof test intervals; maintenance constraints | review | 3 | DD
OWNR-I120 | Operations and maintenance requirements | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | OWNR | OWNR-T120 Review the 3D model for operability and maintenance | iConstruct | O&M requirements as review checklist | manual | 3 | FEL3, DD
OWNR-I120 | Operations and maintenance requirements | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | operating access, isolation, drains, bundle pull and lifting requirements | review | 2 | FEL2, FEL3
OWNR-I120 | Operations and maintenance requirements | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | sampling, isolation/blinding and maintenance intervals | meeting | 2 | FEL2, FEL3, DD
OWNR-I120 | Operations and maintenance requirements | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | operations and maintenance requirements and input | meeting | 1 | FEL1, FEL2
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | control room integration and operator interface requirements | review | 2 | FEL2, FEL3, DD
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | DCS/SIS platform preference, integration with existing control room, operator interface standards; approved system vendors and owner automation standards | review | 1 | FEL1, FEL2
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | DCS/SIS platform, operator interface standards, integration with existing control room and historian | meeting | 2 | FEL2, FEL3, DD
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | INST | INST-T180 Prepare DCS specification | Excel / Word | DCS platform, operator interface and graphics standards | review | 3 | FEL3, DD
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | alarm philosophy and operator interface standards | meeting | 3 | DD
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | operator graphics standards and owner acceptance comments at FAT | meeting | 3 | DD, CON
OWNR-I130 | Control and alarm management requirements | document | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | alarm philosophy and operator interface standards | meeting | 2 | FEL2, FEL3, DD
OWNR-I140 | Owner model review comments | data | OWNR | OWNR-T120 Review the 3D model for operability and maintenance | iConstruct | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | iConstruct | access and maintenance comments with civil actions | meeting | 3 | FEL3, DD
OWNR-I140 | Owner model review comments | data | OWNR | OWNR-T120 Review the 3D model for operability and maintenance | iConstruct | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | owner access, valve reach and maintenance comments | meeting | 3 | FEL3, DD
OWNR-I150 | HAZOP action acceptance | decision | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | owner acceptance of responses and residual risk | review | 3 | FEL3, DD, CON
OWNR-I160 | Tie-in and outage windows | data | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | INST | INST-T230 Verify SIL achievement | Excel / Word | turnaround interval for proof test intervals; maintenance constraints | review | 3 | DD
OWNR-I160 | Tie-in and outage windows | data | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | outage windows and tie-ins allowed per window | manual | 3 | FEL3, DD, CON
OWNR-I160 | Tie-in and outage windows | data | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | outage windows per tie-in | review | 3 | FEL3, DD
OWNR-I160 | Tie-in and outage windows | data | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | PROJ | PROJ-T190 Run interface management | Excel / Word | outage windows and live-plant constraints at tie-ins | meeting | 3 | FEL3, DD, CON
OWNR-I170 | Owner change approval | decision | OWNR | OWNR-T150 Approve changes | Excel / Word | CONS | CONS-T180 Raise field change requests | Procore | owner approve/reject decision with conditions | review | 4 | CON
OWNR-I170 | Owner change approval | decision | OWNR | OWNR-T150 Approve changes | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | owner change approvals and operations requests | review | 3 | FEL3, DD, CON
OWNR-I170 | Owner change approval | decision | OWNR | OWNR-T150 Approve changes | Excel / Word | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | approve/reject decision and conditions per change | review | 3 | FEL3, DD, CON
OWNR-I180 | Spares philosophy | document | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | owner instrument standards, order of precedence, approved vendor list; spares philosophy for specifications | review | 2 | FEL2, FEL3
OWNR-I180 | Spares philosophy | document | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | MECH | MECH-T370 Review spare parts recommendations | Excel / Word | spares policy, criticality and interchangeability targets | review | 3 | DD
OWNR-I180 | Spares philosophy | document | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | spares policy and interchangeability targets | manual | 4 | DD, CON
OWNR-I190 | Approved operating spares list | data | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | approved spares by tag and part number | manual | 4 | COM
OWNR-I190 | Approved operating spares list | data | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | SCM | SCM-T270 Procure commissioning and operating spares | Purchasing DB | approved spares by tag and part number with quantities | review | 4 | DD, CON, COM
OWNR-I200 | CMMS asset data requirements | document | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | asset classes and required attributes | review | 4 | COM
OWNR-I200 | CMMS asset data requirements | document | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | required document metadata and document link rules per asset class for handover | manual | 3 | FEL1, FEL2, FEL3
OWNR-I200 | CMMS asset data requirements | document | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | records format and document link requirements | review | 4 | COM
OWNR-I200 | CMMS asset data requirements | document | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | CMMS asset classes and required attributes | manual | 4 | DD, CON
OWNR-I210 | Permit to work and isolation authorisation | decision | OWNR | OWNR-T180 Issue permits to work and isolations | Excel / Word | COMM | COMM-T190 Energise electrical systems | Smart Completions | permit to energise | manual | 4 | CON, COM
OWNR-I210 | Permit to work and isolation authorisation | decision | OWNR | OWNR-T180 Issue permits to work and isolations | Excel / Word | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | permits to work and isolations for brownfield IWPs | manual | 4 | CON
OWNR-I220 | Operating procedures | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | draft operating procedures | review | 3 | DD, CON
OWNR-I220 | Operating procedures | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | approved operating procedures | meeting | 4 | COM
OWNR-I220 | Operating procedures | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | owner operating procedure format and review | review | 3 | DD, CON
OWNR-I220 | Operating procedures | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | procedure format and owner review | review | 3 | CON, COM
OWNR-I220 | Operating procedures | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | operating and emergency procedures | review | 4 | COM
OWNR-I230 | Owner test witness acceptance | decision | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | owner walkdown signatures and findings | meeting | 4 | CON, COM
OWNR-I230 | Owner test witness acceptance | decision | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | owner witness sign-off | meeting | 4 | COM
OWNR-I230 | Owner test witness acceptance | decision | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | owner walkdown witness signatures | meeting | 4 | CON
OWNR-I240 | Handover acceptance | decision | OWNR | OWNR-T210 Accept system handover | Smart Completions | COMM | COMM-T230 Hand over systems to the owner | Smart Completions | owner acceptance and retained punch | meeting | 4 | COM
OWNR-I240 | Handover acceptance | decision | OWNR | OWNR-T210 Accept system handover | Smart Completions | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | handover acceptance per system | review | 4 | COM
OWNR-I250 | CMMS master data | data | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | COMM | COMM-T230 Hand over systems to the owner | Smart Completions | CMMS loaded before system handover | review | 4 | COM
OWNR-I260 | CMMS data gap list | data | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | missing or inconsistent equipment data returned for correction | review | 4 | COM
OWNR-I270 | Final documentation acceptance and deficiency list | decision | OWNR | OWNR-T230 Accept final documentation | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | final documentation acceptance and deficiency list | review | 4 | COM
OWNR-I280 | Building programme and occupancy | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | Building room programme: staffing, occupancy numbers and required rooms (offices, lab, welfare) for the control building | review | 2 | FEL2, FEL3, DD
OWNR-I280 | Building programme and occupancy | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | Building occupancy hours and personnel counts per building (permanent and portable) | review | 2 | FEL3, DD
OWNR-I281 | Handover requirements and acceptance criteria | document | OWNR | OWNR-T210 Accept system handover | Excel / Word | COMM | COMM-T010 Prepare completions and commissioning execution plan | Excel / Word | owner handover requirements, operating organisation and acceptance criteria | meeting | 2 | FEL3
OWNR-I282 | Contract performance guarantees | document | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | Contract performance guarantees and acceptance criteria | review | 4 | COM
OWNR-I283 | Plant historian start-up data | data | OWNR | OWNR-T200 Witness and accept commissioning tests | Excel / Word | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | Start-up plant operating data (DCS historian) during commissioning | manual | 3 | COM
OWNR-I284 | Owner cost structure and AFE codes | data | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | Owner cost reporting structure, AFE/capital codes and code of accounts mapping | manual | 3 | FEL2, FEL3, DD
OWNR-I285 | Invoices paid and back-charges | data | OWNR | OWNR-T240 Pay invoices and report actual cost | Excel / Word | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | Actual invoices paid (owner finance system) by PO and cost code | file | 4 | DD, CON, COM
OWNR-I285 | Invoices paid and back-charges | data | OWNR | OWNR-T240 Pay invoices and report actual cost | Excel / Word | SCM | SCM-T280 Close out purchase orders | Purchasing DB | Final invoice and back-charge status per PO | manual | 4 | CON, COM
OWNR-I286 | Incident history and previous PHAs | document | OWNR | OWNR-T130 Take part in HAZOP and accept actions | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | Site and corporate incident history and owner HAZID guideword set | meeting | 1 | FEL1, FEL2
OWNR-I286 | Incident history and previous PHAs | document | OWNR | OWNR-T130 Take part in HAZOP and accept actions | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | Operations and maintenance attendees and previous PHAs of similar units | meeting | 3 | FEL3, DD
OWNR-I286 | Incident history and previous PHAs | document | OWNR | OWNR-T130 Take part in HAZOP and accept actions | Excel / Word | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | Offsite public and environmental receptors, five-year accident history and emergency response program for RMP | review | 3 | DD, CON
OWNR-I287 | Surroundings, population and receptors | data | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | Neighbouring facilities, land boundaries and offsite population around candidate sites | review | 1 | FEL1
OWNR-I287 | Surroundings, population and receptors | data | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | Onsite and offsite population distribution and ignition source data for QRA | review | 3 | FEL3, DD
OWNR-I287 | Surroundings, population and receptors | data | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | Offsite public and environmental receptors, five-year accident history and emergency response program for RMP | review | 3 | DD, CON
OWNR-I288 | Emergency response organisation | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | Local fire department and mutual aid capabilities and insurer (property) requirements | meeting | 2 | FEL2, FEL3
OWNR-I288 | Emergency response organisation | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | Offsite public and environmental receptors, five-year accident history and emergency response program for RMP | review | 3 | DD, CON
OWNR-I288 | Emergency response organisation | document | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | Site emergency organization, mutual aid agreements and local responder resources | meeting | 3 | DD, CON, COM
OWNR-I289 | Permit strategy approval | decision | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | Permit strategy approval, responsible official signatory and agency pre-application meeting outcomes | meeting | 3 | FEL3, DD
OWNR-I290 | Operator training and emergency readiness record | document | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | Operator training records and emergency response readiness confirmation | review | 4 | COM
OWNR-I291 | Owner award approval | decision | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | Owner award approval for packages above delegated authority | review | 3 | FEL3, DD
OWNR-I292 | Owner witness point selection | decision | OWNR | OWNR-T090 Review and comment on deliverables | Excel / Word | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | Owner witness point selection per PO and ITP | review | 3 | DD, CON
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | COMM | COMM-T010 Prepare completions and commissioning execution plan | Excel / Word | phase plan, organisation, key procedures | review | 2 | FEL3
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | COMM | COMM-T240 Report completions progress | Smart Completions | reporting requirements | review | 4 | CON, COM
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | construction contract split, phase plan and work split | review | 2 | FEL2, FEL3
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | CONS | CONS-T180 Raise field change requests | Procore | change control procedure and approval thresholds | review | 4 | CON
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | CONS | CONS-T210 Track installed quantities and progress | iConstruct | progress measurement and reporting requirements | review | 4 | CON
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | project scope, phase plan, execution strategy and codes basis | review | 2 | FEL1, FEL2, FEL3
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | phase plan, FEL deliverable list and work split for I&C concept | review | 1 | FEL1, FEL2
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | project codes, key procedures and units convention for the I&C basis | review | 2 | FEL2, FEL3
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | PROC | PROC-T010 Prepare process design basis | Excel / Word | phase plan and design basis scope/structure | review | 2 | FEL1, FEL2, FEL3
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | phase plan and gate criteria setting estimate class and cut-off date | manual | 3 | FEL2, FEL3, DD
PROJ-I010 | Project execution plan | document | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | codes and standards and design basis structure in execution plan | review | 2 | FEL2, FEL3
PROJ-I020 | Contracting and procurement strategy | decision | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | COMM | COMM-T010 Prepare completions and commissioning execution plan | Excel / Word | contract packages and construction/commissioning split | review | 2 | FEL3
PROJ-I020 | Contracting and procurement strategy | decision | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | contract packages and modular vs stick-built assumptions | review | 2 | FEL2, FEL3
PROJ-I020 | Contracting and procurement strategy | decision | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | procurement packages and owner/contractor-furnished split | manual | 3 | FEL2, FEL3
PROJ-I020 | Contracting and procurement strategy | decision | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | approved commercial terms and delivery terms | manual | 4 | FEL2, FEL3, DD
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | WBS, area and cost codes for quantity breakdown | review | 2 | FEL1, FEL2, FEL3, DD
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | WBS levels, area codes and P6 activity codes | manual | 2 | FEL3, DD
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | WBS, area and cost codes | manual | 2 | FEL3, DD
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | WBS, area and cost codes | review | 2 | FEL1, FEL2, FEL3
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | estimate class, quantity template, code of accounts, WBS/area codes and due date | review | 1 | FEL1, FEL2, FEL3
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | area and unit codes used in document numbers | manual | 3 | FEL1, FEL2, FEL3
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | code of accounts and WBS for the quantity templates | manual | 3 | FEL2, FEL3, DD
PROJ-I030 | WBS, area codes and cost codes | data | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | cost codes and WBS per PO line | manual | 4 | FEL3, DD
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | document and requisition numbering | review | 3 | FEL3, DD
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | document numbering and required metadata | review | 2 | DD
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | PIPE | PIPE-T320 Extract and check isometrics | S3D | document numbering, revision and issue-purpose conventions | manual | 3 | DD
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | equipment and document tag/numbering format | review | 3 | FEL2, FEL3, DD
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | numbering format, discipline/type/area codes for assigning numbers | manual | 4 | FEL2, FEL3, DD, CON
PROJ-I040 | Document numbering procedure and codes | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | vendor document numbering and metadata rules | manual | 4 | FEL2, FEL3, DD
PROJ-I050 | Document Locator structure and distribution matrix | data | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | distribution matrix: recipients per document type | integrated | 4 | FEL2, FEL3, DD, CON, COM
PROJ-I050 | Document Locator structure and distribution matrix | data | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Document Locator | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | Document Locator submission workflow | manual | 4 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | CIVL | CIVL-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | deliverables to issue IFC and current revisions | review | 3 | DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | deliverables by discipline and area to group into EWPs | manual | 2 | FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | deliverables with EWP assignment and current status | manual | 3 | DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | ELEC | ELEC-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | deliverables, revisions and status | integrated | 3 | DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | INST | INST-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | PROC | PROC-T005 Plan, measure and report discipline deliverables | Excel / Word | deliverable numbers, titles and register status | review | 2 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | document numbers, types and planned issue dates | manual | 3 | FEL2, FEL3, DD
PROJ-I060 | Deliverables register | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | PROJ | PROJ-T130 Measure engineering progress | P6 | actual issue dates and current revision per deliverable | integrated | 3 | FEL3, DD
PROJ-I070 | Assigned document numbers | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | reserved document and vendor document numbers | review | 3 | FEL3, DD
PROJ-I070 | Assigned document numbers | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | PIPE | PIPE-T320 Extract and check isometrics | S3D | reserved isometric document numbers | manual | 3 | DD
PROJ-I070 | Assigned document numbers | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | SCM | SCM-T120 Set up VDRL tracking | Purchasing DB | project document numbers for vendor documents | manual | 4 | DD
PROJ-I070 | Assigned document numbers | data | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | VEND | VEND-T040 Issue the vendor document schedule | Document Locator | project document numbers per vendor document | manual | 4 | DD
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | estimate class, quantity template, code of accounts and due date | review | 2 | FEL1, FEL2, FEL3, DD
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | estimate class, basis, code of accounts and take-off template | manual | 2 | FEL3, DD
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | quantity take-off template, estimate class, code of accounts, due date | review | 2 | FEL1, FEL2, FEL3
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | estimate class, quantity template, code of accounts, WBS/area codes and due date | review | 1 | FEL1, FEL2, FEL3
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | estimate class, basis, code of accounts and due date for equipment pricing | review | 2 | FEL2, FEL3
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | quantity take-off template, estimate class, code of accounts and due date | manual | 1 | FEL1
PROJ-I080 | Estimate quantity request | document | PROJ | PROJ-T070 Issue estimate quantity requests to disciplines | Excel / Word | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | estimate class, basis, growth and allowance and code of accounts | manual | 2 | FEL2, FEL3
PROJ-I090 | Class 5 estimate | document | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | capital cost range per option | review | 1 | FEL1
PROJ-I090 | Class 5 estimate | document | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | order-of-magnitude capital cost per alternative | review | 2 | FEL2
PROJ-I100 | Class 4 estimate | document | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | estimate basis: labour rates, productivity, location factor | manual | 2 | FEL2, FEL3
PROJ-I100 | Class 4 estimate | document | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | equipment-factored cost per alternative | review | 2 | FEL2
PROJ-I100 | Class 4 estimate | document | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | Class 4 estimate (FEL2 gate) | review | 3 | FEL1, FEL2, FEL3
PROJ-I110 | Class 3 estimate | document | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | approved Class 3 cost by WBS and commodity, contingency | manual | 4 | DD
PROJ-I110 | Class 3 estimate | document | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | Class 3 estimate (FEL3 gate) | review | 3 | FEL1, FEL2, FEL3
PROJ-I110 | Class 3 estimate | document | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | cost basis for risk ranges | manual | 3 | FEL1, FEL2, FEL3, DD, CON
PROJ-I110 | Class 3 estimate | document | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | estimate value per package where no control budget yet | manual | 3 | FEL3, DD
PROJ-I120 | Control budget | data | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | budget per package | manual | 3 | FEL3, DD
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | early-works and milestone dates | review | 3 | FEL3, DD
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | level 2 schedule and start-up milestone | integrated | 3 | DD
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | schedule targets and milestones | manual | 2 | FEL2, FEL3
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CONS | CONS-T050 Define path of construction | P6 | MC, start-up and contract interface milestones | manual | 2 | FEL3
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | level 2 engineering and procurement milestones | manual | 2 | FEL3, DD
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CONS | CONS-T110 Develop construction schedule by CWP | P6 | level 2/3 logic and engineering milestones | integrated | 3 | DD, CON
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | baseline date for permanent power (backfeed) and mechanical completion | review | 2 | FEL1, FEL2, FEL3, DD
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | baseline schedule | review | 3 | FEL1, FEL2, FEL3
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | schedule logic for schedule risk analysis | manual | 3 | FEL1, FEL2, FEL3, DD, CON
PROJ-I130 | Baseline integrated schedule | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | permit-related milestones and construction start date | review | 1 | FEL1, FEL2
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CIVL | CIVL-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | planned IFC dates for civil deliverables | review | 3 | FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | planned IFC dates | review | 3 | DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | planned and forecast IFC dates per deliverable | manual | 3 | DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | ELEC | ELEC-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | planned IFC dates | integrated | 3 | DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | INST | INST-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I140 | Deliverable schedule dates | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | PROC | PROC-T005 Plan, measure and report discipline deliverables | Excel / Word | planned IFR/IFD/IFC dates per deliverable | manual | 2 | FEL2, FEL3, DD
PROJ-I150 | Required-on-site and need dates per MR | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | MR issue need date and ROS per instrument package | review | 3 | FEL3, DD
PROJ-I150 | Required-on-site and need dates per MR | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | ROS and MR/PO need dates | manual | 2 | FEL2, FEL3
PROJ-I150 | Required-on-site and need dates per MR | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | ROS and MR need date per MR | manual | 3 | FEL3, DD
PROJ-I150 | Required-on-site and need dates per MR | data | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | ROS per MR and tag to check against forecast | manual | 3 | DD, CON
PROJ-I160 | Procurement and vendor dates in P6 | data | PROJ | PROJ-T120 Integrate procurement and vendor dates into the schedule | P6 | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | PO award, vendor data and forecast delivery dates | integrated | 3 | FEL3, DD, CON, COM
PROJ-I170 | Engineering progress and earned value | data | PROJ | PROJ-T130 Measure engineering progress | P6 | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | percent complete and earned hours per deliverable | integrated | 3 | FEL3, DD, CON, COM
PROJ-I180 | Schedule update and critical path report | document | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | schedule status and critical path | manual | 3 | FEL2, FEL3, DD, CON, COM
PROJ-I190 | Cost report and forecast | document | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | cost status and forecast | manual | 3 | FEL2, FEL3, DD, CON, COM
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | trends and changes to assess for discipline impact | manual | 2 | FEL2, FEL3, DD
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | OWNR | OWNR-T150 Approve changes | Excel / Word | trend/change description with cost and schedule impact | review | 3 | DD, CON
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | trends and changes to assess for discipline impact | manual | 2 | FEL2, FEL3, DD
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | trend descriptions | review | 3 | FEL3, DD, CON
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | pending trends with rough cost impact for the forecast | manual | 4 | DD, CON, COM
PROJ-I200 | Trend register | data | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | trends | manual | 3 | FEL2, FEL3, DD, CON, COM
PROJ-I210 | Approved change notice | decision | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | approved change scope and affected deliverables | review | 3 | FEL3, DD, CON
PROJ-I210 | Approved change notice | decision | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | approved cost adjustment per change | manual | 4 | DD, CON, COM
PROJ-I210 | Approved change notice | decision | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | approved change notices | review | 3 | DD, CON, COM
PROJ-I210 | Approved change notice | decision | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | SCM | SCM-T110 Process PO amendments | Purchasing DB | approved change scope and affected POs | manual | 4 | DD, CON
PROJ-I220 | Gate review package | document | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | gate package: estimate, schedule, risk, readiness | review | 3 | FEL1, FEL2, FEL3
PROJ-I230 | Gate decision | decision | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | gate approval and conditions on the sanctioned estimate | manual | 4 | DD
PROJ-I240 | Risk register | data | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | risk register | review | 3 | FEL1, FEL2, FEL3
PROJ-I240 | Risk register | data | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | top risks | manual | 3 | FEL2, FEL3, DD, CON, COM
PROJ-I250 | Contingency analysis result | document | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | P50/P90 cost and schedule for the gate decision | review | 3 | FEL1, FEL2, FEL3
PROJ-I250 | Contingency analysis result | document | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | recommended contingency for the control budget | manual | 3 | DD
PROJ-I260 | Interface register | data | PROJ | PROJ-T190 Run interface management | Excel / Word | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | owner-side interfaces and agreements | review | 3 | FEL2, FEL3, DD
PROJ-I260 | Interface register | data | PROJ | PROJ-T190 Run interface management | Excel / Word | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | open interfaces for the monthly report | manual | 3 | FEL2, FEL3, DD, CON, COM
PROJ-I270 | Interface query and agreement | decision | PROJ | PROJ-T190 Run interface management | Excel / Word | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | data requests and required dates | review | 1 | FEL1, FEL2
PROJ-I270 | Interface query and agreement | decision | PROJ | PROJ-T190 Run interface management | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | interface queries | review | 3 | FEL3, DD, CON
PROJ-I280 | Transmittal | document | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | CONS | CONS-T260 Prepare as-built redlines | Procore | IFC transmittals with documents and revisions | manual | 4 | CON, COM
PROJ-I280 | Transmittal | document | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | IFR transmittals with review due dates | review | 2 | FEL2, FEL3, DD
PROJ-I280 | Transmittal | document | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | transmittal, documents and review due dates | integrated | 2 | FEL2, FEL3, DD
PROJ-I290 | Consolidated comment sheet | document | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | consolidated comment sheet | integrated | 2 | DD, CON
PROJ-I300 | Document review status | data | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | review code and return date | integrated | 2 | DD, CON
PROJ-I310 | Hold list | data | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | holds assigned to process | review | 3 | FEL3, DD, CON
PROJ-I310 | Hold list | data | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | holds cleared per document | manual | 4 | DD, CON
PROJ-I320 | IFC release and seal record | data | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | IFC re-issues triggering engineering list deltas | manual | 4 | DD, CON
PROJ-I320 | IFC release and seal record | data | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | current IFC revision and release date per document | manual | 4 | CON
PROJ-I320 | IFC release and seal record | data | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | CONS | CONS-T170 Raise and manage RFIs | Procore | current IFC revision per document | manual | 4 | CON
PROJ-I320 | IFC release and seal record | data | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | CONS | CONS-T260 Prepare as-built redlines | Procore | IFC document list and revisions | manual | 4 | CON, COM
PROJ-I330 | Monthly progress report | document | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | monthly progress, cost, schedule and risk status | review | 4 | FEL2, FEL3, DD
PROJ-I340 | Construction progress in P6 | data | PROJ | PROJ-T250 Load construction progress into P6 | P6 | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | installed progress for cost forecast | manual | 4 | DD, CON, COM
PROJ-I340 | Construction progress in P6 | data | PROJ | PROJ-T250 Load construction progress into P6 | P6 | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | construction progress for the monthly report | manual | 4 | FEL2, FEL3, DD, CON, COM
PROJ-I350 | Final records index | data | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | COMM | COMM-T220 Compile system turnover packages | Document Locator | as-built documents per system and locations | manual | 4 | COM
PROJ-I350 | Final records index | data | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | OWNR | OWNR-T210 Accept system handover | Smart Completions | as-built and turnover records index | review | 4 | COM
PROJ-I350 | Final records index | data | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | OWNR | OWNR-T230 Accept final documentation | Document Locator | final as-built document list and data books | review | 4 | COM
PROJ-I360 | Project close-out report | document | PROJ | PROJ-T260 Compile the final records and close out | Excel / Word | OWNR | OWNR-T230 Accept final documentation | Document Locator | final cost, schedule and open items at close-out | review | 4 | COM
PROJ-I370 | VDRL template by requisition type | document | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | Standard vendor document requirements (VDRL template) for instrument MRs | review | 3 | FEL3, DD
PROJ-I371 | Project specification and code list | document | PROJ | PROJ-T010 Prepare the project execution plan | Document Locator | OWNR | OWNR-T040 Issue owner standards and specifications | Document Locator | list of project specifications and requested deviations from owner standards | review | 2 | FEL1, FEL2
PROJ-I371 | Project specification and code list | document | PROJ | PROJ-T010 Prepare the project execution plan | Document Locator | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | Project specification and code list (ASME B31.3 edition, referenced standards, order of precedence for piping) | manual | 2 | FEL2, FEL3, DD
PROJ-I372 | Engineering data handover specification | document | PROJ | PROJ-T040 Set up document numbering and the Document Locator project | Excel / Word | OWNR | OWNR-T170 Define CMMS asset data requirements | Excel / Word | SPF tag classes and attributes available from engineering systems | review | 2 | DD
PROJ-I373 | Bulk surplus and allowance policy | document | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | Bulk material surplus and allowance policy (percent by commodity and size) | manual | 3 | FEL3, DD
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | ambient design conditions and design cases to align civil environmental data | review | 2 | FEL2, FEL3
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | COMM | COMM-T250 Support performance test run | Excel / Word | design cases and product specifications | review | 4 | COM
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | turndown, design margin philosophy, design cases | manual | 2 | FEL2
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | draft basis of design | review | 1 | FEL2, FEL3
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROC | PROC-T020 Characterise feed and set up assay in simulation | HYSYS | feed slate and design cases | manual | 2 | FEL1, FEL2, FEL3
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | capacity and product specifications | manual | 1 | FEL1, FEL2
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | fouling factors and allowable pressure drops | manual | 3 | FEL1, FEL2, FEL3
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROC | PROC-T290 Prepare process description and design report | Excel / Word | design basis | review | 3 | FEL2, FEL3
PROC-I010 | Process design basis | document | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | process design basis at gate | review | 3 | FEL1, FEL2, FEL3
PROC-I015 | Battery-limit conditions | data | PROC | PROC-T010 Prepare process design basis | Excel / Word | PROC | PROC-T185 Prepare package process specifications | Excel / Word | battery-limit P/T/flows | manual | 3 | FEL3, DD
PROC-I020 | Feed characterisation basis | model | PROC | PROC-T020 Characterise feed and set up assay in simulation | HYSYS | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | pseudo-components, assay cuts and property package | integrated | 1 | FEL1, FEL2
PROC-I020 | Feed characterisation basis | model | PROC | PROC-T020 Characterise feed and set up assay in simulation | HYSYS | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | feed characterisation | integrated | 2 | FEL2
PROC-I020 | Feed characterisation basis | model | PROC | PROC-T020 Characterise feed and set up assay in simulation | HYSYS | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | feed characterisation and property package | integrated | 3 | FEL2, FEL3, DD
PROC-I030 | Screening case results | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | power demand per screening option | manual | 1 | FEL1, FEL2
PROC-I030 | Screening case results | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | major heater/exchanger duties, column count and power demand per option | manual | 1 | FEL1
PROC-I030 | Screening case results | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | product yields per option | review | 1 | FEL1
PROC-I030 | Screening case results | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | per option fuel, power demand and CO2 estimate | manual | 1 | FEL1, FEL2
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | unit blocks and capacities to judge footprint | review | 1 | FEL1
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | unit blocks and main streams per option to size the automation scope | review | 1 | FEL1, FEL2
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | options, unit capacities and main blocks per option | manual | 1 | FEL1
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | OWNR | OWNR-T010 Define business case, capacity and product slate | Excel / Word | blocks and overall balance per option | review | 1 | FEL1
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | process blocks, main streams, capacities and tankage/utility blocks per option | manual | 1 | FEL1
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | unit blocks and main streams per option | review | 1 | FEL2
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | unit blocks, capacities and overall balance per option for capacity factoring | manual | 1 | FEL1
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | block flow options with major streams and capacities | review | 1 | FEL1, FEL2
PROC-I040 | Block flow diagrams | drawing | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | blocks, main streams and capacities | review | 1 | FEL1, FEL2
PROC-I050 | Screening equipment list | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | equipment type, count and power key size per option for factored load estimate | manual | 1 | FEL1, FEL2
PROC-I050 | Screening equipment list | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | equipment type, count, key size parameter and material class per option | manual | 1 | FEL1
PROC-I050 | Screening equipment list | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | equipment type, count, key size and material class per option | manual | 1 | FEL1
PROC-I050 | Screening equipment list | data | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | equipment type, count and key size per option for package definition | manual | 2 | FEL2, FEL3
PROC-I060 | Alternative case balances | data | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | alternative case yields and utilities | review | 3 | FEL1, FEL2, FEL3
PROC-I060 | Alternative case balances | data | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | PROC | PROC-T070 Evaluate technology and licensor process offers | Excel / Word | alternative case balances for normalising licensor yields and utilities | manual | 2 | FEL2
PROC-I060 | Alternative case balances | data | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | yields, utilities and duties per alternative | review | 2 | FEL2
PROC-I060 | Alternative case balances | data | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | utility demand per alternative | manual | 2 | FEL2, FEL3
PROC-I060 | Alternative case balances | data | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | per option H&MB, major equipment duties and inventories | review | 1 | FEL1, FEL2
PROC-I070 | Technology evaluation (process) | document | PROC | PROC-T070 Evaluate technology and licensor process offers | Excel / Word | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | licensor ranking and process risks | review | 2 | FEL2
PROC-I070 | Technology evaluation (process) | document | PROC | PROC-T070 Evaluate technology and licensor process offers | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | technology maturity and process risks | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
PROC-I080 | Selected process configuration | decision | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | selected configuration | review | 3 | FEL1, FEL2, FEL3
PROC-I080 | Selected process configuration | decision | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | PROC | PROC-T095 Define process layout requirements | Excel / Word | selected configuration | review | 2 | FEL2, FEL3
PROC-I080 | Selected process configuration | decision | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | selected configuration and design cases | integrated | 3 | FEL2, FEL3, DD
PROC-I090 | Utility and offsite basis | document | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | utility systems and supply conditions | review | 2 | FEL3
PROC-I090 | Utility and offsite basis | document | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | utility supply conditions (CW, steam, air) for equipment design | manual | 2 | FEL2
PROC-I090 | Utility and offsite basis | document | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | steam header conditions (P, T) for turbine drivers | manual | 2 | FEL2, FEL3
PROC-I090 | Utility and offsite basis | document | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | PROC | PROC-T185 Prepare package process specifications | Excel / Word | utility supply conditions | manual | 3 | FEL3, DD
PROC-I090 | Utility and offsite basis | document | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | utility supply conditions | review | 3 | FEL2, FEL3, DD, COM
PROC-I095 | Process layout requirements | document | PROC | PROC-T095 Define process layout requirements | Excel / Word | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | minimum elevations for NPSHa, thermosiphon and gravity drains | manual | 3 | FEL3, DD
PROC-I095 | Process layout requirements | document | PROC | PROC-T095 Define process layout requirements | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | minimum elevations for NPSH, thermosiphon and gravity drain, close-coupling and adjacency | manual | 2 | FEL2, FEL3, DD
PROC-I095 | Process layout requirements | document | PROC | PROC-T095 Define process layout requirements | Excel / Word | PIPE | PIPE-T070 Study critical line routing | S3D | slope, no-pocket, gravity, NPSH and symmetrical routing requirements | manual | 2 | FEL3
PROC-I095 | Process layout requirements | document | PROC | PROC-T095 Define process layout requirements | Excel / Word | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | minimum elevations for NPSHa | review | 2 | FEL2, FEL3, DD
PROC-I095 | Process layout requirements | document | PROC | PROC-T095 Define process layout requirements | Excel / Word | PROC | PROC-T330 Review 3D model and isometrics for process requirements | S3D | layout requirements | review | 3 | FEL3, DD
PROC-I100 | Calibrated simulation model | model | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | PROC | PROC-T110 Prepare heat and material balance | HYSYS | converged rigorous cases for all design cases | integrated | 3 | FEL2, FEL3, DD
PROC-I100 | Calibrated simulation model | model | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | relieving-condition flash and properties | integrated | 3 | FEL3, DD
PROC-I100 | Calibrated simulation model | model | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | calibrated model | integrated | 3 | DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | INST | INST-T060 Enter instrument process data | SI | per stream and case: flow, P, T, density, viscosity, MW, Cp/Cv, Z, vapour fraction (HYSYS not linked to SI: copied by hand) | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | stream composition, P and T at sample points for sample conditioning | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | stream numbers, flows, P and T for stream table | manual | 3 | FEL2, FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | max/min operating P and T per case | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T140 Size vessels and columns | HYSYS | vapour/liquid loads and properties | integrated | 3 | FEL2, FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | flow, density, viscosity, vapour pressure | manual | 3 | FEL2, FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | stream properties and exchanger duties per case | file | 3 | FEL1, FEL2, FEL3
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | heater duty, coil conditions and fuel composition | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | flow, density, viscosity, phase per line | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | flow, phase and operating P/T per line | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T220 Prepare instrument process data | Excel / Word | fluid properties at instrument location | manual | 3 | FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | stream duties; flows at dosing points | manual | 3 | FEL2, FEL3, DD, COM
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | effluent and vent stream flows and compositions; composition, P, T | manual | 3 | FEL2, FEL3, DD
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | PROC | PROC-T290 Prepare process description and design report | Excel / Word | H&MB | review | 3 | FEL2, FEL3
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | stream composition, phase, P, T, H2S and benzene content | manual | 2 | FEL2, FEL3
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | stream data per case | review | 2 | FEL2, FEL3
PROC-I110 | Stream data | data | PROC | PROC-T110 Prepare heat and material balance | HYSYS | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | H&MB stream data | review | 3 | FEL3, DD
PROC-I111 | Design and operating case list | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | upset and start-up cases governing temperatures | manual | 3 | FEL3, DD
PROC-I111 | Design and operating case list | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | operating cases for load case definition | manual | 3 | DD
PROC-I111 | Design and operating case list | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PROC | PROC-T140 Size vessels and columns | HYSYS | governing case per column/vessel | integrated | 3 | FEL2, FEL3, DD
PROC-I111 | Design and operating case list | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | operating and turndown cases; design and operating cases | review | 2 | FEL2, FEL3, DD
PROC-I111 | Design and operating case list | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | design and operating case list | review | 2 | FEL2, FEL3
PROC-I112 | Corrosion-relevant process data | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | service flags (steam, viscous, cryogenic) and sour/H2S, hydrogen content needing special hook-ups | manual | 3 | DD
PROC-I112 | Corrosion-relevant process data | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | H2S, CO2, chlorides, naphthenic acid, free water, sulfur species and operating T/P per circuit | manual | 2 | FEL2, FEL3
PROC-I112 | Corrosion-relevant process data | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PROC | PROC-T135 Define corrosion basis and agree materials selection with Mechanical | Excel / Word | corrosive species, cases and upsets per stream | manual | 2 | FEL2, FEL3, DD
PROC-I112 | Corrosion-relevant process data | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | corrosive species and free water per circuit | manual | 3 | FEL3, DD
PROC-I112 | Corrosion-relevant process data | data | PROC | PROC-T110 Prepare heat and material balance | Excel / Word | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | corrosive species and solids for materials and sealing | manual | 3 | FEL3, DD
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | major equipment and main lines by unit for system split | review | 2 | FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | equipment count, main control loops, streams needing analyzers; preliminary instrument counts from P&IDs where available | manual | 1 | FEL1, FEL2, FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | PROC | PROC-T095 Define process layout requirements | Excel / Word | equipment and main lines | review | 2 | FEL2, FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | equipment, main lines and loops | manual | 3 | FEL2, FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | PROC | PROC-T290 Prepare process description and design report | Excel / Word | PFDs | review | 3 | FEL2, FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | PFDs at gate maturity | review | 3 | FEL1, FEL2, FEL3
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | major equipment, fluids and main control loops | review | 1 | FEL1, FEL2
PROC-I120 | Process flow diagrams | drawing | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | PFDs with control loops | review | 2 | FEL2, FEL3
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | design P/T, MDMT, steam-out and vacuum conditions per equipment | manual | 2 | FEL2, FEL3
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | design P/T, MDMT, vacuum and steam-out conditions | manual | 3 | FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | max design P/T and MDMT per system | manual | 2 | FEL2, FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | design and minimum design temperatures, steam-out and vacuum conditions | manual | 3 | FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | design and upset temperatures and pressures | manual | 3 | DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T140 Size vessels and columns | HYSYS | design P/T | manual | 3 | FEL2, FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | design P/T per equipment | manual | 3 | FEL2, FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | design P/T | manual | 3 | FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | design P/T | manual | 3 | FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | design P/T for trip settings | manual | 3 | FEL3, DD
PROC-I130 | Design pressure and temperature basis | data | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | design pressures | review | 3 | FEL3, DD
PROC-I136 | Process agreement of materials selection | decision | PROC | PROC-T135 Define corrosion basis and agree materials selection with Mechanical | Excel / Word | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | agreed materials selection per service | meeting | 2 | FEL2, FEL3
PROC-I136 | Process agreement of materials selection | decision | PROC | PROC-T135 Define corrosion basis and agree materials selection with Mechanical | Excel / Word | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | agreed materials selection per service for piping classes | review | 2 | FEL2, FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | LL/LLL/NLL/HLL/HHLL and interface levels for level instrument ranges and bridle elevations | manual | 3 | FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | tray loading per section, flood margin, internals type and count | manual | 3 | FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | vessel/column sizes | manual | 3 | FEL2, FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | ID, T/T, levels, nozzle duties | manual | 3 | FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | liquid hold-up for inventories | manual | 3 | FEL2, FEL3, DD
PROC-I140 | Vessel and column process sizing | data | PROC | PROC-T140 Size vessels and columns | Excel / Word | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | vessel and column liquid levels and dimensions for holdup inventories | manual | 2 | FEL2, FEL3
PROC-I150 | Rotating equipment process duties | data | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | rated/normal/min flow, differential head, NPSHa, fluid properties, sparing and driver preference per machine | manual | 2 | FEL2, FEL3
PROC-I150 | Rotating equipment process duties | data | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | pump/compressor shut-off head basis | manual | 2 | FEL3, DD
PROC-I150 | Rotating equipment process duties | data | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | rotating duties | manual | 3 | FEL2, FEL3, DD
PROC-I150 | Rotating equipment process duties | data | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | rated/normal/min flow, head, NPSHa, operating cases | manual | 3 | FEL3, DD
PROC-I155 | Preliminary exchanger sizing | model | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | process preliminary sizing as the starting point: duty, area, allowable pressure drop, fouling | manual | 3 | FEL3, DD
PROC-I155 | Preliminary exchanger sizing | model | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | process preliminary air cooler duty and area as the starting point | manual | 3 | FEL3, DD
PROC-I155 | Preliminary exchanger sizing | model | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | exchanger area and duty | manual | 3 | FEL2, FEL3, DD
PROC-I155 | Preliminary exchanger sizing | model | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | HTRI thermal results per exchanger and air cooler | manual | 3 | FEL3, DD
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | service, type, duty, operating and design P/T, size, MoC recommendation per tag | manual | 2 | FEL2, FEL3
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | equipment tag, service, type, duty, design P/T | manual | 3 | FEL2, FEL3, DD
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | equipment tag, type, size and operating/design P/T | manual | 2 | FEL2, FEL3, DD
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | equipment tags and duties | manual | 3 | FEL2, FEL3
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | equipment duties | manual | 3 | FEL2, FEL3, DD, COM
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PROC | PROC-T290 Prepare process description and design report | Excel / Word | equipment duties | review | 3 | FEL2, FEL3
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | per tag service, type, duty and MoC for grouping into procurement packages | manual | 2 | FEL2, FEL3
PROC-I160 | Equipment process duties | data | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | per tag type, duty, size, design P/T and MoC | manual | 2 | FEL2
PROC-I170 | Vessel and column process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | ID, T/T, liquid levels, nozzle schedule, internals type, design/operating conditions | manual | 3 | FEL3, DD
PROC-I170 | Vessel and column process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | sketch, dimensions, design and operating conditions, nozzle duties | manual | 3 | FEL3, DD
PROC-I170 | Vessel and column process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | vessel and column process datasheets | review | 2 | FEL2, FEL3, DD
PROC-I170 | Vessel and column process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | vessel/column datasheets | review | 3 | DD
PROC-I170 | Vessel and column process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | vessel/column process data | manual | 3 | FEL3, DD
PROC-I171 | Tank process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | working/gross capacity, fill/draw rates, vapour pressure, blanketing, heating | manual | 3 | FEL3, DD
PROC-I171 | Tank process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | tank throughput, vapour pressure and breathing data | manual | 2 | FEL2, FEL3, DD
PROC-I171 | Tank process datasheets | document | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | tank process data | manual | 3 | FEL3, DD
PROC-I175 | Shell-and-tube and plate exchanger process datasheets | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | duty, fluid allocation, flows, in/out T, properties, fouling, allowable dP, design P/T | manual | 3 | FEL3, DD
PROC-I175 | Shell-and-tube and plate exchanger process datasheets | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | exchanger datasheets | review | 3 | DD
PROC-I175 | Shell-and-tube and plate exchanger process datasheets | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | shell-and-tube/plate exchanger process data | manual | 3 | FEL3, DD
PROC-I176 | Air cooler process datasheets | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | duty, flows, properties, design air temperature, fan control, winterisation, allowable dP | manual | 3 | FEL3, DD
PROC-I176 | Air cooler process datasheets | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | air cooler process data | manual | 3 | FEL3, DD
PROC-I177 | Fired heater process datasheet | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | absorbed duty per case, coil in/out conditions, allowable flux and film temperature, fuel composition, turndown | manual | 3 | FEL3, DD
PROC-I177 | Fired heater process datasheet | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | fired duty and fuel | manual | 3 | FEL2, FEL3, DD
PROC-I177 | Fired heater process datasheet | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | fired duty, fuel composition and emission limits | manual | 2 | FEL2, FEL3, DD
PROC-I177 | Fired heater process datasheet | document | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | fired heater process data | manual | 3 | FEL3, DD
PROC-I180 | Pump process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | pump operating cases, flows, head, NPSHa, fluid properties, solids | manual | 3 | FEL3, DD
PROC-I180 | Pump process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | sealing considerations, solids, vapour pressure | manual | 3 | FEL3, DD
PROC-I180 | Pump process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | pump datasheets | review | 3 | DD
PROC-I180 | Pump process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | pump process data | manual | 3 | FEL3, DD
PROC-I181 | Compressor process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | gas composition per case, inlet/outlet P/T, MW, k, Z, surge/turndown, control method | manual | 3 | FEL3, DD
PROC-I181 | Compressor process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | compressor datasheets | review | 3 | DD
PROC-I181 | Compressor process datasheets | document | PROC | PROC-T180 Prepare rotating equipment process datasheets | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | compressor process data | manual | 3 | FEL3, DD
PROC-I185 | Package process specifications | document | PROC | PROC-T185 Prepare package process specifications | Excel / Word | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | package duty, battery-limit P/T/flows, utility availability, guarantees | manual | 3 | FEL3, DD
PROC-I185 | Package process specifications | document | PROC | PROC-T185 Prepare package process specifications | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | package specifications | review | 3 | DD
PROC-I185 | Package process specifications | document | PROC | PROC-T185 Prepare package process specifications | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | package duties, battery-limit conditions and guarantees | manual | 3 | FEL3, DD
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | line sizes for rack lines | manual | 2 | FEL2, FEL3, DD
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PIPE | PIPE-T070 Study critical line routing | S3D | critical-line flags, two-phase flow regime and line sizes | manual | 2 | FEL3
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | line sizes | manual | 2 | FEL2, FEL3
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | S3D | critical lines requiring hydraulic verification (gravity, two-phase, pump suction) | manual | 3 | DD
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | two-phase flow regime and slug flags | manual | 3 | DD
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | line sizes | manual | 3 | FEL2, FEL3
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | line size and critical-line flags | manual | 3 | FEL3, DD
PROC-I190 | Line sizing results | data | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | PROC | PROC-T330 Review 3D model and isometrics for process requirements | S3D | critical-line flags | review | 3 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | ELEC | ELEC-T100 Review P&IDs and assign electrical attributes | SPID | motor-driven equipment, MOVs, heat tracing/insulation codes, interlocks on IFR P&IDs | review | 2 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | equipment count, main control loops, streams needing analyzers; preliminary instrument counts from P&IDs where available | manual | 1 | FEL1, FEL2, FEL3
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | instruments, control and trip loops, valve fail positions, set points, holds on IFR/HAZOP/IFD P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | INST | INST-T050 Build and maintain the instrument index in SI | SI | instrument tags, loop numbers, service, line/equipment, P&ID number; re-created by hand in SI (SPID and SI not linked) | manual | 3 | FEL3, DD, CON
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | package boundaries shown on IFR P&IDs | manual | 3 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | IFR P&IDs for mechanical markup | review | 2 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | IFR P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | IFR P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | equipment interconnections from IFR P&IDs | integrated | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | from/to of interconnecting lines | integrated | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PIPE | PIPE-T070 Study critical line routing | S3D | IFR P&IDs for routed systems | integrated | 2 | FEL3
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | line numbers, from/to | integrated | 3 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T220 Prepare instrument process data | Excel / Word | instrument tags and locations | manual | 3 | FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | loops and equipment on P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | IFR P&IDs: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
PROC-I200 | P&IDs issued for review | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | IFR P&IDs with relief and trip loops | review | 2 | FEL2, FEL3
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | release sources on P&IDs: pump seals, flanges, vents, drains, sample points, PSV discharges | review | 3 | FEL2, FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | instruments, control and trip loops, valve fail positions, set points, holds on IFR/HAZOP/IFD P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | HAZOP-ready P&IDs for mechanical review | review | 2 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | HAZOP-ready P&IDs | review | 3 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | P&ID trip loops | review | 3 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | relief devices and overpressure sources | review | 3 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | HAZOP P&IDs | review | 3 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | HAZOP-ready P&IDs frozen revision | review | 3 | FEL3, DD
PROC-I201 | HAZOP-ready P&IDs | drawing | PROC | PROC-T200 Develop P&IDs (process content) | SPID | SAFE | SAFE-T210 Specify emergency isolation valve requirements | Excel / Word | pump/compressor suction sources and isolation points | review | 3 | FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | line number, from/to, fluid code per line | file | 4 | DD, CON
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | lines requiring tracing, maintain temperature, design/steam-out temperature, fluid | manual | 3 | DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | INST | INST-T050 Build and maintain the instrument index in SI | SI | line number, from/to and service for instrument line reference | manual | 2 | FEL3, DD, CON
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | INST | INST-T060 Enter instrument process data | SI | per line: fluid code, phase, operating/design P/T | manual | 3 | FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | service flags (steam, viscous, cryogenic) and sour/H2S, hydrogen content needing special hook-ups | manual | 3 | DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | line number, from/to, fluid, design P/T and insulation for rack lines | manual | 2 | FEL2, FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | fluid code and design P/T per line group | manual | 2 | FEL2, FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | flow, operating/design P/T and fluid per SP item line | manual | 3 | FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | line number, fluid, operating/design P/T, test pressure basis, insulation and tracing requirement | manual | 3 | FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | line count per P&ID and fluid | manual | 2 | FEL2, FEL3
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T160 Route piping in the 3D model | S3D | design P/T, fluid, insulation and critical-line flags | manual | 3 | FEL3, DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T170 Check model against P&IDs | SPF | line number, size and spec attributes for correlation | integrated | 3 | DD
PROC-I210 | Line process data | data | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | operating and design temperature per line | manual | 3 | FEL3, DD
PROC-I220 | Instrument process data | data | PROC | PROC-T220 Prepare instrument process data | Excel / Word | INST | INST-T060 Enter instrument process data | SI | per tag: min/normal/max flow, ranges, level ranges, set points, alarm/trip settings, CV allowable dP | manual | 3 | FEL3, DD
PROC-I220 | Instrument process data | data | PROC | PROC-T220 Prepare instrument process data | Excel / Word | INST | INST-T070 Size control valves | SI | CV allowable dP, shut-off dP and flow cases | manual | 3 | FEL3, DD
PROC-I220 | Instrument process data | data | PROC | PROC-T220 Prepare instrument process data | Excel / Word | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | alarm set points; operating limits and integrity operating windows | meeting | 3 | DD
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | control strategy and operating modes to check loop representation | review | 2 | FEL2, FEL3, DD
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | control strategy, process control narratives, operating modes, start-up/shutdown sequences and set points | review | 3 | FEL3, DD
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | PROC | PROC-T120 Prepare process flow diagrams | Excel / Word | main control loops to show | review | 2 | FEL2, FEL3, DD
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | control loops | manual | 2 | FEL2, FEL3
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | control and safeguarding philosophy | review | 3 | FEL3, DD
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | control philosophy | review | 2 | FEL2, FEL3
PROC-I230 | Control philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | control strategy affecting the package | review | 3 | DD
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | control narratives | review | 4 | DD, CON
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | controlled variable and turndown requiring variable speed | review | 3 | FEL3, DD
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | control strategy, process control narratives, operating modes, start-up/shutdown sequences and set points | review | 3 | FEL3, DD
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | control narratives for key loops | review | 2 | FEL3, DD
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | control narratives | manual | 4 | DD, CON
PROC-I231 | Control narratives | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | control narratives | review | 4 | DD, CON
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | final element action, fail position, required closure time; blowdown restriction orifice size and depressuring time targets | manual | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | initiator tags, set points, voting preference, final elements, process safety time | manual | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | INST | INST-T220 Write safety requirements specification | Excel / Word | trip set points, reset type, bypass needs, process safety time | manual | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | INST | INST-T240 Prepare cause and effect charts | Excel / Word | trip initiators, set points, final elements and actions; shutdown philosophy and levels | manual | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | trips and interlocks | manual | 2 | FEL2, FEL3
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | trip schedule | review | 4 | DD, CON
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | trip schedule | review | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | process safety time, trip set points and final elements | review | 3 | FEL3, DD
PROC-I235 | Trip and interlock schedule | data | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | trip initiators, set points and actions | manual | 4 | DD, CON
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | operating modes and start-up/shutdown approach | review | 2 | FEL3
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | operating philosophy | review | 4 | DD, CON
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | operating modes, sparing (A/B), continuous vs intermittent, start-up/shutdown approach for essential and restart loads | review | 1 | FEL1, FEL2, FEL3
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | operating modes and simultaneous operation for demand factors | manual | 3 | FEL3, DD, CON
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | ELEC | ELEC-T230 Run motor-starting study | ETAP | restart and re-acceleration requirements after voltage dips | review | 3 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | control strategy and operating modes to check loop representation | review | 2 | FEL2, FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | control strategy, process control narratives, operating modes, start-up/shutdown sequences and set points | review | 3 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | INST | INST-T240 Prepare cause and effect charts | Excel / Word | trip initiators, set points, final elements and actions; shutdown philosophy and levels | manual | 3 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | operating philosophy | review | 2 | FEL2, FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | operating philosophy as procedure outline | review | 3 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | PIPE | PIPE-T110 Prepare valve specifications and datasheets | Excel / Word | isolation and blinding philosophy, tight shut-off and special service needs | manual | 2 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | operating philosophy | review | 3 | FEL3, DD
PROC-I240 | Operating philosophy | document | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | operating modes and philosophy | manual | 4 | DD, CON
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | INST | INST-T100 Specify relief valves from the process sizing | SI | governing case, relieving rate, set and back pressure, fluid MW/T/Z/k, required area and orifice letter (copied by hand) | manual | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | relief load, set pressure and fluid for PSV reaction forces | manual | 3 | DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | PSV set pressures | manual | 2 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | PSV set pressures | manual | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PROC | PROC-T255 Review vendor relief valve sizing | Excel / Word | relief cases and required capacities to check against | manual | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | relief loads and coincident scenarios | integrated | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Flare / relief tool | relief rate, MW, T and composition per governing scenario | integrated | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | SAFE | SAFE-T140 Review relief and depressuring scenarios | Excel / Word | relief scenarios and loads per device | review | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | SAFE | SAFE-T240 Perform noise study | Excel / Word | PSV and flare noise source rates | manual | 3 | FEL3, DD
PROC-I250 | Relief load summary | data | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | relief design basis | review | 4 | DD, CON, COM
PROC-I251 | PSV process datasheets | document | PROC | PROC-T250 Calculate relief loads and size relief valves | Excel / Word | INST | INST-T100 Specify relief valves from the process sizing | SI | governing case, relieving rate, set and back pressure, fluid MW/T/Z/k, required area and orifice letter (copied by hand) | manual | 3 | FEL3, DD
PROC-I251 | PSV process datasheets | document | PROC | PROC-T250 Calculate relief loads and size relief valves | Excel / Word | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | S3D | PSV tags, inlet/outlet sizes and allowable back pressure for inlet loss and tailpipe checks | manual | 3 | DD
PROC-I251 | PSV process datasheets | document | PROC | PROC-T250 Calculate relief loads and size relief valves | Excel / Word | SAFE | SAFE-T140 Review relief and depressuring scenarios | Excel / Word | PSV relieving conditions | review | 3 | FEL3, DD
PROC-I251 | PSV process datasheets | document | PROC | PROC-T250 Calculate relief loads and size relief valves | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PSV set pressures and governing cases | review | 3 | FEL3, DD
PROC-I255 | Process review of vendor relief valve sizing | decision | PROC | PROC-T255 Review vendor relief valve sizing | Excel / Word | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | process acceptance of vendor sizing per PSV | meeting | 3 | FEL3, DD
PROC-I260 | Flare network hydraulic results | data | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | INST | INST-T100 Specify relief valves from the process sizing | SI | built-up back pressure at each device | manual | 3 | FEL3, DD
PROC-I260 | Flare network hydraulic results | data | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Flare / relief tool | flare tip loads per scenario | integrated | 3 | FEL3, DD
PROC-I261 | Depressuring study results | document | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | final element action, fail position, required closure time; blowdown restriction orifice size and depressuring time targets | manual | 3 | FEL3, DD
PROC-I261 | Depressuring study results | document | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | depressuring time to target pressure | manual | 3 | FEL3, DD
PROC-I261 | Depressuring study results | document | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | SAFE | SAFE-T140 Review relief and depressuring scenarios | Excel / Word | depressuring per segment and time to target | review | 3 | FEL3, DD
PROC-I270 | Utility consumption list | data | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | power estimate per consumer, normal/peak/intermittent | manual | 1 | FEL1, FEL2
PROC-I271 | Utility system balances | document | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | steam balance: availability and levels for turbine drivers | manual | 2 | FEL2, FEL3
PROC-I271 | Utility system balances | document | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | fuel gas balance and flare purge/pilot use | manual | 2 | FEL2, FEL3, DD
PROC-I275 | Chemical and catalyst consumption list | data | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | COMM | COMM-T100 Define commissioning spares, consumables and first fills | Excel / Word | chemical and catalyst first-fill quantities | manual | 3 | DD
PROC-I275 | Chemical and catalyst consumption list | data | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | PROC | PROC-T185 Prepare package process specifications | Excel / Word | chemical consumption and dosing rates | manual | 2 | FEL3, DD
PROC-I275 | Chemical and catalyst consumption list | data | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | first-fill quantities | manual | 3 | DD, CON, COM
PROC-I275 | Chemical and catalyst consumption list | data | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | chemicals and catalysts with hazard class and first-fill/storage quantities | review | 2 | FEL2, FEL3
PROC-I280 | Effluent and emissions data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | effluent and drain flows, composition and frequency per source | manual | 3 | FEL3, DD
PROC-I280 | Effluent and emissions data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | PIPE | PIPE-T270 Design underground piping | S3D | effluent and drain flows and composition | manual | 3 | DD
PROC-I280 | Effluent and emissions data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | CO2/NOx/SOx/VOC per point source, flare and vent streams; fugitive emissions basis and component service counts | manual | 2 | FEL2, FEL3, DD
PROC-I280 | Effluent and emissions data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | wastewater flow, composition, temperature and solid/liquid waste | manual | 2 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | per release source: composition, P, T, phase, flash point, MW, fluid category for HAC | manual | 2 | FEL2, FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | toxic content (H2S), flash point and fluid category | manual | 3 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | composition, inventory, flash point, MW and toxic content per isolatable section | manual | 2 | FEL2, FEL3
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | release streams: composition, P, T, phase, inventory per isolatable section | manual | 1 | FEL2
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | release scenarios: composition, P, T, inventory per isolatable section | manual | 3 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | isolatable section inventory, composition, P, T | manual | 3 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | gas composition and H2S content per area | manual | 3 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T210 Specify emergency isolation valve requirements | Excel / Word | inventories per section | review | 3 | FEL3, DD
PROC-I285 | Release source and fluid data | data | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | maximum inventories per section | manual | 3 | DD, CON
PROC-I290 | Process description and design report | document | PROC | PROC-T290 Prepare process description and design report | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | process design report, key decisions and open items | review | 3 | FEL1, FEL2, FEL3
PROC-I290 | Process description and design report | document | PROC | PROC-T290 Prepare process description and design report | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | open items, assumptions and deviations from basis | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
PROC-I300 | HAZOP action responses (process) | decision | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | process action responses | review | 3 | FEL3, DD, CON
PROC-I301 | P&ID markups from HAZOP | drawing | PROC | PROC-T300 Participate in HAZOP and close process actions | SPID | INST | INST-T055 Close out HAZOP and LOPA actions on I&C design | PHA tool | clouded P&ID changes from HAZOP and the IFD P&IDs that incorporate them | review | 3 | FEL3, DD
PROC-I301 | P&ID markups from HAZOP | drawing | PROC | PROC-T300 Participate in HAZOP and close process actions | SPID | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | clouded HAZOP P&ID changes | integrated | 3 | FEL3, DD
PROC-I301 | P&ID markups from HAZOP | drawing | PROC | PROC-T300 Participate in HAZOP and close process actions | SPID | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | HAZOP markups | manual | 3 | DD
PROC-I301 | P&ID markups from HAZOP | drawing | PROC | PROC-T300 Participate in HAZOP and close process actions | SPID | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | P&ID changes from HAZOP | review | 3 | FEL3, DD, CON
PROC-I305 | Process technical bid evaluation input | document | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | process acceptability of each offer (duty, performance) | manual | 3 | FEL3, DD
PROC-I310 | Process comments on vendor data | document | PROC | PROC-T310 Review vendor data against process duties | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | process review code and comments on vendor performance and P&IDs | review | 2 | DD, CON
PROC-I315 | As-designed H&MB (vendor reconciled) | data | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | reconciled H&MB values | manual | 3 | DD
PROC-I320 | Process TQ responses and hold releases | decision | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | MECH | MECH-T320 Close requisition holds | Excel / Word | process data values confirmed and hold releases | manual | 3 | DD
PROC-I320 | Process TQ responses and hold releases | decision | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | S3D | P&ID hold answers and release dates | manual | 3 | DD
PROC-I325 | Process comments on instrument datasheets | document | PROC | PROC-T325 Review instrument and control valve sizing | Document Locator | INST | INST-T110 Prepare instrument datasheets | SI | process comments on instrument datasheets | review | 3 | FEL3, DD
PROC-I330 | Process 3D model review comments | document | PROC | PROC-T330 Review 3D model and isometrics for process requirements | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | slope, pocket, NPSH, two-phase and PSV location comments | meeting | 3 | FEL3, DD
PROC-I335 | Tie-in process conditions | data | PROC | PROC-T210 Prepare line list and tie-in process data | Excel / Word | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | fluid, operating/design P/T, hot-tap feasibility and isolation/purging per tie-in; hot tap and isolation requirements (taken from process tie-in conditions) | manual | 3 | FEL3, DD, CON
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | drain connections to oily water and closed drain systems on IFD P&IDs | manual | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | IFD P&IDs: line numbers, valves, equipment tags | file | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | running vs spare equipment and motor tags on IFD P&IDs | manual | 3 | FEL3, DD, CON
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | instruments, control and trip loops, valve fail positions, set points, holds on IFR/HAZOP/IFD P&IDs | review | 2 | FEL2, FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | INST | INST-T050 Build and maintain the instrument index in SI | SI | instrument tags, loop numbers, service, line/equipment, P&ID number; re-created by hand in SI (SPID and SI not linked) | manual | 3 | FEL3, DD, CON
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | INST | INST-T055 Close out HAZOP and LOPA actions on I&C design | PHA tool | clouded P&ID changes from HAZOP and the IFD P&IDs that incorporate them | review | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | SP item tags, sizes, line numbers and service on IFD P&IDs | integrated | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T160 Route piping in the 3D model | S3D | IFD P&IDs: line numbers, sizes, specs, valves, SP items, in-line instrument tags | integrated | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T170 Check model against P&IDs | SPF | P&ID lines, valves, SP items and instruments published from SPID | integrated | 3 | DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T270 Design underground piping | S3D | drain system P&IDs | integrated | 3 | DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | updated IFD P&IDs | integrated | 3 | FEL3, DD
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | tie-in points on P&IDs | integrated | 3 | FEL3, DD, CON
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | IFD P&IDs: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | IFD P&IDs | review | 3 | DD, CON
PROC-I340 | P&IDs issued for design | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | P&IDs at package battery limits | review | 3 | DD
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | IFC P&IDs | review | 4 | DD, CON
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | IFC P&IDs for marking test boundaries | manual | 4 | CON
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | INST | INST-T380 Prepare system configuration data for vendors | SI | IFC P&IDs for graphics | review | 4 | DD
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | IFC P&IDs | review | 4 | DD, CON
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | IFC P&IDs | review | 4 | DD, CON, COM
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | IFC P&IDs | integrated | 4 | COM
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | IFC P&IDs: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
PROC-I341 | P&IDs issued for construction | drawing | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | IFC P&IDs approved for construction | review | 4 | DD, CON
PROC-I345 | Process change impact assessment | document | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | affected streams, equipment, lines, rework estimate per change | manual | 2 | FEL3, DD, CON
PROC-I345 | Process change impact assessment | document | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | changes needing HAZOP re-review | review | 3 | DD, CON
PROC-I345 | Process change impact assessment | document | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | process change impact | review | 3 | DD, CON, COM
PROC-I350 | Operating manual process input | document | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | alarm set points; operating limits and integrity operating windows | meeting | 3 | DD
PROC-I350 | Operating manual process input | document | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | operating limits, control and trip descriptions | manual | 4 | DD, CON
PROC-I350 | Operating manual process input | document | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | operating manual process input | review | 4 | CON, COM
PROC-I350 | Operating manual process input | document | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | operating limits | review | 4 | DD, CON, COM
PROC-I355 | Process system boundary markups | drawing | PROC | PROC-T360 Prepare process input to systemization and commissioning | SPID | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | process system/subsystem boundaries, isolation points and commissioning sequence preference | file | 3 | FEL3, DD
PROC-I360 | Process commissioning requirements | document | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | cleaning/flushing method, drying dew point, inerting limits per system | review | 4 | DD, CON
PROC-I360 | Process commissioning requirements | document | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | COMM | COMM-T100 Define commissioning spares, consumables and first fills | Excel / Word | first-fill list per system | manual | 3 | DD
PROC-I365 | Start-up and shutdown procedures | document | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | start-up and shutdown steps and hold points | review | 4 | DD, CON
PROC-I365 | Start-up and shutdown procedures | document | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | control strategy, process control narratives, operating modes, start-up/shutdown sequences and set points | review | 3 | FEL3, DD
PROC-I365 | Start-up and shutdown procedures | document | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | start-up and shutdown steps | manual | 4 | DD, CON
PROC-I370 | Process RFI responses and field change dispositions | decision | PROC | PROC-T370 Respond to field RFIs and review field changes | Procore | COMM | COMM-T210 Raise commissioning technical queries | Procore | process answers and P&ID impact | manual | 4 | COM
PROC-I370 | Process RFI responses and field change dispositions | decision | PROC | PROC-T370 Respond to field RFIs and review field changes | Procore | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | need for MOC/HAZOP review | review | 3 | DD, CON, COM
PROC-I375 | Commissioning process punch and troubleshooting log | data | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | COMM | COMM-T210 Raise commissioning technical queries | Procore | commissioning troubleshooting and set point changes | manual | 4 | COM
PROC-I380 | Performance test procedure and report | document | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | COMM | COMM-T250 Support performance test run | Excel / Word | test conditions, measurements, guarantee figures and acceptance criteria; performance test procedure and acceptance criteria | review | 4 | COM
PROC-I385 | As-built P&IDs | drawing | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | as-built P&IDs | review | 4 | COM
PROC-I385 | As-built P&IDs | drawing | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | as-built P&IDs | review | 4 | DD, CON, COM
PROC-I385 | As-built P&IDs | drawing | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | as-built P&IDs and line data for LDAR tagging | file | 4 | COM
PROC-I390 | Analyzer requirements | data | PROC | PROC-T220 Prepare instrument process data | Excel / Word | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | Analyzer requirements list: stream, components to measure, ranges, response time | manual | 3 | FEL3, DD
PROC-I391 | Assay data gaps and requested cuts | data | PROC | PROC-T020 Characterise feed and set up assay in simulation | Excel / Word | OWNR | OWNR-T020 Supply crude assays and feed cases | Excel / Word | assay characterisation gaps and requested additional assay cuts (TBP, sulfur, metals, acidity) | manual | 1 | FEL1, FEL2
PROC-I392 | Flare stack basis | data | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Flare / relief tool | Flare stack height, tip type and diameter, and flare location basis | manual | 3 | FEL3, DD
PROC-I901 | Process deliverables list | data | PROC | PROC-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | Process deliverables list: titles, document types, sheet counts, planned IFR/IFD/IFC dates | manual | 2 | FEL2, FEL3, DD, CON
PROC-I902 | Process progress measurement | data | PROC | PROC-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Process progress per deliverable (percent complete by rules of credit) | manual | 2 | FEL3, DD
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | wetland, habitat and receiving-water constraints affecting earthworks and drainage | meeting | 1 | FEL1
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | OWNR | OWNR-T050 Define owner design basis requirements | Excel / Word | emission, discharge and noise limits | review | 1 | FEL2, FEL3
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | receiving water limits and air attainment constraints | review | 2 | FEL2, FEL3
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | permit lead times and environmental constraints | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | attainment status, receptors and permit triggers | manual | 1 | FEL1, FEL2
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | environmental aspects and constraints for ENVID | review | 1 | FEL1, FEL2
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | receptors and permit constraints per site | manual | 1 | FEL1
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | environmental limits and permit triggers | manual | 1 | FEL2, FEL3
SAFE-I010 | Environmental constraints register | document | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | SAFE | SAFE-T240 Perform noise study | Excel / Word | property line noise limits | manual | 2 | FEL3, DD
SAFE-I015 | Option SHE screening ranking | decision | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | option SHE ranking and siting risk | review | 3 | FEL1, FEL2, FEL3
SAFE-I015 | Option SHE screening ranking | decision | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | inherent safety score, inventory, offsite distance and emissions per option | meeting | 2 | FEL2
SAFE-I015 | Option SHE screening ranking | decision | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | permitting pathway and SHE risks per option | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
SAFE-I015 | Option SHE screening ranking | decision | SAFE | SAFE-T015 Screen configuration options for inherent safety and environmental impact | Excel / Word | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | option SHE ranking | manual | 1 | FEL1
SAFE-I020 | HAZID / ENVID register | document | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | OWNR | OWNR-T070 Approve gate decisions | Excel / Word | HAZID risk ranking | review | 3 | FEL1, FEL2, FEL3
SAFE-I020 | HAZID / ENVID register | document | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | PROC | PROC-T080 Prepare process input to select decision | Excel / Word | HAZID hazards and risk ranking per option | meeting | 2 | FEL2
SAFE-I020 | HAZID / ENVID register | document | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | PROC | PROC-T290 Prepare process description and design report | Excel / Word | HAZID outcomes | review | 3 | FEL2, FEL3
SAFE-I020 | HAZID / ENVID register | document | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | HAZID register and risk ranking | review | 3 | FEL1, FEL2, FEL3
SAFE-I022 | HAZID actions list | data | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | HAZID layout actions | review | 3 | FEL3, DD
SAFE-I022 | HAZID actions list | data | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | HAZID actions affecting design basis | manual | 1 | FEL2, FEL3
SAFE-I022 | HAZID actions list | data | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | open HAZID actions | review | 2 | FEL2, FEL3
SAFE-I030 | Site selection SHE assessment | document | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | flood/wind exposure, separation to receptors and emergency access per site | meeting | 1 | FEL1
SAFE-I030 | Site selection SHE assessment | document | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | preliminary worst-case hazard zones and receptor distances per site | review | 1 | FEL1
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | LFL/UFL, autoignition temperature, gas group and T-class per material | manual | 2 | FEL2, FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | toxicity (IDLH/ERPG) and flammability of pumped fluids | review | 3 | FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | hazardous materials and inventory basis | meeting | 2 | FEL2, FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | flammability and toxicity properties | manual | 2 | FEL2
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | material properties | manual | 3 | FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | corrosive and toxic materials | manual | 3 | FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | SAFE | SAFE-T255 Review hazardous area classification | Excel / Word | gas group and T-class | manual | 3 | FEL3, DD
SAFE-I035 | Hazardous materials inventory and properties | data | SAFE | SAFE-T035 Compile hazardous materials inventory and properties | Excel / Word | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | RMP threshold check | manual | 3 | DD, CON
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | design blast and fire load method, codes and regulations | review | 1 | FEL2, FEL3
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | codes, design fire loads, F&G targets, fire water basis | manual | 2 | FEL2, FEL3
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | OWNR | OWNR-T060 Set risk tolerance criteria | Excel / Word | study basis and draft risk tolerance criteria | review | 1 | FEL2
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | spacing codes, fire-fighting access and design fire basis | manual | 2 | FEL2, FEL3
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | depressuring and flare design criteria | review | 3 | FEL3, DD
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | study schedule in the SHE design basis: list of safety studies and planned workshop/report dates | manual | 2 | FEL2, FEL3, DD, CON
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | siting criteria and design frequency | manual | 3 | FEL3, DD
SAFE-I040 | SHE design basis | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | risk criteria method | manual | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | overpressure contours, recommended spacing and building locations | review | 2 | FEL1, FEL2, FEL3
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | overpressure contours for open structures | review | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | overpressure and fire distances affecting substation/building locations | review | 1 | FEL2, FEL3
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | flash fire extents and dispersion distances affecting classified extents | review | 2 | FEL2, FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | fire extents | manual | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | recommended block spacing, sterile areas and building locations | review | 1 | FEL1
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | recommended equipment spacing and sterile areas | manual | 2 | FEL2, FEL3
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | hazard distances, spacing changes and marked-up plot plan | review | 2 | FEL2, FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | PROC | PROC-T095 Define process layout requirements | Excel / Word | recommended equipment spacing and hazard distances | review | 2 | FEL2, FEL3
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | toxic dispersion distances | manual | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | release sizes and hazard extents | manual | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | hazard contours | manual | 3 | FEL3, DD
SAFE-I050 | Preliminary hazard distances and spacing comments | document | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | hazard zones | manual | 3 | DD, CON, COM
SAFE-I060 | Emissions inventory | data | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | NOx/CO/SOx limits per source, stack height and diameter | manual | 3 | FEL3, DD
SAFE-I060 | Emissions inventory | data | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | emission inventory format per source | review | 2 | FEL2, FEL3, DD
SAFE-I060 | Emissions inventory | data | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | PTE per source and stack parameters | manual | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | generator emission requirements (EPA tier, NSPS) | review | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | CEMS and flare monitoring requirements; permit monitoring conditions | review | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | fugitive emission/LDAR and tank seal requirements affecting equipment standards | manual | 2 | FEL2
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | low-NOx burner/SCR and CEMS requirements | manual | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | tank seal type and vapour control requirements | manual | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | emission control requirements per source for packages | review | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | LDAR and fugitive emission requirements driving dual seals | review | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | tank seal type and vapour control requirements | review | 2 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | PROC | PROC-T175 Prepare heat transfer equipment process datasheets | Excel / Word | low-NOx burner/SCR and CEMS requirements per fired source | review | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | emission control equipment requirements (SCR, vapour control, CEMS) | manual | 2 | FEL3
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | BACT/NSPS/NESHAP requirements | manual | 3 | FEL3, DD
SAFE-I062 | Emission control requirements | document | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | CEMS and LDAR requirements | manual | 4 | COM
SAFE-I070 | Air permit application package | document | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | air permit application package | review | 3 | FEL2, FEL3
SAFE-I072 | Permit conditions register | data | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | CEMS and flare monitoring requirements; permit monitoring conditions | review | 3 | FEL3, DD
SAFE-I072 | Permit conditions register | data | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | permit conditions and limits | review | 2 | FEL2, FEL3, DD
SAFE-I072 | Permit conditions register | data | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | permit conditions | manual | 4 | CON
SAFE-I072 | Permit conditions register | data | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | notification and testing conditions | manual | 4 | COM
SAFE-I080 | Wastewater and stormwater permit data | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | outfall data, pretreatment limits and monitoring points | manual | 3 | FEL3, DD
SAFE-I080 | Wastewater and stormwater permit data | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | wastewater and stormwater permit data | review | 3 | FEL2, FEL3
SAFE-I080 | Wastewater and stormwater permit data | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | SWPPP basis | manual | 4 | CON
SAFE-I082 | Secondary containment and spill control requirements | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | curbed and contained areas, containment volumes, dike and curb locations | review | 2 | FEL3, DD
SAFE-I082 | Secondary containment and spill control requirements | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | contaminated firewater runoff containment and oil/water separator basis | manual | 3 | FEL3, DD
SAFE-I082 | Secondary containment and spill control requirements | document | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | CIVL | CIVL-T120 Design tank dikes and containment | Excel / Word | required containment volumes (110% plus rainfall), dike locations, remote impounding | review | 3 | FEL3, DD
SAFE-I090 | Preliminary HAZOP actions | data | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | Excel / Word | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | preliminary HAZOP layout and isolation actions | review | 3 | FEL3, DD
SAFE-I090 | Preliminary HAZOP actions | data | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | Excel / Word | PROC | PROC-T290 Prepare process description and design report | Excel / Word | preliminary HAZOP actions affecting process design | review | 3 | FEL2, FEL3
SAFE-I100 | Building blast loads | data | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | side-on and reflected overpressure, impulse and duration per building | manual | 3 | FEL3, DD
SAFE-I100 | Building blast loads | data | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | blast overpressure and impulse per building | review | 3 | FEL2, FEL3, DD
SAFE-I100 | Building blast loads | data | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | siting consequence results | manual | 3 | FEL3, DD
SAFE-I100 | Building blast loads | data | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | siting results | manual | 4 | DD, CON, COM
SAFE-I100 | Building blast loads | data | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | siting | manual | 4 | COM
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | building acceptability and relocation decisions | review | 2 | FEL1, FEL2, FEL3
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | building acceptability and occupancy restrictions | review | 2 | FEL2, FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | required hardening per building | manual | 3 | FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | building acceptability per API 752, hardening or relocation required | review | 3 | FEL2, FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | building acceptability, relocation and occupancy restrictions | review | 2 | FEL2, FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | building siting decisions | review | 3 | FEL1, FEL2, FEL3
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | occupied building locations and siting decisions | manual | 3 | FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | building siting | review | 3 | FEL2, FEL3, DD
SAFE-I102 | Building siting decisions and occupancy restrictions | decision | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | building siting | manual | 3 | DD, CON, COM
SAFE-I104 | Portable building siting restrictions | document | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | API 753 exclusion zones for trailers and temporary buildings, allowed locations | review | 3 | FEL2, FEL3, DD
SAFE-I110 | Building toxic ingress and HVAC shutdown requirements | document | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | H2S/flammable detectors at intakes, damper closure times, building tightness | review | 3 | FEL3, DD
SAFE-I110 | Building toxic ingress and HVAC shutdown requirements | document | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | F&G philosophy, zones, voting, executive actions, deluge activation logic, HVAC intake detection and damper closure | review | 3 | FEL3, DD
SAFE-I120 | QRA results | document | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | QRA | manual | 4 | DD, CON, COM
SAFE-I120 | QRA results | document | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | QRA | manual | 4 | COM
SAFE-I122 | QRA risk reduction recommendations | data | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | QRA spacing and isolation recommendations | review | 3 | FEL3, DD
SAFE-I122 | QRA risk reduction recommendations | data | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | SAFE | SAFE-T210 Specify emergency isolation valve requirements | Excel / Word | QRA isolation recommendations | manual | 3 | FEL3, DD
SAFE-I130 | Flare radiation and sterile zone results | document | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | flare sterile zone radius and radiation contours at grade | review | 2 | FEL2, FEL3, DD
SAFE-I130 | Flare radiation and sterile zone results | document | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Excel / Word | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | radiation limits and sterile zone | review | 3 | FEL3, DD
SAFE-I140 | Relief study review comments | document | SAFE | SAFE-T140 Review relief and depressuring scenarios | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | relief study comments | review | 2 | FEL2, FEL3, DD
SAFE-I150 | HAZOP worksheets and report | document | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | HAZOP worksheets | meeting | 3 | FEL3, DD
SAFE-I150 | HAZOP worksheets and report | document | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | HAZOP nodes, deviations and safeguards | manual | 3 | FEL3, DD
SAFE-I150 | HAZOP worksheets and report | document | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | HAZOP report | review | 3 | FEL1, FEL2, FEL3
SAFE-I150 | HAZOP worksheets and report | document | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | scenarios, causes and severity | integrated | 3 | FEL3, DD
SAFE-I150 | HAZOP worksheets and report | document | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | HAZOP report | manual | 4 | DD, CON, COM
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | HAZOP recommendations affecting vents, drains and release sources | review | 3 | FEL3, DD, CON
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | HAZOP recommendations adding or changing instruments, alarms and interlocks | review | 3 | FEL2, FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | INST | INST-T055 Close out HAZOP and LOPA actions on I&C design | PHA tool | HAZOP recommendations and LOPA SIF/IPL actions assigned to I&C, with priority and due date | manual | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | HAZOP recommendations assigned to mechanical | manual | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | recommendations register | meeting | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | S3D | HAZOP recommendations assigned to piping | review | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | HAZOP recommendations for new trips/interlocks | manual | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | recommendations assigned to process | manual | 3 | FEL3, DD
SAFE-I152 | HAZOP recommendations register | data | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | SAFE | SAFE-T140 Review relief and depressuring scenarios | Excel / Word | overpressure HAZOP recommendations | manual | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | SIL targets and process safety time per SIF | review | 4 | COM
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | INST | INST-T055 Close out HAZOP and LOPA actions on I&C design | PHA tool | HAZOP recommendations and LOPA SIF/IPL actions assigned to I&C, with priority and due date | manual | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | INST | INST-T190 Prepare SIS specification | Excel / Word | number of SIFs and SIL targets | review | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | LOPA scenarios, required RRF/SIL per SIF | meeting | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | INST | INST-T220 Write safety requirements specification | Excel / Word | required SIL/RRF, safe state, process safety time, LOPA assumptions | review | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | PROC | PROC-T235 Define trips, interlocks and process input to SIF | Excel / Word | SIF requirements and target SIL per scenario | manual | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | LOPA scenarios and SIL targets | review | 3 | FEL3, DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | SIL targets | manual | 3 | DD
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | LOPA | manual | 4 | DD, CON, COM
SAFE-I160 | LOPA scenarios and SIL targets | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | SIF tags, SIL and safe state affecting the package | manual | 3 | DD
SAFE-I162 | Non-SIF IPL and safeguard requirements | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | mechanical IPLs (check valves, PSVs) requiring independence and testing | manual | 3 | FEL3, DD
SAFE-I162 | Non-SIF IPL and safeguard requirements | data | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | PROC | PROC-T300 Participate in HAZOP and close process actions | PHA tool | credited non-SIF IPLs | review | 3 | FEL3, DD
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | OWNR | OWNR-T130 Take part in HAZOP and accept actions | PHA tool | action responses and close-out evidence | meeting | 3 | FEL3, DD
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | HAZOP/LOPA action close-out status | review | 4 | DD
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | PROJ | PROJ-T130 Measure engineering progress | P6 | action close-out status and closure dates for safety progress | manual | 2 | FEL3, DD
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | PROJ | PROJ-T170 Prepare gate review packages and record gate decisions | Document Locator | open safety actions | review | 3 | FEL1, FEL2, FEL3
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | close-out records | manual | 4 | DD, CON, COM
SAFE-I170 | Action close-out records | data | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | open actions | manual | 4 | COM
SAFE-I180 | F&G detector layout and coverage | drawing | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | detector tag, type, coordinates, elevation, orientation, coverage per zone | manual | 3 | FEL3, DD
SAFE-I180 | F&G detector layout and coverage | drawing | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | F&G mapping | manual | 4 | COM
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | HVAC trip executive actions per F&G zone | review | 3 | FEL3, DD
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | F&G zones and deluge actions | manual | 3 | FEL3, DD
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | F&G philosophy, zones, voting, executive actions, deluge activation logic, HVAC intake detection and damper closure | review | 3 | FEL3, DD
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | INST | INST-T240 Prepare cause and effect charts | Excel / Word | F&G zones, voting and executive actions | review | 3 | FEL3, DD
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | F&G executive actions | manual | 3 | DD
SAFE-I182 | F&G zones and executive action requirements | data | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | F&G zones | manual | 3 | DD, CON, COM
SAFE-I210 | Emergency isolation valve requirements | data | SAFE | SAFE-T210 Specify emergency isolation valve requirements | Excel / Word | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | EIV locations, closure time, fire-safe test (API 607); actuator and cable fireproofing rating | review | 3 | FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | escape routes, muster points and emergency access | review | 3 | FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | escape route requirements | review | 3 | FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | escape routes and exits | review | 3 | DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | escape routes, muster points, safety showers for emergency lighting | review | 3 | DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | alarm tones, muster and evacuation; beacon and horn locations; alarm and beacon philosophy for PA/GA zoning | review | 3 | FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | safety shower, escape route and muster locations | meeting | 3 | FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | safety equipment layout | review | 3 | FEL2, FEL3, DD
SAFE-I230 | Safety equipment and escape route layout | drawing | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | muster and escape routes | manual | 3 | DD, CON, COM
SAFE-I240 | Equipment noise limits | data | SAFE | SAFE-T240 Perform noise study | Excel / Word | INST | INST-T070 Size control valves | SI | maximum sound pressure level at 1 m for control valves | review | 2 | FEL3, DD
SAFE-I240 | Equipment noise limits | data | SAFE | SAFE-T240 Perform noise study | Excel / Word | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | maximum sound pressure level at 1 m per equipment type | manual | 2 | FEL2
SAFE-I240 | Equipment noise limits | data | SAFE | SAFE-T240 Perform noise study | Excel / Word | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | noise limit per air-cooler fan | manual | 2 | FEL3, DD
SAFE-I240 | Equipment noise limits | data | SAFE | SAFE-T240 Perform noise study | Excel / Word | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | heater and burner noise limits | manual | 2 | FEL3, DD
SAFE-I242 | Noise study results and mitigation | document | SAFE | SAFE-T240 Perform noise study | Excel / Word | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | noise limits and mitigation per machine | manual | 3 | FEL3, DD
SAFE-I250 | Safety model review comments | document | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | spacing, escape, fire-fighting access and valve operability comments | meeting | 3 | FEL3, DD
SAFE-I255 | Hazardous area classification review comments | document | SAFE | SAFE-T255 Review hazardous area classification | Document Locator | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | comments on missing sources, extents, gas group/T-class | review | 3 | FEL3, DD, CON
SAFE-I255 | Hazardous area classification review comments | document | SAFE | SAFE-T255 Review hazardous area classification | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | hazardous area classification comments | review | 2 | FEL2, FEL3, DD
SAFE-I260 | C&E and SIL verification review comments | document | SAFE | SAFE-T260 Review cause and effect and SIL verification | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | C&E and SIL verification comments | review | 2 | FEL2, FEL3, DD
SAFE-I270 | Vendor SHE review comments | document | SAFE | SAFE-T270 Review vendor packages and bids for SHE compliance | Document Locator | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | SHE compliance of each package offer | manual | 3 | FEL3, DD
SAFE-I280 | Package and revalidation HAZOP actions | data | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | package and revalidation HAZOP actions affecting P&IDs | manual | 3 | DD
SAFE-I290 | PSM process safety information package | document | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | process safety information for operating procedures and training | review | 4 | DD, CON
SAFE-I300 | RMP offsite consequence and registration data | document | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | RMP registration data to submit | review | 4 | FEL2, FEL3
SAFE-I310 | Emergency response planning data | document | SAFE | SAFE-T310 Provide emergency response planning input | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | alarm tones, muster and evacuation; beacon and horn locations; alarm and beacon philosophy for PA/GA zoning | review | 3 | FEL3, DD
SAFE-I320 | Construction environmental compliance requirements | document | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | environmental compliance requirements for construction | review | 3 | FEL3, DD
SAFE-I330 | MOC safety review decisions | decision | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | MOC decisions | manual | 4 | COM
SAFE-I330 | MOC safety review decisions | decision | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | MOC decisions | manual | 4 | COM
SAFE-I340 | PSSR checklist and findings | data | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | PSSR findings per system | review | 4 | COM
SAFE-I342 | PSSR sign-off | decision | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | PSSR sign-off | review | 4 | COM
SAFE-I350 | Startup environmental compliance records | document | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | OWNR | OWNR-T210 Accept system handover | Smart Completions | startup environmental compliance records at handover | review | 4 | COM
SAFE-I360 | As-built safety studies | document | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | OWNR | OWNR-T230 Accept final documentation | Document Locator | as-built safety studies in the handover documentation | review | 4 | COM
SAFE-I370 | Security vulnerability assessment | document | SAFE | SAFE-T040 Prepare SHE design basis and risk criteria | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | Security vulnerability assessment defining CCTV coverage and access control requirements | review | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | CIVL | CIVL-T020 Prepare civil and structural design basis | Excel / Word | fireproofing criteria (API 2218) for structural design criteria | review | 1 | FEL2, FEL3
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | fire water source/redundancy and F&G basis for emergency power | review | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | fire water design basis | manual | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | fixed system philosophy | manual | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | detector types and F&G philosophy; ambient design temperatures, humidity and wind for instrument selection | review | 2 | FEL2, FEL3
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | F&G philosophy, zones, voting, executive actions, deluge activation logic, HVAC intake detection and damper closure | review | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | alarm tones, muster and evacuation; beacon and horn locations; alarm and beacon philosophy for PA/GA zoning | review | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | F&G and fixed fire protection philosophy for packages | review | 3 | FEL3, DD
FIRE-I045 | Fire protection and F&G philosophy | document | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | coverage targets and detector types | manual | 3 | FEL3, DD
FIRE-I190 | Fire water demand and pump duty | data | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | firewater design flows and duration for runoff sizing | manual | 3 | FEL3, DD
FIRE-I190 | Fire water demand and pump duty | data | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | fire water pump duty (electric vs diesel driver) | review | 3 | FEL3, DD
FIRE-I190 | Fire water demand and pump duty | data | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | fire water demand and pressure | manual | 3 | FEL3, DD
FIRE-I190 | Fire water demand and pump duty | data | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | fire water demand and fire pump duty | manual | 3 | FEL3, DD
FIRE-I192 | Fire water network, hydrant and monitor layout requirements | drawing | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | hydrant and monitor locations to keep accessible by fire vehicles | review | 3 | FEL3, DD
FIRE-I192 | Fire water network, hydrant and monitor layout requirements | drawing | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | ring main routing basis, hydrant and monitor locations, isolation valve sectioning | file | 3 | DD, CON
FIRE-I192 | Fire water network, hydrant and monitor layout requirements | drawing | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | firewater line penetrations | manual | 3 | DD
FIRE-I192 | Fire water network, hydrant and monitor layout requirements | drawing | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | PIPE | PIPE-T270 Design underground piping | S3D | ring main sizing basis, hydrant and monitor locations, isolation valve sectioning | manual | 3 | DD
FIRE-I192 | Fire water network, hydrant and monitor layout requirements | drawing | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | hydrant and monitor layout | review | 3 | FEL2, FEL3, DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | CIVL | CIVL-T260 Define structural fireproofing extent | Excel / Word | fire-scenario envelopes in plan and elevation | manual | 3 | DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | fire zones | manual | 3 | FEL3, DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | PROC | PROC-T170 Prepare static equipment process datasheets | Excel / Word | fire zones for fire-case nozzle/venting basis | review | 2 | FEL3, DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | fire zone boundaries for fire-case grouping | manual | 3 | FEL3, DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | SAFE | SAFE-T140 Review relief and depressuring scenarios | Excel / Word | fire zones | manual | 3 | FEL3, DD
FIRE-I200 | Fire zones and fireproofing envelopes | drawing | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | SAFE | SAFE-T210 Specify emergency isolation valve requirements | Excel / Word | fire zones | manual | 3 | FEL3, DD
FIRE-I202 | Fireproofing requirements list | data | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | CIVL | CIVL-T260 Define structural fireproofing extent | Excel / Word | members, skirts and supports needing fireproofing, rating hours and test standard | manual | 3 | DD
FIRE-I202 | Fireproofing requirements list | data | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | EIV locations, closure time, fire-safe test (API 607); actuator and cable fireproofing rating | review | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | CIVL | CIVL-T120 Design tank dikes and containment | Excel / Word | foam and fixed fire protection coverage for diked areas | review | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | deluge valve locations needing pits or housings | manual | 3 | DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | fixed fire suppression and detection per building | review | 3 | DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | fixed fire protection for generator and fuel tank | review | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | fixed fire protection system requirements | manual | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | F&G philosophy, zones, voting, executive actions, deluge activation logic, HVAC intake detection and damper closure | review | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | foam and cooling ring requirements for tanks | manual | 3 | FEL3, DD
FIRE-I220 | Fixed fire protection system requirements | document | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | fixed fire protection systems and coverage per area | manual | 2 | FEL3
FIRE-I230 | Fire pump and fire protection equipment datasheets | document | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | fire pump house and skid footprints | manual | 3 | FEL2, FEL3, DD
FIRE-I230 | Fire pump and fire protection equipment datasheets | document | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | fire pump motor rating and supply requirements | manual | 3 | FEL3, DD, CON
FIRE-I230 | Fire pump and fire protection equipment datasheets | document | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | fire pump controller and deluge skid signals to the F&G system | manual | 3 | FEL3, DD
FIRE-I230 | Fire pump and fire protection equipment datasheets | document | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | PIPE | PIPE-T160 Route piping in the 3D model | S3D | fire pump and skid nozzle connections for firewater piping | manual | 3 | FEL3, DD
FIRE-I231 | Fire protection material requisitions | document | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Purchasing DB | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | fire protection MRs to register | manual | 3 | FEL3, DD
FIRE-I240 | Fire protection vendor data comments | document | FIRE | FIRE-T240 Review fire protection vendor data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | review codes on fire protection vendor documents | integrated | 3 | DD, CON
MECH-I010 | FEL 1 equipment type and size list (mechanical attributes) | data | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | FEL1 equipment sizes and rough empty weights | manual | 2 | FEL1, FEL2, FEL3, DD
MECH-I010 | FEL 1 equipment type and size list (mechanical attributes) | data | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | equipment type and size class per option | review | 1 | FEL1, FEL2
MECH-I020 | FEL 1 equipment cost factors | data | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | PROC | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | HYSYS | factored equipment costs and weight factors per equipment type | review | 1 | FEL1, FEL2
MECH-I020 | FEL 1 equipment cost factors | data | MECH | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | factored equipment costs and weight factors per equipment type | manual | 4 | FEL1
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | corrosion allowance rules and design life | manual | 3 | FEL2, FEL3
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | sparing philosophy and driver preferences | manual | 3 | FEL2, FEL3
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | codes and design margins | manual | 3 | FEL3, DD
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | codes, margins, corrosion allowance rules | manual | 3 | FEL3, DD
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | design margins on P/T and MDMT rules | review | 3 | FEL3, DD
MECH-I030 | Mechanical design basis | document | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | TEMA and tube preferences in mechanical design basis | review | 2 | FEL1, FEL2, FEL3
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | tube and shell materials and corrosion allowance | manual | 2 | FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | materials and corrosion allowance per component | manual | 3 | FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | materials and corrosion allowance | manual | 3 | FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | base material, corrosion allowance, sour/NACE, PWHT and impact test per circuit | manual | 2 | FEL2, FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | PWHT, hardness, sour service and impact test requirements | manual | 3 | FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | PROC | PROC-T135 Define corrosion basis and agree materials selection with Mechanical | Excel / Word | proposed materials and corrosion allowances to agree | meeting | 2 | FEL2, FEL3, DD
MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | document | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | materials, corrosion allowance, PWHT, impact test | manual | 4 | DD
MECH-I050 | Rotating equipment sparing and driver selection list | data | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | driver type, fixed/variable speed, estimated absorbed and rated power, voltage class per machine | manual | 1 | FEL1, FEL2
MECH-I050 | Rotating equipment sparing and driver selection list | data | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | machines with variable speed (VFD) and rated power | manual | 3 | FEL3, DD
MECH-I050 | Rotating equipment sparing and driver selection list | data | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | running/spare, driver type and power | manual | 3 | FEL2, FEL3, DD
MECH-I050 | Rotating equipment sparing and driver selection list | data | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | running/spare and driver type per machine | manual | 3 | FEL3, DD
MECH-I050 | Rotating equipment sparing and driver selection list | data | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | driver type and VFD requirement | manual | 3 | FEL3, DD
MECH-I060 | Budget enquiry package | document | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Document Locator | VEND | VEND-T010 Prepare budget quotations | Excel / Word | short-form datasheets and scope for budget pricing; enquiry due date; enquiry scope and due date | manual | 1 | FEL1, FEL2
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | CIVL | CIVL-T040 Specify the geotechnical investigation | Excel / Word | per-tag weight estimates to set borehole depths | manual | 1 | FEL2, FEL3
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | per-tag weights for foundation quantities | manual | 2 | FEL1, FEL2, FEL3, DD
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | outline dimensions from budget quotes | manual | 2 | FEL2, FEL3, DD
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | delivery lead time and long-lead flag per tag | meeting | 2 | FEL2, FEL3
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | budget price or factored cost, weight and lead time per tag | manual | 2 | FEL2
MECH-I070 | Equipment cost, weight and delivery data for estimate | data | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | lead time and long-lead flag per tag | manual | 2 | FEL2, FEL3
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | CIVL | CIVL-T040 Specify the geotechnical investigation | Excel / Word | approximate empty/operating weights of columns, tanks and heavy equipment | manual | 1 | FEL2, FEL3
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | equipment tag, type, service | file | 4 | DD, CON
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | per tag: type, size, empty/operating weight, package scope | manual | 2 | FEL2, FEL3
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | equipment weights and field-erected scope | manual | 2 | FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | tags, service, driver power, vendor/PO status | manual | 2 | FEL3, DD, CON
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | INST | INST-T050 Build and maintain the instrument index in SI | SI | equipment numbers and services for instruments on equipment | manual | 2 | FEL3, DD, CON
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | equipment list | review | 2 | FEL2, FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | equipment tag list with size and operating weight | manual | 2 | FEL2, FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | equipment type: rotating, air coolers, heaters | manual | 2 | FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | equipment tags, types and mechanical attributes | manual | 2 | FEL2, FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | type, size/rating, material and weights per tag | manual | 2 | FEL2
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | oil-filled equipment and capacities | manual | 2 | FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | SAFE | SAFE-T240 Perform noise study | Excel / Word | equipment list | manual | 3 | FEL3, DD
MECH-I080 | Mechanical equipment list | data | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | type, size, material per tag | manual | 2 | FEL2, FEL3
MECH-I090 | Shell-and-tube exchanger thermal design | model | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | TEMA type, geometry, area, pressure drops | file | 3 | FEL3, DD
MECH-I090 | Shell-and-tube exchanger thermal design | model | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | shell diameter, tube length, bundle pull length | manual | 2 | FEL2, FEL3, DD
MECH-I090 | Shell-and-tube exchanger thermal design | model | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | final area, pressure drop and configuration from the HTRI design | manual | 3 | FEL2, FEL3, DD
MECH-I100 | Air-cooled exchanger thermal design | model | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | air cooler bays, plot area and fans to place on rack | manual | 2 | FEL2, FEL3
MECH-I100 | Air-cooled exchanger thermal design | model | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | bays, bundles, fans, fan power | file | 3 | FEL3, DD
MECH-I100 | Air-cooled exchanger thermal design | model | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | bay dimensions and plot area | manual | 2 | FEL2, FEL3, DD
MECH-I100 | Air-cooled exchanger thermal design | model | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | PROC | PROC-T160 Prepare equipment list process data | Excel / Word | final area, pressure drop and configuration from the HTRI design | manual | 3 | FEL2, FEL3, DD
MECH-I110 | Fired heater datasheet and specification | document | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | fired heater datasheet | manual | 3 | FEL3, DD
MECH-I110 | Fired heater datasheet and specification | document | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | burner type, NOx guarantee, stack height | manual | 2 | FEL2, FEL3, DD
MECH-I110 | Fired heater datasheet and specification | document | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | stack height | manual | 3 | FEL3, DD
MECH-I120 | Fired heater burner management and combustion control requirements | document | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | BMS and combustion control points; compressor anti-surge/capacity control; seal system alarms and trips | review | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | skirt/saddle design, wind and seismic moments, hydrotest weights | manual | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | CIVL | CIVL-T260 Define structural fireproofing extent | Excel / Word | skirt and saddle geometry for fireproofing extent | review | 3 | DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | shell ID and support ring elevations | manual | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | thicknesses, MAWP and weights | manual | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | shell thickness and nozzle reinforcement basis for allowable loads | manual | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | vessel dimensions and support type | manual | 2 | FEL2, FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | empty/operating/test weights, wind and seismic moments | manual | 3 | FEL3, DD
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | calculated empty and dressed weights | manual | 3 | DD, CON
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | equipment hydrotest pressure and MAWP | manual | 3 | DD, CON
MECH-I130 | Vessel and column mechanical design calculations | model | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | empty weights/metal masses | manual | 3 | FEL3, DD
MECH-I140 | Column and vessel internals datasheets | document | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | internals datasheets | manual | 3 | FEL3, DD
MECH-I140 | Column and vessel internals datasheets | document | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | PROC | PROC-T140 Size vessels and columns | HYSYS | tray/packing type, spacing, passes and vendor hydraulic rating results | manual | 3 | FEL2, FEL3, DD
MECH-I140 | Column and vessel internals datasheets | document | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | final tray/packing type and hydraulic ratings | manual | 4 | DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | CIVL | CIVL-T120 Design tank dikes and containment | Excel / Word | tank diameters, heights and capacities | manual | 3 | FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | CIVL | CIVL-T170 Design tank foundations | Excel / Word | tank diameter, height, roof type and annular plate | manual | 3 | FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | tank diameter, bottom design and appurtenances | review | 3 | DD, CON
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | tank diameter and roof type | manual | 3 | FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | tank roof type, rim seal and diameter | manual | 3 | FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | tank datasheets | manual | 3 | FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | SAFE | SAFE-T060 Develop emissions inventory | Excel / Word | tank roof type, seals, size | manual | 2 | FEL2, FEL3, DD
MECH-I150 | Storage tank datasheets and calculations | document | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | tank capacities | manual | 2 | FEL3, DD
MECH-I160 | Tank foundation loads and settlement criteria | data | MECH | MECH-T120 Design storage tanks | Excel / Word | CIVL | CIVL-T170 Design tank foundations | Excel / Word | shell and bottom loads, hydrotest load, overturning, anchorage, allowable settlement | manual | 3 | FEL3, DD
MECH-I160 | Tank foundation loads and settlement criteria | data | MECH | MECH-T120 Design storage tanks | Excel / Word | CIVL | CIVL-T370 Evaluate settlement monitoring during hydrotest | Excel / Word | allowable differential and edge settlement | review | 4 | CON, COM
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | vessel dimensions for cooling area | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | vessel surface area data | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | nozzle schedule with sizes/ratings, nozzle elevations and orientations, internals interference | review | 2 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | vessel size, design data, material, weights | manual | 3 | FEL2, FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | nozzle schedule, sizes, ratings | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | vessel datasheets | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | mechanical datasheets | review | 3 | FEL2, FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PIPE | PIPE-T050 Build 3D layout model | S3D | preliminary nozzle schedule sizes and ratings | manual | 2 | FEL2, FEL3
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PIPE | PIPE-T070 Study critical line routing | S3D | nozzle schedule sizes, ratings and duties on columns and vessels | manual | 2 | FEL3
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | S3D | nozzle schedule | review | 2 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PIPE | PIPE-T160 Route piping in the 3D model | S3D | nozzle size, rating, facing and location | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | equipment design P/T to include or isolate | manual | 3 | DD, CON
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | vessel dimensions, liquid levels and insulation for wetted area | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | vessel volumes, materials and thickness | manual | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | vessel/column datasheets: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | design P/T and MAWP | review | 3 | FEL3, DD
MECH-I170 | Vessel and column mechanical datasheets | document | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | approved datasheet values | review | 4 | DD, CON
MECH-I180 | Shell-and-tube exchanger datasheets (TEMA) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | exchanger type, area, weights | manual | 3 | FEL2, FEL3, DD
MECH-I180 | Shell-and-tube exchanger datasheets (TEMA) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | exchanger empty/full weights and bundle weight | manual | 3 | FEL3, DD
MECH-I180 | Shell-and-tube exchanger datasheets (TEMA) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | exchanger datasheets | manual | 3 | FEL3, DD
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | air cooler structure and weights | manual | 2 | FEL2, FEL3
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | air cooler weights, structure and support locations | manual | 3 | FEL3, DD
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | air cooler bays, fan power, weights | manual | 3 | FEL2, FEL3, DD
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | air cooler weights | manual | 3 | FEL3, DD
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | air cooler datasheets | manual | 3 | FEL3, DD
MECH-I190 | Air-cooled exchanger datasheets (API 661) | document | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | SAFE | SAFE-T240 Perform noise study | Excel / Word | air cooler fan noise | manual | 3 | FEL3, DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | pump type, driver and baseplate requirements | manual | 3 | DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | pump rated duty and driver kW | manual | 3 | FEL2, FEL3, DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | pump type, speed and seal chamber data | manual | 3 | FEL3, DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | pump and driver weights | manual | 3 | FEL3, DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | pump rated power and speed | manual | 3 | FEL3, DD
MECH-I200 | Pump datasheets (API 610 / ASME) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | pump datasheets | manual | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | compressor/blower type, speeds and foundation requirements | manual | 3 | DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | ELEC | ELEC-T230 Run motor-starting study | ETAP | compressor start conditions (unloaded/loaded, valve position) | manual | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | BMS and combustion control points; compressor anti-surge/capacity control; seal system alarms and trips | review | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | compressor type and driver kW | manual | 3 | FEL2, FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | compressor seal and lube system scope | manual | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | compressor weights and dynamic data | manual | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | compressor rated power and speed | manual | 3 | FEL3, DD
MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | document | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | compressor datasheets | manual | 3 | FEL3, DD
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | packaged equipment controls philosophy (vendor PLC vs DCS) and communication interfaces | manual | 2 | FEL2, FEL3, DD
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | INST | INST-T050 Build and maintain the instrument index in SI | SI | package scope of supply: which instruments are vendor supplied | manual | 2 | FEL3, DD, CON
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | INST | INST-T270 Integrate vendor package controls | Excel / Word | package requisitions, vendor instrument index and package I/O, controls philosophy and scope split | review | 3 | DD, CON
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | package battery limits and scope | manual | 3 | FEL3, DD
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | package scope of supply | manual | 3 | FEL3, DD
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | PROC | PROC-T185 Prepare package process specifications | Excel / Word | package scope of supply and terminal points | review | 2 | FEL3, DD
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | package battery limits and terminal points | review | 2 | FEL2, FEL3
MECH-I220 | Package specifications and scope-of-supply split | document | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | package scope of supply and terminal points | manual | 3 | FEL3, DD
MECH-I230 | Equipment and package utility consumption data | data | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | package and equipment utility demands per tag | manual | 3 | FEL2, FEL3, DD, COM
MECH-I240 | Seal plans and auxiliary system requirements | document | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | BMS and combustion control points; compressor anti-surge/capacity control; seal system alarms and trips | review | 3 | FEL3, DD
MECH-I240 | Seal plans and auxiliary system requirements | document | MECH | MECH-T170 Select seal, flush and lube oil systems | Excel / Word | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | SPID | seal plans and auxiliary system scope to show on P&IDs | manual | 3 | FEL3, DD
MECH-I250 | Mechanical P&ID markups | drawing | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | Document Locator | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | mechanical P&ID markups (seal plans, vents, drains) | manual | 4 | DD
MECH-I260 | Mechanical HAZOP action responses | decision | MECH | MECH-T180 Provide mechanical input to P&IDs and HAZOP | Excel / Word | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | mechanical action responses | review | 3 | FEL3, DD, CON
MECH-I270 | Nozzle orientation drawings (engineering) | drawing | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Document Locator | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | platform clip, davit and ladder positions on vessels | manual | 3 | FEL3, DD
MECH-I270 | Nozzle orientation drawings (engineering) | drawing | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Document Locator | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | nozzle schedule with sizes/ratings, nozzle elevations and orientations, internals interference | review | 2 | FEL3, DD
MECH-I270 | Nozzle orientation drawings (engineering) | drawing | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Document Locator | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | S3D | engineering nozzle angles, elevations, platform clips and davits to comment | review | 2 | FEL3, DD
MECH-I270 | Nozzle orientation drawings (engineering) | drawing | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Document Locator | VEND | VEND-T050 Prepare GA and outline drawings for review | Excel / Word | required nozzle orientations, platform clips and davits | manual | 4 | DD
MECH-I280 | Allowable nozzle loads | data | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | MECH | MECH-T330 Check piping loads against equipment nozzle allowables | Excel / Word | allowable forces and moments per nozzle | manual | 3 | DD
MECH-I280 | Allowable nozzle loads | data | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | PIPE | PIPE-T210 Perform screening stress analysis | CAESAR II | preliminary allowable forces and moments per nozzle | manual | 2 | FEL3
MECH-I280 | Allowable nozzle loads | data | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | allowable nozzle forces and moments | manual | 3 | DD
MECH-I280 | Allowable nozzle loads | data | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | allowable nozzle load basis | manual | 4 | DD
MECH-I290 | Equipment outline drawings (preliminary GA) | drawing | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Document Locator | ELEC | ELEC-T280 Design lightning protection | Excel / Word | overall heights of columns, stacks and tanks | review | 3 | DD
MECH-I290 | Equipment outline drawings (preliminary GA) | drawing | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Document Locator | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | overall dimensions, support type and location | manual | 2 | FEL2, FEL3, DD
MECH-I290 | Equipment outline drawings (preliminary GA) | drawing | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Document Locator | PIPE | PIPE-T050 Build 3D layout model | S3D | outline dimensions, skirt/saddle heights and nozzle positions | manual | 2 | FEL2, FEL3
MECH-I290 | Equipment outline drawings (preliminary GA) | drawing | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Document Locator | PIPE | PIPE-T070 Study critical line routing | S3D | preliminary nozzle positions on heaters, pumps and exchangers | manual | 2 | FEL3
MECH-I290 | Equipment outline drawings (preliminary GA) | drawing | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Document Locator | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | S3D | nozzle positions and support details | review | 2 | FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | equipment footprints for foundation sizes | manual | 2 | FEL1, FEL2, FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | bundle pull, removal space and crane access per tag | review | 3 | FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | MECH | MECH-T400 Review 3D model for equipment access and maintenance | S3D | maintenance and removal envelopes to verify | review | 3 | FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | OWNR | OWNR-T100 Provide operations and maintenance input | Excel / Word | maintenance envelopes, bundle and rotor removal | review | 2 | FEL2, FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | footprint, height, bundle pull, internals removal and crane access envelopes | manual | 2 | FEL2, FEL3, DD
MECH-I300 | Equipment footprints and maintenance envelopes | data | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | bundle pull length and maintenance envelope | review | 2 | FEL1, FEL2, FEL3
MECH-I310 | Equipment weights and foundation load data | data | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | empty/operating/test weights, wind and seismic shear and moment, bundle pull force, anchor bolt circle | manual | 3 | FEL3, DD
MECH-I310 | Equipment weights and foundation load data | data | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | dynamic loads (unbalanced forces, operating frequencies) | manual | 3 | DD
MECH-I310 | Equipment weights and foundation load data | data | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | air cooler operating weights and dynamic loads | manual | 3 | FEL3, DD
MECH-I310 | Equipment weights and foundation load data | data | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | equipment weights on structures | manual | 3 | FEL3, DD
MECH-I310 | Equipment weights and foundation load data | data | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | empty/operating weights per tag | manual | 3 | FEL2, FEL3, DD
MECH-I320 | Equipment lifting data | data | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | lift weight, CoG, lifting and tailing lug locations and capacities, shipping dimensions | manual | 3 | FEL3, DD
MECH-I320 | Equipment lifting data | data | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | lift weight, CoG, shipping dimensions | manual | 2 | FEL3, DD
MECH-I330 | Motor and driver electrical data | data | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | absorbed and rated motor power, voltage, speed, starting method, VFD, duty, space heater | manual | 2 | FEL3, DD, CON
MECH-I330 | Motor and driver electrical data | data | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | speed range, starting limitations, duty for VFD-driven motors | manual | 3 | FEL3, DD
MECH-I330 | Motor and driver electrical data | data | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | motor rating, voltage, starting method and limitations per tag | manual | 3 | DD
MECH-I340 | Mechanical technical specifications | document | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | technical specifications | manual | 3 | FEL3, DD
MECH-I340 | Mechanical technical specifications | document | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | testing and NDE requirements | manual | 3 | DD, CON
MECH-I340 | Mechanical technical specifications | document | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | project mechanical specifications | manual | 3 | FEL3, DD
MECH-I340 | Mechanical technical specifications | document | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | NDE, PWHT and testing requirements | manual | 4 | DD
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | INST | INST-T270 Integrate vendor package controls | Excel / Word | package requisitions, vendor instrument index and package I/O, controls philosophy and scope split | review | 3 | DD, CON
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | requisitions: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | MR number, revision, scope, tags, datasheets, VDRL, inspection requirements | manual | 3 | FEL3, DD
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | inspection level and testing requirements in the requisition | manual | 3 | DD, CON
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | requisition scope, datasheets, spares and inspection requirements | manual | 3 | FEL3, DD
MECH-I350 | Requisition technical package for bid | document | MECH | MECH-T250 Prepare requisition technical packages for bid | Document Locator | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | inspection level and required tests | manual | 4 | DD
MECH-I360 | Requisition hold list | data | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | MECH | MECH-T320 Close requisition holds | Excel / Word | open holds per requisition | manual | 3 | DD
MECH-I360 | Requisition hold list | data | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | requisition holds pending process data | manual | 3 | FEL3, DD, CON
MECH-I360 | Requisition hold list | data | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | open holds per requisition with source and expected date | manual | 2 | DD, CON
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | agreed clarifications and open deviations per bidder | manual | 3 | FEL3, DD
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | MECH | MECH-T280 Prepare requisitions for purchase | Excel / Word | agreed clarifications to incorporate | manual | 3 | FEL3, DD
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | technical queries and clarifications per bidder | review | 3 | FEL3, DD
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | technical queries and vendor deviations | manual | 3 | FEL3, DD, CON
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | technical query responses and agreed clarifications | manual | 3 | FEL3, DD
MECH-I370 | Bidder technical query log and clarifications | document | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | VEND | VEND-T030 Answer bid clarifications | Excel / Word | technical queries and deviations to answer | manual | 3 | FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | MECH | MECH-T280 Prepare requisitions for purchase | Excel / Word | selected bidder and accepted deviations | manual | 3 | FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | OWNR | OWNR-T090 Review and comment on deliverables | Document Locator | technical bid evaluations | review | 3 | FEL2, FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | compliance matrix and evaluation criteria | review | 3 | FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | SAFE | SAFE-T270 Review vendor packages and bids for SHE compliance | Excel / Word | TBE compliance matrix | review | 3 | FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | technically acceptable bidders, deviations accepted, evaluation adders | review | 3 | FEL3, DD
MECH-I380 | Technical bid evaluation and recommendation | decision | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | preferred bidder and technical acceptability | review | 3 | FEL3, DD
MECH-I390 | Requisition for purchase (conformed technical package) | document | MECH | MECH-T280 Prepare requisitions for purchase | Document Locator | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | conformed datasheets, scope, VDRL and remaining holds | manual | 3 | FEL3, DD
MECH-I390 | Requisition for purchase (conformed technical package) | document | MECH | MECH-T280 Prepare requisitions for purchase | Document Locator | SCM | SCM-T110 Process PO amendments | Purchasing DB | revised conformed requisition scope and data | manual | 3 | DD, CON
MECH-I390 | Requisition for purchase (conformed technical package) | document | MECH | MECH-T280 Prepare requisitions for purchase | Document Locator | SCM | SCM-T120 Set up VDRL tracking | Purchasing DB | VDRL document types, review/information and due weeks after PO | manual | 3 | DD
MECH-I390 | Requisition for purchase (conformed technical package) | document | MECH | MECH-T280 Prepare requisitions for purchase | Document Locator | VEND | VEND-T050 Prepare GA and outline drawings for review | Excel / Word | conformed datasheets and nozzle schedule | manual | 4 | DD
MECH-I390 | Requisition for purchase (conformed technical package) | document | MECH | MECH-T280 Prepare requisitions for purchase | Document Locator | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | design P/T, code and nozzle schedule | manual | 4 | DD
MECH-I400 | Vendor kick-off meeting minutes | document | MECH | MECH-T290 Hold vendor kick-off meetings | Document Locator | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | agreed vendor data due dates and interface data needed to release engineering deliverables | meeting | 2 | FEL2, FEL3, DD
MECH-I400 | Vendor kick-off meeting minutes | document | MECH | MECH-T290 Hold vendor kick-off meetings | Document Locator | SCM | SCM-T120 Set up VDRL tracking | Purchasing DB | agreed VDRL dates from kick-off | manual | 3 | DD
MECH-I410 | Vendor document comment sheets (coded returns) | document | MECH | MECH-T300 Review vendor drawings and data | Document Locator | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | review code confirming certified status | manual | 4 | DD
MECH-I410 | Vendor document comment sheets (coded returns) | document | MECH | MECH-T300 Review vendor drawings and data | Document Locator | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | S3D | consolidated vendor document review codes | review | 3 | DD
MECH-I410 | Vendor document comment sheets (coded returns) | document | MECH | MECH-T300 Review vendor drawings and data | Document Locator | PROC | PROC-T310 Review vendor data against process duties | Document Locator | consolidated comment sheet and status codes | review | 3 | DD
MECH-I410 | Vendor document comment sheets (coded returns) | document | MECH | MECH-T300 Review vendor drawings and data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | consolidated comments and review code per vendor document | review | 2 | DD, CON
MECH-I410 | Vendor document comment sheets (coded returns) | document | MECH | MECH-T300 Review vendor drawings and data | Document Locator | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | review code on GA and calculations | review | 3 | DD, CON
MECH-I420 | Certified equipment GA and nozzle data | drawing | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | PIPE | PIPE-T160 Route piping in the 3D model | S3D | certified nozzle locations, sizes and ratings for final routing | manual | 4 | FEL3, DD
MECH-I420 | Certified equipment GA and nozzle data | drawing | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | certified nozzle locations for anchor points | manual | 3 | DD
MECH-I420 | Certified equipment GA and nozzle data | drawing | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | S3D | certified equipment nozzle data for model update | review | 4 | DD
MECH-I420 | Certified equipment GA and nozzle data | drawing | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | certified dimensions and nozzle data for checks | review | 4 | DD, CON
MECH-I430 | Certified foundation loads and anchor bolt data | document | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | certified foundation loads and anchor bolt sizes and pattern | manual | 4 | FEL3, DD
MECH-I430 | Certified foundation loads and anchor bolt data | document | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | certified dynamic data and grouting requirements | manual | 4 | DD
MECH-I430 | Certified foundation loads and anchor bolt data | document | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | certified anchor bolt sizes and pattern | manual | 4 | DD
MECH-I440 | Certified vendor electrical data | document | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | certified motor datasheets: kW, FLA, LRC, PF, efficiency, inertia, speed-torque, accessories | manual | 3 | DD
MECH-I440 | Certified vendor electrical data | document | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | ELEC | ELEC-T230 Run motor-starting study | ETAP | load torque curve and load inertia from certified motor/driven-equipment data | manual | 3 | FEL3, DD
MECH-I450 | Vendor instrument lists and package I/O | data | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | INST | INST-T260 Develop I/O list and assign I/O | SI | package I/O list and serial link maps | manual | 3 | FEL3, DD
MECH-I450 | Vendor instrument lists and package I/O | data | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | INST | INST-T270 Integrate vendor package controls | Excel / Word | package requisitions, vendor instrument index and package I/O, controls philosophy and scope split | review | 3 | DD, CON
MECH-I460 | Hold list status update | data | MECH | MECH-T320 Close requisition holds | Excel / Word | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | S3D | hold status per requisition and vendor document | review | 3 | DD
MECH-I460 | Hold list status update | data | MECH | MECH-T320 Close requisition holds | Excel / Word | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | hold closure status per requisition and vendor document | manual | 2 | DD, CON
MECH-I470 | Nozzle load acceptance and exceedance resolutions | decision | MECH | MECH-T330 Check piping loads against equipment nozzle allowables | Excel / Word | PIPE | PIPE-T230 Resolve nozzle loads with mechanical and vendors | Excel / Word | acceptance or required piping changes per nozzle | review | 3 | DD
MECH-I480 | Rotordynamic and pulsation study acceptance | decision | MECH | MECH-T340 Review rotordynamic, torsional and pulsation studies | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | pulsation study results (orifices, dampeners, support spacing) for stress | manual | 3 | DD
MECH-I490 | Approved inspection and test plans | document | MECH | MECH-T350 Review and approve inspection and test plans | Document Locator | CIVL | CIVL-T370 Evaluate settlement monitoring during hydrotest | Excel / Word | hydrotest pressures and test hold points | review | 4 | CON, COM
MECH-I490 | Approved inspection and test plans | document | MECH | MECH-T350 Review and approve inspection and test plans | Document Locator | MECH | MECH-T360 Witness shop tests and factory acceptance tests | Excel / Word | witness and hold points to attend | review | 4 | DD
MECH-I490 | Approved inspection and test plans | document | MECH | MECH-T350 Review and approve inspection and test plans | Document Locator | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | approved ITP with witness/hold points | manual | 3 | DD, CON
MECH-I500 | Shop test witness reports and release notes | document | MECH | MECH-T360 Witness shop tests and factory acceptance tests | Document Locator | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | shop test performance results vs guarantees | manual | 4 | DD
MECH-I510 | Reviewed spare parts list | data | MECH | MECH-T370 Review spare parts recommendations | Excel / Word | COMM | COMM-T100 Define commissioning spares, consumables and first fills | Excel / Word | commissioning/start-up spares per tag | manual | 3 | DD
MECH-I510 | Reviewed spare parts list | data | MECH | MECH-T370 Review spare parts recommendations | Excel / Word | SCM | SCM-T270 Procure commissioning and operating spares | Purchasing DB | reviewed commissioning, operating and capital spares per tag | manual | 4 | DD, CON, COM
MECH-I520 | Manufacturer's data book acceptance | decision | MECH | MECH-T380 Review manufacturer's data books | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | MDR acceptance | review | 4 | COM
MECH-I520 | Manufacturer's data book acceptance | decision | MECH | MECH-T380 Review manufacturer's data books | Document Locator | SCM | SCM-T280 Close out purchase orders | Purchasing DB | MDR acceptance | review | 4 | CON, COM
MECH-I530 | Equipment preservation requirements | document | MECH | MECH-T390 Define equipment preservation and storage requirements | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | preservation requirements before commissioning | manual | 4 | DD, CON
MECH-I530 | Equipment preservation requirements | document | MECH | MECH-T390 Define equipment preservation and storage requirements | Excel / Word | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | storage class, N2 blanket, shaft rotation intervals | manual | 4 | CON, COM
MECH-I540 | Equipment model review comments | document | MECH | MECH-T400 Review 3D model for equipment access and maintenance | Excel / Word | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | equipment access, removal clearance and nozzle discrepancy comments | meeting | 3 | FEL3, DD
MECH-I550 | Mechanical RFI responses and field change dispositions | decision | MECH | MECH-T410 Respond to field RFIs and equipment issues | Procore | CONS | CONS-T170 Raise and manage RFIs | Procore | mechanical RFI responses and field change dispositions | integrated | 4 | CON
MECH-I560 | Vendor site service schedule and reports | data | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | COMM | COMM-T110 Define vendor commissioning support requirements | Excel / Word | vendor representative schedule for commissioning | manual | 4 | DD
MECH-I560 | Vendor site service schedule and reports | data | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | SCM | SCM-T260 Call off vendor site services | Purchasing DB | vendor site service dates to call off | manual | 4 | CON, COM
MECH-I570 | Mechanical equipment ITR and check requirements | data | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Excel / Word | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | per equipment type: installation, box-up, flush and run-in test criteria | manual | 3 | DD
MECH-I570 | Mechanical equipment ITR and check requirements | data | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | vendor pre-commissioning: lube flush, box-up, solo run criteria | manual | 4 | DD, CON
MECH-I570 | Mechanical equipment ITR and check requirements | data | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Excel / Word | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | installation checks and alignment tolerances per equipment type | review | 4 | CON
MECH-I580 | Mechanical punch items and MC acceptance | decision | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | mechanical punch status and MC acceptance by equipment | review | 4 | CON
MECH-I590 | As-built equipment datasheets and equipment register | data | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | as-built equipment attributes per tag | file | 4 | COM
MECH-I590 | As-built equipment datasheets and equipment register | data | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | final certified design data per tag | manual | 4 | DD
MECH-I590 | As-built equipment datasheets and equipment register | data | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | as-built equipment data | review | 4 | DD, CON, COM
MECH-I600 | Equipment thermal growth and nozzle flexibility | data | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | Equipment thermal growth and nozzle displacements (columns, heaters, exchangers) and nozzle flexibility data for CAESAR II | manual | 3 | DD
MECH-I601 | Technically acceptable bidders | data | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | Mechanical technical acceptability of proposed bidders per equipment type | review | 3 | FEL3, DD
MECH-I901 | Mechanical deliverables list | data | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | Mechanical deliverables list: datasheets, calculations and requisitions per equipment item with planned dates | manual | 2 | FEL2, FEL3, DD, CON
MECH-I902 | Mechanical progress measurement | data | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Mechanical progress: datasheets and requisitions percent complete | manual | 2 | FEL3, DD
MECH-I904 | Mechanical change impact | data | MECH | MECH-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | Mechanical change impact: equipment changes with vendor price and schedule impact | manual | 2 | FEL3, DD, CON
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Excel / Word | block footprints, rack corridor, tank farm and approximate area per option | review | 1 | FEL1
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | FEL1 block arrangement options | review | 2 | FEL1, FEL2, FEL3
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | block arrangement per option, candidate substation locations | review | 1 | FEL2, FEL3
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | block footprints and interconnecting run lengths for cable, tray and JB factors | manual | 1 | FEL1, FEL2, FEL3
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | block footprints, rack corridor length and interconnecting run lengths per option | manual | 1 | FEL1
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | SAFE | SAFE-T020 Facilitate concept HAZID and ENVID | PHA tool | block footprints, flare location, tank farm, roads and neighbours | review | 1 | FEL1, FEL2
PIPE-I010 | Block plot plan options | drawing | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | block layout options | review | 1 | FEL2
PIPE-I020 | FEL1 factored piping quantities | data | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | FEL1 rack length per option | manual | 2 | FEL1, FEL2, FEL3, DD
PIPE-I020 | FEL1 factored piping quantities | data | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | PROJ | PROJ-T060 Prepare the Class 5 estimate | Excel / Word | piping weight factors and interconnecting lengths per option | manual | 4 | FEL1
PIPE-I020 | FEL1 factored piping quantities | data | PIPE | PIPE-T020 Estimate piping quantities for FEL1 estimate | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | piping weight factors, length by size range, alloy fraction | manual | 1 | FEL2
PIPE-I030 | Piping layout design basis | document | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | maximum tube length, bundle pull and spacing rules | meeting | 2 | FEL3, DD
PIPE-I030 | Piping layout design basis | document | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | spacing tables, access and maintenance rules | manual | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T030 Specify and manage the topographic survey | Excel / Word | plot limits, battery limits and tie-in areas to survey | review | 1 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T040 Specify the geotechnical investigation | Excel / Word | locations of heavy equipment, columns, tanks and rack corridors for borehole placement | review | 2 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | equipment, rack, road and building areas for take-off | manual | 2 | FEL1, FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | equipment, rack, building, road and tank locations per revision | review | 2 | FEL1, FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | equipment, paving and road layout | manual | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T120 Design tank dikes and containment | Excel / Word | tank farm layout | review | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | roads, equipment and maintenance areas on the plot plan | review | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | unit boundaries, equipment locations, pipe rack runs, roads and access ways | review | 1 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | plot limits, equipment coordinates, roads, lay-down and maintenance areas, battery limits | file | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | plot areas that can be modularised, equipment locations | review | 2 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CONS | CONS-T050 Define path of construction | P6 | plot plan with areas, rack sections and equipment locations | review | 3 | FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | area numbering, unit boundaries and plant grid coordinates | file | 3 | FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | unit areas, rack corridors and building locations | review | 1 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | area dimensions and rack corridors for cable and tray lengths | manual | 2 | FEL1, FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | equipment locations, buildings and enclosed areas | review | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | plot plan background to grid | file | 3 | FEL3, DD, CON
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | substation location and access roads | review | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T270 Design grounding system | Excel / Word | equipment, tank and building locations to bond | review | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | plot plan background | file | 3 | DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | FIRE | FIRE-T190 Calculate fire water demand | Excel / Word | fire zones, dikes and equipment positions | manual | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | equipment layout | file | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | analyzer shelter location and plot space | review | 2 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | routed lines, plot plan, in-line instrument positions with orientation and access | integrated | 3 | DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | MECH | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | plot space available at exchanger locations | meeting | 2 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | MECH | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | equipment locations and access/maintenance areas | review | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | plot plan and stack locations | review | 3 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | PIPE | PIPE-T050 Build 3D layout model | S3D | equipment locations, rack corridors and roads | integrated | 2 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | rack corridors and road crossings | integrated | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | PROC | PROC-T095 Define process layout requirements | Excel / Word | equipment locations, rack corridors and grade elevations | review | 2 | FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | PROC | PROC-T155 Estimate exchanger duties and preliminary areas | HYSYS | available plot space for exchangers | review | 2 | FEL1, FEL2, FEL3
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | area numbering, unit and battery limits for WBS area codes | review | 2 | FEL2, FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | equipment and building locations to grid | review | 1 | FEL2
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | building and stack locations for downwash | manual | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | equipment and building coordinates | file | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | SAFE | SAFE-T130 Check flare radiation, noise and dispersion | Flare / relief tool | flare location, access roads and nearby equipment | review | 3 | FEL3, DD
PIPE-I040 | Plot plan | drawing | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | plot plan | review | 3 | FEL3, DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | foundation top/grade elevation needs per equipment tag | manual | 3 | FEL3, DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | equipment coordinates, orientation and foundation top elevation | file | 3 | FEL3, DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | equipment coordinates and elevations | file | 3 | DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | PIPE | PIPE-T050 Build 3D layout model | S3D | equipment coordinates, elevations and orientation | integrated | 2 | FEL2, FEL3
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | equipment elevations for static head | manual | 2 | FEL2, FEL3, DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | SAFE | SAFE-T070 Prepare air permit application | Excel / Word | stack coordinates | manual | 3 | FEL3, DD
PIPE-I050 | Equipment location list | data | PIPE | PIPE-T040 Develop plot plan and equipment layout | Excel / Word | SAFE | SAFE-T240 Perform noise study | Excel / Word | equipment coordinates | manual | 3 | FEL3, DD
PIPE-I060 | 3D layout model | model | PIPE | PIPE-T050 Build 3D layout model | S3D | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | structure placeholders and platform levels in the layout model | manual | 2 | FEL2, FEL3
PIPE-I060 | 3D layout model | model | PIPE | PIPE-T050 Build 3D layout model | S3D | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | structure layouts and access levels | file | 3 | FEL3, DD
PIPE-I060 | 3D layout model | model | PIPE | PIPE-T050 Build 3D layout model | S3D | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | equipment elevations and structures for elevation views | file | 3 | FEL3, DD, CON
PIPE-I060 | 3D layout model | model | PIPE | PIPE-T050 Build 3D layout model | S3D | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | rack and corridor lengths for factored areas | integrated | 2 | FEL2, FEL3
PIPE-I060 | 3D layout model | model | PIPE | PIPE-T050 Build 3D layout model | S3D | SAFE | SAFE-T230 Lay out safety equipment and escape routes | Excel / Word | platforms, stairs and access | review | 3 | FEL3, DD
PIPE-I070 | Pipe rack layout and widths | drawing | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | rack routes, widths, bay spacing and tiers for steel and foundation quantities | manual | 2 | FEL1, FEL2, FEL3, DD
PIPE-I070 | Pipe rack layout and widths | drawing | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | rack routes, widths, bay spacing, tier elevations, line allocation and future space | manual | 2 | FEL2, FEL3
PIPE-I070 | Pipe rack layout and widths | drawing | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | rack routes, widths, bay spacing and tier elevations for pre-assembled rack modules | review | 2 | FEL2, FEL3
PIPE-I070 | Pipe rack layout and widths | drawing | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | rack tier elevations and cable tray levels | integrated | 3 | FEL3, DD
PIPE-I070 | Pipe rack layout and widths | drawing | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | rack routes, widths and bay spacing available for air coolers on the rack top | meeting | 2 | FEL3, DD
PIPE-I080 | Pipe rack preliminary loads | data | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | Excel / Word | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | uniform pipe load per tier and concentrated anchor/guide loads | manual | 2 | FEL2, FEL3
PIPE-I080 | Pipe rack preliminary loads | data | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | pipe weights per tier and future allowance | manual | 3 | FEL3, DD
PIPE-I090 | Critical line routing studies | model | PIPE | PIPE-T070 Study critical line routing | S3D | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | critical line routing requiring nozzle relocation | meeting | 2 | FEL3, DD
PIPE-I090 | Critical line routing studies | model | PIPE | PIPE-T070 Study critical line routing | S3D | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | S3D | critical line routing and required nozzle positions | integrated | 2 | FEL3, DD
PIPE-I090 | Critical line routing studies | model | PIPE | PIPE-T070 Study critical line routing | S3D | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | model quantities in routed areas | integrated | 2 | FEL2, FEL3
PIPE-I090 | Critical line routing studies | model | PIPE | PIPE-T070 Study critical line routing | S3D | PIPE | PIPE-T210 Perform screening stress analysis | CAESAR II | critical line geometry exported to CAESAR II | file | 2 | FEL3
PIPE-I100 | Nozzle orientation and elevation requests | drawing | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | Excel / Word | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | nozzle orientations, elevations, platform, ladder and davit locations | manual | 2 | FEL3, DD
PIPE-I100 | Nozzle orientation and elevation requests | drawing | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | Excel / Word | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | requested nozzle angles, elevations, platform and ladder locations | meeting | 2 | FEL3, DD
PIPE-I100 | Nozzle orientation and elevation requests | drawing | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | Excel / Word | MECH | MECH-T320 Close requisition holds | Excel / Word | final nozzle orientations | manual | 3 | DD
PIPE-I100 | Nozzle orientation and elevation requests | drawing | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | Excel / Word | VEND | VEND-T050 Prepare GA and outline drawings for review | Excel / Word | nozzle orientation and elevation requests | manual | 3 | DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | piping class ratings, flange facings and branch connections for instrument process connection standards | review | 2 | FEL2, FEL3
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T060 Enter instrument process data | SI | piping class per line; rating and materials of the class for instrument wetted parts and flange rating | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T090 Calculate flow elements and thermowells | SI | line class and size; wall thickness/schedule by size for internal diameter | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T110 Prepare instrument datasheets | SI | wetted part material, flange rating and facing per class | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | branch table and branch connection types for instrument take-offs | review | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | root valve type, branch size and rating | review | 3 | DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | MECH | MECH-T030 Select equipment materials and corrosion allowances with Process | Excel / Word | material families and corrosion allowance per piping class at equipment nozzles | review | 2 | FEL2, FEL3
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PIPE | PIPE-T100 Build S3D piping specification catalogue | S3D | class rules, components by size, wall thickness, branch tables, valve codes | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PIPE | PIPE-T110 Prepare valve specifications and datasheets | Excel / Word | valve codes per class with rating and materials | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | class rating and materials for SP items | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | class assignment by service and P/T | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | S3D | class components and materials for pricing | manual | 2 | FEL2, FEL3
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | wall thickness/schedule by size per class for internal diameters | manual | 3 | FEL3, DD
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | class breaks and P-T limits | review | 3 | FEL2, FEL3
PIPE-I110 | Piping material class specification | document | PIPE | PIPE-T090 Develop piping material classes | Excel / Word | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | class materials and component descriptions | manual | 3 | FEL3, DD
PIPE-I120 | S3D piping spec and commodity catalogue | data | PIPE | PIPE-T100 Build S3D piping specification catalogue | S3D | PIPE | PIPE-T160 Route piping in the 3D model | S3D | spec rules, commodity codes and dimensional tables | integrated | 3 | FEL3, DD
PIPE-I120 | S3D piping spec and commodity catalogue | data | PIPE | PIPE-T100 Build S3D piping specification catalogue | S3D | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | short codes and commodity codes (idents) | manual | 3 | FEL3, DD
PIPE-I130 | Valve datasheets | document | PIPE | PIPE-T110 Prepare valve specifications and datasheets | Excel / Word | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | valve datasheets | manual | 3 | FEL3, DD
PIPE-I140 | Specialty piping item list and datasheets | data | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | specialty item tags with P&ID and line number | file | 4 | DD, CON
PIPE-I140 | Specialty piping item list and datasheets | data | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | SP item list | manual | 3 | FEL3, DD
PIPE-I140 | Specialty piping item list and datasheets | data | PIPE | PIPE-T120 Prepare specialty item list and datasheets | Excel / Word | PROC | PROC-T200 Develop P&IDs (process content) | SPID | specialty item tags and types | review | 3 | FEL2, FEL3
PIPE-I150 | Piping fabrication, erection and inspection specification | document | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | flushing and cleaning rules | review | 4 | DD, CON
PIPE-I150 | Piping fabrication, erection and inspection specification | document | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | hydrotest, flushing and NDE rules | review | 2 | DD
PIPE-I150 | Piping fabrication, erection and inspection specification | document | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | CONS | CONS-T220 Track welds and NDE | Excel / Word | WPS, NDE class and PWHT rules | manual | 4 | CON
PIPE-I150 | Piping fabrication, erection and inspection specification | document | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | painting and insulation systems and PWHT/NDE rules for interface | review | 3 | FEL3, DD
PIPE-I150 | Piping fabrication, erection and inspection specification | document | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | NDE category, PWHT and test rules | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | line class, test medium per line | review | 4 | DD, CON
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | CONS | CONS-T220 Track welds and NDE | Excel / Word | per line: class, NDE category, PWHT | manual | 4 | CON
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | test pressure and medium per line | manual | 4 | CON
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | insulation type and thickness per line | manual | 3 | DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | paint/coating system per line | review | 3 | DD, CON
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | INST | INST-T060 Enter instrument process data | SI | piping class per line; rating and materials of the class for instrument wetted parts and flange rating | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | INST | INST-T070 Size control valves | SI | line size and piping class at the valve; reducer arrangement as routed | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | INST | INST-T090 Calculate flow elements and thermowells | SI | line class and size; wall thickness/schedule by size for internal diameter | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | INST | INST-T100 Specify relief valves from the process sizing | SI | inlet/outlet line class and rating | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | class, size and insulation per line | manual | 3 | FEL3, DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | PIPE | PIPE-T320 Extract and check isometrics | S3D | test pressure, NDE, PWHT, paint and insulation per line | manual | 4 | DD
PIPE-I160 | Line list piping attributes | data | PIPE | PIPE-T140 Add piping data to the line list | Excel / Word | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | test pressure and medium per line | manual | 4 | DD, CON
PIPE-I170 | Estimate piping bulk MTO | data | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | Excel / Word | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | pipe length, inch-dia and field/shop weld counts by area to size piping CWPs | file | 2 | FEL3, DD
PIPE-I170 | Estimate piping bulk MTO | data | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | pipe, fittings, valves by class and size; shop and field weld counts | file | 2 | FEL3, DD
PIPE-I170 | Estimate piping bulk MTO | data | PIPE | PIPE-T150 Prepare FEL3 piping MTO for the estimate | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | pipe length, fittings, flanges, valves, SP items by class/size; weld counts; growth allowances | file | 2 | FEL3
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | drain hub, funnel and sump locations in the routed model | review | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | S3D routed piping and equipment as reference model for clash checks | file | 3 | FEL3, DD, CON
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | COMM | COMM-T120 Plan temporary commissioning facilities | Excel / Word | flushing connections and spool breaks in the model | review | 4 | DD, CON
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | setting elevations, obstructions and crane access corridors in the model (via Navisworks) | integrated | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | ELEC | ELEC-T270 Design grounding system | Excel / Word | structures and piping in model for bonding points | review | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | platforms, stairs, equipment and valve operating points | file | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | routed piping and equipment for tray routing and clearances | integrated | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | equipment and rack elevations | file | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | INST | INST-T070 Size control valves | SI | line size and piping class at the valve; reducer arrangement as routed | manual | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | routed lines, plot plan, in-line instrument positions with orientation and access | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | model distances for cable lengths | file | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T170 Check model against P&IDs | SPF | modelled lines and components | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T180 Position in-line instruments and instrument access | S3D | routed lines for instrument placement | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | S3D | as-routed geometry | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | stress line geometry exported from S3D | file | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T250 Design pipe supports | S3D | routed lines | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | S3D | routing, valve and instrument access points | integrated | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | routed piping | integrated | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T290 Detect and resolve clashes | S3D | routed piping for interference checks | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T320 Extract and check isometrics | S3D | routed lines | integrated | 4 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | model quantities | integrated | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | routed piping | integrated | 3 | DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | piping model | file | 4 | DD, CON
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | congestion and confinement (equipment, piping density) per area | file | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | flange, valve and instrument counts per section for leak frequency | file | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | 3D model geometry for obstruction | file | 3 | FEL3, DD
PIPE-I180 | Routed piping model | model | PIPE | PIPE-T160 Route piping in the 3D model | S3D | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | routed model | review | 3 | FEL2, FEL3, DD
PIPE-I190 | P&ID to model consistency report | data | PIPE | PIPE-T170 Check model against P&IDs | SPF | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | P&ID-to-model mismatches | integrated | 3 | DD
PIPE-I200 | In-line instrument positions | data | PIPE | PIPE-T180 Position in-line instruments and instrument access | S3D | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | routed lines, plot plan, in-line instrument positions with orientation and access | integrated | 3 | DD
PIPE-I210 | As-routed line hydraulic data | data | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | Excel / Word | PROC | PROC-T150 Define rotating equipment process duties | Excel / Word | suction/discharge equivalent lengths, fittings and elevation changes | manual | 2 | FEL2, FEL3, DD
PIPE-I210 | As-routed line hydraulic data | data | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | Excel / Word | PROC | PROC-T190 Size lines and run hydraulics | Excel / Word | equivalent lengths, fittings, elevation changes and pockets per routed line | manual | 3 | FEL3, DD
PIPE-I210 | As-routed line hydraulic data | data | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | Excel / Word | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | PSV inlet/outlet routing and tailpipe lengths | manual | 3 | FEL3, DD
PIPE-I210 | As-routed line hydraulic data | data | PIPE | PIPE-T190 Issue as-routed line data for hydraulic checks | Excel / Word | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | flare header equivalent lengths and fittings | file | 3 | FEL3, DD
PIPE-I220 | Stress-critical line list | data | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | PIPE | PIPE-T210 Perform screening stress analysis | CAESAR II | lines and load cases to screen | manual | 2 | FEL3
PIPE-I220 | Stress-critical line list | data | PIPE | PIPE-T200 Prepare stress-critical line list | Excel / Word | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | stress category, load cases and temperatures | manual | 3 | DD
PIPE-I230 | Screening stress results and layout markups | drawing | PIPE | PIPE-T210 Perform screening stress analysis | Excel / Word | PIPE | PIPE-T160 Route piping in the 3D model | S3D | screening stress markups (loops, supports, routing changes) | manual | 2 | FEL3, DD
PIPE-I240 | Stress calculation report | model | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | MECH | MECH-T340 Review rotordynamic, torsional and pulsation studies | Excel / Word | CAESAR II models and supports around reciprocating machinery | file | 3 | DD
PIPE-I240 | Stress calculation report | model | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | PIPE | PIPE-T240 Specify and requisition spring and engineered supports | Excel / Word | spring loads, travel and support type | manual | 3 | DD
PIPE-I240 | Stress calculation report | model | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | PIPE | PIPE-T320 Extract and check isometrics | S3D | stress sign-off per stress system | review | 4 | DD
PIPE-I250 | Nozzle loads for equipment | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | MECH | MECH-T320 Close requisition holds | Excel / Word | final piping nozzle loads | manual | 3 | DD
PIPE-I250 | Nozzle loads for equipment | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | MECH | MECH-T330 Check piping loads against equipment nozzle allowables | Excel / Word | forces and moments per nozzle and load case | manual | 3 | DD
PIPE-I250 | Nozzle loads for equipment | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | PIPE | PIPE-T230 Resolve nozzle loads with mechanical and vendors | Excel / Word | calculated nozzle loads vs allowables | manual | 3 | DD
PIPE-I250 | Nozzle loads for equipment | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | VEND | VEND-T050 Prepare GA and outline drawings for review | Excel / Word | calculated nozzle loads to accept | manual | 3 | DD
PIPE-I260 | Support loads for civil and structural | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | pipe support loads landing on equipment foundations | file | 3 | FEL3, DD
PIPE-I260 | Support loads for civil and structural | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | CAESAR II anchor, guide and friction loads per support tag | manual | 3 | FEL3, DD
PIPE-I260 | Support loads for civil and structural | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | pipe support loads on structures | file | 3 | FEL3, DD
PIPE-I260 | Support loads for civil and structural | data | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | PIPE | PIPE-T250 Design pipe supports | S3D | support loads for support selection | manual | 3 | DD
PIPE-I270 | Stress markups to the model | drawing | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | Excel / Word | PIPE | PIPE-T250 Design pipe supports | S3D | support type changes, guides, anchors and spring locations | manual | 3 | DD
PIPE-I280 | Nozzle load acceptance | decision | PIPE | PIPE-T230 Resolve nozzle loads with mechanical and vendors | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | nozzle load acceptance or exceedance | review | 2 | DD, CON
PIPE-I290 | Spring and engineered support requisition | document | PIPE | PIPE-T240 Specify and requisition spring and engineered supports | Purchasing DB | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | spring and engineered support MR | manual | 3 | FEL3, DD
PIPE-I300 | Pipe support model and special support drawings | model | PIPE | PIPE-T250 Design pipe supports | S3D | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | pipe support foundation locations and types | file | 3 | DD
PIPE-I300 | Pipe support model and special support drawings | model | PIPE | PIPE-T250 Design pipe supports | S3D | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | pipe support model for steel attachment points | file | 3 | FEL3, DD, CON
PIPE-I300 | Pipe support model and special support drawings | model | PIPE | PIPE-T250 Design pipe supports | S3D | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | support tags and special support details | manual | 4 | CON
PIPE-I300 | Pipe support model and special support drawings | model | PIPE | PIPE-T250 Design pipe supports | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | supports | integrated | 3 | FEL3, DD
PIPE-I300 | Pipe support model and special support drawings | model | PIPE | PIPE-T250 Design pipe supports | S3D | PIPE | PIPE-T320 Extract and check isometrics | S3D | supports | integrated | 4 | DD
PIPE-I310 | Secondary steel and support steel requests | data | PIPE | PIPE-T250 Design pipe supports | Excel / Word | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | secondary steel, stub columns, dummy legs and attachment points with loads | manual | 3 | FEL3, DD, CON
PIPE-I310 | Secondary steel and support steel requests | data | PIPE | PIPE-T250 Design pipe supports | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | embedded plates and support attachment points | manual | 3 | DD
PIPE-I320 | Platform, access and penetration requests | drawing | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | Excel / Word | CIVL | CIVL-T120 Design tank dikes and containment | Excel / Word | pipe penetrations and sleeves through dike walls | review | 3 | FEL3, DD
PIPE-I320 | Platform, access and penetration requests | drawing | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | platform and ladder locations for valve and instrument access | file | 3 | FEL3, DD
PIPE-I320 | Platform, access and penetration requests | drawing | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | sleeves and wall openings with sizes, trench and culvert crossings | manual | 3 | DD
PIPE-I330 | Underground piping layout | drawing | PIPE | PIPE-T270 Design underground piping | S3D | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | underground line routes, inverts, catch basins and tie points | review | 3 | FEL3, DD
PIPE-I330 | Underground piping layout | drawing | PIPE | PIPE-T270 Design underground piping | S3D | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | underground piping routes, sizes, inverts and cover depths | file | 3 | DD, CON
PIPE-I330 | Underground piping layout | drawing | PIPE | PIPE-T270 Design underground piping | S3D | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | buried piping routes, sizes, crossings | review | 3 | DD, CON
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | iConstruct | Navisworks review model and checklists | file | 3 | FEL3, DD
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | Navisworks review model by area with checklists and previous action status | integrated | 2 | FEL3, DD
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | MECH | MECH-T400 Review 3D model for equipment access and maintenance | S3D | review model and checklists by area | meeting | 3 | FEL3, DD
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | OWNR | OWNR-T120 Review the 3D model for operability and maintenance | iConstruct | Navisworks review model with valve and platform access | integrated | 2 | FEL3, DD
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | PROC | PROC-T330 Review 3D model and isometrics for process requirements | S3D | Navisworks review model and checklists | meeting | 3 | FEL3, DD
PIPE-I340 | Model review package | model | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | SAFE | SAFE-T250 Review plot plan and 3D model for safety | S3D | model review package and checklists | review | 3 | FEL2, FEL3, DD
PIPE-I350 | Model review action list | data | PIPE | PIPE-T280 Run 30/60/90 model reviews | Excel / Word | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | iConstruct | model review actions assigned to civil | file | 3 | FEL3, DD
PIPE-I350 | Model review action list | data | PIPE | PIPE-T280 Run 30/60/90 model reviews | Excel / Word | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | model review actions assigned to electrical | meeting | 3 | DD
PIPE-I350 | Model review action list | data | PIPE | PIPE-T280 Run 30/60/90 model reviews | Excel / Word | MECH | MECH-T400 Review 3D model for equipment access and maintenance | S3D | review actions assigned to mechanical | meeting | 3 | FEL3, DD
PIPE-I360 | Clash report | data | PIPE | PIPE-T290 Detect and resolve clashes | S3D | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | iConstruct | clashes involving steel and foundations | file | 3 | FEL3, DD
PIPE-I360 | Clash report | data | PIPE | PIPE-T290 Detect and resolve clashes | S3D | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | clashes involving electrical objects | meeting | 3 | DD
PIPE-I360 | Clash report | data | PIPE | PIPE-T290 Detect and resolve clashes | S3D | MECH | MECH-T400 Review 3D model for equipment access and maintenance | S3D | clashes involving equipment | meeting | 3 | FEL3, DD
PIPE-I370 | Piping safety action responses | decision | PIPE | PIPE-T300 Respond to HAZOP and safety layout actions | Excel / Word | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | piping action responses | review | 3 | FEL3, DD, CON
PIPE-I380 | Piping vendor data review comments | document | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | piping comments on nozzle orientation, connections and clips | review | 2 | DD, CON
PIPE-I380 | Piping vendor data review comments | document | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | nozzle orientation and connection comments | review | 2 | DD, CON
PIPE-I390 | Piping hold list | data | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Excel / Word | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | holds per line/iso with reason and release date | manual | 3 | CON
PIPE-I390 | Piping hold list | data | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Excel / Word | MECH | MECH-T290 Hold vendor kick-off meetings | Excel / Word | piping holds awaiting vendor data (nozzle loads, preliminary GA) | meeting | 3 | DD
PIPE-I390 | Piping hold list | data | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Excel / Word | PIPE | PIPE-T320 Extract and check isometrics | S3D | released holds | manual | 4 | DD
PIPE-I390 | Piping hold list | data | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Excel / Word | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | piping holds pending process data (slopes, SP items) | manual | 3 | FEL3, DD, CON
PIPE-I390 | Piping hold list | data | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | Excel / Word | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | hold per line/iso, reason, owner, due date, release status | manual | 2 | DD, CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | COMM | COMM-T120 Plan temporary commissioning facilities | Excel / Word | isos at flushing points | review | 4 | DD, CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | sample isometrics: field welds, spool breaks | review | 2 | DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | IFC isos with BOM, welds, supports | manual | 4 | CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | CONS | CONS-T220 Track welds and NDE | Excel / Word | weld numbers and shop/field welds per iso | manual | 4 | CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | IFC isos for marking test limits | manual | 4 | CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | isometric geometry, line lengths, valves, flanges, supports | file | 3 | DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | MECH | MECH-T340 Review rotordynamic, torsional and pulsation studies | Excel / Word | piping geometry for acoustic model | file | 3 | DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | S3D | IFC isometrics with welds and BOM | file | 4 | DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | isometric BOM by ident | integrated | 3 | FEL3, DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | isometrics for circuit definition | manual | 4 | DD, CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | iso attributes | file | 4 | DD, CON
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PROC | PROC-T330 Review 3D model and isometrics for process requirements | S3D | critical-line isometrics (slopes, pockets) | meeting | 3 | FEL3, DD
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | IFC isometrics: number, sheet, revision | integrated | 2 | FEL2, FEL3, DD, CON, COM
PIPE-I400 | IFC isometrics | drawing | PIPE | PIPE-T320 Extract and check isometrics | S3D | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | IFC isometric geometry, BOM, weld numbers, NDE, PWHT | file | 4 | DD, CON
PIPE-I410 | Spool list and fabrication package | data | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | Excel / Word | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | spool IDs and spool BOMs | manual | 4 | CON
PIPE-I410 | Spool list and fabrication package | data | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | Excel / Word | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | spool attributes | file | 4 | DD, CON
PIPE-I410 | Spool list and fabrication package | data | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | Excel / Word | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | spool IDs, welds, NDE, paint and fabrication package release | file | 4 | DD, CON
PIPE-I420 | Piping MTO by ident | data | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Excel / Word | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Jovix | required quantities by ident | manual | 4 | CON
PIPE-I420 | Piping MTO by ident | data | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Excel / Word | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | commodity ident, description, class, size, schedule, material, quantity by area and iso, delta to previous MTO; surplus allowance per ident | file | 3 | FEL3, DD
PIPE-I420 | Piping MTO by ident | data | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Excel / Word | SCM | SCM-T110 Process PO amendments | Purchasing DB | MTO delta to previous revision by ident | file | 3 | DD, CON
PIPE-I420 | Piping MTO by ident | data | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Excel / Word | SCM | SCM-T230 Report material availability to AWP | Jovix | MTO quantities by iso and area | file | 4 | CON
PIPE-I420 | Piping MTO by ident | data | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Excel / Word | SCM | SCM-T250 Reconcile materials and dispose of surplus | Jovix | final IFC MTO totals by ident | file | 4 | CON, COM
PIPE-I430 | Piping bulk material requisitions | document | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Purchasing DB | PIPE | PIPE-T350 Evaluate piping bids | Excel / Word | requisition technical requirements | manual | 3 | DD
PIPE-I430 | Piping bulk material requisitions | document | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Purchasing DB | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | bulk requisition technical specs and delivery split | file | 3 | FEL3, DD
PIPE-I430 | Piping bulk material requisitions | document | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | Purchasing DB | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | bulk requisition lines, quantities and delivery split | integrated | 3 | FEL3, DD
PIPE-I440 | Piping technical bid evaluation | document | PIPE | PIPE-T350 Evaluate piping bids | Document Locator | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | piping technical acceptability per bidder | manual | 3 | FEL3, DD
PIPE-I450 | Valve and SP item vendor data review | document | PIPE | PIPE-T360 Review valve and specialty item vendor data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | review codes on valve and SP item vendor documents | integrated | 3 | DD, CON
PIPE-I460 | Piping GA drawings and key plans | drawing | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | IFR piping plans and sections | review | 2 | DD
PIPE-I460 | Piping GA drawings and key plans | drawing | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | piping GA plans for equipment and tray drops | file | 3 | DD
PIPE-I460 | Piping GA drawings and key plans | drawing | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | piping GA drawings: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
PIPE-I470 | Tie-in list | data | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | tie-in points as system limits | review | 3 | FEL3, DD
PIPE-I470 | Tie-in list | data | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | tie-in locations, type and shutdown requirement | review | 2 | DD
PIPE-I470 | Tie-in list | data | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | tie-ins: type, size, shutdown requirement | review | 3 | FEL3, DD, CON
PIPE-I470 | Tie-in list | data | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | PROC | PROC-T210 Prepare line list and tie-in process data | SPID | tie-in numbers, existing/new line numbers, size, class, type | manual | 3 | FEL3, DD
PIPE-I470 | Tie-in list | data | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | PROJ | PROJ-T190 Run interface management | Excel / Word | tie-in number, P&ID, lines, type and shutdown requirement | manual | 3 | FEL3, DD, CON
PIPE-I480 | Tie-in packages | drawing | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Document Locator | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | tie-in sketches, isolation and method | manual | 4 | CON
PIPE-I480 | Tie-in packages | drawing | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Document Locator | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | isolation and method per tie-in | review | 3 | FEL3, DD, CON
PIPE-I490 | Test pack boundaries | drawing | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | test circuit limits to align with subsystems | review | 3 | FEL3, DD
PIPE-I490 | Test pack boundaries | drawing | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | test circuits, vents and drains | review | 4 | DD, CON
PIPE-I490 | Test pack boundaries | drawing | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | test circuit limits, blinds, vents, drains, test pressure and medium | manual | 4 | CON
PIPE-I500 | Test pack register | data | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Smart Completions | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | test pack number, lines and isos included | manual | 4 | CON
PIPE-I510 | Piping construction model export | model | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | Navisworks piping model with line, iso, spool, test pack and CWP attributes | integrated | 4 | DD, CON
PIPE-I520 | Spool drawing review comments | document | PIPE | PIPE-T410 Review fabricator spool drawings | Document Locator | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | spool drawing review comments to incorporate | review | 3 | DD, CON
PIPE-I530 | Piping RFI responses | document | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | CONS | CONS-T170 Raise and manage RFIs | Procore | piping answers, sketches, affected isos | manual | 4 | CON
PIPE-I530 | Piping RFI responses | document | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | CONS | CONS-T180 Raise field change requests | Procore | piping disposition of the change | manual | 4 | CON
PIPE-I540 | Field change isometrics | drawing | PIPE | PIPE-T420 Respond to piping RFIs and field changes | S3D | CONS | CONS-T180 Raise field change requests | Procore | revised field-change isometrics | manual | 4 | CON
PIPE-I540 | Field change isometrics | drawing | PIPE | PIPE-T420 Respond to piping RFIs and field changes | S3D | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | field change isos | manual | 4 | CON, COM
PIPE-I550 | Piping material shortage and surplus list | data | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Excel / Word | SCM | SCM-T250 Reconcile materials and dispose of surplus | Jovix | shortage and surplus by ident | file | 4 | CON, COM
PIPE-I560 | As-built isometrics | drawing | PIPE | PIPE-T440 Prepare as-built isometrics and model | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | as-built isometrics | review | 4 | COM
PIPE-I570 | As-built piping model | model | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | as-built model | review | 4 | COM
PIPE-I901 | Piping deliverables list | data | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | Piping deliverables list: drawing types and isometric counts by area with planned dates | manual | 2 | FEL2, FEL3, DD, CON
PIPE-I902 | Piping progress measurement | data | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Piping progress: model completion and isometrics issued vs planned by area | manual | 2 | FEL3, DD
PIPE-I904 | Piping change impact | data | PIPE | PIPE-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | Piping rework estimate (isometrics, model hours) for design changes | manual | 2 | FEL3, DD, CON
CIVL-I010 | Site civil screening assessment | document | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Document Locator | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | topography, flood elevation and access routes per candidate site | manual | 1 | FEL1
CIVL-I010 | Site civil screening assessment | document | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Document Locator | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | per site topography, flood elevation and relocation needs; wetland/floodplain screening | manual | 1 | FEL1, FEL2
CIVL-I010 | Site civil screening assessment | document | CIVL | CIVL-T010 Assess candidate sites for civil constraints | Document Locator | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | topography, flood elevation, access routes per candidate site | review | 1 | FEL1
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | rack load allowances, deflection limits and load combinations | manual | 2 | FEL2, FEL3
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | load combinations and stability criteria | manual | 3 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | load combinations and deflection limits | manual | 3 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | load combinations and drift limits | manual | 3 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | design criteria | manual | 3 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | structural design criteria for E-house skid and support | review | 2 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | MECH | MECH-T210 Compile equipment weights and foundation loads | Excel / Word | load cases and combinations, required load data format | meeting | 2 | FEL3, DD
CIVL-I020 | Structural design criteria | document | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | structure deflection limits and rack load allowance assumptions | manual | 3 | DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | flood level and rainfall for drainage fall comments | manual | 2 | FEL1, FEL2, FEL3
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | rainfall intensity and flood level for falls and HPFG | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | rainfall intensity-duration-frequency | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | CIVL | CIVL-T300 Design building HVAC | Excel / Word | HVAC ambient design temperatures | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | ambient max/min temperatures, wind, seismic parameters, snow/ice for equipment ratings and derating | manual | 2 | FEL1, FEL2, FEL3
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | wind and seismic design data for E-house structure | review | 2 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | detector types and F&G philosophy; ambient design temperatures, humidity and wind for instrument selection | review | 2 | FEL2, FEL3
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | MECH | MECH-T020 Develop mechanical design basis | Excel / Word | basic wind speed, seismic parameters, ambient min/max design temperatures | manual | 2 | FEL2
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | MECH | MECH-T080 Perform air-cooled exchanger thermal design | HTRI | summer and winter design dry-bulb temperature, elevation | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | MECH | MECH-T100 Perform vessel and column mechanical design calculations | Mechanical calc tool | basic wind speed and exposure, seismic parameters | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | wind and seismic parameters | manual | 3 | FEL3, DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | wind speed and exposure, seismic parameters | manual | 3 | DD
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | PROC | PROC-T010 Prepare process design basis | Excel / Word | design ambient dry/wet bulb temperatures, rainfall, frost data | manual | 2 | FEL1, FEL2, FEL3
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | SAFE | SAFE-T030 Provide safety and environmental input to site selection | Excel / Word | seismic parameters, wind and flood level | review | 1 | FEL1
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | SAFE | SAFE-T050 Run preliminary consequence modelling for layout spacing | Excel / Word | wind speed and ambient design data | manual | 1 | FEL2
CIVL-I030 | Site environmental design data | data | CIVL | CIVL-T020 Prepare civil and structural design basis | Document Locator | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | wind speed, exposure and seismic parameters | manual | 4 | DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | CIVL | CIVL-T040 Specify the geotechnical investigation | Excel / Word | plant grid and ground levels for borehole coordinates | manual | 2 | FEL2, FEL3
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | CIVL | CIVL-T070 Review plot plan for civil constraints | Excel / Word | existing ground levels and existing features | manual | 2 | FEL1, FEL2, FEL3
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | CIVL | CIVL-T090 Design site preparation and earthworks | Excel / Word | existing ground levels for cut/fill | manual | 3 | FEL3, DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Excel / Word | existing ground levels | manual | 3 | FEL3, DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | property and plant grid, existing overhead lines and roads for utility line routing and substation location | review | 1 | FEL1, FEL2, FEL3, DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | PIPE | PIPE-T010 Prepare block plot plan options | Excel / Word | existing ground levels, plant grid, existing roads and underground services | manual | 1 | FEL1
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | plant coordinate system, benchmarks, existing ground levels and grid | file | 2 | FEL2, FEL3, DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | plant grid references | manual | 3 | DD
CIVL-I040 | Topographic survey and plant grid | drawing | CIVL | CIVL-T030 Specify and manage the topographic survey | Document Locator | SAFE | SAFE-T010 Compile environmental baseline and site constraints | Excel / Word | existing ground levels, outfalls, existing roads and buildings | manual | 1 | FEL1, FEL2
CIVL-I050 | Geotechnical investigation scope and borehole plan | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Excel / Word | planned borehole/CPT locations and tests to check coverage of the report | review | 3 | FEL3, DD
CIVL-I050 | Geotechnical investigation scope and borehole plan | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | geotechnical contractor scope | manual | 3 | FEL3, DD
CIVL-I050 | Geotechnical investigation scope and borehole plan | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | OWNR | OWNR-T030 Supply site and existing facility data | Excel / Word | borehole locations and site access needs | review | 1 | FEL1, FEL2
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T090 Design site preparation and earthworks | Excel / Word | soil parameters for compaction and soil improvement | manual | 3 | FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | bearing pressure, subgrade modulus and pile capacities | manual | 3 | FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | dynamic soil properties | manual | 3 | DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T170 Design tank foundations | Excel / Word | settlement predictions and bearing capacity | manual | 3 | FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | pile axial and lateral capacities | manual | 3 | FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | allowable bearing pressure for laydown and temporary building areas | review | 2 | FEL2, FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | bearing capacity for crane pads | review | 3 | FEL3, DD
CIVL-I060 | Foundation design parameters | data | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | MECH | MECH-T120 Design storage tanks | Mechanical calc tool | allowable bearing pressure, predicted settlement | manual | 3 | FEL3, DD
CIVL-I065 | Foundation type recommendation by area | decision | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Document Locator | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | foundation type (shallow/piled) by area | manual | 2 | FEL1, FEL2, FEL3, DD
CIVL-I070 | Civil and structural estimate quantities | data | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | concrete, steel and pile quantities by area | manual | 2 | FEL3, DD
CIVL-I070 | Civil and structural estimate quantities | data | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | earthworks, concrete m3, piles, steel tonnes by area | manual | 2 | FEL3, DD
CIVL-I070 | Civil and structural estimate quantities | data | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | earthworks, piles, concrete, steel, paving, building areas by area | manual | 1 | FEL2
CIVL-I070 | Civil and structural estimate quantities | data | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | concrete m3, piles, rebar, steel tonnage, building areas by area and WBS | manual | 2 | FEL3
CIVL-I080 | Civil comments on plot plan | document | CIVL | CIVL-T070 Review plot plan for civil constraints | Document Locator | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | road widths, drainage falls, dike footprints and foundation interference markups | review | 2 | FEL2, FEL3, DD
CIVL-I090 | Site preparation and earthworks drawings | drawing | CIVL | CIVL-T090 Design site preparation and earthworks | Document Locator | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | earthworks scope and sequence for CWP boundaries | review | 4 | FEL3, DD
CIVL-I100 | Grading plan and finished grade elevations | drawing | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Document Locator | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | finished grades and area falls | manual | 3 | FEL3, DD
CIVL-I100 | Grading plan and finished grade elevations | drawing | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | finished grade and top-of-concrete reference | manual | 3 | DD
CIVL-I100 | Grading plan and finished grade elevations | drawing | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Document Locator | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | finished grade elevations and slopes at laydown areas | review | 2 | FEL2, FEL3, DD
CIVL-I100 | Grading plan and finished grade elevations | drawing | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Document Locator | PIPE | PIPE-T270 Design underground piping | S3D | finished grade elevations | manual | 3 | DD
CIVL-I105 | Paving and curbing layout | drawing | CIVL | CIVL-T100 Prepare grading plan and finished elevations | Document Locator | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | paving scope and areas for CWPs | review | 4 | FEL3, DD
CIVL-I110 | Drainage area plan and sewer layout | drawing | CIVL | CIVL-T110 Design surface drainage and sewers | Document Locator | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | sewer routes and inverts | manual | 3 | DD, CON
CIVL-I110 | Drainage area plan and sewer layout | drawing | CIVL | CIVL-T110 Design surface drainage and sewers | Document Locator | PIPE | PIPE-T270 Design underground piping | S3D | sewer routes, inverts, catch basins and manholes | manual | 3 | DD
CIVL-I110 | Drainage area plan and sewer layout | drawing | CIVL | CIVL-T110 Design surface drainage and sewers | Document Locator | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | drainage areas and sewer outfalls | manual | 2 | FEL3, DD
CIVL-I115 | Stormwater runoff and discharge data | data | CIVL | CIVL-T110 Design surface drainage and sewers | Excel / Word | SAFE | SAFE-T080 Prepare water, stormwater and spill permit data | Excel / Word | runoff volumes, first flush, discharge points | manual | 2 | FEL3, DD
CIVL-I120 | Dike and containment design | drawing | CIVL | CIVL-T120 Design tank dikes and containment | Document Locator | SAFE | SAFE-T300 Prepare RMP hazard assessment and registration data | Excel / Word | dike capacities as passive mitigation | manual | 3 | DD, CON
CIVL-I130 | Preliminary pipe rack and structure configuration | drawing | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | CIVL | CIVL-T060 Prepare civil and structural quantities for estimates | Excel / Word | rack and structure steel tonnage per area | manual | 2 | FEL1, FEL2, FEL3, DD
CIVL-I130 | Preliminary pipe rack and structure configuration | drawing | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | rack configuration | manual | 3 | FEL3, DD
CIVL-I130 | Preliminary pipe rack and structure configuration | drawing | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | rack and structure configuration | review | 3 | FEL3, DD
CIVL-I130 | Preliminary pipe rack and structure configuration | drawing | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | PIPE | PIPE-T050 Build 3D layout model | S3D | rack widths, bent spacing, tier elevations and structure frame sizes | manual | 1 | FEL2, FEL3
CIVL-I135 | Pipe rack design load allowances | data | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | load allowances | manual | 3 | FEL3, DD
CIVL-I135 | Pipe rack design load allowances | data | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Document Locator | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | uniform tier load and anchor/guide load limits assumed by civil | manual | 2 | FEL2, FEL3, DD
CIVL-I140 | Roads, access and fencing layout | drawing | CIVL | CIVL-T130 Design roads, access and fencing | Document Locator | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | permanent roads, gates, fencing, crane pads and bearing capacity | review | 2 | FEL2, FEL3, DD
CIVL-I140 | Roads, access and fencing layout | drawing | CIVL | CIVL-T130 Design roads, access and fencing | Document Locator | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | crane pad locations and bearing capacity, road access | review | 3 | FEL3, DD
CIVL-I140 | Roads, access and fencing layout | drawing | CIVL | CIVL-T130 Design roads, access and fencing | Document Locator | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | building room layouts; fence and gate locations for access control and CCTV | review | 3 | FEL3, DD
CIVL-I140 | Roads, access and fencing layout | drawing | CIVL | CIVL-T130 Design roads, access and fencing | Document Locator | PIPE | PIPE-T270 Design underground piping | S3D | road crossings | manual | 3 | DD
CIVL-I150 | Underground composite drawing | drawing | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | underground composite for check | review | 3 | DD
CIVL-I150 | Underground composite drawing | drawing | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Document Locator | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | underground services under crane positions | review | 3 | FEL3, DD
CIVL-I150 | Underground composite drawing | drawing | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Document Locator | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | underground services and crossings | file | 3 | FEL3, DD
CIVL-I150 | Underground composite drawing | drawing | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Document Locator | PIPE | PIPE-T270 Design underground piping | S3D | underground composite: crossings and depths | manual | 3 | DD
CIVL-I155 | Underground conflict list | data | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | conflicts between duct banks and other underground services | manual | 3 | FEL3, DD
CIVL-I155 | Underground conflict list | data | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | PIPE | PIPE-T270 Design underground piping | S3D | conflicts between underground piping and other services | manual | 3 | DD
CIVL-I160 | Static equipment foundation calculations | document | CIVL | CIVL-T150 Design static equipment foundations | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | static equipment foundation loads | manual | 3 | FEL3, DD
CIVL-I160 | Static equipment foundation calculations | document | CIVL | CIVL-T150 Design static equipment foundations | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | footing and pedestal sizes, reinforcement | manual | 3 | DD
CIVL-I165 | Rotating equipment foundation calculations | document | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | rotating equipment foundation loads | manual | 3 | FEL3, DD
CIVL-I165 | Rotating equipment foundation calculations | document | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | block sizes and anchor bolt details | manual | 3 | DD
CIVL-I166 | Dynamic analysis results for vendor review | document | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | foundation dynamic analysis results to agree with the machine vendor | review | 3 | DD, CON
CIVL-I170 | Tank foundation design | drawing | CIVL | CIVL-T170 Design tank foundations | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | tank foundation loads | manual | 3 | FEL3, DD
CIVL-I170 | Tank foundation design | drawing | CIVL | CIVL-T170 Design tank foundations | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | ringwall dimensions | manual | 3 | DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | foundation outlines and depths | manual | 3 | DD, CON
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | foundation geometry for concrete modelling | manual | 3 | FEL3, DD, CON
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | foundation plans for check | review | 3 | DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | foundation locations and top-of-concrete elevations | review | 3 | FEL3, DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | foundation dimensions and elevations | review | 2 | DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | IFC foundation drawings | manual | 4 | CON
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | foundation coordinates and top-of-concrete elevations | manual | 4 | CON
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | ELEC | ELEC-T270 Design grounding system | Excel / Word | foundation plans for ground rod and embed locations | review | 3 | FEL3, DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | foundation drawings | review | 3 | DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | S3D | foundation locations and top of concrete | manual | 2 | FEL3, DD
CIVL-I190 | Foundation plans and details | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | PIPE | PIPE-T270 Design underground piping | S3D | foundation outlines and depths | manual | 3 | DD
CIVL-I195 | Anchor bolt layouts and schedule | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | anchor bolt layouts for check | review | 3 | DD
CIVL-I195 | Anchor bolt layouts and schedule | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | anchor bolt layouts and projections | review | 2 | DD
CIVL-I195 | Anchor bolt layouts and schedule | drawing | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Document Locator | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | anchor bolt coordinates, size and projection | manual | 4 | CON
CIVL-I200 | Pile layout and schedule | drawing | CIVL | CIVL-T180 Design piles and prepare piling layout | Document Locator | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | pile locations | manual | 3 | DD, CON
CIVL-I200 | Pile layout and schedule | drawing | CIVL | CIVL-T180 Design piles and prepare piling layout | Document Locator | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | pile quantities and types | manual | 3 | FEL3, DD
CIVL-I200 | Pile layout and schedule | drawing | CIVL | CIVL-T180 Design piles and prepare piling layout | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | pile layout for check | review | 3 | DD
CIVL-I205 | Test pile programme | document | CIVL | CIVL-T180 Design piles and prepare piling layout | Document Locator | CONS | CONS-T110 Develop construction schedule by CWP | P6 | test pile scope, locations and durations for the construction schedule | manual | 3 | DD, CON
CIVL-I210 | Pipe rack design calculations and reactions | document | CIVL | CIVL-T200 Analyse and design pipe racks | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | rack column base reactions | manual | 3 | FEL3, DD
CIVL-I210 | Pipe rack design calculations and reactions | document | CIVL | CIVL-T200 Analyse and design pipe racks | Document Locator | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | rack member sizes and geometry | manual | 3 | FEL3, DD, CON
CIVL-I210 | Pipe rack design calculations and reactions | document | CIVL | CIVL-T200 Analyse and design pipe racks | Document Locator | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Tekla | rack connection forces | manual | 3 | DD
CIVL-I220 | Process structure design calculations and reactions | document | CIVL | CIVL-T210 Analyse and design process structures and platforms | Document Locator | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | structure base reactions | manual | 3 | FEL3, DD
CIVL-I220 | Process structure design calculations and reactions | document | CIVL | CIVL-T210 Analyse and design process structures and platforms | Document Locator | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | structure member sizes and geometry | manual | 3 | FEL3, DD, CON
CIVL-I220 | Process structure design calculations and reactions | document | CIVL | CIVL-T210 Analyse and design process structures and platforms | Document Locator | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Tekla | structure connection forces | manual | 3 | DD
CIVL-I230 | Tekla structural model | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Tekla | members, marks and connections for GA and erection drawings | integrated | 3 | DD
CIVL-I230 | Tekla structural model | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | CIVL | CIVL-T240 Prepare structural steel MTO | Tekla | member profiles, grades, coatings, lengths and weights | integrated | 3 | FEL3, DD
CIVL-I230 | Tekla structural model | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | CIVL | CIVL-T260 Define structural fireproofing extent | Excel / Word | member list within fire envelopes | integrated | 3 | DD
CIVL-I230 | Tekla structural model | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | steel members and supports | review | 3 | FEL3, DD
CIVL-I230 | Tekla structural model | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | Tekla model with members, connections and fabrication attributes | file | 4 | DD, CON
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | Tekla steel and concrete reference geometry | file | 3 | FEL3, DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | platforms and structural members for instrument and JB supports | file | 3 | DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | PIPE | PIPE-T160 Route piping in the 3D model | S3D | steel and concrete geometry, platforms and rack steel as S3D reference | file | 3 | FEL3, DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | PIPE | PIPE-T250 Design pipe supports | S3D | available steel members and platforms | file | 3 | DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | PIPE | PIPE-T260 Request civil and structural openings, platforms and foundations | S3D | structure layout | file | 2 | FEL3, DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | PIPE | PIPE-T290 Detect and resolve clashes | S3D | structural reference geometry | file | 3 | DD
CIVL-I235 | Structural reference model for S3D | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | Tekla | PIPE | PIPE-T370 Produce piping GA and key plan drawings | S3D | structural references | file | 3 | DD
CIVL-I236 | Structural model for iConstruct | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | iConstruct | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | Tekla steel, platforms and foundations in iConstruct | integrated | 2 | FEL3, DD
CIVL-I236 | Structural model for iConstruct | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | iConstruct | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | Tekla model in iConstruct with assembly marks, CWP and erection sequence | integrated | 4 | DD, CON
CIVL-I236 | Structural model for iConstruct | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | iConstruct | OWNR | OWNR-T120 Review the 3D model for operability and maintenance | iConstruct | platforms, ladders and stairs in iConstruct | integrated | 2 | FEL3, DD
CIVL-I236 | Structural model for iConstruct | model | CIVL | CIVL-T220 Model structures in Tekla and share reference models | iConstruct | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | Tekla structural model published to Navisworks | file | 3 | FEL3, DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | steel GA drawings for check | review | 3 | DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | steel GA, erection marks and sequence notes | review | 2 | DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | IFC steel erection drawings | manual | 4 | CON
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | ELEC | ELEC-T270 Design grounding system | Excel / Word | steel structures and pipe rack columns to ground | review | 3 | FEL3, DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | ELEC | ELEC-T280 Design lightning protection | Excel / Word | structure heights and layouts | review | 3 | DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | steel for fixture supports | review | 3 | DD
CIVL-I240 | Steel GA and erection drawings | drawing | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | steel GA and erection drawings | file | 4 | DD, CON
CIVL-I245 | Connection design forces and criteria | document | CIVL | CIVL-T230 Prepare steel GA drawings and connection design data | Document Locator | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | connection design forces and criteria | file | 4 | DD, CON
CIVL-I248 | Structural steel MTO | data | CIVL | CIVL-T240 Prepare structural steel MTO | Excel / Word | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | steel tonnage by profile and grade for fabrication requisition | manual | 3 | FEL3, DD
CIVL-I250 | Embedment and sleeve schedule | data | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | embedments, sleeves and stub-ups to show on foundation drawings | manual | 3 | DD
CIVL-I260 | Structural fireproofing schedule | drawing | CIVL | CIVL-T260 Define structural fireproofing extent | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | fireproofing schedule for check | review | 3 | DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | building layouts | manual | 3 | FEL3, DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | room layouts | manual | 3 | DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | CIVL | CIVL-T300 Design building HVAC | Excel / Word | room layouts and volumes | manual | 3 | FEL3, DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | building layouts, doors and openings near classified areas | review | 2 | FEL3, DD, CON
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | building layouts, cable entry and trenches | review | 3 | DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | electrical and I&C room layouts for clean agent | review | 3 | FEL3, DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | control/rack room dimensions, false floor and cable entry, room HVAC capacity and design conditions | review | 2 | FEL2, FEL3, DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | INST | INST-T200 Specify fire and gas system and device list | SI | room layouts for building smoke/heat detection; HVAC trip and damper signals to F&G | review | 3 | FEL3, DD
CIVL-I270 | Building layouts for electrical and I&C | drawing | CIVL | CIVL-T270 Develop building space programme and layouts | Document Locator | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | building room layouts; fence and gate locations for access control and CCTV | review | 3 | FEL3, DD
CIVL-I280 | Building structural design | document | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Document Locator | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | wall/roof construction and blast doors | manual | 3 | DD
CIVL-I290 | Architectural drawings | drawing | CIVL | CIVL-T290 Prepare architectural drawings | Document Locator | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | architectural drawings for check | review | 3 | DD
CIVL-I290 | Architectural drawings | drawing | CIVL | CIVL-T290 Prepare architectural drawings | Document Locator | ELEC | ELEC-T280 Design lightning protection | Excel / Word | building dimensions and roofing | review | 3 | DD
CIVL-I290 | Architectural drawings | drawing | CIVL | CIVL-T290 Prepare architectural drawings | Document Locator | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | room layouts and functions | review | 3 | DD
CIVL-I290 | Architectural drawings | drawing | CIVL | CIVL-T290 Prepare architectural drawings | Document Locator | FIRE | FIRE-T220 Specify fixed fire protection systems | Excel / Word | room functions and fire ratings | review | 3 | FEL3, DD
CIVL-I290 | Architectural drawings | drawing | CIVL | CIVL-T290 Prepare architectural drawings | Document Locator | SAFE | SAFE-T100 Perform facility siting study (API RP 752/753) | Excel / Word | building plans, construction type and dimensions | manual | 2 | FEL3, DD
CIVL-I300 | HVAC heat load calculations and equipment sizing | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | HVAC pressurisation and air changes per room | review | 2 | FEL3, DD, CON
CIVL-I300 | HVAC heat load calculations and equipment sizing | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | control/rack room dimensions, false floor and cable entry, room HVAC capacity and design conditions | review | 2 | FEL2, FEL3, DD
CIVL-I300 | HVAC heat load calculations and equipment sizing | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | air change rates and pressurization | review | 2 | FEL3, DD
CIVL-I305 | HVAC electrical loads | data | CIVL | CIVL-T300 Design building HVAC | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | HVAC consumer tag, kW, voltage, duty/standby, essential/UPS need | manual | 2 | FEL3, DD, CON
CIVL-I306 | HVAC control and shutdown interface | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | INST | INST-T200 Specify fire and gas system and device list | SI | room layouts for building smoke/heat detection; HVAC trip and damper signals to F&G | review | 3 | FEL3, DD
CIVL-I306 | HVAC control and shutdown interface | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | SAFE | SAFE-T110 Assess toxic gas ingress and shelter-in-place | Excel / Word | intake gas detection, damper closure and HVAC trips | review | 2 | FEL3, DD
CIVL-I307 | HVAC datasheets and requisition scope | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | HVAC datasheets | manual | 3 | FEL3, DD
CIVL-I307 | HVAC datasheets and requisition scope | document | CIVL | CIVL-T300 Design building HVAC | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | HVAC requisition scope and datasheets | manual | 3 | FEL3, DD
CIVL-I310 | Civil and structural requisitions and TBEs | document | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | civil and structural MRs and scopes | manual | 3 | FEL3, DD
CIVL-I320 | Civil vendor data review comments | document | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | anchor bolt confirmation and load acceptance comments | review | 2 | DD, CON
CIVL-I320 | Civil vendor data review comments | document | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | anchor bolt and load acceptance comments | review | 2 | DD, CON
CIVL-I330 | Civil model review responses and clash resolutions | data | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | Excel / Word | PIPE | PIPE-T290 Detect and resolve clashes | S3D | civil resolution and model change status per clash | review | 3 | DD
CIVL-I340 | Civil and structural CWP scope and sequence | data | CIVL | CIVL-T340 Provide civil inputs to construction packaging | Excel / Word | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | civil/steel CWP list, pour and erection sequence | manual | 2 | FEL3, DD
CIVL-I340 | Civil and structural CWP scope and sequence | data | CIVL | CIVL-T340 Provide civil inputs to construction packaging | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | deliverables per civil/steel CWP and their release dates | manual | 2 | FEL2, FEL3, DD, CON
CIVL-I340 | Civil and structural CWP scope and sequence | data | CIVL | CIVL-T340 Provide civil inputs to construction packaging | Excel / Word | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | steel erection sequence and release dates | manual | 3 | DD, CON
CIVL-I350 | Sealed IFC civil and structural package | decision | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | sealed IFC civil/structural package: documents and revisions | integrated | 2 | FEL2, FEL3, DD, CON, COM
CIVL-I350 | Sealed IFC civil and structural package | decision | CIVL | CIVL-T350 Check, seal and issue civil and structural IFC packages | Document Locator | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | sealed IFC civil and structural documents with PE seal | review | 4 | DD, CON
CIVL-I360 | Civil RFI responses and field change dispositions | decision | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Tekla | approved RFI and field change revisions | manual | 4 | CON, COM
CIVL-I360 | Civil RFI responses and field change dispositions | decision | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | CONS | CONS-T170 Raise and manage RFIs | Procore | civil answers and drawing revisions | manual | 4 | CON
CIVL-I365 | Civil non-conformance dispositions | decision | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Tekla | non-conformance repairs affecting as-built | manual | 4 | CON, COM
CIVL-I370 | Settlement evaluation and acceptance | decision | CIVL | CIVL-T370 Evaluate settlement monitoring during hydrotest | Document Locator | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | settlement acceptance before tank or foundation turnover | review | 4 | CON
CIVL-I380 | As-built civil and structural drawings and model | drawing | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | as-built civil and structural drawings | review | 4 | COM
CIVL-I380 | As-built civil and structural drawings and model | drawing | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Document Locator | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | as-built buildings | review | 4 | COM
CIVL-I390 | Geotechnical and soil corrosivity report | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | CIVL | CIVL-T050 Set foundation design parameters from the geotechnical report | Excel / Word | Geotechnical factual and interpretive report (soil profiles, bearing and pile capacities, settlement, groundwater, soil chemistry) from the geotechnical contractor; no VEND item exists | manual | 3 | FEL3, DD
CIVL-I390 | Geotechnical and soil corrosivity report | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | ELEC | ELEC-T270 Design grounding system | Excel / Word | Soil resistivity survey (Wenner four-pin) and soil chemistry for grounding design | manual | 3 | FEL3, DD
CIVL-I390 | Geotechnical and soil corrosivity report | document | CIVL | CIVL-T040 Specify the geotechnical investigation | Document Locator | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | Soil resistivity and soil chemistry (pH, chlorides) survey along buried routes and tank pads for CP design | manual | 3 | DD, CON
CIVL-I901 | Civil deliverables list | data | CIVL | CIVL-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | civil deliverables with planned dates | manual | 2 | FEL2, FEL3, DD, CON
CIVL-I902 | Civil progress measurement | data | CIVL | CIVL-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Civil progress: foundation and steel drawing completion counts | manual | 2 | FEL3, DD
CIVL-I903 | Civil holds | data | CIVL | CIVL-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | Civil hold list: foundation drawings on hold awaiting certified vendor loads | manual | 2 | DD, CON
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | FIRE | FIRE-T045 Prepare fire protection and F&G philosophy | Excel / Word | DCS/SIS/F&G split and F&G system concept | review | 1 | FEL2, FEL3
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | DCS/SIS/F&G split, conventional vs fieldbus I/O, package control approach for pricing | manual | 1 | FEL1, FEL2, FEL3
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | system split, control room concept, remote I/O approach | review | 1 | FEL2, FEL3, DD
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | MECH | MECH-T090 Design and specify fired heaters | Excel / Word | DCS/SIS split and packaged control approach for BMS | review | 2 | FEL3, DD
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | DCS/SIS/F&G split and packaged unit control approach | review | 3 | FEL3, DD
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | control and safety system concept | review | 2 | FEL3, DD
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | DCS/SIS split and level of automation | review | 2 | FEL2, FEL3, DD
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | SAFE | SAFE-T090 Facilitate preliminary (coarse) HAZOP | PHA tool | preliminary SIS scope | review | 2 | FEL2, FEL3
INST-I010 | Preliminary control and safety system concept | decision | INST | INST-T010 Define preliminary control and safety concept | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | DCS/SIS/F&G split and packaged control approach | manual | 2 | FEL2, FEL3
INST-I020 | I&C quantities and estimate input | data | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | instrument counts by type, valve counts, JBs, cable allowances | manual | 2 | FEL3, DD
INST-I020 | I&C quantities and estimate input | data | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | instrument counts by type, I/O counts, valve and analyzer counts, bulk factors | manual | 1 | FEL2
INST-I020 | I&C quantities and estimate input | data | INST | INST-T020 Prepare factored instrument count and I&C estimate input | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | instrument counts by type, I/O counts, cable per I/O, JB and cabinet counts | manual | 2 | FEL3
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | control system cabinets and networks for control-system subsystems | review | 3 | FEL3, DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | electrical network protocol (Modbus TCP/IEC 61850) and DCS/ECMS links | review | 2 | FEL3, DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | intelligent MCC communication protocol to DCS | review | 2 | FEL3, DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | network protocol, marshalling and electrical system interfaces | review | 3 | DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | INST | INST-T180 Prepare DCS specification | Excel / Word | system architecture, redundancy, network | review | 3 | FEL3, DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | OWNR | OWNR-T110 Specify control and alarm management requirements | Excel / Word | ICS architecture | review | 2 | FEL3, DD
INST-I030 | ICS architecture diagram | drawing | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | PROC | PROC-T230 Prepare control and operating philosophy and control narratives | Excel / Word | APC/historian capability in architecture | review | 2 | FEL2, FEL3, DD
INST-I031 | Control and rack room space, cabinet layout and heat loads | document | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | cable entries in control and rack rooms | manual | 3 | DD
INST-I031 | Control and rack room space, cabinet layout and heat loads | document | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | cabinet and console count and footprint, cable entry, floor loading | manual | 2 | FEL2, FEL3, DD
INST-I031 | Control and rack room space, cabinet layout and heat loads | document | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | cabinet heat dissipation (kW) per room | manual | 3 | FEL3, DD
INST-I031 | Control and rack room space, cabinet layout and heat loads | document | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | INST | INST-T280 Compile instrument utility loads | Excel / Word | cabinet power and clean power needs per room | manual | 3 | FEL3, DD
INST-I031 | Control and rack room space, cabinet layout and heat loads | document | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | control and rack room footprint and cabinet space | meeting | 1 | FEL2, FEL3, DD
INST-I040 | I&C design basis and general instrument specifications | document | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | installation and connection standards | review | 4 | CON
INST-I040 | I&C design basis and general instrument specifications | document | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | INST | INST-T110 Prepare instrument datasheets | SI | instrument selection rules and general specifications | review | 3 | FEL3, DD
INST-I040 | I&C design basis and general instrument specifications | document | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | approved instrument and control vendor list | review | 3 | FEL3, DD
INST-I040 | I&C design basis and general instrument specifications | document | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | general instrument specifications | manual | 3 | FEL3, DD
INST-I040 | I&C design basis and general instrument specifications | document | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | instrument standards and tagging rules | manual | 3 | DD
INST-I045 | I&C P&ID markups | document | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | INST | INST-T050 Build and maintain the instrument index in SI | SI | confirmed instrument tagging and types | review | 2 | FEL3, DD, CON
INST-I045 | I&C P&ID markups | document | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | PROC | PROC-T200 Develop P&IDs (process content) | SPID | instrument tags, symbols, signal lines and fail positions | review | 3 | FEL2, FEL3
INST-I045 | I&C P&ID markups | document | INST | INST-T045 Review P&IDs for instrumentation and controls | SPID | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | instrument tag updates | manual | 3 | DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | tag, type, loop, P&ID | file | 4 | DD, CON
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | instrument count by type and area (via P&ID/unit) | manual | 2 | FEL3, DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | ELEC | ELEC-T100 Review P&IDs and assign electrical attributes | SPID | motor-related instrument tags: run status, trips, permissives | review | 2 | FEL3, DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | tag list for the alarm database | manual | 3 | DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T260 Develop I/O list and assign I/O | SI | tags, I/O type, system | integrated | 3 | FEL3, DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T280 Compile instrument utility loads | Excel / Word | instrument consumers by type and location | manual | 3 | FEL3, DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | tag list and instrument types | manual | 3 | DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T380 Prepare system configuration data for vendors | SI | tags and descriptions | integrated | 3 | DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | instrument, cable and JB tags | file | 4 | CON, COM
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | PIPE | PIPE-T180 Position in-line instruments and instrument access | S3D | tag, type, line number and P&ID | manual | 3 | DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | in-line instrument types to remove or isolate | manual | 3 | DD, CON
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | PROC | PROC-T220 Prepare instrument process data | Excel / Word | tag, type, service, loop and line/equipment number | manual | 3 | FEL3, DD
INST-I050 | Instrument index | data | INST | INST-T050 Build and maintain the instrument index in SI | SI | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | instrument index | manual | 3 | DD
INST-I055 | I&C HAZOP/LOPA action responses | document | INST | INST-T055 Close out HAZOP and LOPA actions on I&C design | PHA tool | SAFE | SAFE-T170 Track and close out PHA and study actions | PHA tool | I&C action responses | review | 3 | FEL3, DD, CON
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | INST | INST-T070 Size control valves | SI | flow cases, P, T, fluid properties per CV | integrated | 3 | FEL3, DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | process conditions per on/off valve | integrated | 3 | FEL3, DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | INST | INST-T090 Calculate flow elements and thermowells | SI | flow cases and fluid properties per flow element and thermowell | integrated | 3 | FEL3, DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | INST | INST-T110 Prepare instrument datasheets | SI | process data per tag | integrated | 3 | FEL3, DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | INST | INST-T380 Prepare system configuration data for vendors | SI | ranges and units | integrated | 3 | DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | PROC | PROC-T220 Prepare instrument process data | Excel / Word | SI process data fields to be filled per tag | manual | 3 | FEL3, DD
INST-I060 | Instrument process data in SI | data | INST | INST-T060 Enter instrument process data | SI | PROC | PROC-T320 Respond to technical queries, holds and change requests | Excel / Word | instrument process data queries and set points | manual | 3 | FEL3, DD, CON
INST-I070 | Control valve sizing calculations | document | INST | INST-T070 Size control valves | SI | INST | INST-T110 Prepare instrument datasheets | SI | CV size, trim, actuator, noise results | integrated | 3 | FEL3, DD
INST-I070 | Control valve sizing calculations | document | INST | INST-T070 Size control valves | SI | PROC | PROC-T325 Review instrument and control valve sizing | SI | Cv, % opening, noise, cavitation, trim | review | 3 | FEL3, DD
INST-I070 | Control valve sizing calculations | document | INST | INST-T070 Size control valves | SI | SAFE | SAFE-T240 Perform noise study | Excel / Word | control valve noise dB(A) | manual | 3 | FEL3, DD
INST-I071 | Control valve sizes and ratings for P&ID | data | INST | INST-T070 Size control valves | SI | PROC | PROC-T200 Develop P&IDs (process content) | SPID | control valve sizes, ratings and reducers | manual | 3 | FEL2, FEL3
INST-I072 | Preliminary in-line valve dimensions and weights | data | INST | INST-T070 Size control valves | SI | PIPE | PIPE-T160 Route piping in the 3D model | S3D | control and on/off valve face-to-face, weights and actuator envelopes | manual | 3 | FEL3, DD
INST-I080 | On/off and ESD valve sizing and actuator data | data | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | ESD valve fire-proofing need and locations | manual | 3 | FEL3, DD
INST-I080 | On/off and ESD valve sizing and actuator data | data | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | INST | INST-T110 Prepare instrument datasheets | SI | on/off valve size, actuator, stroke time, failure position | integrated | 3 | FEL3, DD
INST-I080 | On/off and ESD valve sizing and actuator data | data | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | PIPE | PIPE-T110 Prepare valve specifications and datasheets | Excel / Word | actuated on/off valve type, size, rating, shut-off class and fire-proofing | manual | 2 | FEL3, DD
INST-I080 | On/off and ESD valve sizing and actuator data | data | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | ESD valve stroke time and failure position | manual | 3 | FEL3, DD
INST-I090 | Flow element and thermowell calculations | document | INST | INST-T090 Calculate flow elements and thermowells | SI | PROC | PROC-T325 Review instrument and control valve sizing | SI | flow element bore, dP and permanent loss | review | 3 | FEL3, DD
INST-I091 | Flow element sizes and straight-run requirements | data | INST | INST-T090 Calculate flow elements and thermowells | SI | PIPE | PIPE-T160 Route piping in the 3D model | S3D | flow element sizes and upstream/downstream straight runs | manual | 3 | FEL3, DD
INST-I091 | Flow element sizes and straight-run requirements | data | INST | INST-T090 Calculate flow elements and thermowells | SI | PIPE | PIPE-T180 Position in-line instruments and instrument access | S3D | straight-run requirements | manual | 3 | DD
INST-I100 | Relief valve datasheets | document | INST | INST-T100 Specify relief valves from the process sizing | SI | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | instrument and PSV datasheets attached to each MR | file | 3 | FEL3, DD
INST-I100 | Relief valve datasheets | document | INST | INST-T100 Specify relief valves from the process sizing | SI | PROC | PROC-T325 Review instrument and control valve sizing | SI | PSV set pressure, rate and selected orifice | review | 3 | FEL3, DD
INST-I110 | Instrument datasheets for requisition | document | INST | INST-T110 Prepare instrument datasheets | SI | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | instrument and PSV datasheets attached to each MR | file | 3 | FEL3, DD
INST-I110 | Instrument datasheets for requisition | document | INST | INST-T110 Prepare instrument datasheets | SI | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | process connection and mounting per tag | manual | 3 | DD
INST-I110 | Instrument datasheets for requisition | document | INST | INST-T110 Prepare instrument datasheets | SI | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | instrument datasheets for vendor-supplied instruments | manual | 3 | FEL3, DD
INST-I110 | Instrument datasheets for requisition | document | INST | INST-T110 Prepare instrument datasheets | SI | PROC | PROC-T325 Review instrument and control valve sizing | SI | instrument datasheets process data and ranges | review | 3 | FEL3, DD
INST-I110 | Instrument datasheets for requisition | document | INST | INST-T110 Prepare instrument datasheets | SI | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | instrument datasheets: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
INST-I115 | Instrument connection requirements on equipment and piping | data | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | MECH | MECH-T130 Prepare mechanical datasheets for vessels and columns | Excel / Word | instrument connection type, size, rating, bridle arrangement on vessels | manual | 2 | FEL3, DD
INST-I115 | Instrument connection requirements on equipment and piping | data | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | MECH | MECH-T140 Prepare mechanical datasheets for exchangers | Excel / Word | instrument connections on exchangers and air-cooler vibration switch connections | manual | 2 | FEL3, DD
INST-I115 | Instrument connection requirements on equipment and piping | data | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | MECH | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | Excel / Word | instrument nozzle orientation and elevation/level range | manual | 2 | FEL3, DD
INST-I115 | Instrument connection requirements on equipment and piping | data | INST | INST-T115 Define instrument connections on equipment and lines | Excel / Word | PIPE | PIPE-T180 Position in-line instruments and instrument access | S3D | connection type, size, orientation and elevation | manual | 3 | DD
INST-I130 | Instrument material requisitions | document | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | MR number, scope, datasheets, quantities, VDRL | manual | 3 | FEL3, DD
INST-I140 | Instrument technical bid evaluations | document | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | technical evaluation of the relief valve offers | manual | 3 | FEL3, DD
INST-I140 | Instrument technical bid evaluations | document | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | technical clarifications for instrument packages | manual | 3 | FEL3, DD
INST-I140 | Instrument technical bid evaluations | document | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | technically acceptable bidders for instrument packages | review | 3 | FEL3, DD
INST-I145 | Agreed final relief valve sizing for purchase | decision | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | INST | INST-T150 Review instrument vendor data | Document Locator | agreed sizing to check certified relief valve data against | manual | 4 | DD, CON
INST-I145 | Agreed final relief valve sizing for purchase | decision | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | PIPE | PIPE-T160 Route piping in the 3D model | S3D | final PSV inlet and outlet sizes and ratings | manual | 3 | FEL3, DD
INST-I145 | Agreed final relief valve sizing for purchase | decision | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | PROC | PROC-T260 Run flare and blowdown hydraulics | Flare / relief tool | rated capacities and outlet sizes for flare back-pressure checks | manual | 3 | FEL3, DD
INST-I145 | Agreed final relief valve sizing for purchase | decision | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | agreed relief valve sizing before award | manual | 3 | FEL3, DD
INST-I150 | Instrument vendor data comments | document | INST | INST-T150 Review instrument vendor data | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | comments on vendor instrument data | review | 2 | DD, CON
INST-I150 | Instrument vendor data comments | document | INST | INST-T150 Review instrument vendor data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | return code and comments on instrument vendor data | review | 2 | DD, CON
INST-I151 | Certified in-line instrument dimensions and weights | data | INST | INST-T150 Review instrument vendor data | SI | INST | INST-T330 Generate loop diagrams | SI | certified instrument wiring data | integrated | 4 | DD, CON
INST-I151 | Certified in-line instrument dimensions and weights | data | INST | INST-T150 Review instrument vendor data | SI | PIPE | PIPE-T160 Route piping in the 3D model | S3D | certified face-to-face and weights for model update | manual | 4 | FEL3, DD
INST-I160 | Analyzer datasheets and system specification | document | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | CEMS/analyzer tags and scope | review | 4 | COM
INST-I160 | Analyzer datasheets and system specification | document | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | analyzer systems scope | manual | 2 | FEL2, FEL3
INST-I160 | Analyzer datasheets and system specification | document | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | analyzer system specification and test requirements | review | 4 | DD, CON
INST-I161 | Analyzer shelter utility and space requirements | data | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | analyzer shelter HVAC requirements | manual | 3 | FEL3, DD
INST-I161 | Analyzer shelter utility and space requirements | data | INST | INST-T160 Specify analyzers and analyzer shelters | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | analyzer shelter power and UPS | manual | 2 | FEL3, DD, CON
INST-I170 | Control narratives and functional logic | document | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | motor control logic: start/stop, auto/manual, permissives | review | 3 | DD
INST-I170 | Control narratives and functional logic | document | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | INST | INST-T380 Prepare system configuration data for vendors | SI | control logic, shutdown and F&G logic for configuration | review | 3 | DD
INST-I170 | Control narratives and functional logic | document | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | C&E and narratives to test against | review | 4 | DD, CON
INST-I170 | Control narratives and functional logic | document | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | control narratives | review | 3 | FEL3, DD
INST-I170 | Control narratives and functional logic | document | INST | INST-T170 Write control narratives and functional design specifications | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | control narratives and functional logic | manual | 4 | DD, CON
INST-I180 | DCS specification | document | INST | INST-T180 Prepare DCS specification | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | DCS FAT requirements | review | 4 | DD, CON
INST-I190 | SIS specification | document | INST | INST-T190 Prepare SIS specification | Excel / Word | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | SIS specification for the RFQ package | review | 3 | FEL2, FEL3, DD
INST-I190 | SIS specification | document | INST | INST-T190 Prepare SIS specification | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | SIS functional and hardware requirements to configure | review | 3 | DD, CON
INST-I200 | F&G system specification | document | INST | INST-T200 Specify fire and gas system and device list | Excel / Word | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | F&G system specification for the RFQ package | review | 3 | FEL2, FEL3, DD
INST-I200 | F&G system specification | document | INST | INST-T200 Specify fire and gas system and device list | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | F&G system functional and hardware requirements to configure | review | 3 | DD, CON
INST-I201 | F&G device list and locations | data | INST | INST-T200 Specify fire and gas system and device list | SI | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | detector locations and voting | review | 2 | FEL3, DD
INST-I210 | SIF list with initiators and final elements | data | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | SIF final elements that are motors or breakers | review | 3 | DD
INST-I210 | SIF list with initiators and final elements | data | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | INST | INST-T220 Write safety requirements specification | Excel / Word | SIF initiators, logic and final elements | manual | 3 | FEL3, DD
INST-I210 | SIF list with initiators and final elements | data | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SIF references for C&E lines | manual | 3 | FEL3, DD
INST-I210 | SIF list with initiators and final elements | data | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | SIF list and boundaries | review | 4 | DD
INST-I210 | SIF list with initiators and final elements | data | INST | INST-T210 Define SIFs and input to SIL determination | PHA tool | SAFE | SAFE-T160 Run LOPA and set SIL targets | PHA tool | SIF definitions with initiators, voting and final elements | manual | 3 | FEL3, DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | SRS per SIF | review | 4 | DD, CON
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | SIF safe state, response time, trip set points | manual | 4 | COM
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | INST | INST-T080 Size on/off and emergency shutdown valves and actuators | SI | SIF final element requirements: response time, safe state, partial stroke testing | review | 3 | FEL3, DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | INST | INST-T190 Prepare SIS specification | Excel / Word | SIF functions, SIL, response time, bypass rules | review | 3 | FEL3, DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | INST | INST-T230 Verify SIL achievement | Excel / Word | SIL targets, architecture, proof test assumptions | review | 3 | DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | INST | INST-T430 Support SAT, SIS validation and integrated testing | DCS / SIS config | SRS and proof test steps for validation | review | 4 | COM
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | SAFE | SAFE-T120 Perform quantitative risk assessment | Excel / Word | SIF response times | review | 2 | FEL3, DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | SRS | review | 3 | DD
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | SRS | review | 4 | DD, CON, COM
INST-I220 | Safety requirements specification | document | INST | INST-T220 Write safety requirements specification | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | SRS per SIF | manual | 4 | DD, CON
INST-I230 | SIL verification report | document | INST | INST-T230 Verify SIL achievement | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | PFDavg, RRF, HFT per SIF | review | 3 | DD
INST-I230 | SIL verification report | document | INST | INST-T230 Verify SIL achievement | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | SIL verification | review | 4 | DD, CON, COM
INST-I231 | Proof test intervals and procedures | document | INST | INST-T230 Verify SIL achievement | Excel / Word | INST | INST-T430 Support SAT, SIS validation and integrated testing | DCS / SIS config | SRS and proof test steps for validation | review | 4 | COM
INST-I231 | Proof test intervals and procedures | document | INST | INST-T230 Verify SIL achievement | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | proof test intervals | review | 3 | DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | process shutdown C&E | review | 4 | DD, CON
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | C&E causes, set points and effects | manual | 4 | COM
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | SIS/ESD trips of motors and breakers | review | 3 | DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | cause and effect trip actions on motors | review | 3 | DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | INST | INST-T380 Prepare system configuration data for vendors | SI | control logic, shutdown and F&G logic for configuration | review | 3 | DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | C&E and narratives to test against | review | 4 | DD, CON
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | trip set points | manual | 4 | DD, CON
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | cause and effect | review | 4 | CON, COM
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | preliminary SIS C&E | review | 3 | FEL3, DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | process shutdown C&E | review | 3 | DD
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | package trips in C&E | review | 3 | DD, CON
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | C&E | review | 4 | DD, CON, COM
INST-I240 | Process shutdown cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | process shutdown C&E | manual | 4 | DD, CON
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | F&G C&E | review | 4 | DD, CON
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | F&G C&E | manual | 4 | COM
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | INST | INST-T380 Prepare system configuration data for vendors | SI | control logic, shutdown and F&G logic for configuration | review | 3 | DD
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | C&E and narratives to test against | review | 4 | DD, CON
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | SAFE | SAFE-T260 Review cause and effect and SIL verification | Excel / Word | F&G C&E | review | 3 | DD
INST-I241 | F&G cause and effect | document | INST | INST-T240 Prepare cause and effect charts | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | F&G C&E | manual | 4 | DD, CON
INST-I250 | Master alarm database | data | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | INST | INST-T380 Prepare system configuration data for vendors | SI | alarm limits and priorities | file | 3 | DD
INST-I250 | Master alarm database | data | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | alarm set points and operator actions | manual | 4 | DD, CON
INST-I250 | Master alarm database | data | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | alarm settings | review | 4 | COM
INST-I250 | Master alarm database | data | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | alarm set points and priorities | review | 3 | FEL3, DD
INST-I250 | Master alarm database | data | INST | INST-T250 Rationalize alarms and build master alarm database | Excel / Word | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | alarm set points | review | 4 | DD, CON, COM
INST-I260 | I/O list | data | INST | INST-T260 Develop I/O list and assign I/O | SI | COMM | COMM-T170 Execute loop checks | Smart Completions | I/O assignment | manual | 4 | CON, COM
INST-I260 | I/O list | data | INST | INST-T260 Develop I/O list and assign I/O | SI | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | cabinet/card/channel assignments | integrated | 3 | DD
INST-I260 | I/O list | data | INST | INST-T260 Develop I/O list and assign I/O | SI | INST | INST-T380 Prepare system configuration data for vendors | SI | I/O assignment | integrated | 3 | DD
INST-I260 | I/O list | data | INST | INST-T260 Develop I/O list and assign I/O | SI | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | tag, signal type, system, cabinet, card, channel | file | 4 | DD, CON
INST-I261 | I/O counts and typicals for system vendors | data | INST | INST-T260 Develop I/O list and assign I/O | SI | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | I/O counts per system for cabinet counts | manual | 2 | FEL2, FEL3, DD
INST-I261 | I/O counts and typicals for system vendors | data | INST | INST-T260 Develop I/O list and assign I/O | SI | INST | INST-T180 Prepare DCS specification | Excel / Word | I/O counts per type for DCS sizing | manual | 3 | FEL3, DD
INST-I261 | I/O counts and typicals for system vendors | data | INST | INST-T260 Develop I/O list and assign I/O | SI | INST | INST-T190 Prepare SIS specification | Excel / Word | SIS I/O counts | manual | 3 | FEL3, DD
INST-I270 | Package instrumentation and control requirements | document | INST | INST-T270 Integrate vendor package controls | Excel / Word | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | package PLC requirements, interface signals, communications, SIS/F&G interfaces | review | 3 | FEL3, DD
INST-I270 | Package instrumentation and control requirements | document | INST | INST-T270 Integrate vendor package controls | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | I&C scope and requirements for packages | manual | 3 | FEL3, DD
INST-I270 | Package instrumentation and control requirements | document | INST | INST-T270 Integrate vendor package controls | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | package I&C requirements, PLC and interfaces | manual | 3 | FEL3, DD
INST-I270 | Package instrumentation and control requirements | document | INST | INST-T270 Integrate vendor package controls | Excel / Word | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | PLC requirements, communication and SIS interfaces | manual | 3 | DD
INST-I271 | Package control vendor data comments | document | INST | INST-T270 Integrate vendor package controls | Document Locator | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | comments on package instrument lists and control offers | review | 3 | FEL3, DD
INST-I271 | Package control vendor data comments | document | INST | INST-T270 Integrate vendor package controls | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | comments on package P&IDs, instrument lists and panels | review | 2 | DD, CON
INST-I271 | Package control vendor data comments | document | INST | INST-T270 Integrate vendor package controls | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | comments on package P&IDs, instrument lists, panels | review | 2 | DD, CON
INST-I272 | Package interface signal list | data | INST | INST-T270 Integrate vendor package controls | Excel / Word | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | package interface signals | review | 3 | DD, CON
INST-I272 | Package interface signal list | data | INST | INST-T270 Integrate vendor package controls | Excel / Word | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | interface signal list | manual | 3 | DD
INST-I280 | Instrument power and UPS load list | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | DCS/SIS/F&G cabinet and instrument power kW/kVA, UPS vs normal | manual | 2 | FEL3, DD, CON
INST-I280 | Instrument power and UPS load list | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | UPS-powered control system loads, redundancy and autonomy | manual | 3 | FEL3, DD
INST-I280 | Instrument power and UPS load list | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | UPS load list and autonomy for DCS/SIS/F&G | manual | 3 | FEL3, DD
INST-I281 | Instrument winterization and heat tracing requirements | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | impulse and analyzer sample lines needing tracing, maintain temperature | manual | 3 | DD
INST-I281 | Instrument winterization and heat tracing requirements | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | impulse lines needing tracing | review | 3 | DD
INST-I282 | Instrument air consumers | data | INST | INST-T280 Compile instrument utility loads | Excel / Word | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | instrument air consumers and consumption | manual | 3 | FEL2, FEL3, DD, COM
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | instrument cable routes and junction box locations for underground crossings | file | 3 | DD, CON
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | instrument and JB locations needing conduit stub-ups | manual | 3 | DD
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | instrument and JB location plans | review | 2 | DD
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | instrument objects and locations (S3D via Navisworks) | integrated | 4 | DD, CON
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | instrument tray routing and JB locations | integrated | 3 | FEL3, DD
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | instrument and JB locations | integrated | 3 | FEL3, DD
INST-I290 | Instrument location plans | drawing | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | PIPE | PIPE-T290 Detect and resolve clashes | S3D | instrument locations and tray routing | integrated | 3 | DD
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | junction box locations and sizes in the model | integrated | 2 | FEL3, DD
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | junction box objects with tags (S3D via Navisworks) | integrated | 4 | DD, CON
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | JB tags and sizes | manual | 3 | DD
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | INST | INST-T340 Prepare instrument bulk MTO | Excel / Word | cable lengths by type; JB list | file | 3 | DD, CON
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | instrument, cable and JB tags | file | 4 | CON, COM
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | JB coordinates and sizes | integrated | 3 | FEL3, DD
INST-I291 | Junction box locations and sizes | data | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | PIPE | PIPE-T290 Detect and resolve clashes | S3D | JB positions and sizes | integrated | 3 | DD
INST-I292 | 3D model review comments for I&C | document | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | instrument access and valve orientation comments | meeting | 3 | FEL3, DD
INST-I300 | Hook-up drawings and tag assignments | drawing | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | hook-up typicals and bills of material | review | 2 | DD
INST-I300 | Hook-up drawings and tag assignments | drawing | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | hook-ups and tag assignments | manual | 4 | CON
INST-I300 | Hook-up drawings and tag assignments | drawing | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | hook-up details per tag | review | 4 | CON
INST-I300 | Hook-up drawings and tag assignments | drawing | INST | INST-T300 Prepare hook-up drawings and assign typicals | Excel / Word | INST | INST-T340 Prepare instrument bulk MTO | Excel / Word | hook-up bills of material and tag assignments | manual | 3 | DD, CON
INST-I310 | Wiring, marshalling and termination diagrams | drawing | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | termination diagrams | manual | 4 | CON
INST-I310 | Wiring, marshalling and termination diagrams | drawing | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | cable allocation from wiring diagrams | integrated | 3 | DD
INST-I310 | Wiring, marshalling and termination diagrams | drawing | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | INST | INST-T330 Generate loop diagrams | SI | terminations | integrated | 3 | DD, CON
INST-I320 | Instrument cable schedule | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | instrument cable from/to and lengths | manual | 4 | CON
INST-I320 | Instrument cable schedule | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | INST | INST-T330 Generate loop diagrams | SI | cable tags | integrated | 3 | DD, CON
INST-I320 | Instrument cable schedule | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | INST | INST-T340 Prepare instrument bulk MTO | Excel / Word | cable lengths by type; JB list | file | 3 | DD, CON
INST-I320 | Instrument cable schedule | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | instrument, cable and JB tags | file | 4 | CON, COM
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | instrument tray segments, cable weight and segregation on rack | meeting | 1 | FEL2, FEL3
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | instrument cable weight per tray segment | manual | 3 | FEL3, DD
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | instrument cables sharing trays: count, diameter, segregation | review | 3 | DD, CON
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | instrument tray loading and segregation | integrated | 3 | FEL3, DD
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | FIRE | FIRE-T200 Define fire scenario envelopes and fireproofing zones | Excel / Word | instrument cable routes | manual | 3 | FEL3, DD
INST-I321 | Instrument cable routing and tray loading requirements | data | INST | INST-T320 Prepare instrument cable schedule and tray loading | Excel / Word | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | instrument cable count and tray loading per segment | meeting | 2 | FEL2, FEL3, DD
INST-I330 | Loop diagrams | drawing | INST | INST-T330 Generate loop diagrams | SI | COMM | COMM-T170 Execute loop checks | Smart Completions | loop terminals, ranges, set points | manual | 4 | CON, COM
INST-I330 | Loop diagrams | drawing | INST | INST-T330 Generate loop diagrams | SI | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | loop diagrams | manual | 4 | CON
INST-I330 | Loop diagrams | drawing | INST | INST-T330 Generate loop diagrams | SI | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | IFC loop diagrams | review | 4 | CON, COM
INST-I330 | Loop diagrams | drawing | INST | INST-T330 Generate loop diagrams | SI | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | loop diagrams: number, revision, issue purpose | integrated | 2 | FEL2, FEL3, DD, CON, COM
INST-I340 | Instrument bulk MTO | data | INST | INST-T340 Prepare instrument bulk MTO | Excel / Word | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | instrument bulk MR lines (tubing, fittings, cable, supports) | manual | 3 | FEL3, DD
INST-I350 | Telecom system design | document | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | telecom scope for CWPs | review | 4 | FEL3, DD
INST-I350 | Telecom system design | document | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | telecom and CCTV power loads | manual | 3 | FEL3, DD, CON
INST-I351 | Telecom device list, locations and power | data | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | telecom device power and UPS load | manual | 2 | FEL3, DD, CON
INST-I380 | System configuration database | data | INST | INST-T380 Prepare system configuration data for vendors | SI | COMM | COMM-T170 Execute loop checks | Smart Completions | ranges, units, alarm limits as configured | manual | 4 | CON, COM
INST-I380 | System configuration database | data | INST | INST-T380 Prepare system configuration data for vendors | SI | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | ranges, units, alarm limits, I/O assignment for configuration | file | 4 | DD, CON
INST-I390 | FAT report and punch list | document | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | COMM | COMM-T170 Execute loop checks | Smart Completions | FAT punch closed and configuration released | review | 4 | CON, COM
INST-I400 | I&C RFI responses and field changes | document | INST | INST-T400 Answer construction RFIs and issue I&C field changes | Procore | COMM | COMM-T210 Raise commissioning technical queries | Procore | I&C RFI responses | manual | 4 | COM
INST-I400 | I&C RFI responses and field changes | document | INST | INST-T400 Answer construction RFIs and issue I&C field changes | Procore | CONS | CONS-T170 Raise and manage RFIs | Procore | I&C answers and revised hook-up/termination details | manual | 4 | CON
INST-I410 | Instrument tag register for completions | data | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | instrument, cable, JB and loop tag types and ITR form types | manual | 3 | DD
INST-I410 | Instrument tag register for completions | data | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | instrument, cable, JB and loop tags with type and system | file | 4 | DD, CON
INST-I420 | I&C punch and loop check resolutions | document | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | COMM | COMM-T210 Raise commissioning technical queries | Procore | loop check and set point corrections | manual | 4 | COM
INST-I420 | I&C punch and loop check resolutions | document | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | range/set point corrections | manual | 4 | COM
INST-I430 | SAT and SIS validation records and as-configured database | document | INST | INST-T430 Support SAT, SIS validation and integrated testing | DCS / SIS config | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | SIS validation and SAT records | review | 4 | COM
INST-I440 | As-built I&C database and drawings | data | INST | INST-T440 Prepare as-built I&C database and drawings | SI | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | as-built instrument index | file | 4 | COM
INST-I440 | As-built I&C database and drawings | data | INST | INST-T440 Prepare as-built I&C database and drawings | SI | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | as-built I&C database and drawings | review | 4 | COM
INST-I440 | As-built I&C database and drawings | data | INST | INST-T440 Prepare as-built I&C database and drawings | SI | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | as-built detector and F&G locations | review | 4 | COM
INST-I450 | Electrical communication FAT setup | document | INST | INST-T390 Review configuration and witness system FAT | Excel / Word | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | DCS/ECMS emulator or test rig and communication map for integrated switchgear/MCC communication FAT | meeting | 3 | DD, CON
INST-I901 | Instrumentation deliverables list | data | INST | INST-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | Instrumentation deliverables list: index, datasheets, loops, C&E, layouts with planned dates | manual | 2 | FEL2, FEL3, DD, CON
INST-I902 | Instrumentation progress measurement | data | INST | INST-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Instrumentation progress: datasheet and loop diagram completion counts | manual | 2 | FEL3, DD
INST-I903 | Instrumentation holds | data | INST | INST-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | Instrumentation hold list: loops and datasheets on hold awaiting vendor data | manual | 2 | DD, CON
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | demand and diversity factors, power factor, voltage thresholds | review | 1 | FEL1, FEL2
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | protection and metering philosophy | review | 2 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | ambient, enclosure, standards and design basis | review | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T140 Specify power transformers | Excel / Word | ambient, enclosure, standards and design basis | review | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | ambient, enclosure, standards and design basis | review | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | ambient, enclosure, standards and design basis | review | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | ambient, enclosure, standards and design basis | review | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | voltage levels and power supply for electric fire pump drivers | manual | 2 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | enclosure and codes basis; area classification method (Class/Division or Zone), gas group and T-code by area for Ex protection concept | review | 2 | FEL2, FEL3
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T040 Define rotating equipment sparing and driver selection | Excel / Word | system voltages, motor voltage by kW range, VFD policy | meeting | 2 | FEL2, FEL3
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | motor voltage by kW range | manual | 3 | FEL3, DD
ELEC-I010 | Electrical design basis and philosophy | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | VEND | VEND-T080 Prepare package electrical data | Excel / Word | system voltages and frequency | manual | 3 | DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | motor electrical requirements for compliance check | review | 3 | DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | motor voltage by size, enclosure, efficiency and electrical requirements for driven equipment | manual | 3 | FEL3, DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T160 Prepare package specifications and scope split | Excel / Word | power supply voltages and electrical requirements for vendor panels and motors | review | 3 | FEL3, DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T240 Prepare mechanical technical specifications | Excel / Word | electrical requirements section for driven-equipment specifications | review | 3 | FEL3, DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | motor and electrical requirements for vendor scope | manual | 3 | FEL3, DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | motor and package electrical requirements | manual | 3 | FEL3, DD
ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | document | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Document Locator | VEND | VEND-T080 Prepare package electrical data | Excel / Word | motor specification requirements | manual | 3 | DD
ELEC-I020 | Preliminary power demand estimate | data | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | peak MW/MVA, growth margin, largest motor size | manual | 1 | FEL1, FEL2, FEL3, DD
ELEC-I020 | Preliminary power demand estimate | data | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | demand by area for substation count and transformer sizing | manual | 1 | FEL2, FEL3
ELEC-I020 | Preliminary power demand estimate | data | ELEC | ELEC-T020 Prepare preliminary electrical load estimate | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | connected/peak demand, largest motor | manual | 1 | FEL2
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | service voltage, available fault MVA and X/R, utility-owned equipment boundary | review | 2 | FEL2, FEL3
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | utility fault levels and X/R | file | 2 | FEL3, DD
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | point of interconnection, metering and utility protection requirements | manual | 3 | FEL3, DD
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | utility fault MVA, X/R and voltage range | manual | 3 | FEL3, DD
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T240 Run harmonic analysis | ETAP | utility IEEE 519 limits at point of interconnection | review | 3 | DD
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | utility protection settings at interconnect | manual | 4 | DD, COM
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | ELEC | ELEC-T380 Design temporary construction power | Excel / Word | utility backfeed date and service arrangements | review | 3 | DD, CON
ELEC-I030 | Utility interconnect requirements | decision | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Excel / Word | PROC | PROC-T090 Define utility and offsite basis | Excel / Word | point of interconnection, service voltage and available capacity | review | 2 | FEL2, FEL3
ELEC-I032 | Utility interconnection application and load forecast | document | ELEC | ELEC-T030 Coordinate utility interconnect and power supply | Document Locator | OWNR | OWNR-T080 Act as permit applicant | Excel / Word | utility interconnection application to sign and submit | review | 2 | FEL2, FEL3
ELEC-I040 | Preliminary key one-line diagram | drawing | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | number and rating of transformers, switchgear, generators and UPS | manual | 2 | FEL1, FEL2, FEL3
ELEC-I040 | Preliminary key one-line diagram | drawing | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | substation configuration and section count | manual | 2 | FEL2, FEL3, DD
ELEC-I040 | Preliminary key one-line diagram | drawing | ELEC | ELEC-T040 Develop configuration options and preliminary key one-line | Excel / Word | INST | INST-T030 Develop ICS architecture and control/rack room requirements | Excel / Word | UPS location and distribution feeding control system rooms | review | 2 | FEL2, FEL3, DD
ELEC-I050 | Electrical estimate quantities and pricing | data | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | cable, tray and conduit quantities by area | manual | 2 | FEL3, DD
ELEC-I050 | Electrical estimate quantities and pricing | data | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | cable, tray, conduit, grounding and lighting quantities | manual | 2 | FEL3, DD
ELEC-I050 | Electrical estimate quantities and pricing | data | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | major electrical equipment with budget prices and bulk quantities | manual | 1 | FEL2
ELEC-I050 | Electrical estimate quantities and pricing | data | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | cable by size, tray, conduit, grounding, lighting quantities and equipment prices | manual | 2 | FEL3
ELEC-I060 | Hazardous area release source list | data | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | Class/Division, group, T-code and extent per source | manual | 3 | FEL3, DD, CON
ELEC-I060 | Hazardous area release source list | data | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | PROC | PROC-T280 Prepare process input to environmental and safety studies | Excel / Word | release source list requiring fluid data | meeting | 2 | FEL2, FEL3, DD
ELEC-I060 | Hazardous area release source list | data | ELEC | ELEC-T060 Prepare hazardous area release source list | Excel / Word | SAFE | SAFE-T255 Review hazardous area classification | Excel / Word | release source list | review | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | CIVL | CIVL-T300 Design building HVAC | Excel / Word | classified area boundaries around buildings and air intakes | review | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | building location relative to classified areas, pressurization need | review | 3 | FEL2, FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | INST | INST-T110 Prepare instrument datasheets | SI | Class/Division or Zone, gas group, T-code at instrument location | manual | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | INST | INST-T200 Specify fire and gas system and device list | SI | Class/Division or Zone, gas group, T-code for detector Ex rating | manual | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | cable tray routes and levels; hazardous area boundaries for JB location | review | 3 | DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | SAFE | SAFE-T180 Perform fire and gas detector mapping | Excel / Word | area classification for detector Ex rating | review | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | SAFE | SAFE-T255 Review hazardous area classification | Excel / Word | HAC drawings | review | 3 | FEL3, DD
ELEC-I070 | Hazardous area classification drawings | drawing | ELEC | ELEC-T070 Prepare hazardous area classification drawings | S3D | SAFE | SAFE-T290 Compile process safety information for PSM | Document Locator | HAC drawings | review | 4 | DD, CON, COM
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | Class/Division, gas group and T-code for HVAC equipment | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | Class/Division, group and T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T140 Specify power transformers | Excel / Word | Class/Division, group and T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | Class/Division, group and T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | Class/Division, group and T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | Class/Division, group and T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | Class/Division and T-code for fixture certification | review | 3 | DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | T-code limit on sheath temperature | review | 3 | DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | INST | INST-T040 Write I&C design basis and general instrument specifications | Excel / Word | enclosure and codes basis; area classification method (Class/Division or Zone), gas group and T-code by area for Ex protection concept | review | 2 | FEL2, FEL3
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | INST | INST-T110 Prepare instrument datasheets | SI | Class/Division or Zone, gas group, T-code at instrument location | manual | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | INST | INST-T200 Specify fire and gas system and device list | SI | Class/Division or Zone, gas group, T-code for detector Ex rating | manual | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | INST | INST-T350 Design telecom, CCTV and security systems | Excel / Word | area classification for telecom device Ex rating | manual | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | Class/Division or Zone, gas group, T-code at equipment location | review | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | area classification, gas group, T-code per tag | manual | 3 | FEL3, DD
ELEC-I072 | Equipment certification requirements by area | data | ELEC | ELEC-T070 Prepare hazardous area classification drawings | Excel / Word | VEND | VEND-T080 Prepare package electrical data | Excel / Word | area classification per tag | manual | 3 | DD
ELEC-I080 | Substation and electrical building requirements to civil | document | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | substation footprint, equipment arrangement, cable vault, clearances, doors, transformer pads | manual | 2 | FEL2, FEL3, DD
ELEC-I080 | Substation and electrical building requirements to civil | document | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | floor loads and equipment weights, blast rating | manual | 3 | FEL3, DD
ELEC-I080 | Substation and electrical building requirements to civil | document | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | cable entry and cable vault locations | review | 3 | FEL3, DD
ELEC-I080 | Substation and electrical building requirements to civil | document | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | PIPE | PIPE-T040 Develop plot plan and equipment layout | S3D | substation and electrical building footprint and clearances | meeting | 1 | FEL2, FEL3, DD
ELEC-I082 | Electrical building HVAC and pressurization requirements | data | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | CIVL | CIVL-T300 Design building HVAC | Excel / Word | heat dissipation per room, battery room ventilation, pressurisation needs | manual | 3 | FEL3, DD
ELEC-I082 | Electrical building HVAC and pressurization requirements | data | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | room heat loads and HVAC/pressurization requirements | review | 3 | FEL3, DD
ELEC-I084 | Prefabricated E-house scope definition | decision | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | stick-built vs E-house decision | manual | 2 | FEL2, FEL3, DD
ELEC-I084 | Prefabricated E-house scope definition | decision | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | E-house scope, modules and shipping splits | review | 3 | FEL3, DD
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | number and size of motors and loads by voltage | manual | 2 | FEL1, FEL2, FEL3
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | running/peak kVA per bus, essential/UPS loads | integrated | 3 | FEL3, DD
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | loads with bus/MCC assignment and starter type | integrated | 3 | FEL3, DD
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | loads, ratings and bus assignments exported from SPEL | file | 3 | FEL3, DD
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | loads, ratings, voltage | integrated | 3 | DD, CON
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | starter types per load | integrated | 3 | DD
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | equipment tags | file | 4 | DD, CON, COM
ELEC-I090 | Electrical load list | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | motor loads per tag | review | 3 | FEL2, FEL3, DD, COM
ELEC-I092 | Plant power demand summary to process and owner | data | ELEC | ELEC-T090 Develop electrical load list in SPEL | Excel / Word | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | total electrical demand and kWh/yr | review | 3 | FEL2, FEL3, DD, COM
ELEC-I100 | Electrical P&ID review comments | document | ELEC | ELEC-T100 Review P&IDs and assign electrical attributes | Document Locator | PROC | PROC-T200 Develop P&IDs (process content) | SPID | electrical comments on P&IDs (motor tags, heat tracing, interlocks) | review | 2 | FEL2, FEL3
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | equipment ratings for pricing | manual | 2 | FEL1, FEL2, FEL3
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | transformer MVA, MCC bucket counts, UPS/battery sizes | manual | 2 | FEL2, FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | transformer, switchgear, MCC, generator and UPS ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T140 Specify power transformers | Excel / Word | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | equipment ratings | manual | 3 | FEL3, DD
ELEC-I110 | Electrical equipment ratings | data | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | transformer, switchgear, MCC, generator and UPS ratings | manual | 2 | FEL2, FEL3
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | switchboard and feeder IDs | file | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | one-line configuration, feeders, protection and metering | manual | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T140 Specify power transformers | Excel / Word | one-line configuration, feeders, protection and metering | manual | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | one-line configuration, feeders, protection and metering | manual | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | one-line configuration, feeders, protection and metering | manual | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | one-line configuration, feeders, protection and metering | manual | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | network topology from one-lines | file | 3 | FEL3, DD
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | from/to feeders and protective devices | integrated | 3 | DD, CON
ELEC-I120 | Single-line diagrams | drawing | ELEC | ELEC-T120 Develop one-line diagrams in SPEL | SPEL | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | one-lines for boundary marking | file | 4 | DD, CON, COM
ELEC-I130 | MV switchgear requisition package | document | ELEC | ELEC-T130 Specify MV switchgear | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | MV switchgear requirements | review | 3 | FEL3, DD
ELEC-I130 | MV switchgear requisition package | document | ELEC | ELEC-T130 Specify MV switchgear | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | MV switchgear MR scope and datasheets | manual | 3 | FEL3, DD
ELEC-I140 | Power transformer requisition package | document | ELEC | ELEC-T140 Specify power transformers | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | transformer requirements | review | 3 | FEL3, DD
ELEC-I140 | Power transformer requisition package | document | ELEC | ELEC-T140 Specify power transformers | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | power transformer MR scope and datasheets | manual | 3 | FEL3, DD
ELEC-I150 | LV switchgear, MCC and E-house requisition package | document | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | LV switchgear/MCC/E-house requirements | review | 3 | FEL3, DD
ELEC-I150 | LV switchgear, MCC and E-house requisition package | document | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | LV switchgear/MCC/E-house MR scope | manual | 3 | FEL3, DD
ELEC-I160 | VFD requisition package | document | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | VFD requirements | review | 3 | FEL3, DD
ELEC-I160 | VFD requisition package | document | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | VFD MR scope | manual | 3 | FEL3, DD
ELEC-I170 | UPS, DC and generator requisition package | document | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | UPS/DC/generator requirements | review | 3 | FEL3, DD
ELEC-I170 | UPS, DC and generator requisition package | document | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Document Locator | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | UPS, DC and generator MR scope | manual | 3 | FEL3, DD
ELEC-I180 | Electrical technical bid evaluations | document | ELEC | ELEC-T180 Evaluate electrical bids technically | Document Locator | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | clarifications for electrical packages | manual | 3 | FEL3, DD
ELEC-I180 | Electrical technical bid evaluations | document | ELEC | ELEC-T180 Evaluate electrical bids technically | Document Locator | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | recommended vendor and technical conditions for electrical packages | review | 3 | FEL3, DD
ELEC-I190 | Electrical vendor document comments | document | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | comments on vendor electrical drawings | review | 2 | DD, CON
ELEC-I190 | Electrical vendor document comments | document | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | electrical coded returns | review | 2 | DD, CON
ELEC-I192 | Certified electrical equipment data | data | ELEC | ELEC-T190 Review electrical vendor drawings and data | SPEL | CIVL | CIVL-T280 Design blast-resistant and other buildings structurally | Excel / Word | certified switchgear and transformer weights | manual | 3 | FEL3, DD
ELEC-I192 | Certified electrical equipment data | data | ELEC | ELEC-T190 Review electrical vendor drawings and data | SPEL | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | certified transformer %Z, X/R, losses and tap ranges | manual | 3 | FEL3, DD
ELEC-I192 | Certified electrical equipment data | data | ELEC | ELEC-T190 Review electrical vendor drawings and data | SPEL | ELEC | ELEC-T220 Run short-circuit study | ETAP | certified equipment impedances | integrated | 3 | FEL3, DD
ELEC-I192 | Certified electrical equipment data | data | ELEC | ELEC-T190 Review electrical vendor drawings and data | SPEL | ELEC | ELEC-T260 Perform arc flash study | ETAP | enclosure type, gaps, electrode configuration | manual | 4 | DD, COM
ELEC-I192 | Certified electrical equipment data | data | ELEC | ELEC-T190 Review electrical vendor drawings and data | SPEL | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | certified equipment dimensions | review | 3 | DD
ELEC-I200 | Motor data review comments | document | ELEC | ELEC-T200 Review motor and package electrical data | Document Locator | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | comments on vendor motor voltage, enclosure, starting and VFD compatibility | review | 3 | FEL3, DD
ELEC-I200 | Motor data review comments | document | ELEC | ELEC-T200 Review motor and package electrical data | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | motor data review comments | review | 2 | DD, CON
ELEC-I200 | Motor data review comments | document | ELEC | ELEC-T200 Review motor and package electrical data | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | motor data comments | review | 2 | DD, CON
ELEC-I202 | Certified motor data | data | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | ELEC | ELEC-T220 Run short-circuit study | ETAP | motor kW, LRC and X/R for motor contribution | manual | 3 | FEL3, DD
ELEC-I202 | Certified motor data | data | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | ELEC | ELEC-T230 Run motor-starting study | ETAP | LRC, inertia, speed-torque curves | manual | 3 | FEL3, DD
ELEC-I202 | Certified motor data | data | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | FLA, LRC, accelerating time, thermal limit curves | manual | 4 | DD, COM
ELEC-I210 | Load flow study results | document | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | preliminary bus loading and voltage drop | file | 2 | FEL3, DD
ELEC-I210 | Load flow study results | document | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | ELEC | ELEC-T220 Run short-circuit study | ETAP | ETAP network model and operating cases | integrated | 3 | FEL3, DD
ELEC-I210 | Load flow study results | document | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | ELEC | ELEC-T230 Run motor-starting study | ETAP | ETAP network model | integrated | 3 | FEL3, DD
ELEC-I210 | Load flow study results | document | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | ELEC | ELEC-T240 Run harmonic analysis | ETAP | ETAP model and load flow cases | integrated | 3 | DD
ELEC-I210 | Load flow study results | document | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | ETAP network model | integrated | 3 | DD, COM
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T110 Size major electrical equipment | Excel / Word | preliminary short-circuit duties | file | 2 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T130 Specify MV switchgear | Excel / Word | short-circuit interrupting and withstand duties at the bus | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T140 Specify power transformers | Excel / Word | short-circuit interrupting and withstand duties at the bus | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T150 Specify LV switchgear, MCCs and E-houses | Excel / Word | short-circuit interrupting and withstand duties at the bus | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T160 Specify VFDs and harmonic mitigation | Excel / Word | short-circuit interrupting and withstand duties at the bus | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T170 Specify UPS, DC systems and emergency generator | Excel / Word | short-circuit interrupting and withstand duties at the bus | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | fault currents per bus | integrated | 3 | DD, COM
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T260 Perform arc flash study | ETAP | bolted fault currents per bus | integrated | 4 | DD, COM
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T270 Design grounding system | Excel / Word | SLG fault current and clearing times | manual | 3 | FEL3, DD
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | short-circuit duties and clearing times for withstand check | manual | 3 | DD, CON
ELEC-I220 | Short-circuit study results | document | ELEC | ELEC-T220 Run short-circuit study | ETAP | VEND | VEND-T080 Prepare package electrical data | Excel / Word | fault level at the supply bus | manual | 3 | DD
ELEC-I230 | Motor-starting study results | document | ELEC | ELEC-T230 Run motor-starting study | ETAP | MECH | MECH-T150 Prepare rotating equipment datasheets | Excel / Word | starting method and voltage dip limits for driver selection | manual | 3 | FEL3, DD
ELEC-I232 | Motor starting method requirements | decision | ELEC | ELEC-T230 Run motor-starting study | Excel / Word | MECH | MECH-T230 Issue motor and driver electrical data | Excel / Word | maximum DOL motor size per bus, motors needing soft starter/VFD | manual | 3 | FEL3, DD
ELEC-I240 | Harmonic study results and filter requirements | document | ELEC | ELEC-T240 Run harmonic analysis | ETAP | VEND | VEND-T080 Prepare package electrical data | Excel / Word | harmonic limits and filter requirements for package VFDs | manual | 3 | DD
ELEC-I250 | Protective device coordination study | document | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | ELEC | ELEC-T260 Perform arc flash study | ETAP | protective device clearing times and settings | integrated | 4 | DD, COM
ELEC-I252 | Relay and breaker setting files | data | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | relay settings to test | review | 4 | DD, CON
ELEC-I252 | Relay and breaker setting files | data | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | COMM | COMM-T190 Energise electrical systems | Smart Completions | relay and trip unit settings | manual | 4 | CON, COM
ELEC-I252 | Relay and breaker setting files | data | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | relay setting files | file | 4 | COM
ELEC-I252 | Relay and breaker setting files | data | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | ELEC | ELEC-T440 Produce as-built electrical records | SPEL | as-left relay settings recorded against setting files | manual | 4 | CON, COM
ELEC-I260 | Arc flash study and labels | document | ELEC | ELEC-T260 Perform arc flash study | ETAP | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | arc flash label data | file | 4 | COM
ELEC-I270 | Ground grid study | document | ELEC | ELEC-T270 Design grounding system | Excel / Word | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | ground grid routing and grounding connections at foundations | manual | 3 | DD
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | ground grid routing and ground wells | file | 3 | DD, CON
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | grounding embeds and pigtails in foundations | manual | 3 | DD
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | ELEC | ELEC-T280 Design lightning protection | Excel / Word | ground grid for down-conductor connection | review | 3 | DD
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | ground grid layout for interference and isolation | review | 3 | DD, CON
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | grounding materials | manual | 3 | DD, CON
ELEC-I272 | Grounding layouts and details | drawing | ELEC | ELEC-T270 Design grounding system | Excel / Word | PIPE | PIPE-T270 Design underground piping | S3D | ground grid routing | manual | 3 | DD
ELEC-I280 | Lightning protection design | drawing | ELEC | ELEC-T280 Design lightning protection | Excel / Word | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | lightning protection on buildings and structures | manual | 3 | DD
ELEC-I290 | Lighting and small power layouts | drawing | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | CIVL | CIVL-T290 Prepare architectural drawings | Excel / Word | fixture and receptacle locations in buildings | review | 3 | DD
ELEC-I290 | Lighting and small power layouts | drawing | ELEC | ELEC-T290 Design lighting and small power | Excel / Word | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | lighting fixtures and panels | manual | 3 | DD, CON
ELEC-I292 | Lighting panel schedules and loads | data | ELEC | ELEC-T290 Design lighting and small power | SPEL | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | lighting panel loads | manual | 3 | FEL3, DD, CON
ELEC-I300 | Heat tracing circuit list and loads | data | ELEC | ELEC-T300 Design electric heat tracing | SPEL | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | heat tracing panel loads | manual | 3 | FEL3, DD, CON
ELEC-I302 | Heat tracing isometrics and requirements to piping | drawing | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | heat tracing materials | manual | 3 | DD, CON
ELEC-I304 | Heat tracing control and alarm interface to I&C | data | ELEC | ELEC-T300 Design electric heat tracing | Excel / Word | INST | INST-T260 Develop I/O list and assign I/O | SI | heat tracing panel alarms and signals to the DCS | manual | 3 | FEL3, DD
ELEC-I310 | Cathodic protection design | drawing | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | anode bed, test station and CP cable routing locations | manual | 3 | DD, CON
ELEC-I310 | Cathodic protection design | drawing | ELEC | ELEC-T310 Design cathodic protection | Excel / Word | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | CP materials | manual | 3 | DD, CON
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | cable from/to | file | 4 | DD, CON
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | cables, from/to, route segments, length | manual | 4 | CON
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | cable from/to and type | review | 4 | CON
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | ELEC | ELEC-T210 Build ETAP model and run load flow study | ETAP | cable sizes and lengths for impedances | file | 3 | FEL3, DD
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | cable types and lengths | file | 3 | DD, CON
ELEC-I320 | Cable schedule | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | cable tags | file | 4 | DD, CON, COM
ELEC-I322 | Cable pull cards and terminations | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | pull cards and terminations | manual | 4 | CON
ELEC-I322 | Cable pull cards and terminations | data | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | termination details | review | 4 | CON
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | CIVL | CIVL-T080 Size pipe racks and process structures conceptually | Excel / Word | cable tray widths and rack levels reserved | meeting | 1 | FEL2, FEL3
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | tray and conduit routes, sizes and elevations in the model | integrated | 2 | FEL3, DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | tray and conduit objects with tags (S3D via Navisworks) | integrated | 4 | DD, CON
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | ELEC | ELEC-T320 Size cables and build cable schedule in SPEL | SPEL | route lengths per raceway segment | manual | 3 | DD, CON
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | tray model | review | 3 | DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | tray, fittings and support quantities | file | 3 | DD, CON
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | INST | INST-T290 Prepare instrument location plans and JB locations | S3D | cable tray routes and levels; hazardous area boundaries for JB location | review | 3 | DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | INST | INST-T320 Prepare instrument cable schedule and tray loading | SI | tray and trench route segments and segregation | manual | 3 | DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | PIPE | PIPE-T060 Lay out pipe racks and assign tiers | S3D | electrical tray widths and rack levels reserved | meeting | 2 | FEL2, FEL3, DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | PIPE | PIPE-T160 Route piping in the 3D model | S3D | tray and conduit routes, elevations and reserved rack levels | integrated | 2 | FEL3, DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | electrical tray and equipment in model | integrated | 3 | FEL3, DD
ELEC-I330 | Cable tray routing model | model | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | PIPE | PIPE-T290 Detect and resolve clashes | S3D | tray and conduit routes | integrated | 3 | DD
ELEC-I332 | Cable tray support loads to civil/structural | data | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | Excel / Word | CIVL | CIVL-T200 Analyse and design pipe racks | Excel / Word | tray loads per rack level (kg/m) and support locations | manual | 3 | FEL3, DD
ELEC-I332 | Cable tray support loads to civil/structural | data | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | tray loads on structures | manual | 3 | FEL3, DD
ELEC-I334 | Underground duct bank and trench layout | drawing | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | CIVL | CIVL-T140 Coordinate underground services and prepare composite | Excel / Word | duct bank routes, sections, manholes and depths | file | 3 | DD, CON
ELEC-I334 | Underground duct bank and trench layout | drawing | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | duct bank routes and crossings | review | 2 | DD
ELEC-I334 | Underground duct bank and trench layout | drawing | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | PIPE | PIPE-T270 Design underground piping | S3D | duct bank routes, depths and crossings | file | 3 | DD
ELEC-I340 | MCC and switchgear interface signal list | data | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | interface signals per motor and breaker | integrated | 3 | DD
ELEC-I340 | MCC and switchgear interface signal list | data | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | INST | INST-T240 Prepare cause and effect charts | Excel / Word | motor trip/SIS trip signals and MCC interlock schematics | review | 3 | FEL3, DD
ELEC-I340 | MCC and switchgear interface signal list | data | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | INST | INST-T260 Develop I/O list and assign I/O | SI | per motor: run/trip/start/stop/SIS trip signals, hardwired vs serial (SPEL not linked: keyed in by hand) | manual | 3 | FEL3, DD
ELEC-I340 | MCC and switchgear interface signal list | data | ELEC | ELEC-T340 Define MCC and switchgear interface signals with I&C | SPEL | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | MCC interposing relay terminals and signal list (SPEL not linked) | manual | 3 | DD
ELEC-I350 | Control and interlock schematics | drawing | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | INST | INST-T240 Prepare cause and effect charts | Excel / Word | motor trip/SIS trip signals and MCC interlock schematics | review | 3 | FEL3, DD
ELEC-I350 | Control and interlock schematics | drawing | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | MCC interposing relay terminals and signal list (SPEL not linked) | manual | 3 | DD
ELEC-I360 | Electrical layouts and power plans | drawing | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | conduit drops and cable trench locations | manual | 3 | DD
ELEC-I360 | Electrical layouts and power plans | drawing | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CIVL | CIVL-T270 Develop building space programme and layouts | Excel / Word | substation room layouts | manual | 2 | FEL2, FEL3, DD
ELEC-I360 | Electrical layouts and power plans | drawing | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | power plans with tray and conduit drops | review | 2 | DD
ELEC-I360 | Electrical layouts and power plans | drawing | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | power plans and tray/conduit drops | manual | 4 | CON
ELEC-I360 | Electrical layouts and power plans | drawing | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | ELEC | ELEC-T330 Route raceway, cable tray and duct banks in S3D | S3D | substation and equipment locations | review | 3 | FEL3, DD
ELEC-I362 | Electrical equipment foundation and embed requirements | data | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CIVL | CIVL-T210 Analyse and design process structures and platforms | Excel / Word | electrical equipment weights and anchorage on structures | manual | 3 | FEL3, DD
ELEC-I362 | Electrical equipment foundation and embed requirements | data | ELEC | ELEC-T360 Prepare electrical layouts and installation details | Excel / Word | CIVL | CIVL-T250 Coordinate embedments, sleeves and penetrations | Excel / Word | conduit stub-ups and embeds for transformers, switchgear and E-houses | manual | 3 | DD
ELEC-I370 | Electrical bulk MTO | data | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Purchasing DB | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | electrical bulk MR lines (cable, tray, fittings) | manual | 3 | FEL3, DD
ELEC-I380 | Temporary construction power design | drawing | ELEC | ELEC-T380 Design temporary construction power | Excel / Word | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | temporary construction power layout and demand | manual | 3 | FEL2, FEL3, DD
ELEC-I390 | IFC electrical deliverable package | document | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | PROJ | PROJ-T200 Issue documents by transmittal | Document Locator | IFC electrical package: documents and revisions | integrated | 2 | FEL2, FEL3, DD, CON, COM
ELEC-I390 | IFC electrical deliverable package | document | ELEC | ELEC-T390 Seal and issue electrical deliverables IFC | Document Locator | PROJ | PROJ-T230 Track IFC issue and PE seal status | Document Locator | sealed IFC electrical documents | review | 4 | DD, CON
ELEC-I400 | Electrical FAT reports and punch | document | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | open electrical FAT punch items carried to site | manual | 4 | CON, COM
ELEC-I400 | Electrical FAT reports and punch | document | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | FAT results for inspection release | review | 4 | DD, CON
ELEC-I410 | Electrical RFI responses and field changes | decision | ELEC | ELEC-T410 Answer RFIs and issue field changes | Procore | CONS | CONS-T170 Raise and manage RFIs | Procore | electrical answers and revised sketches | manual | 4 | CON
ELEC-I420 | Electrical energization sequence and system boundaries | decision | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | electrical systems/subsystems and energisation order | file | 3 | FEL3, DD
ELEC-I420 | Electrical energization sequence and system boundaries | decision | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | energisation order | review | 4 | DD, CON
ELEC-I420 | Electrical energization sequence and system boundaries | decision | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | COMM | COMM-T190 Energise electrical systems | Smart Completions | energisation sequence | manual | 4 | CON, COM
ELEC-I422 | Electrical tag and cable lists for completions | data | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | electrical equipment and cable types for ITRs | manual | 3 | DD
ELEC-I422 | Electrical tag and cable lists for completions | data | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | equipment, cable and circuit tags with system | file | 4 | DD, CON
ELEC-I430 | Energization readiness sign-off | decision | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | COMM | COMM-T170 Execute loop checks | Smart Completions | control system power and UPS energised | manual | 4 | CON, COM
ELEC-I430 | Energization readiness sign-off | decision | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | COMM | COMM-T190 Energise electrical systems | Smart Completions | engineering readiness to energise | manual | 4 | CON, COM
ELEC-I440 | As-built electrical records | document | ELEC | ELEC-T440 Produce as-built electrical records | Document Locator | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | as-built SPEL electrical equipment data | file | 4 | COM
ELEC-I440 | As-built electrical records | document | ELEC | ELEC-T440 Produce as-built electrical records | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | as-built electrical records | review | 4 | COM
ELEC-I450 | Electrical acceptable manufacturers | data | ELEC | ELEC-T010 Prepare electrical design basis and philosophy | Excel / Word | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | Electrical acceptable manufacturers per equipment type | review | 3 | FEL3, DD
ELEC-I901 | Electrical deliverables list | data | ELEC | ELEC-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T050 Compile and maintain the deliverables register | Document Locator | Electrical deliverables list: SLDs, studies, cable schedule, layouts with planned dates | manual | 2 | FEL2, FEL3, DD, CON
ELEC-I902 | Electrical progress measurement | data | ELEC | ELEC-T005 Plan, measure and report discipline deliverables | Excel / Word | PROJ | PROJ-T130 Measure engineering progress | P6 | Electrical progress: deliverable completion counts | manual | 2 | FEL3, DD
SCM-I010 | Procurement plan | document | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | bidders per MR, sourcing route and procurement package split | review | 3 | FEL3, DD
SCM-I010 | Procurement plan | document | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | procurement packages, sourcing route and RFQ dates | review | 3 | FEL3, DD
SCM-I010 | Procurement plan | document | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | RFQ, bid, award, vendor data and delivery durations and ROS per MR | manual | 3 | FEL2, FEL3, DD
SCM-I020 | Long-lead items list | data | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | lead time, ROS and commitment date of long-lead items; market lead-time feedback | meeting | 2 | FEL2, FEL3
SCM-I020 | Long-lead items list | data | SCM | SCM-T010 Prepare the procurement plan and long-lead list | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | long-lead items and commitment dates | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | approved bidders per MR | manual | 3 | FEL3, DD
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | FIRE | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | bidders for fire protection equipment | manual | 3 | FEL3, DD
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | INST | INST-T130 Prepare instrument material requisitions | Purchasing DB | bidders per MR, sourcing route and procurement package split | review | 3 | FEL3, DD
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | approved bidders per commodity for budget enquiries | review | 2 | FEL2, FEL3
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | MECH | MECH-T250 Prepare requisition technical packages for bid | Excel / Word | bidders list per requisition | review | 3 | FEL3, DD
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | PIPE | PIPE-T240 Specify and requisition spring and engineered supports | Excel / Word | approved bidders for spring supports | manual | 3 | DD
SCM-I030 | Bidders list | data | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | bidders per MR | integrated | 3 | FEL2, FEL3, DD
SCM-I040 | Vendor prequalification record | document | SCM | SCM-T020 Prepare bidders lists and prequalify vendors | Purchasing DB | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | prequalified bidders for the RFQ distribution | manual | 2 | FEL2, FEL3, DD
SCM-I050 | MR register entry | data | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | PIPE | PIPE-T240 Specify and requisition spring and engineered supports | Excel / Word | MR number and need date | manual | 3 | DD
SCM-I050 | MR register entry | data | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | MRs issued and status | manual | 3 | FEL2, FEL3, DD, CON, COM
SCM-I050 | MR register entry | data | SCM | SCM-T030 Register material requisitions in the Purchasing DB | Purchasing DB | SCM | SCM-T050 Issue RFQ packages | Purchasing DB | MR number, revision, scope and need date | integrated | 3 | FEL2, FEL3, DD
SCM-I060 | Bulk material MR lines | data | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | commodity codes and bulk MR lines | manual | 3 | DD, CON
SCM-I060 | Bulk material MR lines | data | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | INST | INST-T340 Prepare instrument bulk MTO | Excel / Word | commodity codes and surplus allowances for bulk MR lines | review | 3 | DD, CON
SCM-I060 | Bulk material MR lines | data | SCM | SCM-T040 Load piping bulk MTO into the Purchasing DB | Purchasing DB | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | previous bulk MR lines with surplus | file | 3 | FEL3, DD
SCM-I070 | RFQ package | document | SCM | SCM-T050 Issue RFQ packages | Document Locator | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | commercial terms, instructions to bidders, VDRL | manual | 3 | FEL3, DD
SCM-I070 | RFQ package | document | SCM | SCM-T050 Issue RFQ packages | Document Locator | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | MR, commercial terms, instructions to bidders, VDRL, bid due date | manual | 3 | FEL3, DD
SCM-I080 | Bid bulletin | document | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | bid questions and answers issued | manual | 3 | FEL3, DD
SCM-I080 | Bid bulletin | document | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | unpriced technical offers with TBE due date; bid bulletins and MR changes | review | 3 | FEL3, DD
SCM-I080 | Bid bulletin | document | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | VEND | VEND-T030 Answer bid clarifications | Excel / Word | bid bulletins and commercial questions | manual | 3 | FEL3, DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | unpriced technical offers for evaluation | review | 3 | FEL3, DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | unpriced technical offers and TBE due date | review | 2 | FEL3, DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | unpriced technical offers with TBE due date; bid bulletins and MR changes | review | 3 | FEL3, DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | technical part of each bid and TBE due date | review | 3 | FEL3, DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | PIPE | PIPE-T350 Evaluate piping bids | Excel / Word | technical portions of bids | file | 3 | DD
SCM-I090 | Unpriced technical offers for TBE | document | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | unpriced technical offers | review | 3 | FEL3, DD
SCM-I100 | Commercial bid evaluation | document | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | MECH | MECH-T280 Prepare requisitions for purchase | Excel / Word | commercial ranking | review | 3 | FEL3, DD
SCM-I100 | Commercial bid evaluation | document | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | PROC | PROC-T070 Evaluate technology and licensor process offers | Excel / Word | normalised price, delivery and commercial ranking per licensor | review | 2 | FEL2
SCM-I100 | Commercial bid evaluation | document | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | normalised bid prices and delivery per package | manual | 3 | FEL3
SCM-I100 | Commercial bid evaluation | document | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | commercial ranking and normalised price | manual | 3 | FEL3, DD
SCM-I110 | Award recommendation | decision | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | MECH | MECH-T280 Prepare requisitions for purchase | Excel / Word | recommended vendor | review | 3 | FEL3, DD
SCM-I110 | Award recommendation | decision | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | recommended vendor and evaluated price | manual | 3 | FEL3
SCM-I110 | Award recommendation | decision | SCM | SCM-T090 Prepare the bid tabulation and award recommendation | Excel / Word | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | approved vendor, price and delivery | manual | 4 | FEL3, DD
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | COMM | COMM-T110 Define vendor commissioning support requirements | Excel / Word | PO scope for vendor site services | review | 4 | DD
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | MECH | MECH-T290 Hold vendor kick-off meetings | Excel / Word | PO scope, VDRL and delivery | review | 4 | DD
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | PO site service provisions and rates | review | 4 | CON, COM
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | VEND | VEND-T040 Issue the vendor document schedule | Document Locator | PO VDRL and document instructions | manual | 4 | DD
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | PO inspection requirements and delivery dates | manual | 4 | DD
SCM-I120 | Purchase order | document | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Document Locator | VEND | VEND-T150 Report manufacturing progress | Excel / Word | PO progress reporting requirements | manual | 4 | DD, CON
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | PO number, vendor, award date | manual | 3 | FEL2, FEL3, DD
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | MECH | MECH-T290 Hold vendor kick-off meetings | Excel / Word | PO number, vendor, buyer and expeditor | review | 4 | DD
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | OWNR | OWNR-T240 Pay invoices and report actual cost | Excel / Word | PO number, value and payment terms | manual | 4 | DD, CON
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PROJ | PROJ-T120 Integrate procurement and vendor dates into the schedule | P6 | PO number, vendor and award date | manual | 4 | FEL3, DD, CON
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | POs placed and values | manual | 3 | FEL2, FEL3, DD, CON, COM
SCM-I130 | PO header data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | SCM | SCM-T190 Pass PO data to Jovix for receiving | Jovix | PO number, vendor | integrated | 4 | DD, CON
SCM-I140 | PO line items | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | PO lines with tag/commodity and contract delivery date | file | 3 | DD
SCM-I140 | PO line items | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | MECH | MECH-T060 Maintain mechanical equipment list | Excel / Word | tag-to-PO line mapping | manual | 3 | FEL2, FEL3, DD
SCM-I140 | PO line items | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | previous PO line quantities by commodity code | file | 3 | FEL3, DD
SCM-I140 | PO line items | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PROJ | PROJ-T120 Integrate procurement and vendor dates into the schedule | P6 | contract delivery date per PO line | manual | 4 | FEL3, DD, CON
SCM-I140 | PO line items | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | SCM | SCM-T190 Pass PO data to Jovix for receiving | Jovix | PO lines, quantities, descriptions | integrated | 4 | DD, CON
SCM-I150 | PO amendment | document | SCM | SCM-T110 Process PO amendments | Purchasing DB | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | PO amendment price and delivery changes | manual | 3 | FEL3, DD, CON
SCM-I150 | PO amendment | document | SCM | SCM-T110 Process PO amendments | Purchasing DB | SCM | SCM-T190 Pass PO data to Jovix for receiving | Jovix | amended lines and quantities | integrated | 4 | DD, CON
SCM-I160 | VDRL tracking records | data | SCM | SCM-T120 Set up VDRL tracking | Purchasing DB | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | VDRL per PO: documents and due dates | review | 3 | DD, CON
SCM-I170 | Vendor print status report | data | SCM | SCM-T130 Expedite vendor documents and route them for review | Purchasing DB | INST | INST-T150 Review instrument vendor data | Document Locator | vendor document due/received dates and PO milestone status | review | 3 | DD, CON
SCM-I170 | Vendor print status report | data | SCM | SCM-T130 Expedite vendor documents and route them for review | Purchasing DB | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | SPIR submission status per PO | review | 3 | DD, CON
SCM-I170 | Vendor print status report | data | SCM | SCM-T130 Expedite vendor documents and route them for review | Purchasing DB | PROJ | PROJ-T120 Integrate procurement and vendor dates into the schedule | P6 | due, received and returned dates per vendor document | manual | 3 | FEL3, DD, CON
SCM-I170 | Vendor print status report | data | SCM | SCM-T130 Expedite vendor documents and route them for review | Purchasing DB | PROJ | PROJ-T220 Maintain the hold list | Excel / Word | overdue vendor documents and days late | manual | 3 | DD, CON
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | vendor documents routed for civil review with return date | review | 3 | DD, CON
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | vendor documents routed for review with return date | review | 3 | DD, CON
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | FIRE | FIRE-T240 Review fire protection vendor data | Document Locator | fire protection vendor documents for review | review | 3 | DD
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | INST | INST-T150 Review instrument vendor data | Document Locator | vendor drawings and data routed for review: dimensional drawings, sizing confirmation, wiring, certificates; certified data | review | 3 | DD, CON
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | PIPE | PIPE-T360 Review valve and specialty item vendor data | Document Locator | vendor documents routed for review with return date | review | 3 | DD, CON
SCM-I180 | Vendor documents routed for review | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | PROC | PROC-T310 Review vendor data against process duties | Document Locator | vendor documents routed for review with return date | review | 3 | DD
SCM-I190 | Review comments returned to vendor | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | VEND | VEND-T050 Prepare GA and outline drawings for review | Excel / Word | comments and review code on previous revision | integrated | 2 | DD
SCM-I190 | Review comments returned to vendor | document | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | consolidated comments and review code | integrated | 2 | DD, CON
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | CONS | CONS-T110 Develop construction schedule by CWP | P6 | forecast site delivery dates by PO line | manual | 3 | DD, CON
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | forecast ex-works and site delivery dates by PO line | file | 3 | DD
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | forecast site delivery for outstanding PO lines | manual | 3 | CON
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | INST | INST-T150 Review instrument vendor data | Document Locator | vendor document due/received dates and PO milestone status | review | 3 | DD, CON
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | PROJ | PROJ-T120 Integrate procurement and vendor dates into the schedule | P6 | forecast ex-works and site delivery dates per PO line, exceptions | manual | 3 | FEL3, DD, CON
SCM-I200 | Expediting forecast | data | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | expediting exceptions | manual | 3 | FEL2, FEL3, DD, CON, COM
SCM-I210 | Inspection assignment and agreed ITP | data | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | inspection level and witness points per PO | review | 3 | DD, CON
SCM-I210 | Inspection assignment and agreed ITP | data | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | MECH | MECH-T350 Review and approve inspection and test plans | Document Locator | inspection level and assigned inspector per PO | review | 3 | DD
SCM-I210 | Inspection assignment and agreed ITP | data | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | MECH | MECH-T360 Witness shop tests and factory acceptance tests | Excel / Word | assigned inspector and agreed witness points | meeting | 3 | DD
SCM-I210 | Inspection assignment and agreed ITP | data | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | agreed hold/witness points and inspector | manual | 4 | DD, CON
SCM-I220 | Inspection report | document | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | fabricator non-conformances from shop inspection | review | 4 | CON
SCM-I230 | Inspection release note | decision | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | release for shipment | review | 3 | DD, CON
SCM-I230 | Inspection release note | decision | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | OWNR | OWNR-T240 Pay invoices and report actual cost | Excel / Word | release for shipment as the payment milestone | review | 4 | DD, CON
SCM-I230 | Inspection release note | decision | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | SCM | SCM-T180 Manage shipping and traffic | Excel / Word | release for shipment per PO line | manual | 4 | DD, CON
SCM-I230 | Inspection release note | decision | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | release for shipment | manual | 4 | DD, CON
SCM-I240 | Logistics plan | document | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | transport routes, heavy-haul and oversize limits (max load dimensions and weights) | review | 2 | FEL2, FEL3
SCM-I240 | Logistics plan | document | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | MECH | MECH-T390 Define equipment preservation and storage requirements | Excel / Word | logistics and receipt plan | review | 3 | DD, CON
SCM-I240 | Logistics plan | document | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | logistics routes, heavy-haul and customs risks | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
SCM-I240 | Logistics plan | document | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | routing, envelope and transport constraints | manual | 3 | DD, CON
SCM-I250 | Shipping notice | document | SCM | SCM-T180 Manage shipping and traffic | Excel / Word | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | shipping pieces and expected arrival | manual | 4 | CON
SCM-I260 | Expected receipts in Jovix | data | SCM | SCM-T190 Pass PO data to Jovix for receiving | Jovix | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | expected PO lines and quantities | integrated | 4 | CON
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | CONS | CONS-T200 Request and receive materials from the warehouse | Jovix | received quantity, heat numbers and location by PO line | integrated | 4 | CON
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | CONS | CONS-T220 Track welds and NDE | Excel / Word | heat numbers and MTR reference per received item | manual | 4 | CON
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | CONS | CONS-T280 Compile construction quality dossier | Document Locator | receiving records with heat numbers and MTR references | manual | 4 | CON, COM
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Jovix | received quantities | file | 4 | CON
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | SCM | SCM-T210 Raise OS&D reports | Jovix | receipt discrepancies by PO line | integrated | 4 | CON
SCM-I270 | Material receipt record | data | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | SCM | SCM-T280 Close out purchase orders | Purchasing DB | final receipts per PO line | integrated | 4 | CON, COM
SCM-I280 | OS&D report | document | SCM | SCM-T210 Raise OS&D reports | Jovix | SCM | SCM-T280 Close out purchase orders | Purchasing DB | OS&D dispositions closed | integrated | 4 | CON, COM
SCM-I290 | Storage location and preservation records | data | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | storage location by item | integrated | 4 | CON
SCM-I290 | Storage location and preservation records | data | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | CONS | CONS-T200 Request and receive materials from the warehouse | Jovix | storage location and preservation status | integrated | 4 | CON
SCM-I290 | Storage location and preservation records | data | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | MECH | MECH-T390 Define equipment preservation and storage requirements | Excel / Word | site storage locations and preservation records | review | 3 | DD, CON
SCM-I300 | Material availability status | data | SCM | SCM-T230 Report material availability to AWP | Jovix | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | material availability by item code, spool and PO line fed to iConstruct | integrated | 3 | DD, CON
SCM-I300 | Material availability status | data | SCM | SCM-T230 Report material availability to AWP | Jovix | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | availability per IWP: received, reserved and issued quantity by item code and spool | integrated | 4 | CON
SCM-I300 | Material availability status | data | SCM | SCM-T230 Report material availability to AWP | Jovix | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | material availability per IWP | manual | 4 | CON, COM
SCM-I300 | Material availability status | data | SCM | SCM-T230 Report material availability to AWP | Jovix | PROJ | PROJ-T250 Load construction progress into P6 | P6 | material availability per IWP | file | 3 | CON, COM
SCM-I310 | Material issue record | data | SCM | SCM-T240 Issue materials to construction | Jovix | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Jovix | issued quantities | file | 4 | CON
SCM-I310 | Material issue record | data | SCM | SCM-T240 Issue materials to construction | Jovix | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | free-issue material issued with heat numbers | manual | 4 | DD, CON
SCM-I320 | Material shortage report | data | SCM | SCM-T230 Report material availability to AWP | Jovix | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | material shortages per IWP | manual | 4 | CON, COM
SCM-I330 | Material reconciliation and surplus report | document | SCM | SCM-T250 Reconcile materials and dispose of surplus | Jovix | ELEC | ELEC-T370 Prepare electrical MTO and bulk requisitions | Excel / Word | surplus and reconciliation by commodity | manual | 3 | DD, CON
SCM-I330 | Material reconciliation and surplus report | document | SCM | SCM-T250 Reconcile materials and dispose of surplus | Jovix | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Jovix | ordered vs received vs issued by commodity | file | 4 | CON
SCM-I340 | Vendor site service request | document | SCM | SCM-T260 Call off vendor site services | Purchasing DB | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | vendor site service requests and PO reference | review | 4 | CON, COM
SCM-I340 | Vendor site service request | document | SCM | SCM-T260 Call off vendor site services | Purchasing DB | VEND | VEND-T210 Provide site services | Excel / Word | service type, dates and location | manual | 4 | CON, COM
SCM-I350 | Spares purchase order and register | data | SCM | SCM-T270 Procure commissioning and operating spares | Purchasing DB | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | spares ordered and handed over | manual | 4 | COM
SCM-I360 | PO close-out record | data | SCM | SCM-T280 Close out purchase orders | Purchasing DB | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | PO close-out status | manual | 4 | COM
SCM-I370 | Committed cost data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PROJ | PROJ-T100 Prepare the control estimate and budget | Excel / Word | committed PO values by cost code and WBS | file | 4 | DD
SCM-I370 | Committed cost data | data | SCM | SCM-T100 Award the purchase order in the Purchasing DB | Purchasing DB | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | PO and amendment values by cost code and WBS | file | 4 | DD, CON, COM
VEND-I010 | Budget quotation | document | VEND | VEND-T010 Prepare budget quotations | Excel / Word | ELEC | ELEC-T050 Prepare electrical cost estimate inputs | Excel / Word | budget prices, weights and dimensions of major electrical equipment | manual | 2 | FEL1, FEL2, FEL3
VEND-I010 | Budget quotation | document | VEND | VEND-T010 Prepare budget quotations | Excel / Word | MECH | MECH-T050 Obtain budget quotations and equipment cost data | Excel / Word | budget price, delivery, weight and main dimensions | manual | 2 | FEL2, FEL3
VEND-I010 | Budget quotation | document | VEND | VEND-T010 Prepare budget quotations | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | budget price, delivery, scope, weight | manual | 1 | FEL2
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | compliance, datasheets, fabricator capacity and piling method | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | COMM | COMM-T250 Support performance test run | Excel / Word | equipment performance guarantees | review | 4 | COM
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | ELEC | ELEC-T080 Size substations and electrical buildings | Excel / Word | outline dimensions, weights and heat losses of switchgear, MCC, VFD, UPS | manual | 2 | FEL2, FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | compliance statement, completed datasheets, outline drawings | review | 2 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | completed datasheets, model codes, sizing confirmation, deviations and clarification responses | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | INST | INST-T145 Align final relief valve sizing with Process and vendor | SI | vendor final sizing: orifice, model, rating, inlet/outlet sizes | manual | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | INST | INST-T280 Compile instrument utility loads | Excel / Word | analyzer, system and panel power consumption | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | MECH | MECH-T110 Specify column and vessel internals | Excel / Word | internals vendor hydraulic rating, tray layout and completed datasheets | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | completed datasheets, performance, outline drawings | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | performance, power, weights and utilities | manual | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PIPE | PIPE-T100 Build S3D piping specification catalogue | S3D | valve and component outline dimensions and weights from preferred vendor offers | manual | 2 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | quoted shut-off head and maximum discharge pressure from performance curves | manual | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T255 Review vendor relief valve sizing | Excel / Word | vendor relief valve sizing: orifice, rated capacity, model | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | performance curves, guaranteed duties, utilities | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | performance data as confirmed | review | 3 | DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SAFE | SAFE-T240 Perform noise study | Excel / Word | vendor quoted sound pressure levels | manual | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SAFE | SAFE-T270 Review vendor packages and bids for SHE compliance | Excel / Word | technical quotations | review | 3 | FEL3, DD
VEND-I020 | Technical quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | technical offer to forward unpriced for TBE | manual | 3 | FEL3, DD
VEND-I030 | Commercial quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | priced offer held for commercial evaluation | manual | 3 | FEL3, DD
VEND-I030 | Commercial quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | price breakdown, options, spares, delivery, payment and validity | manual | 3 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | technical exceptions | review | 2 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | completed datasheets, model codes, sizing confirmation, deviations and clarification responses | review | 3 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | technical deviations and exceptions | review | 3 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T305 Process input to technical bid evaluations | Excel / Word | technical deviations | review | 3 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T070 Receive bids and distribute technical portions | Document Locator | technical exceptions to forward for TBE | manual | 3 | FEL3, DD
VEND-I040 | Deviations and exceptions list | data | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T080 Prepare the commercial bid evaluation | Excel / Word | commercial exceptions to price | manual | 3 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | CIVL | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | Purchasing DB | clarification responses | review | 3 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | ELEC | ELEC-T180 Evaluate electrical bids technically | Excel / Word | clarification responses | review | 2 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | INST | INST-T140 Evaluate instrument bids technically | Excel / Word | completed datasheets, model codes, sizing confirmation, deviations and clarification responses | review | 3 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | MECH | MECH-T260 Issue technical queries and clarifications to bidders | Excel / Word | responses to technical queries | review | 3 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | MECH | MECH-T270 Prepare technical bid evaluations | Excel / Word | revised offers | manual | 3 | FEL3, DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | PIPE | PIPE-T230 Resolve nozzle loads with mechanical and vendors | Excel / Word | vendor responses accepting or rejecting exceeded nozzle loads | review | 3 | DD
VEND-I050 | Clarification responses | document | VEND | VEND-T030 Answer bid clarifications | Excel / Word | PIPE | PIPE-T350 Evaluate piping bids | Excel / Word | technical clarification answers | manual | 3 | DD
VEND-I060 | Vendor document schedule | data | VEND | VEND-T040 Issue the vendor document schedule | Document Locator | MECH | MECH-T290 Hold vendor kick-off meetings | Excel / Word | vendor document numbers and planned submission dates | meeting | 3 | DD
VEND-I060 | Vendor document schedule | data | VEND | VEND-T040 Issue the vendor document schedule | Document Locator | SCM | SCM-T120 Set up VDRL tracking | Purchasing DB | vendor document numbers and planned submission dates | manual | 3 | DD
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | dimensions, weights, terminal points | review | 3 | DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | vendor GA: dimensions, weights, cable entry, access | review | 3 | DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | dimensions, nozzles, weights, lifting points | review | 2 | DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | PIPE | PIPE-T080 Request equipment nozzle orientations and elevations | S3D | package, pump, compressor and exchanger nozzle sizes and orientations | review | 2 | FEL3, DD
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | PIPE | PIPE-T240 Specify and requisition spring and engineered supports | Excel / Word | spring and engineered support drawings and load tables | review | 3 | DD
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | PIPE | PIPE-T360 Review valve and specialty item vendor data | Document Locator | valve and SP item drawings and dimensions | review | 3 | DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | PROJ | PROJ-T190 Run interface management | Excel / Word | terminal points, nozzle sizes and orientations | review | 3 | FEL3, DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | GA drawings for review | integrated | 2 | DD, CON
VEND-I070 | Vendor GA drawings for review | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | weights, dimensions and lifting points | manual | 3 | FEL3, DD
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | CIVL | CIVL-T150 Design static equipment foundations | Excel / Word | anchor bolt layout, base ring/saddle dimensions, static loads | manual | 4 | FEL3, DD
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | CIVL | CIVL-T160 Design rotating equipment foundations with dynamic analysis | Excel / Word | machine and rotor weights, unbalanced forces, baseplate and anchor bolt layout | manual | 4 | DD
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | CIVL | CIVL-T170 Design tank foundations | Excel / Word | tank vendor anchor and shell loads | manual | 4 | FEL3, DD
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | anchor bolt layout and loads to check against foundation design | review | 3 | DD, CON
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | anchor bolts, static and dynamic loads | review | 2 | DD, CON
VEND-I080 | Vendor foundation and load data | drawing | VEND | VEND-T050 Prepare GA and outline drawings for review | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | foundation and load data for review | integrated | 2 | DD, CON
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | MECH | MECH-T300 Review vendor drawings and data | Document Locator | thicknesses, MAWP, allowable nozzle loads | review | 2 | DD, CON
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | MECH | MECH-T330 Check piping loads against equipment nozzle allowables | Excel / Word | vendor allowable or increased nozzle loads | review | 3 | DD
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | MECH | MECH-T340 Review rotordynamic, torsional and pulsation studies | Excel / Word | lateral and torsional analysis and pulsation study reports (vendor calculations) | review | 3 | DD
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | vendor allowable nozzle loads | manual | 4 | DD
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | calculations for review | integrated | 2 | DD, CON
VEND-I090 | Vendor design calculations | document | VEND | VEND-T060 Prepare vendor design calculations | Mechanical calc tool | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | design thicknesses and materials | manual | 4 | DD
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | INST | INST-T270 Integrate vendor package controls | Excel / Word | package P&IDs, I/O list and control narrative with protocol, package instrument list and datasheets | review | 3 | DD, CON
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | MECH | MECH-T300 Review vendor drawings and data | Document Locator | package P&IDs | review | 2 | DD, CON
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | PROC | PROC-T200 Develop P&IDs (process content) | SPID | vendor package P&ID scheme and battery-limit points | review | 2 | FEL2, FEL3
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | PROC | PROC-T310 Review vendor data against process duties | Document Locator | package P&IDs | review | 3 | DD
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | PROJ | PROJ-T190 Run interface management | Excel / Word | package battery-limit points | review | 3 | FEL3, DD, CON
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | SAFE | SAFE-T150 Facilitate formal HAZOP | PHA tool | vendor package P&IDs | review | 3 | FEL3, DD
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | SAFE | SAFE-T270 Review vendor packages and bids for SHE compliance | Excel / Word | package P&IDs | review | 3 | FEL3, DD
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | package P&IDs | review | 3 | DD, CON
VEND-I100 | Package P&IDs | drawing | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Document Locator | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | package P&IDs for review | integrated | 2 | DD, CON
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | INST | INST-T270 Integrate vendor package controls | Excel / Word | package P&IDs, I/O list and control narrative with protocol, package instrument list and datasheets | review | 3 | DD, CON
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | package I/O list and control narrative | review | 4 | DD
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | PROC | PROC-T310 Review vendor data against process duties | Document Locator | package control narrative | review | 3 | DD
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | SAFE | SAFE-T280 Facilitate vendor package and design change HAZOPs | PHA tool | package control and shutdown narrative | review | 3 | DD, CON
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | package I/O and narrative for review | integrated | 2 | DD, CON
VEND-I110 | Package I/O list and control narrative | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | package signals and communication protocol | file | 4 | DD, CON
VEND-I120 | Package electrical data | data | VEND | VEND-T080 Prepare package electrical data | Excel / Word | ELEC | ELEC-T090 Develop electrical load list in SPEL | SPEL | package motor ratings, electrical loads and panel requirements | manual | 3 | FEL3, DD, CON
VEND-I120 | Package electrical data | data | VEND | VEND-T080 Prepare package electrical data | Excel / Word | ELEC | ELEC-T200 Review motor and package electrical data | SPEL | package motor ratings, starting data, panel loads and requirements | review | 3 | DD
VEND-I120 | Package electrical data | data | VEND | VEND-T080 Prepare package electrical data | Excel / Word | INST | INST-T280 Compile instrument utility loads | Excel / Word | analyzer, system and panel power consumption | review | 3 | FEL3, DD
VEND-I120 | Package electrical data | data | VEND | VEND-T080 Prepare package electrical data | Excel / Word | MECH | MECH-T300 Review vendor drawings and data | Document Locator | motor ratings and electrical loads | review | 2 | DD, CON
VEND-I120 | Package electrical data | data | VEND | VEND-T080 Prepare package electrical data | Excel / Word | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | package electrical data for review | integrated | 2 | DD, CON
VEND-I130 | Package instrument list and datasheets | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | INST | INST-T150 Review instrument vendor data | Document Locator | vendor drawings and data routed for review: dimensional drawings, sizing confirmation, wiring, certificates; certified data | review | 3 | DD, CON
VEND-I130 | Package instrument list and datasheets | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | INST | INST-T270 Integrate vendor package controls | Excel / Word | package P&IDs, I/O list and control narrative with protocol, package instrument list and datasheets | review | 3 | DD, CON
VEND-I130 | Package instrument list and datasheets | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | MECH | MECH-T300 Review vendor drawings and data | Document Locator | vendor instrument list and datasheets | review | 2 | DD, CON
VEND-I130 | Package instrument list and datasheets | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | vendor instrument list and datasheets | review | 4 | DD
VEND-I130 | Package instrument list and datasheets | data | VEND | VEND-T070 Prepare package P&IDs, I/O and control narrative | Excel / Word | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | package instrument list and datasheets for review | integrated | 2 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | CIVL | CIVL-T190 Prepare foundation plans and anchor bolt layouts | Excel / Word | certified anchor bolt templates and baseplate drawings | manual | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | certified GA and foundation data | review | 3 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | certified GA with shipping and lift weights and lift points | manual | 4 | FEL3, DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | certified base plate and anchor bolt pattern | manual | 4 | CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | ELEC | ELEC-T190 Review electrical vendor drawings and data | Document Locator | certified one-lines, schematics, wiring, relay data, impedance test reports | review | 3 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | ELEC | ELEC-T240 Run harmonic analysis | ETAP | certified VFD harmonic spectra and front-end type | manual | 3 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | ELEC | ELEC-T250 Perform protective relay coordination study | ETAP | certified relay models, CT ratios, breaker trip units, fuse curves | manual | 4 | DD, COM
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | ELEC | ELEC-T350 Prepare control and interlock schematics | SPEL | certified MCC/switchgear schematics | review | 3 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | FIRE | FIRE-T240 Review fire protection vendor data | Document Locator | certified fire pump curves, skid drawings and data | review | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | INST | INST-T150 Review instrument vendor data | Document Locator | vendor drawings and data routed for review: dimensional drawings, sizing confirmation, wiring, certificates; certified data | review | 3 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | INST | INST-T230 Verify SIL achievement | Excel / Word | certified device failure rate data, FMEDA and SIL certificates | review | 3 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | INST | INST-T310 Design instrument wiring, marshalling and terminations | SI | system cabinet arrangement, marshalling terminal numbering, barrier types | manual | 3 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | INST | INST-T400 Answer construction RFIs and issue I&C field changes | Procore | late certified data changes affecting installation | review | 4 | CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | certified weights and centre of gravity | manual | 4 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | MECH | MECH-T310 Release certified vendor data to other disciplines | Document Locator | certified GA, foundation, electrical and instrument data | review | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | final certified data | manual | 4 | COM
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PIPE | PIPE-T160 Route piping in the 3D model | S3D | certified package GA and terminal point nozzle data | review | 4 | FEL3, DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PIPE | PIPE-T220 Perform detailed stress analysis in CAESAR II | CAESAR II | certified nozzle data for rotating equipment and packages | manual | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PIPE | PIPE-T310 Incorporate vendor data and manage piping holds | S3D | certified GA nozzle locations, sizes, ratings and terminal points | review | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T130 Set design pressures and temperatures | Excel / Word | certified shut-off pressure from certified performance data | manual | 4 | FEL3, DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T250 Calculate relief loads and size relief valves | Flare / relief tool | certified exchanger design pressures, pump/compressor shut-off data | manual | 4 | FEL3, DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T315 Reconcile simulation with certified vendor data | HYSYS | certified pump performance curves and NPSHr; certified exchanger rating sheets and fired heater performance; certified compressor performance maps and settle-out data | manual | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T340 Update P&IDs to IFD and IFC | SPID | certified package P&IDs and nozzle data | manual | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | SAFE | SAFE-T270 Review vendor packages and bids for SHE compliance | Excel / Word | certified noise and safety device data | review | 3 | FEL3, DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | certified bill of materials | manual | 4 | DD
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | certified drawings for fabrication | manual | 4 | DD, CON
VEND-I140 | Certified vendor drawings and data | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | VEND | VEND-T180 Compile the MDR / data book | Document Locator | certified drawings and data | manual | 4 | CON, COM
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | FAT procedures, acceptance criteria, witness points | review | 3 | DD, CON
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | configured database, logic, graphics, FAT punch; FAT procedures and hold points | review | 3 | DD, CON
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | MECH | MECH-T350 Review and approve inspection and test plans | Document Locator | inspection activities, acceptance criteria, hold and witness points | review | 3 | DD
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | MECH | MECH-T360 Witness shop tests and factory acceptance tests | Excel / Word | test procedures and acceptance criteria | review | 3 | DD
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | SCM | SCM-T130 Expedite vendor documents and route them for review | Document Locator | ITP for review | integrated | 2 | DD, CON
VEND-I150 | Inspection and test plan | document | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | SCM | SCM-T150 Coordinate inspection and test plans | Excel / Word | inspection activities, hold and witness points | review | 2 | DD, CON
VEND-I160 | Manufacturing schedule | data | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | MECH | MECH-T290 Hold vendor kick-off meetings | Excel / Word | fabrication milestones and ex-works date | meeting | 3 | DD
VEND-I160 | Manufacturing schedule | data | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | baseline milestone dates | manual | 3 | DD, CON
VEND-I160 | Manufacturing schedule | data | VEND | VEND-T100 Prepare the ITP and manufacturing schedule | Excel / Word | VEND | VEND-T150 Report manufacturing progress | Excel / Word | baseline milestones | manual | 4 | DD, CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | MECH | MECH-T380 Review manufacturer's data books | Document Locator | material test reports | review | 4 | DD, CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | PIPE | PIPE-T360 Review valve and specialty item vendor data | Document Locator | MTRs per component | review | 3 | DD, CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | MTRs and heat numbers | review | 4 | DD, CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | MTR reference per heat number | manual | 4 | CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | material heat numbers for traceability | manual | 4 | DD, CON
VEND-I170 | Material test reports | document | VEND | VEND-T110 Procure raw materials and issue MTRs | Excel / Word | VEND | VEND-T180 Compile the MDR / data book | Document Locator | MTRs | manual | 4 | CON, COM
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | ELEC | ELEC-T400 Witness factory acceptance tests | Excel / Word | FAT certificates and test results | review | 3 | DD, CON
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | INST | INST-T440 Prepare as-built I&C database and drawings | SI | final data books and calibration/test certificates | review | 4 | COM
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | MECH | MECH-T380 Review manufacturer's data books | Document Locator | hydrotest, NDE, PMI and performance certificates | review | 4 | DD, CON
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | PIPE | PIPE-T360 Review valve and specialty item vendor data | Document Locator | hydrotest, NDE and fire-safe test certificates | review | 3 | DD, CON
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | hydrotest, NDE, PMI, performance and FAT certificates | review | 4 | DD, CON
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | VEND | VEND-T170 Prepare nameplate and as-built data | Excel / Word | test results and test pressures | manual | 4 | DD, CON
VEND-I180 | Test certificates | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | VEND | VEND-T180 Compile the MDR / data book | Document Locator | test certificates | manual | 4 | CON, COM
VEND-I190 | Inspection notification | data | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | MECH | MECH-T360 Witness shop tests and factory acceptance tests | Excel / Word | test due date and location | review | 3 | DD
VEND-I190 | Inspection notification | data | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | test due, date and location | manual | 3 | DD, CON
VEND-I200 | Spool fabrication status | data | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | spool fabrication status for IWP material checks | manual | 3 | CON
VEND-I200 | Spool fabrication status | data | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | spool fabrication status for expediting | manual | 3 | DD, CON
VEND-I210 | Steel shop drawings and fabrication status | drawing | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | CIVL | CIVL-T320 Review vendor and fabricator drawings | Document Locator | steel shop drawings, piece marks and erection drawings | review | 3 | DD, CON
VEND-I220 | Packing list and shipping documents | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | SCM | SCM-T180 Manage shipping and traffic | Excel / Word | shipping pieces, weights, dimensions, certificates of origin | manual | 4 | DD, CON
VEND-I220 | Packing list and shipping documents | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | SCM | SCM-T200 Receive materials at site in Jovix | Jovix | item marks, tags and heat numbers per piece | manual | 4 | CON
VEND-I230 | Nameplate and as-built data | data | VEND | VEND-T170 Prepare nameplate and as-built data | Excel / Word | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | serial number, nameplate rating, MAWP, as-built weights | manual | 4 | COM
VEND-I230 | Nameplate and as-built data | data | VEND | VEND-T170 Prepare nameplate and as-built data | Excel / Word | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | nameplate and serial data | manual | 4 | COM
VEND-I230 | Nameplate and as-built data | data | VEND | VEND-T170 Prepare nameplate and as-built data | Excel / Word | VEND | VEND-T180 Compile the MDR / data book | Document Locator | nameplate data | manual | 4 | CON, COM
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | COMM | COMM-T220 Compile system turnover packages | Document Locator | data books | manual | 4 | COM
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | INST | INST-T440 Prepare as-built I&C database and drawings | SI | final data books and calibration/test certificates | review | 4 | COM
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | MECH | MECH-T380 Review manufacturer's data books | Document Locator | certified drawings, calcs, MTRs, weld maps, NDE and test records | review | 4 | DD, CON
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | data books | manual | 4 | COM
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | final MDR/data book per PO | review | 4 | COM
VEND-I240 | MDR / data book | document | VEND | VEND-T180 Compile the MDR / data book | Document Locator | SCM | SCM-T280 Close out purchase orders | Purchasing DB | final data book delivered | review | 4 | CON, COM
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | IOM pre-commissioning instructions | manual | 4 | DD, CON
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | COMM | COMM-T220 Compile system turnover packages | Document Locator | IOM manuals | manual | 4 | COM
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | MECH | MECH-T380 Review manufacturer's data books | Document Locator | IOM manuals | review | 4 | DD, CON
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | installation and run-in instructions | manual | 4 | CON, COM
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | OWNR | OWNR-T190 Write operating procedures and train operators | Excel / Word | package operating instructions | manual | 4 | DD, CON
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | IOM manuals | manual | 4 | COM
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | PROC | PROC-T350 Prepare operating manual process input | Excel / Word | package operating instructions | review | 4 | DD, CON
VEND-I250 | IOM manuals | document | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Document Locator | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | vendor pre-commissioning, catalyst loading and first-fill instructions | review | 4 | DD, CON, COM
VEND-I260 | Spare parts interchangeability records | data | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Excel / Word | COMM | COMM-T100 Define commissioning spares, consumables and first fills | Excel / Word | commissioning spares part numbers and quantities | manual | 4 | DD
VEND-I260 | Spare parts interchangeability records | data | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Excel / Word | MECH | MECH-T370 Review spare parts recommendations | Excel / Word | part numbers, recommended quantities, lead times per tag | review | 3 | DD
VEND-I260 | Spare parts interchangeability records | data | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Excel / Word | OWNR | OWNR-T160 Define spare parts philosophy and approve spares | Excel / Word | SPIR part numbers, recommended quantities and prices | manual | 3 | DD, CON
VEND-I260 | Spare parts interchangeability records | data | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Excel / Word | OWNR | OWNR-T220 Load asset register and CMMS | Excel / Word | spare part numbers per tag | manual | 4 | COM
VEND-I260 | Spare parts interchangeability records | data | VEND | VEND-T190 Prepare IOM manuals and spare parts lists | Excel / Word | SCM | SCM-T270 Procure commissioning and operating spares | Purchasing DB | part numbers, recommended quantities, prices and lead times | manual | 4 | DD, CON, COM
VEND-I270 | Site service reports | document | VEND | VEND-T210 Provide site services | Excel / Word | COMM | COMM-T160 Execute pre-commissioning (B-ITRs) | Smart Completions | vendor site service reports and sign-offs | manual | 4 | CON, COM
VEND-I270 | Site service reports | document | VEND | VEND-T210 Provide site services | Excel / Word | CONS | CONS-T280 Compile construction quality dossier | Document Locator | vendor site installation and inspection reports | manual | 4 | CON, COM
VEND-I270 | Site service reports | document | VEND | VEND-T210 Provide site services | Excel / Word | ELEC | ELEC-T410 Answer RFIs and issue field changes | Procore | vendor field service findings | review | 4 | CON
VEND-I270 | Site service reports | document | VEND | VEND-T210 Provide site services | Excel / Word | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | field service reports for switchgear, VFD, UPS | review | 4 | COM
VEND-I270 | Site service reports | document | VEND | VEND-T210 Provide site services | Excel / Word | MECH | MECH-T410 Respond to field RFIs and equipment issues | Procore | vendor findings and recommended repairs | review | 3 | CON, COM
VEND-I280 | DCS/SIS configuration and FAT records | data | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | INST | INST-T330 Generate loop diagrams | SI | final I/O assignment and terminal numbers after FAT | manual | 4 | DD, CON
VEND-I280 | DCS/SIS configuration and FAT records | data | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | INST | INST-T390 Review configuration and witness system FAT | DCS / SIS config | configured database, logic, graphics, FAT punch; FAT procedures and hold points | review | 3 | DD, CON
VEND-I280 | DCS/SIS configuration and FAT records | data | VEND | VEND-T200 Configure and test the DCS/SIS | DCS / SIS config | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | configured DCS/SIS logic and permissives | review | 4 | CON, COM
VEND-I290 | Preservation and storage instructions | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | preservation and storage instructions | manual | 4 | DD, CON
VEND-I290 | Preservation and storage instructions | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | MECH | MECH-T390 Define equipment preservation and storage requirements | Excel / Word | storage conditions and preservation frequencies per item | manual | 4 | DD, CON
VEND-I290 | Preservation and storage instructions | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | SCM | SCM-T180 Manage shipping and traffic | Excel / Word | preservation requirements in transit | manual | 4 | DD, CON
VEND-I290 | Preservation and storage instructions | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | storage conditions and preservation frequencies | manual | 4 | CON, COM
VEND-I300 | Weld maps and NDE records | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | PIPE | PIPE-T410 Review fabricator spool drawings | Document Locator | fabricator weld maps and NDE records | review | 3 | CON
VEND-I300 | Weld maps and NDE records | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | SCM | SCM-T160 Carry out shop inspection and release | Excel / Word | weld maps and NDE results | review | 4 | DD, CON
VEND-I300 | Weld maps and NDE records | document | VEND | VEND-T120 Fabricate and test the equipment | Excel / Word | VEND | VEND-T180 Compile the MDR / data book | Document Locator | weld maps and NDE records | manual | 4 | CON, COM
VEND-I310 | Manufacturing progress report | data | VEND | VEND-T150 Report manufacturing progress | Excel / Word | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | milestone actuals, percent complete and forecast ex-works date | manual | 3 | DD, CON
VEND-I320 | Fabricator spool shop drawings | drawing | VEND | VEND-T130 Fabricate pipe spools | Document Locator | PIPE | PIPE-T410 Review fabricator spool drawings | Document Locator | Fabricator spool shop drawings for review against IFC isometrics | review | 3 | CON
VEND-I321 | Licensor process proposal | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T060 Develop and simulate FEL2 alternatives | HYSYS | Licensor/technology yield and performance data for proprietary sections (no licensor process data item in catalog) | manual | 1 | FEL2
VEND-I321 | Licensor process proposal | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | PROC | PROC-T070 Evaluate technology and licensor process offers | Excel / Word | Licensor proposals: yields, utilities, catalyst/chemical consumption, guarantees (no licensor offer item; VEND-I020 is equipment quotation) | review | 2 | FEL2
VEND-I322 | Licensor process design package | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T100 Build and calibrate rigorous simulation | HYSYS | Licensor process design package: H&MB and operating conditions | manual | 3 | FEL2, FEL3, DD
VEND-I322 | Licensor process design package | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | Licensor/chemical vendor dosing rates and catalyst volumes | manual | 3 | FEL2, FEL3, DD, COM
VEND-I322 | Licensor process design package | document | VEND | VEND-T090 Incorporate comments and issue certified final data | Document Locator | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | Licensor performance test procedure and guarantee correction curves | review | 4 | COM
VEND-I323 | Bidder questions | data | VEND | VEND-T030 Answer bid clarifications | Excel / Word | SCM | SCM-T060 Manage bid clarifications and bid bulletins | Excel / Word | Bidder questions raised during the bid period (technical and commercial) | manual | 2 | FEL3, DD
VEND-I324 | Change-order quotation | document | VEND | VEND-T020 Prepare firm technical and commercial quotations | Excel / Word | SCM | SCM-T110 Process PO amendments | Purchasing DB | Vendor change-order quotation: price and delivery impact of post-award changes | manual | 3 | DD, CON
VEND-I325 | OS&D response | document | VEND | VEND-T160 Pack, preserve and ship | Excel / Word | SCM | SCM-T210 Raise OS&D reports | Jovix | Vendor response to OS&D: replacement, repair or credit proposal | manual | 3 | CON
CONS-I010 | Constructability input register | document | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | PIPE | PIPE-T030 Write piping layout design basis | Excel / Word | access widths, crane corridors and module transport limits | meeting | 1 | FEL2, FEL3
CONS-I010 | Constructability input register | document | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | preferred spool sizes and shop vs field work preferences | meeting | 2 | FEL3, DD
CONS-I010 | Constructability input register | document | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | S3D | preferred spool sizes and field weld preferences | meeting | 3 | DD
CONS-I010 | Constructability input register | document | CONS | CONS-T010 Compile constructability input and lessons learned | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | site labour limits and sequence constraints | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | CIVL | CIVL-T090 Design site preparation and earthworks | Excel / Word | laydown areas, temporary buildings and haul roads to grade | meeting | 2 | FEL3, DD
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | haul roads and construction gates | meeting | 2 | FEL3, DD
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | ELEC | ELEC-T380 Design temporary construction power | Excel / Word | laydown, temporary buildings and utility connection points | meeting | 2 | DD, CON
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | laydown and temporary buildings | review | 3 | CON
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | laydown areas, haul roads and gates | meeting | 2 | FEL3, DD
CONS-I020 | Site logistics and laydown plan | drawing | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | SCM | SCM-T220 Manage the warehouse, laydown and preservation | Jovix | laydown and storage areas | manual | 3 | CON, COM
CONS-I025 | Temporary facility and utility requirements | data | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | CIVL | CIVL-T090 Design site preparation and earthworks | Excel / Word | temporary building locations and loads | meeting | 2 | FEL3, DD
CONS-I025 | Temporary facility and utility requirements | data | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | ELEC | ELEC-T380 Design temporary construction power | Excel / Word | temporary power demand and building loads | meeting | 2 | DD, CON
CONS-I025 | Temporary facility and utility requirements | data | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | temporary facilities and utilities scope | manual | 2 | FEL3
CONS-I025 | Temporary facility and utility requirements | data | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | temporary facilities | review | 3 | CON
CONS-I030 | Modularisation and prefabrication decision | decision | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | module and prefabrication scope | manual | 3 | FEL3, DD
CONS-I030 | Modularisation and prefabrication decision | decision | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | PIPE | PIPE-T130 Prepare piping fabrication, erection and inspection specifications | Excel / Word | shop versus field fabrication split and module scope | meeting | 2 | FEL3, DD
CONS-I030 | Modularisation and prefabrication decision | decision | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | PIPE | PIPE-T330 Prepare spool lists and fabrication packages | S3D | module boundaries and maximum dimensions | meeting | 3 | DD
CONS-I030 | Modularisation and prefabrication decision | decision | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | module/skid/pre-assembly scope and shop vs field split | meeting | 1 | FEL1, FEL2, FEL3, DD
CONS-I030 | Modularisation and prefabrication decision | decision | CONS | CONS-T030 Evaluate modularisation and prefabrication strategy | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | module boundaries and prefabrication scope affecting purchase packages | meeting | 2 | FEL2, FEL3
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | crane positions, crane pad loads and lift sequence | meeting | 2 | FEL3, DD
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | heavy lift plan affecting steel leave-outs and erection sequence | meeting | 2 | FEL3, DD
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | CONS | CONS-T050 Define path of construction | P6 | lift sequence, dates and crane positions that constrain area sequence | manual | 2 | FEL3
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | heavy lift cranes and durations | manual | 3 | FEL3, DD
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | heavy lift list, crane selection, lift sequence | meeting | 2 | DD, CON
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | heavy lift list and crane selection for crane costs | manual | 2 | FEL3
CONS-I040 | Heavy lift and crane plan | document | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | SCM | SCM-T170 Prepare the logistics plan | Excel / Word | heavy lift list, crane and set dates | meeting | 2 | FEL3, DD
CONS-I045 | Lift and setting requirements to design | data | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | CIVL | CIVL-T130 Design roads, access and fencing | Excel / Word | crane pad bearing and keep-clear zones | meeting | 2 | FEL3, DD
CONS-I045 | Lift and setting requirements to design | data | CONS | CONS-T040 Prepare heavy lift and crane study | Excel / Word | MECH | MECH-T220 Prepare equipment lifting data | Excel / Word | lifting and tailing lug type and position, dressed lift requirements | meeting | 2 | DD, CON
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | area sequence for piling and early works | meeting | 2 | FEL3, DD
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | area sequence from underground to steel | meeting | 2 | FEL3, DD
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | area sequence | manual | 3 | DD
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | area sequence | manual | 2 | FEL3
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | area sequence and target dates | manual | 3 | FEL3, DD
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | ELEC | ELEC-T380 Design temporary construction power | Excel / Word | area sequence and dates | meeting | 2 | DD, CON
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | area sequence | review | 3 | DD, CON, COM
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | area sequence and target dates | review | 3 | CON, COM
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | OWNR | OWNR-T140 Provide tie-in and outage windows | P6 | construction sequence for tie-ins | meeting | 3 | FEL3, DD, CON
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | area sequence | file | 3 | DD, CON
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | area sequence and target dates by area/system | manual | 2 | FEL2, FEL3, DD
CONS-I050 | Path of construction | document | CONS | CONS-T050 Define path of construction | P6 | SAFE | SAFE-T320 Prepare construction environmental compliance plan | Excel / Word | path of construction | review | 3 | CON
CONS-I060 | CWA boundaries | drawing | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | CWA boundaries | meeting | 2 | FEL3, DD
CONS-I060 | CWA boundaries | drawing | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CWA IDs and boundaries | manual | 3 | FEL3, DD
CONS-I060 | CWA boundaries | drawing | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | CWA boundaries | file | 3 | DD, CON
CONS-I060 | CWA boundaries | drawing | CONS | CONS-T060 Define construction work areas (CWAs) | iConstruct | PROJ | PROJ-T030 Set up the WBS, cost codes and P6 project structure | P6 | CWA IDs and boundaries for WBS/AWP alignment | meeting | 2 | FEL2, FEL3, DD
CONS-I070 | CWP breakdown and boundaries | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CIVL | CIVL-T340 Provide civil inputs to construction packaging | iConstruct | CWP IDs and boundaries | meeting | 2 | FEL3, DD
CONS-I070 | CWP breakdown and boundaries | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CONS | CONS-T110 Develop construction schedule by CWP | P6 | CWP scope and budget quantities | manual | 3 | DD, CON
CONS-I070 | CWP breakdown and boundaries | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | CWP boundaries | review | 3 | DD, CON, COM
CONS-I070 | CWP breakdown and boundaries | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | PIPE | PIPE-T400 Issue model to AWP and construction model | iConstruct | CWP IDs and scope boundaries | file | 3 | DD, CON
CONS-I070 | CWP breakdown and boundaries | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | PROJ | PROJ-T190 Run interface management | Excel / Word | CWP scope boundaries between construction packages | meeting | 3 | FEL3, DD, CON
CONS-I080 | CWP sequence and EWP need dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CIVL | CIVL-T180 Design piles and prepare piling layout | Excel / Word | CWP start dates for early piling package | meeting | 2 | FEL3, DD
CONS-I080 | CWP sequence and EWP need dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | CWP sequence | manual | 3 | DD
CONS-I080 | CWP sequence and EWP need dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CONS | CONS-T110 Develop construction schedule by CWP | P6 | CWP sequence and start dates | manual | 3 | DD, CON
CONS-I080 | CWP sequence and EWP need dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | EWP need dates by CWP | manual | 3 | DD
CONS-I080 | CWP sequence and EWP need dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CWP start dates and EWP need dates | manual | 2 | FEL2, FEL3, DD
CONS-I090 | CWP material required-on-site dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | material ROS dates by CWP | manual | 3 | DD
CONS-I090 | CWP material required-on-site dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | PIPE | PIPE-T340 Produce MTO by ident and bulk requisitions | S3D | ROS dates by CWP for delivery split | manual | 3 | FEL3, DD
CONS-I090 | CWP material required-on-site dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | VEND | VEND-T130 Fabricate pipe spools | Excel / Word | ROS dates for spools by CWP | manual | 3 | DD, CON
CONS-I090 | CWP material required-on-site dates | data | CONS | CONS-T070 Define CWPs, boundaries and sequence | P6 | VEND | VEND-T140 Detail and fabricate structural steel | Tekla | ROS dates for steel by CWP | manual | 3 | DD, CON
CONS-I100 | Model review constructability comments | data | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | CIVL | CIVL-T330 Take part in 3D model reviews and clash resolution | iConstruct | constructability comments on steel, foundations and access | meeting | 3 | FEL3, DD
CONS-I100 | Model review constructability comments | data | CONS | CONS-T080 Review 3D model for constructability (30/60/90 % reviews) | iConstruct | PIPE | PIPE-T280 Run 30/60/90 model reviews | iConstruct | access, rigging, scaffolding and spool break comments | meeting | 3 | FEL3, DD
CONS-I110 | Drawing constructability comments | document | CONS | CONS-T090 Review IFR drawings for constructability | Document Locator | PROJ | PROJ-T210 Run review cycles and consolidate comments | Document Locator | constructability comment sheets on IFR documents | review | 2 | FEL2, FEL3, DD
CONS-I120 | Construction execution plan | document | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | PROJ | PROJ-T010 Prepare the project execution plan | Excel / Word | construction strategy, contracting split, work hours, temporary facilities and AWP approach | meeting | 1 | FEL1, FEL2, FEL3, DD
CONS-I120 | Construction execution plan | document | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | PROJ | PROJ-T020 Develop the contracting and procurement strategy | Excel / Word | construction contracting split (civil, mechanical, E&I) and organisation | meeting | 2 | FEL2, FEL3
CONS-I120 | Construction execution plan | document | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | PROJ | PROJ-T180 Maintain the risk register and contingency analysis | Excel / Word | construction strategy, work hours and contracting assumptions | meeting | 2 | FEL1, FEL2, FEL3, DD, CON
CONS-I130 | Construction hours and indirects estimate input | data | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | PROJ | PROJ-T080 Prepare the Class 4 estimate | Excel / Word | direct field hours, crew sizes, construction equipment and indirects | manual | 2 | FEL2
CONS-I130 | Construction hours and indirects estimate input | data | CONS | CONS-T100 Prepare construction execution plan and estimate input | Excel / Word | PROJ | PROJ-T090 Prepare the Class 3 estimate | Excel / Word | field hours by discipline and CWA, indirects and construction equipment | manual | 2 | FEL3
CONS-I140 | Construction schedule by CWP | data | CONS | CONS-T110 Develop construction schedule by CWP | P6 | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | installation activities and dates per CWP/IWP | review | 3 | CON, COM
CONS-I140 | Construction schedule by CWP | data | CONS | CONS-T110 Develop construction schedule by CWP | P6 | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | MC walkdown dates from the CWP schedule | meeting | 4 | CON, COM
CONS-I140 | Construction schedule by CWP | data | CONS | CONS-T110 Develop construction schedule by CWP | P6 | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | CWP/IWP activities, logic and durations | manual | 2 | FEL2, FEL3, DD
CONS-I140 | Construction schedule by CWP | data | CONS | CONS-T110 Develop construction schedule by CWP | P6 | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | CWP/IWP schedule and look-ahead | manual | 3 | FEL3, DD, CON, COM
CONS-I140 | Construction schedule by CWP | data | CONS | CONS-T110 Develop construction schedule by CWP | P6 | SCM | SCM-T260 Call off vendor site services | Purchasing DB | installation dates by CWP/IWP needing vendor supervision | manual | 3 | CON, COM
CONS-I150 | EWP-CWP alignment and gap report | data | CONS | CONS-T120 Align EWPs and procurement packages to CWPs | P6 | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | EWPs not aligned with CWP need dates for the schedule update | manual | 3 | FEL3, DD, CON, COM
CONS-I160 | Construction model with CWP/IWP attributes | model | CONS | CONS-T130 Build construction model and attach CWP/IWP attributes | iConstruct | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | objects by CWP for IWP selection | integrated | 4 | CON
CONS-I170 | Installation work package (IWP) | document | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | IWP bill of materials | integrated | 4 | CON
CONS-I170 | Installation work package (IWP) | document | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | CONS | CONS-T200 Request and receive materials from the warehouse | Jovix | IWP bill of materials for released IWPs | integrated | 4 | CON
CONS-I170 | Installation work package (IWP) | document | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | CONS | CONS-T210 Track installed quantities and progress | iConstruct | IWP scope, budget quantities and hours | integrated | 4 | CON
CONS-I170 | Installation work package (IWP) | document | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | OWNR | OWNR-T180 Issue permits to work and isolations | Excel / Word | IWP scope, location and hazards | manual | 4 | CON, COM
CONS-I170 | Installation work package (IWP) | document | CONS | CONS-T140 Develop installation work packages (IWPs) | iConstruct | SCM | SCM-T230 Report material availability to AWP | Jovix | IWP bill of materials and quantities | integrated | 3 | CON
CONS-I180 | IWP material shortage report | data | CONS | CONS-T150 Check IWP material availability against Jovix | iConstruct | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | short items per IWP | integrated | 4 | CON
CONS-I190 | IWP constraint log | data | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | open IWP constraints driving the look-ahead | manual | 4 | FEL3, DD, CON, COM
CONS-I190 | IWP constraint log | data | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | SCM | SCM-T140 Expedite manufacturing and forecast deliveries | Purchasing DB | material constraints on IWPs to expedite | manual | 4 | DD, CON
CONS-I200 | Released IWP backlog | data | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | OWNR | OWNR-T180 Issue permits to work and isolations | Excel / Word | planned IWP start dates | manual | 4 | CON, COM
CONS-I200 | Released IWP backlog | data | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | SCM | SCM-T230 Report material availability to AWP | Jovix | released IWPs and planned start | integrated | 3 | CON
CONS-I200 | Released IWP backlog | data | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | SCM | SCM-T240 Issue materials to construction | Jovix | released IWPs for issue | integrated | 3 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | RFI question, location and marked-up extract | manual | 4 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | open RFIs by IWP | integrated | 4 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | CONS | CONS-T180 Raise field change requests | Procore | RFI responses that change design | manual | 4 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | CONS | CONS-T260 Prepare as-built redlines | Procore | RFI responses | manual | 4 | CON, COM
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | ELEC | ELEC-T410 Answer RFIs and issue field changes | Procore | electrical RFIs with markups | manual | 4 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | INST | INST-T400 Answer construction RFIs and issue I&C field changes | Procore | RFIs and field change requests with markups on I&C drawings | review | 3 | CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | MECH | MECH-T410 Respond to field RFIs and equipment issues | Procore | RFI question and markup on equipment | review | 3 | CON, COM
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | RFI question, location and markups | integrated | 4 | CON, COM
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | PROC | PROC-T370 Respond to field RFIs and review field changes | Procore | RFIs with markups | manual | 3 | CON, COM
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | RFIs that lead to change | manual | 3 | FEL3, DD, CON
CONS-I210 | Request for information (RFI) | document | CONS | CONS-T170 Raise and manage RFIs | Procore | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | RFIs | review | 3 | DD, CON, COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | proposed field change and affected drawings | manual | 4 | CON
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | CONS | CONS-T260 Prepare as-built redlines | Procore | approved field changes | manual | 4 | CON, COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | ELEC | ELEC-T410 Answer RFIs and issue field changes | Procore | field change requests on electrical work | manual | 4 | CON
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | INST | INST-T400 Answer construction RFIs and issue I&C field changes | Procore | RFIs and field change requests with markups on I&C drawings | review | 3 | CON
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | INST | INST-T440 Prepare as-built I&C database and drawings | SI | closed punch and approved field changes | review | 4 | COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | MECH | MECH-T410 Respond to field RFIs and equipment issues | Procore | proposed field change on equipment | review | 3 | CON, COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | OWNR | OWNR-T150 Approve changes | Excel / Word | field change requests | review | 4 | DD, CON
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | proposed field change, markups and affected drawings | integrated | 4 | CON, COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | PROC | PROC-T370 Respond to field RFIs and review field changes | Procore | field change requests; field-routed small-bore, drain and vent changes | manual | 3 | CON, COM
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | proposed field change, reason, affected drawings | manual | 3 | FEL3, DD, CON
CONS-I220 | Field change request | document | CONS | CONS-T180 Raise field change requests | Procore | SAFE | SAFE-T330 Perform MOC safety reviews of field and design changes | Procore | field change requests | review | 3 | DD, CON, COM
CONS-I230 | Field change cost and schedule impact | data | CONS | CONS-T180 Raise field change requests | Procore | OWNR | OWNR-T150 Approve changes | Excel / Word | field change cost and schedule impact | review | 4 | DD, CON
CONS-I230 | Field change cost and schedule impact | data | CONS | CONS-T180 Raise field change requests | Procore | PROJ | PROJ-T160 Run change control: trends and change notices | Excel / Word | hours, material and schedule impact per field change | manual | 3 | FEL3, DD, CON
CONS-I240 | Foundation and setting-out survey record | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | as-built foundation elevations and anchor bolt deviations | manual | 4 | CON
CONS-I240 | Foundation and setting-out survey record | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Tekla | as-built foundation elevations and anchor bolt positions | manual | 4 | CON, COM
CONS-I240 | Foundation and setting-out survey record | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | CONS | CONS-T260 Prepare as-built redlines | Procore | as-built foundation elevations and anchor bolt positions | manual | 4 | CON, COM
CONS-I240 | Foundation and setting-out survey record | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | foundation and anchor bolt survey for equipment setting | review | 4 | CON, COM
CONS-I250 | Material issue request | data | CONS | CONS-T200 Request and receive materials from the warehouse | Jovix | SCM | SCM-T240 Issue materials to construction | Jovix | pick list by IWP: item code, quantity, heat number, date | integrated | 3 | CON
CONS-I260 | Field shortage, overage and damage report | data | CONS | CONS-T200 Request and receive materials from the warehouse | Jovix | PIPE | PIPE-T430 Reconcile piping material shortages and surplus | Jovix | work-face shortages and damage | manual | 4 | CON
CONS-I270 | Installed quantities and progress | data | CONS | CONS-T210 Track installed quantities and progress | iConstruct | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | installed quantities and percent complete by IWP/CWP | manual | 3 | FEL3, DD, CON, COM
CONS-I270 | Installed quantities and progress | data | CONS | CONS-T210 Track installed quantities and progress | iConstruct | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | construction installed quantities and percent complete | manual | 3 | FEL2, FEL3, DD, CON, COM
CONS-I270 | Installed quantities and progress | data | CONS | CONS-T210 Track installed quantities and progress | iConstruct | PROJ | PROJ-T250 Load construction progress into P6 | P6 | installed quantities and percent complete by IWP/CWP | file | 3 | CON, COM
CONS-I270 | Installed quantities and progress | data | CONS | CONS-T210 Track installed quantities and progress | iConstruct | SCM | SCM-T250 Reconcile materials and dispose of surplus | Jovix | installed quantities by IWP/CWP | manual | 4 | CON, COM
CONS-I280 | Weld log and NDE register | data | CONS | CONS-T220 Track welds and NDE | Excel / Word | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | welds complete and NDE accepted for lines in the pack | manual | 4 | CON
CONS-I280 | Weld log and NDE register | data | CONS | CONS-T220 Track welds and NDE | Excel / Word | CONS | CONS-T280 Compile construction quality dossier | Document Locator | weld and NDE records | manual | 4 | CON, COM
CONS-I280 | Weld log and NDE register | data | CONS | CONS-T220 Track welds and NDE | Excel / Word | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | final weld numbers and NDE/PWHT records | manual | 4 | CON, COM
CONS-I290 | Pressure test pack | document | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | COMM | COMM-T130 Track test pack status by subsystem | Smart Completions | test packs and lines included | manual | 4 | CON
CONS-I300 | Pressure test and reinstatement record | document | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | COMM | COMM-T130 Track test pack status by subsystem | Smart Completions | tested/reinstated status | manual | 4 | CON
CONS-I300 | Pressure test and reinstatement record | document | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | test packs tested and reinstated | manual | 4 | CON
CONS-I300 | Pressure test and reinstatement record | document | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | CONS | CONS-T280 Compile construction quality dossier | Document Locator | test records | manual | 4 | CON, COM
CONS-I310 | Completed construction ITRs (A sheets) | data | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | signed A-ITRs by tag | integrated | 4 | CON
CONS-I310 | Completed construction ITRs (A sheets) | data | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | COMM | COMM-T190 Energise electrical systems | Smart Completions | electrical A-ITRs and cable test records | integrated | 4 | CON, COM
CONS-I310 | Completed construction ITRs (A sheets) | data | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | completed A-ITRs including alignment and installation checks | review | 4 | CON, COM
CONS-I320 | Construction punch clearance status | data | CONS | CONS-T250 Clear construction punch items | Smart Completions | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | punch items cleared by construction | integrated | 4 | CON, COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | CIVL | CIVL-T380 Incorporate as-built civil and structural changes | Tekla | redlined foundation, underground and layout drawings | manual | 4 | CON, COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | ELEC | ELEC-T440 Produce as-built electrical records | SPEL | redlined cable routes, terminations, layouts | manual | 4 | CON, COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | INST | INST-T440 Prepare as-built I&C database and drawings | SI | redlines on loop, wiring, location and hook-up drawings | manual | 4 | COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | MECH | MECH-T440 Issue as-built equipment data for handover | Excel / Word | field deviations affecting equipment | manual | 4 | COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | redlined isometrics and layout drawings | manual | 4 | CON, COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | as-built redline P&IDs | manual | 4 | COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | redlined drawings with field deviations | review | 4 | COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | as-built redlines | review | 4 | COM
CONS-I330 | As-built redline markups | drawing | CONS | CONS-T260 Prepare as-built redlines | Procore | SAFE | SAFE-T360 Update safety studies to as-built and hand over | Excel / Word | redlines | review | 4 | COM
CONS-I340 | Mechanical completion certificate | decision | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | MC certificate with outstanding B punch | manual | 4 | CON
CONS-I350 | Construction quality dossier | document | CONS | CONS-T280 Compile construction quality dossier | Document Locator | CIVL | CIVL-T360 Answer RFIs and disposition field changes and NCRs | Procore | pile records and concrete test results in the quality dossier | manual | 4 | CON
CONS-I350 | Construction quality dossier | document | CONS | CONS-T280 Compile construction quality dossier | Document Locator | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | quality dossier per subsystem | manual | 4 | CON
CONS-I350 | Construction quality dossier | document | CONS | CONS-T280 Compile construction quality dossier | Document Locator | COMM | COMM-T220 Compile system turnover packages | Document Locator | construction quality dossier per subsystem | manual | 4 | COM
CONS-I360 | Settlement monitoring readings | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | CIVL | CIVL-T370 Evaluate settlement monitoring during hydrotest | Excel / Word | Settlement monitoring survey readings at tank/foundation monitoring points during hydrotest filling and holding | manual | 4 | CON, COM
CONS-I361 | Tie-in field verification survey | data | CONS | CONS-T190 Survey, set out and verify foundations | Excel / Word | PIPE | PIPE-T380 Identify tie-ins and issue tie-in packages | Excel / Word | Field verification survey of existing tie-in points (dimensions, wall thickness, condition, photos) | manual | 3 | FEL3, DD, CON
CONS-I362 | Field labour hours and subcontractor claims | data | CONS | CONS-T210 Track installed quantities and progress | Excel / Word | PROJ | PROJ-T150 Track cost and forecast at completion | Excel / Word | Field labour hours spent and subcontractor progress claims by cost code | manual | 3 | DD, CON, COM
CONS-I363 | Construction HSE statistics | data | CONS | CONS-T210 Track installed quantities and progress | Excel / Word | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | Construction HSE statistics (hours worked, incidents, rates) | manual | 3 | FEL2, FEL3, DD, CON, COM
COMM-I010 | Completions and commissioning execution plan | document | COMM | COMM-T010 Prepare completions and commissioning execution plan | Excel / Word | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | completions and commissioning plan | review | 3 | DD, CON, COM
COMM-I020 | Preliminary system list and start-up sequence | data | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | system list | manual | 2 | FEL3, DD
COMM-I020 | Preliminary system list and start-up sequence | data | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | CONS | CONS-T050 Define path of construction | P6 | preliminary system list and start-up sequence with required ready-for-commissioning dates by system | manual | 2 | FEL3
COMM-I020 | Preliminary system list and start-up sequence | data | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | system list and start-up order | meeting | 3 | DD, CON, COM
COMM-I020 | Preliminary system list and start-up sequence | data | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | system list and start-up order | review | 3 | DD, CON, COM
COMM-I020 | Preliminary system list and start-up sequence | data | COMM | COMM-T020 Develop preliminary system list and start-up sequence | Excel / Word | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | system list and start-up order with RFC dates | manual | 2 | FEL2, FEL3, DD
COMM-I030 | System boundary P&IDs | drawing | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | subsystem limits on P&IDs | manual | 4 | DD, CON
COMM-I030 | System boundary P&IDs | drawing | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | subsystem limits on P&IDs | manual | 3 | CON
COMM-I030 | System boundary P&IDs | drawing | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | system/subsystem numbers and boundaries; tag-to-subsystem register format | manual | 3 | CON, COM
COMM-I030 | System boundary P&IDs | drawing | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | OWNR | OWNR-T180 Issue permits to work and isolations | Excel / Word | isolation points on boundary P&IDs | manual | 4 | CON, COM
COMM-I030 | System boundary P&IDs | drawing | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | SPID | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | system and subsystem limits and isolation points | file | 3 | DD, CON
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | systems and subsystems with priority | manual | 3 | DD
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | subsystem priority | manual | 3 | CON
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | CONS | CONS-T230 Prepare and execute pressure test packs | Excel / Word | subsystem numbers | manual | 3 | CON
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | subsystem boundaries | integrated | 4 | CON
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | ELEC | ELEC-T420 Define electrical systems and energization sequence | Smart Completions | system and subsystem numbers and boundaries | meeting | 3 | DD, CON, COM
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | system/subsystem numbers and boundaries; tag-to-subsystem register format | manual | 3 | CON, COM
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | system and subsystem boundaries | manual | 3 | CON, COM
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | PIPE | PIPE-T390 Define hydrotest and test pack boundaries | Excel / Word | subsystem numbers and descriptions | file | 3 | DD, CON
COMM-I040 | System and subsystem register | data | COMM | COMM-T030 Mark system and subsystem boundaries on P&IDs | Excel / Word | PROC | PROC-T360 Prepare process input to systemization and commissioning | Excel / Word | system and subsystem numbering and boundaries | review | 3 | DD, CON, COM
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | COMM | COMM-T110 Define vendor commissioning support requirements | Excel / Word | commissioning sequence by subsystem | manual | 3 | DD
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | CONS | CONS-T110 Develop construction schedule by CWP | P6 | required MC/turnover date per subsystem | manual | 3 | DD, CON
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | CONS | CONS-T160 Manage IWP constraints and release IWPs | iConstruct | subsystem turnover dates | manual | 3 | CON
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | INST | INST-T430 Support SAT, SIS validation and integrated testing | DCS / SIS config | C&E/SIF test procedures and commissioning sequence | review | 3 | COM
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | subsystem sequence and turnover dates | review | 3 | CON, COM
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | commissioning sequence | review | 4 | CON, COM
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | PROC | PROC-T365 Prepare start-up, shutdown and emergency procedures | Excel / Word | commissioning sequence and turnover dates | review | 3 | CON, COM
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | PROJ | PROJ-T110 Build and baseline the integrated schedule in P6 | P6 | subsystem sequence and required MC/turnover dates | manual | 2 | FEL2, FEL3, DD
COMM-I050 | Commissioning sequence and required turnover dates | data | COMM | COMM-T040 Set commissioning sequence and required subsystem turnover dates | P6 | SAFE | SAFE-T350 Set up environmental startup compliance | Excel / Word | system startup dates | review | 4 | COM
COMM-I060 | ITR library and ITR matrix | data | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | ITR matrix by tag type | integrated | 4 | DD, CON
COMM-I060 | ITR library and ITR matrix | data | COMM | COMM-T050 Define ITR library and ITR matrix by tag type | Smart Completions | MECH | MECH-T430 Provide mechanical completion and pre-commissioning input | Smart Completions | ITR forms and tag-type mapping | manual | 3 | CON, COM
COMM-I070 | Tag-to-subsystem register | data | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | tag-to-subsystem register for spreadsheet load | file | 4 | DD, CON
COMM-I070 | Tag-to-subsystem register | data | COMM | COMM-T060 Build tag-to-subsystem register | Excel / Word | INST | INST-T410 Prepare instrument tag register for completions | Excel / Word | system/subsystem numbers and boundaries; tag-to-subsystem register format | manual | 3 | CON, COM
COMM-I080 | ITR assignment register | data | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | COMM | COMM-T160 Execute pre-commissioning (B-ITRs) | Smart Completions | B-ITRs per tag | integrated | 4 | CON, COM
COMM-I080 | ITR assignment register | data | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | COMM | COMM-T240 Report completions progress | Smart Completions | ITR status | integrated | 4 | CON, COM
COMM-I080 | ITR assignment register | data | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | CONS | CONS-T240 Complete construction ITRs (A sheets) | Smart Completions | ITRs assigned per tag and subsystem | integrated | 4 | CON
COMM-I080 | ITR assignment register | data | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | tags and ITR status per subsystem (A-ITRs complete) | integrated | 4 | CON
COMM-I080 | ITR assignment register | data | COMM | COMM-T070 Load tags and assign ITRs in Smart Completions | Smart Completions | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | ITRs requiring owner witness | review | 4 | CON, COM
COMM-I090 | Pre-commissioning procedures | document | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | COMM | COMM-T120 Plan temporary commissioning facilities | Excel / Word | flushing and blowing methods by system | manual | 4 | DD, CON
COMM-I090 | Pre-commissioning procedures | document | COMM | COMM-T080 Write pre-commissioning procedures | Excel / Word | COMM | COMM-T160 Execute pre-commissioning (B-ITRs) | Smart Completions | pre-commissioning procedures | integrated | 4 | CON, COM
COMM-I100 | Commissioning and function test procedures | document | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | INST | INST-T430 Support SAT, SIS validation and integrated testing | DCS / SIS config | C&E/SIF test procedures and commissioning sequence | review | 3 | COM
COMM-I100 | Commissioning and function test procedures | document | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | OWNR | OWNR-T200 Witness and accept commissioning tests | Smart Completions | test procedures | review | 4 | CON, COM
COMM-I100 | Commissioning and function test procedures | document | COMM | COMM-T090 Write commissioning and function test procedures | Excel / Word | VEND | VEND-T210 Provide site services | Excel / Word | commissioning and run-in procedures | meeting | 4 | CON, COM
COMM-I110 | Commissioning spares and first-fill list | data | COMM | COMM-T100 Define commissioning spares, consumables and first fills | Excel / Word | SCM | SCM-T270 Procure commissioning and operating spares | Purchasing DB | commissioning spares and first fill by system and need date | manual | 3 | DD, CON, COM
COMM-I120 | Vendor commissioning support requirements | data | COMM | COMM-T110 Define vendor commissioning support requirements | Excel / Word | MECH | MECH-T420 Coordinate vendor site representatives | Excel / Word | vendor representative scope and call-off dates per package | review | 3 | CON, COM
COMM-I120 | Vendor commissioning support requirements | data | COMM | COMM-T110 Define vendor commissioning support requirements | Excel / Word | SCM | SCM-T260 Call off vendor site services | Purchasing DB | vendor representative scope, man-days and call-off dates | manual | 3 | CON, COM
COMM-I130 | Temporary commissioning facility requirements | data | COMM | COMM-T120 Plan temporary commissioning facilities | Excel / Word | CONS | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | Excel / Word | temporary commissioning facilities to include in site logistics | manual | 3 | FEL2, FEL3, DD
COMM-I140 | Test pack status by subsystem | data | COMM | COMM-T130 Track test pack status by subsystem | Smart Completions | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | test pack status | manual | 4 | CON, COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | COMM | COMM-T240 Report completions progress | Smart Completions | punch status | integrated | 4 | CON, COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | CONS | CONS-T250 Clear construction punch items | Smart Completions | punch items by subsystem with category and action-by construction | integrated | 4 | CON, COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | CONS | CONS-T270 Walk down and certify mechanical completion by subsystem | Smart Completions | open A punch per subsystem | integrated | 4 | CON
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | loop check results, loop/configuration defects and I&C punch items | review | 3 | CON, COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | INST | INST-T440 Prepare as-built I&C database and drawings | SI | closed punch and approved field changes | review | 4 | COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | OWNR | OWNR-T210 Accept system handover | Smart Completions | punch list | review | 4 | COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | PIPE | PIPE-T440 Prepare as-built isometrics and model | S3D | punch items affecting piping | manual | 4 | CON, COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | process punch items | manual | 3 | COM
COMM-I150 | Punch list | data | COMM | COMM-T140 Raise and manage punch lists | Smart Completions | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | category A punch | integrated | 4 | COM
COMM-I160 | Subsystem turnover certificate (construction to commissioning) | decision | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | subsystem turnover status | integrated | 4 | COM
COMM-I160 | Subsystem turnover certificate (construction to commissioning) | decision | COMM | COMM-T150 Accept subsystem turnover from construction | Smart Completions | VEND | VEND-T210 Provide site services | Excel / Word | subsystem turnover status (readiness) | meeting | 4 | CON, COM
COMM-I170 | Completed pre-commissioning ITRs (B sheets) | data | COMM | COMM-T160 Execute pre-commissioning (B-ITRs) | Smart Completions | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | insulation resistance, hi-pot, solo run B-ITRs | review | 4 | COM
COMM-I180 | Loop check records | data | COMM | COMM-T170 Execute loop checks | Smart Completions | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | loop check records | integrated | 4 | COM
COMM-I180 | Loop check records | data | COMM | COMM-T170 Execute loop checks | Smart Completions | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | loop check results, loop/configuration defects and I&C punch items | review | 3 | CON, COM
COMM-I190 | Loop and configuration defect list | data | COMM | COMM-T170 Execute loop checks | Smart Completions | INST | INST-T420 Support loop checks and resolve I&C punch | Smart Completions | loop check results, loop/configuration defects and I&C punch items | review | 3 | CON, COM
COMM-I190 | Loop and configuration defect list | data | COMM | COMM-T170 Execute loop checks | Smart Completions | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | loop and configuration defects | review | 4 | COM
COMM-I200 | C&E and SIF function test records | document | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | C&E/SIF test records | integrated | 4 | COM
COMM-I200 | C&E and SIF function test records | document | COMM | COMM-T180 Execute C&E and SIF function tests | DCS / SIS config | SAFE | SAFE-T340 Lead pre-startup safety review (PSSR) | Smart Completions | C&E and SIF function test records | review | 4 | COM
COMM-I210 | Energisation certificates | decision | COMM | COMM-T190 Energise electrical systems | Smart Completions | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | energisation certificates | integrated | 4 | COM
COMM-I220 | Commissioning ITR records (C sheets) | data | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | ELEC | ELEC-T430 Support electrical testing, setting and energization | Smart Completions | run-in and commissioning results | review | 4 | COM
COMM-I230 | Ready-for-start-up certificate | decision | COMM | COMM-T200 Commission systems and confirm ready for start-up | Smart Completions | OWNR | OWNR-T210 Accept system handover | Smart Completions | RFSU certificate | review | 4 | COM
COMM-I240 | Commissioning technical query | document | COMM | COMM-T210 Raise commissioning technical queries | Procore | PIPE | PIPE-T420 Respond to piping RFIs and field changes | Procore | commissioning queries on piping | manual | 4 | CON, COM
COMM-I240 | Commissioning technical query | document | COMM | COMM-T210 Raise commissioning technical queries | Procore | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | commissioning technical queries | manual | 3 | COM
COMM-I240 | Commissioning technical query | document | COMM | COMM-T210 Raise commissioning technical queries | Procore | PROC | PROC-T385 Incorporate as-built redlines into P&IDs | SPID | commissioning modifications | manual | 4 | COM
COMM-I250 | System turnover package | document | COMM | COMM-T220 Compile system turnover packages | Document Locator | COMM | COMM-T230 Hand over systems to the owner | Smart Completions | complete turnover package | manual | 4 | COM
COMM-I250 | System turnover package | document | COMM | COMM-T220 Compile system turnover packages | Document Locator | OWNR | OWNR-T210 Accept system handover | Smart Completions | turnover package | review | 4 | COM
COMM-I250 | System turnover package | document | COMM | COMM-T220 Compile system turnover packages | Document Locator | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | system turnover packages | review | 4 | COM
COMM-I260 | System handover certificate | decision | COMM | COMM-T230 Hand over systems to the owner | Smart Completions | PROJ | PROJ-T260 Compile the final records and close out | Document Locator | system handover certificates | review | 4 | COM
COMM-I270 | Completions progress report | data | COMM | COMM-T240 Report completions progress | Smart Completions | PROJ | PROJ-T140 Update the schedule and analyse the critical path | P6 | ITR, punch and certificate progress by system | manual | 3 | FEL3, DD, CON, COM
COMM-I270 | Completions progress report | data | COMM | COMM-T240 Report completions progress | Smart Completions | PROJ | PROJ-T240 Prepare monthly progress reports | Excel / Word | ITR, punch and certificate progress | manual | 3 | FEL2, FEL3, DD, CON, COM
COMM-I280 | Performance test report | document | COMM | COMM-T250 Support performance test run | Excel / Word | PROC | PROC-T375 Support commissioning, start-up and performance test | Excel / Word | measured yields, product quality and utilities | manual | 4 | COM

## Tasks
ID | Discipline | Task | System | Phases | Activity | Description | Inputs | Outputs
OWNR-T010 | OWNR | Define business case, capacity and product slate | Excel / Word | FEL1 | FEL-01 | Sets the business objective, nameplate capacity, product slate and economic hurdle rate that frame the project. | 3 | 3
OWNR-T020 | OWNR | Supply crude assays and feed cases | Excel / Word | FEL1, FEL2 | PRJ-02 | Provides the crude assay library and selects the design, check and turndown crude/blend cases. | 1 | 1
OWNR-T030 | OWNR | Supply site and existing facility data | Excel / Word | FEL1, FEL2 | FEL-03 | Provides site survey control, historic geotechnical data, climatic data and as-built drawings and capacities of existing units, utilities and offsites. | 2 | 3
OWNR-T040 | OWNR | Issue owner standards and specifications | Document Locator | FEL1, FEL2 | PRJ-01 | Issues the owner engineering standards, the order of precedence against codes, and the approved vendor list. | 1 | 1
OWNR-T050 | OWNR | Define owner design basis requirements | Excel / Word | FEL2, FEL3 | PRJ-01 | States design life, on-stream factor, turndown, sparing philosophy, overdesign margins, utility conditions and environmental limits for the BOD. | 4 | 2
OWNR-T060 | OWNR | Set risk tolerance criteria | Excel / Word | FEL2 | SAF-04 | Issues individual and societal risk criteria, the corporate risk matrix and LOPA target frequencies. | 1 | 1
OWNR-T070 | OWNR | Approve gate decisions | Excel / Word | FEL1, FEL2, FEL3 | SEL-01 | Reviews the gate package and approves the select decision, entry to FEED and final investment decision. | 6 | 2
OWNR-T080 | OWNR | Act as permit applicant | Excel / Word | FEL2, FEL3 | SEL-04 | Submits environmental and construction permit applications as operator and passes permit conditions back to the project. | 5 | 2
OWNR-T090 | OWNR | Review and comment on deliverables | Document Locator | FEL2, FEL3, DD | PRJ-04 | Reviews IFR deliverables (P&IDs, datasheets, layouts, specifications) and returns comment sheets through Document Locator. | 7 | 2
OWNR-T100 | OWNR | Provide operations and maintenance input | Excel / Word | FEL2, FEL3, DD | PRJ-01 | States operating, sampling, isolation and blinding, drainage, access and maintenance (removal, lifting, cleaning) requirements. | 4 | 3
OWNR-T110 | OWNR | Specify control and alarm management requirements | Excel / Word | FEL3, DD | ICS-01 | Gives operator interface, alarm management, DCS/SIS platform and integration with existing plant control requirements. | 3 | 1
OWNR-T120 | OWNR | Review the 3D model for operability and maintenance | iConstruct | FEL3, DD | LAY-03 | Reviews the federated model with operators and maintainers for access, valve reach, maintenance clearances and escape routes. | 3 | 1
OWNR-T130 | OWNR | Take part in HAZOP and accept actions | PHA tool | FEL3, DD | SAF-03 | Provides operations staff for HAZOP and LOPA, and approves action close-outs and residual risk. | 5 | 2
OWNR-T140 | OWNR | Provide tie-in and outage windows | P6 | FEL3, DD, CON | PRJ-05 | Sets turnaround and outage windows, live-plant constraints and isolation availability for tie-ins. | 3 | 1
OWNR-T150 | OWNR | Approve changes | Excel / Word | DD, CON | PRJ-05 | Approves change requests and field changes that alter scope, cost, schedule or operability. | 3 | 1
OWNR-T160 | OWNR | Define spare parts philosophy and approve spares | Excel / Word | DD, CON | PRJ-01 | Sets the spares philosophy (commissioning, capital, two-year operating) and approves spares from SPIRs. | 2 | 2
OWNR-T170 | OWNR | Define CMMS asset data requirements | Excel / Word | DD | PRJ-01 | Defines asset hierarchy, equipment classes, required attributes, criticality ranking and document links to be delivered at handover. | 2 | 1
OWNR-T180 | OWNR | Issue permits to work and isolations | Excel / Word | CON, COM | PRJ-05 | Issues permits to work, isolations and site access for construction and commissioning work in or near operating plant. | 3 | 1
OWNR-T190 | OWNR | Write operating procedures and train operators | Excel / Word | DD, CON | PRJ-01 | Writes normal, start-up, shutdown and emergency procedures and trains the operating crew. | 7 | 2
OWNR-T200 | OWNR | Witness and accept commissioning tests | Smart Completions | CON, COM | CON-02 | Witnesses MC walkdowns, loop checks, C&E tests and run-in, and signs acceptance. | 4 | 2
OWNR-T210 | OWNR | Accept system handover | Smart Completions | COM | CON-02 | Reviews turnover packages and accepts each system with an agreed retained punch list. | 5 | 2
OWNR-T220 | OWNR | Load asset register and CMMS | Excel / Word | COM | CON-02 | Builds the asset register and loads CMMS master data from handover data, and returns gaps to the project. | 8 | 2
OWNR-T230 | OWNR | Accept final documentation | Document Locator | COM | PRJ-03 | Checks final as-built documentation and data books against the handover specification and accepts or rejects them. | 3 | 1
OWNR-T240 | OWNR | Pay invoices and report actual cost | Excel / Word | DD, CON | CST-03 | Approve and pay vendor and contractor invoices against POs and report actual cost and back-charges. | 2 | 1
PROJ-T010 | PROJ | Prepare the project execution plan | Excel / Word | FEL1, FEL2, FEL3, DD | PRJ-05 | Write and update the execution plan: scope, organisation, phase plan, work split, gate criteria and key procedures. | 5 | 2
PROJ-T020 | PROJ | Develop the contracting and procurement strategy | Excel / Word | FEL2, FEL3 | PRJ-05 | Define contract packages, procurement packages, split of owner-furnished and contractor-furnished items and the long-lead strategy. | 6 | 3
PROJ-T030 | PROJ | Set up the WBS, cost codes and P6 project structure | P6 | FEL2, FEL3, DD | PRJ-05 | Build the work breakdown structure, area and unit codes, cost codes and P6 calendars and activity codes used by all disciplines. | 3 | 1
PROJ-T040 | PROJ | Set up document numbering and the Document Locator project | Document Locator | FEL1, FEL2, FEL3 | PRJ-03 | Issue the numbering procedure, document type and discipline codes, folder structure, workflows and distribution matrix in Document Locator. | 3 | 3
PROJ-T050 | PROJ | Compile and maintain the deliverables register | Document Locator | FEL2, FEL3, DD, CON | PRJ-03 | Collect each discipline's deliverables list, assign document numbers and keep the register with planned and actual issue dates and revisions. | 9 | 2
PROJ-T060 | PROJ | Prepare the Class 5 estimate | Excel / Word | FEL1 | FEL-04 | Build the capacity-factored or curve-based order-of-magnitude estimate for the business case. | 5 | 1
PROJ-T070 | PROJ | Issue estimate quantity requests to disciplines | Excel / Word | FEL2, FEL3, DD | CST-01 | Send each discipline the quantity take-off template, basis and due dates for the estimate. | 2 | 1
PROJ-T080 | PROJ | Prepare the Class 4 estimate | Excel / Word | FEL2 | CST-01 | Equipment-factored estimate from the equipment list, budget quotes and factored bulks. | 10 | 1
PROJ-T090 | PROJ | Prepare the Class 3 estimate | Excel / Word | FEL3 | CST-02 | Semi-detailed estimate from vendor quotes and discipline MTOs priced with unit rates. | 11 | 1
PROJ-T100 | PROJ | Prepare the control estimate and budget | Excel / Word | DD | CST-03 | Re-base the approved estimate into the control budget by WBS and cost code for cost tracking. | 5 | 1
PROJ-T110 | PROJ | Build and baseline the integrated schedule in P6 | P6 | FEL2, FEL3, DD | PRJ-05 | Build the level 2/3 schedule linking engineering, procurement, construction and commissioning and set the baseline. | 8 | 3
PROJ-T120 | PROJ | Integrate procurement and vendor dates into the schedule | P6 | FEL3, DD, CON | PRJ-05 | Update P6 with PO award dates, vendor drawing return dates and forecast delivery dates from the Purchasing DB. | 4 | 1
PROJ-T130 | PROJ | Measure engineering progress | P6 | FEL3, DD | PRJ-05 | Collect deliverable progress by rules of credit, compute earned value and update P6. | 8 | 1
PROJ-T140 | PROJ | Update the schedule and analyse the critical path | P6 | FEL3, DD, CON, COM | PRJ-05 | Statusing, critical path and float analysis, look-ahead and recovery proposals. | 7 | 1
PROJ-T150 | PROJ | Track cost and forecast at completion | Excel / Word | DD, CON, COM | CST-03 | Track commitments, actuals and forecasts against the control budget and issue the cost report. | 6 | 1
PROJ-T160 | PROJ | Run change control: trends and change notices | Excel / Word | FEL3, DD, CON | PRJ-05 | Log trends raised by any discipline, estimate cost and schedule impact, and take change notices to approval. | 8 | 2
PROJ-T170 | PROJ | Prepare gate review packages and record gate decisions | Document Locator | FEL1, FEL2, FEL3 | SEL-01 | Assemble the deliverables, estimate, schedule and risk for each gate and record the owner's decision. | 12 | 2
PROJ-T180 | PROJ | Maintain the risk register and contingency analysis | Excel / Word | FEL1, FEL2, FEL3, DD, CON | PRJ-05 | Run risk workshops, maintain the register and run cost and schedule risk analysis to set contingency. | 10 | 2
PROJ-T190 | PROJ | Run interface management | Excel / Word | FEL3, DD, CON | PRJ-05 | Keep the interface register between disciplines, contractors, vendors and owner and chase interface agreements to closure. | 6 | 2
PROJ-T200 | PROJ | Issue documents by transmittal | Document Locator | FEL2, FEL3, DD, CON, COM | PRJ-03 | Check issued documents for numbering and metadata and transmit them to owner, vendors and construction per the distribution matrix. | 12 | 1
PROJ-T210 | PROJ | Run review cycles and consolidate comments | Document Locator | FEL2, FEL3, DD | PRJ-03 | Route documents for owner and inter-discipline review, collect and consolidate comments and return them with review status. | 6 | 2
PROJ-T220 | PROJ | Maintain the hold list | Excel / Word | DD, CON | PRJ-03 | Track holds on drawings and documents with their cause, owner and target release date. | 6 | 1
PROJ-T230 | PROJ | Track IFC issue and PE seal status | Document Locator | DD, CON | PRJ-04 | Confirm each document is checked, approved and sealed before IFC release and record the seal status. | 4 | 1
PROJ-T240 | PROJ | Prepare monthly progress reports | Excel / Word | FEL2, FEL3, DD, CON, COM | PRJ-05 | Compile progress, cost, schedule, change, risk, procurement and HSE status into the owner report. | 12 | 1
PROJ-T250 | PROJ | Load construction progress into P6 | P6 | CON, COM | CON-02 | Load installed quantities and CWP/IWP completion from the field into P6 for earned value. | 2 | 1
PROJ-T260 | PROJ | Compile the final records and close out | Document Locator | COM | PRJ-03 | Assemble as-built documents, vendor data books and the final records index for handover to the owner and close the project. | 15 | 2
PROC-T005 | PROC | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 2 | 2
PROC-T010 | PROC | Prepare process design basis | Excel / Word | FEL1, FEL2, FEL3 | PRJ-01 | Compile feed, product, capacity, on-stream factor, ambient and battery-limit conditions into the process design basis. | 7 | 2
PROC-T020 | PROC | Characterise feed and set up assay in simulation | HYSYS | FEL1, FEL2, FEL3 | PRJ-02 | Build the feed characterisation (assay cuts, pseudo-components, contaminants) and blend cases in the simulation. | 2 | 2
PROC-T030 | PROC | Run screening simulations and prepare BFDs and screening equipment list | HYSYS | FEL1, FEL2 | FEL-02 | Simulate candidate configurations at screening level and issue block flow diagrams and a sized major-equipment list per option. | 6 | 3
PROC-T060 | PROC | Develop and simulate FEL2 alternatives | HYSYS | FEL2 | SEL-01 | Simulate the shortlisted alternatives including heat integration and design/turndown cases. | 4 | 1
PROC-T070 | PROC | Evaluate technology and licensor process offers | Excel / Word | FEL2 | SEL-02 | Compare licensor/technology offers on yields, utilities, catalyst, guarantees and process risk. | 3 | 1
PROC-T080 | PROC | Prepare process input to select decision | Excel / Word | FEL2 | SEL-01 | Rank alternatives on process merit and document the recommended configuration. | 7 | 1
PROC-T090 | PROC | Define utility and offsite basis | Excel / Word | FEL2, FEL3 | SEL-03 | Define utility systems, supply conditions and offsite tankage/interconnection requirements. | 5 | 1
PROC-T095 | PROC | Define process layout requirements | Excel / Word | FEL2, FEL3 | LAY-01 | Set process requirements on layout: elevations for gravity flow and NPSH, adjacency, segregation and access for operation. | 4 | 1
PROC-T100 | PROC | Build and calibrate rigorous simulation | HYSYS | FEL2, FEL3, DD | PRC-00 | Build the rigorous unit model with column internals, exchangers and recycles, and calibrate to licensor or plant data. | 4 | 1
PROC-T110 | PROC | Prepare heat and material balance | HYSYS | FEL2, FEL3, DD | PRC-01 | Extract and issue stream data per design case from the simulation. | 2 | 3
PROC-T120 | PROC | Prepare process flow diagrams | Excel / Word | FEL2, FEL3, DD | PRC-06 | Draw PFDs with equipment, main control loops and stream numbers tied to the stream table. | 3 | 1
PROC-T130 | PROC | Set design pressures and temperatures | Excel / Word | FEL3, DD | PRC-02 | Build the pressure profile and set design and minimum design pressure/temperature per equipment and line system. | 7 | 1
PROC-T135 | PROC | Define corrosion basis and agree materials selection with Mechanical | Excel / Word | FEL2, FEL3, DD | PIP-01 | Process sets the corrosion basis (corrosive species, cases, upsets) and agrees the materials selection with Mechanical. | 2 | 1
PROC-T140 | PROC | Size vessels and columns | HYSYS | FEL2, FEL3, DD | PRC-02 | Size separators, drums and columns: diameter, height, nozzles, internals and hydraulics. | 4 | 1
PROC-T150 | PROC | Define rotating equipment process duties | Excel / Word | FEL2, FEL3, DD | PRC-02 | Calculate pump and compressor duties, differential head, NPSHa and operating range. | 4 | 1
PROC-T155 | PROC | Estimate exchanger duties and preliminary areas | HYSYS | FEL1, FEL2, FEL3 | PRC-02 | Preliminary exchanger duties, areas and pressure drops for screening and the equipment list; final thermal design is Mechanical's in HTRI. | 5 | 1
PROC-T160 | PROC | Prepare equipment list process data | Excel / Word | FEL2, FEL3, DD | PRC-02 | Issue the process data columns of the equipment list (duty, size, design conditions). | 7 | 1
PROC-T170 | PROC | Prepare static equipment process datasheets | Excel / Word | FEL3, DD | MEC-02 | Prepare process datasheets for vessels, columns, drums and tanks. | 5 | 2
PROC-T175 | PROC | Prepare heat transfer equipment process datasheets | Excel / Word | FEL3, DD | MEC-02 | Prepare process datasheets for shell-and-tube exchangers, air coolers, plate exchangers and fired heaters. | 3 | 3
PROC-T180 | PROC | Prepare rotating equipment process datasheets | Excel / Word | FEL3, DD | MEC-02 | Prepare process datasheets for pumps, compressors and blowers. | 2 | 2
PROC-T185 | PROC | Prepare package process specifications | Excel / Word | FEL3, DD | MEC-02 | Specify process duty and battery limits for packaged units (e.g. chemical injection, nitrogen, air, water treatment). | 4 | 1
PROC-T190 | PROC | Size lines and run hydraulics | Excel / Word | FEL3, DD | PRC-02 | Size process and utility lines and check pressure drop, velocity, two-phase regime and erosion. | 3 | 1
PROC-T200 | PROC | Develop P&IDs (process content) | SPID | FEL2, FEL3 | PRC-08 | Draw P&IDs in SPID with equipment, lines, valves, instruments and control from PFDs and sizing. | 13 | 2
PROC-T210 | PROC | Prepare line list and tie-in process data | SPID | FEL3, DD | PRC-08 | Enter line process data against P&ID lines for the line list and specify process conditions at each tie-in. | 7 | 2
PROC-T220 | PROC | Prepare instrument process data | Excel / Word | FEL3, DD | PRC-08 | Provide process conditions for each instrument and control valve tag for instrument sizing and datasheets. | 4 | 2
PROC-T230 | PROC | Prepare control and operating philosophy and control narratives | Excel / Word | FEL2, FEL3, DD | PRC-04 | Define operating modes, sparing and turndown, the control strategy, and write control narratives per unit section. | 6 | 3
PROC-T235 | PROC | Define trips, interlocks and process input to SIF | Excel / Word | FEL3, DD | PRC-04 | List trips and permissives with initiators, actions and set points as process input to C&E and LOPA. | 6 | 1
PROC-T250 | PROC | Calculate relief loads and size relief valves | Flare / relief tool | FEL3, DD | PRC-03 | Identify relief scenarios per device, calculate loads and size PSVs and rupture discs. | 7 | 2
PROC-T255 | PROC | Review vendor relief valve sizing | Excel / Word | FEL3, DD | PRC-03 | Check the vendor's orifice selection and rated capacity against every relief case and the inlet and back-pressure limits. | 2 | 1
PROC-T260 | PROC | Run flare and blowdown hydraulics | Flare / relief tool | FEL3, DD | SAF-02 | Model the flare network for governing scenarios and run depressuring/blowdown studies. | 7 | 3
PROC-T270 | PROC | Prepare utility, chemical and catalyst consumption lists and balances | Excel / Word | FEL2, FEL3, DD, COM | SEL-03 | Compile utility, chemical and catalyst consumption per consumer and balance each utility system for normal and peak cases. | 8 | 3
PROC-T280 | PROC | Prepare process input to environmental and safety studies | Excel / Word | FEL2, FEL3, DD | SEL-04 | Summarise effluents and emissions, and provide release-source fluid and inventory data for HAC, consequence modelling and QRA. | 7 | 2
PROC-T290 | PROC | Prepare process description and design report | Excel / Word | FEL2, FEL3 | PRC-07 | Write the process description and process design report summarising basis, cases and design decisions. | 6 | 1
PROC-T300 | PROC | Participate in HAZOP and close process actions | PHA tool | FEL3, DD | SAF-03 | Present P&IDs at HAZOP/LOPA, then respond to and close process-owned actions. | 5 | 2
PROC-T305 | PROC | Process input to technical bid evaluations | Excel / Word | FEL3, DD | PRO-01 | Check vendor offers against process datasheets and state process acceptability. | 5 | 1
PROC-T310 | PROC | Review vendor data against process duties | Document Locator | DD | VEN-01 | Review vendor drawings and data for process compliance and return comments. | 10 | 1
PROC-T315 | PROC | Reconcile simulation with certified vendor data | HYSYS | DD | PRC-00 | Rerun the model with certified equipment performance and update the H&MB and affected process data. | 5 | 1
PROC-T320 | PROC | Respond to technical queries, holds and change requests | Excel / Word | FEL3, DD, CON | PRC-08 | Answer process technical queries, release process holds and assess the process impact of change requests and deviations. | 9 | 2
PROC-T325 | PROC | Review instrument and control valve sizing | SI | FEL3, DD | ICS-04 | Review control valve, flow element and PSV sizing outputs against process data and controllability. | 4 | 1
PROC-T330 | PROC | Review 3D model and isometrics for process requirements | S3D | FEL3, DD | LAY-03 | Check model and critical isometrics for slopes, pockets, symmetry, elevations and process access. | 4 | 1
PROC-T340 | PROC | Update P&IDs to IFD and IFC | SPID | DD | PRC-08 | Incorporate HAZOP markups, vendor data and discipline comments and issue P&IDs IFD then IFC. | 11 | 2
PROC-T350 | PROC | Prepare operating manual process input | Excel / Word | DD, CON | PRC-07 | Write process sections of the operating manual: description, limits, control and safeguarding. | 5 | 1
PROC-T360 | PROC | Prepare process input to systemization and commissioning | Excel / Word | DD, CON, COM | PRC-07 | Mark process systems on P&IDs and define flushing, drying, purging, catalyst loading and initial fill requirements per system. | 6 | 2
PROC-T365 | PROC | Prepare start-up, shutdown and emergency procedures | Excel / Word | CON, COM | PRC-07 | Write initial start-up, normal start-up/shutdown and emergency shutdown procedures. | 5 | 1
PROC-T370 | PROC | Respond to field RFIs and review field changes | Procore | CON, COM | CON-01 | Answer process-related RFIs and assess field changes for process impact. | 2 | 1
PROC-T375 | PROC | Support commissioning, start-up and performance test | Excel / Word | COM | PRC-00 | Support commissioning and start-up at site, then define, run and evaluate the performance/guarantee test. | 8 | 2
PROC-T385 | PROC | Incorporate as-built redlines into P&IDs | SPID | COM | PRC-08 | Update P&IDs and line process data to as-built from field redlines and commissioning changes. | 4 | 1
SAFE-T010 | SAFE | Compile environmental baseline and site constraints | Excel / Word | FEL1, FEL2 | SEL-04 | Collect air attainment status, receiving waters, wetlands, endangered species, zoning, nearby receptors and existing permit limits for candidate sites. | 6 | 1
SAFE-T015 | SAFE | Screen configuration options for inherent safety and environmental impact | Excel / Word | FEL1, FEL2 | FEL-02 | Rank configuration and site options for inventory, toxic exposure, offsite consequence, emissions and permit risk. | 7 | 1
SAFE-T020 | SAFE | Facilitate concept HAZID and ENVID | PHA tool | FEL1, FEL2 | SAF-01 | Run HAZID/ENVID workshops on the selected concept and record hazards, safeguards and actions. | 7 | 2
SAFE-T030 | SAFE | Provide safety and environmental input to site selection | Excel / Word | FEL1 | FEL-03 | Evaluate candidate sites for separation from public receptors, flood/seismic exposure, permit difficulty and emergency access. | 6 | 1
SAFE-T035 | SAFE | Compile hazardous materials inventory and properties | Excel / Word | FEL2, FEL3 | PRJ-01 | List hazardous materials, inventories and flammability/toxicity properties by process area for studies, HAC and PSI. | 6 | 1
SAFE-T040 | SAFE | Prepare SHE design basis and risk criteria | Excel / Word | FEL2, FEL3 | PRJ-01 | Define applicable codes (OSHA PSM, EPA RMP, API 752/753/2218, NFPA), risk tolerance criteria, design accidental loads and study scope. | 6 | 2
SAFE-T050 | SAFE | Run preliminary consequence modelling for layout spacing | Excel / Word | FEL2 | SAF-04 | Model representative fire, explosion and toxic releases to set spacing, building locations and sterile zones on the plot plan. | 6 | 1
SAFE-T060 | SAFE | Develop emissions inventory | Excel / Word | FEL2, FEL3, DD | SEL-04 | Calculate potential-to-emit for each source (heaters, flares, tanks, fugitives, loading, cooling towers) to establish permit applicability. | 8 | 2
SAFE-T070 | SAFE | Prepare air permit application | Excel / Word | FEL3, DD | SEL-04 | Compile air construction permit (NSR/PSD or minor) application with dispersion modelling and BACT analysis. | 6 | 2
SAFE-T080 | SAFE | Prepare water, stormwater and spill permit data | Excel / Word | FEL3, DD | SEL-04 | Prepare NPDES/pretreatment data, construction and industrial stormwater basis, and SPCC containment requirements. | 5 | 2
SAFE-T090 | SAFE | Facilitate preliminary (coarse) HAZOP | PHA tool | FEL2, FEL3 | SAF-01 | Run a coarse HAZOP on PFDs and preliminary P&IDs to find major design changes before FEED freeze. | 7 | 1
SAFE-T100 | SAFE | Perform facility siting study (API RP 752/753) | Excel / Word | FEL3, DD | SAF-04 | Assess explosion, fire and toxic hazards to occupied permanent and portable buildings and set building design loads. | 8 | 3
SAFE-T110 | SAFE | Assess toxic gas ingress and shelter-in-place | Excel / Word | FEL3, DD | SAF-04 | Evaluate toxic and smoke ingress to occupied buildings and set HVAC shutdown, gas detection at intakes and shelter-in-place requirements. | 4 | 1
SAFE-T120 | SAFE | Perform quantitative risk assessment | Excel / Word | FEL3, DD | SAF-04 | Calculate individual and societal risk from leak frequencies and consequences and compare to criteria. | 10 | 2
SAFE-T130 | SAFE | Check flare radiation, noise and dispersion | Flare / relief tool | FEL3, DD | SAF-02 | Verify flare stack height and sterile radius for radiation, flame-out dispersion and noise against personnel and equipment limits. | 4 | 1
SAFE-T140 | SAFE | Review relief and depressuring scenarios | Excel / Word | FEL3, DD | PRC-03 | Check that relief and blowdown scenarios cover HAZOP causes and fire zones and comment on the relief study. | 5 | 1
SAFE-T150 | SAFE | Facilitate formal HAZOP | PHA tool | FEL3, DD | SAF-03 | Organize, facilitate and record the node-by-node HAZOP of IFH P&IDs with all disciplines and operations. | 11 | 2
SAFE-T160 | SAFE | Run LOPA and set SIL targets | PHA tool | FEL3, DD | ICS-02 | Analyse HAZOP high-consequence scenarios with LOPA, credit IPLs and assign required SIL to each SIF. | 4 | 2
SAFE-T170 | SAFE | Track and close out PHA and study actions | PHA tool | FEL3, DD, CON | SAF-03 | Track HAZID, HAZOP, LOPA, siting and QRA actions to closure with documented discipline responses. | 6 | 1
SAFE-T180 | SAFE | Perform fire and gas detector mapping | Excel / Word | FEL3, DD | SAF-04 | Place flame, gas, H2S and heat detectors and verify geographic/scenario coverage against targets. | 5 | 2
SAFE-T210 | SAFE | Specify emergency isolation valve requirements | Excel / Word | FEL3, DD | SAF-04 | Identify where remotely operated emergency isolation valves are needed and set fire-safe and closure requirements. | 4 | 1
SAFE-T230 | SAFE | Lay out safety equipment and escape routes | Excel / Word | FEL3, DD | LAY-01 | Locate safety showers, eyewashes, escape routes, muster points, windsocks and second means of egress. | 4 | 1
SAFE-T240 | SAFE | Perform noise study | Excel / Word | FEL3, DD | SEL-04 | Set equipment noise limits and model plant and fence-line noise against occupational and community limits. | 7 | 2
SAFE-T250 | SAFE | Review plot plan and 3D model for safety | S3D | FEL2, FEL3, DD | LAY-03 | Participate in model reviews checking spacing, escape, access for firefighting, safety equipment and siting conformance. | 5 | 1
SAFE-T255 | SAFE | Review hazardous area classification | Excel / Word | FEL3, DD | ELE-02 | Check hazardous area classification against release sources, gas groups and ventilation assumptions. | 3 | 1
SAFE-T260 | SAFE | Review cause and effect and SIL verification | Excel / Word | DD | ICS-08 | Check C&E charts and SIL verification against LOPA targets, F&G executive actions and HAZOP recommendations. | 7 | 1
SAFE-T270 | SAFE | Review vendor packages and bids for SHE compliance | Excel / Word | FEL3, DD | PRO-01 | Review technical bids and vendor data for noise, emissions guarantees, fire-safe valves, safety devices and package HAZOP needs. | 4 | 1
SAFE-T280 | SAFE | Facilitate vendor package and design change HAZOPs | PHA tool | DD, CON | SAF-03 | Run HAZOPs on vendor package P&IDs and HAZOP revalidation of design changes since the main HAZOP. | 6 | 1
SAFE-T290 | SAFE | Compile process safety information for PSM | Document Locator | DD, CON, COM | SAF-03 | Assemble OSHA 1910.119 process safety information and PHA records for handover to the owner PSM program. | 14 | 1
SAFE-T300 | SAFE | Prepare RMP hazard assessment and registration data | Excel / Word | DD, CON | SEL-04 | Model worst-case and alternative release scenarios and prepare EPA RMP registration and program data. | 6 | 1
SAFE-T310 | SAFE | Provide emergency response planning input | Excel / Word | DD, CON, COM | SAF-04 | Provide scenarios, zones, alarms, muster and fire response resources for the owner emergency response plan. | 5 | 1
SAFE-T320 | SAFE | Prepare construction environmental compliance plan | Excel / Word | CON | SEL-04 | Translate permit conditions into construction requirements for stormwater, dust, waste, spill and notifications. | 6 | 1
SAFE-T330 | SAFE | Perform MOC safety reviews of field and design changes | Procore | DD, CON, COM | SAF-03 | Screen field changes and RFIs for process safety impact and decide whether HAZOP revalidation, siting or PSI updates are needed. | 5 | 1
SAFE-T340 | SAFE | Lead pre-startup safety review (PSSR) | Smart Completions | COM | SAF-03 | Verify construction matches design, PHA actions are closed, procedures and training are in place and systems are safe to start. | 9 | 2
SAFE-T350 | SAFE | Set up environmental startup compliance | Excel / Word | COM | SEL-04 | Prepare startup notifications, initial performance tests, CEMS certification and LDAR component inventory. | 5 | 1
SAFE-T360 | SAFE | Update safety studies to as-built and hand over | Excel / Word | COM | SAF-04 | Revise siting, F&G mapping, QRA and fire protection studies to as-built condition for the owner PSM records. | 8 | 1
FIRE-T045 | FIRE | Prepare fire protection and F&G philosophy | Excel / Word | FEL2, FEL3 | SAF-04 | Set the strategy for active and passive fire protection, fire water, F&G detection, voting and executive actions. | 5 | 1
FIRE-T190 | FIRE | Calculate fire water demand | Excel / Word | FEL3, DD | SAF-04 | Size fire water demand for the largest credible fire scenario and set pump capacity, storage and network requirements. | 6 | 2
FIRE-T200 | FIRE | Define fire scenario envelopes and fireproofing zones | Excel / Word | FEL3, DD | SAF-04 | Define fire-potential envelopes (API 2218) and list structures, supports, cables and valves requiring fireproofing. | 7 | 2
FIRE-T220 | FIRE | Specify fixed fire protection systems | Excel / Word | FEL3, DD | SAF-04 | Define deluge, water spray, foam, clean agent and portable extinguisher requirements by area per NFPA. | 7 | 1
FIRE-T230 | FIRE | Prepare fire pump and fire protection equipment datasheets and requisitions | Excel / Word | FEL3, DD | PRO-01 | Fire protection specifies the fire pumps and drivers, deluge and foam skids, monitors and hydrants, and issues the requisitions. | 4 | 2
FIRE-T240 | FIRE | Review fire protection vendor data | Document Locator | DD | VEN-01 | Review fire pump, skid and fire equipment vendor drawings and data, and accept certified data. | 2 | 1
MECH-T005 | MECH | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 3 | 3
MECH-T010 | MECH | Prepare mechanical input to FEL 1 equipment list and configuration screening | Excel / Word | FEL1 | FEL-02 | Assigns equipment types, rough sizes, materials and weights to the block-level equipment list for each configuration option. | 6 | 2
MECH-T020 | MECH | Develop mechanical design basis | Excel / Word | FEL2 | PRJ-01 | Defines codes, design margins, corrosion allowances, sparing, driver and equipment standardisation rules for mechanical design. | 7 | 1
MECH-T030 | MECH | Select equipment materials and corrosion allowances with Process | Excel / Word | FEL2, FEL3 | MEC-01 | Mechanical and Process jointly select materials and corrosion allowances from the corrosion basis; Mechanical issues the result. | 5 | 1
MECH-T040 | MECH | Define rotating equipment sparing and driver selection | Excel / Word | FEL2, FEL3 | MEC-02 | Sets the installed spare, driver type (motor, steam turbine, engine) and speed control for each rotating machine. | 5 | 1
MECH-T050 | MECH | Obtain budget quotations and equipment cost data | Excel / Word | FEL2, FEL3 | VEN-01 | Issues budget enquiries for major and long-lead equipment and compiles equipment cost, weight and delivery data for estimates. | 4 | 2
MECH-T060 | MECH | Maintain mechanical equipment list | Excel / Word | FEL2, FEL3, DD | MEC-02 | Keeps the master mechanical attributes for every equipment tag current through design and procurement. | 10 | 1
MECH-T070 | MECH | Perform shell-and-tube exchanger thermal and hydraulic design | HTRI | FEL3, DD | PRC-02 | Rates or designs shell-and-tube exchangers to fix TEMA type, geometry, area and pressure drops. | 5 | 1
MECH-T080 | MECH | Perform air-cooled exchanger thermal design | HTRI | FEL3, DD | PRC-02 | Sizes air coolers for bays, bundles, fans and fan power at design ambient conditions. | 5 | 1
MECH-T090 | MECH | Design and specify fired heaters | Excel / Word | FEL3, DD | MEC-02 | Defines fired heater configuration, coil, burners, stack and combustion air system and prepares the API 560 datasheet. | 5 | 2
MECH-T100 | MECH | Perform vessel and column mechanical design calculations | Mechanical calc tool | FEL3, DD | MEC-01 | Calculates wall thicknesses, heads, nozzle reinforcement, skirt/saddle, wind and seismic loads and weights for pressure vessels and columns. | 5 | 1
MECH-T110 | MECH | Specify column and vessel internals | Excel / Word | FEL3, DD | MEC-02 | Prepares tray, packing, distributor, demister and other internals specifications and support ring/manway requirements. | 3 | 1
MECH-T120 | MECH | Design storage tanks | Mechanical calc tool | FEL3, DD | MEC-01 | Designs atmospheric and low-pressure storage tanks for shell courses, roof, seals, venting and foundation loads. | 5 | 2
MECH-T130 | MECH | Prepare mechanical datasheets for vessels and columns | Excel / Word | FEL3, DD | MEC-02 | Issues mechanical datasheets with sketches for pressure vessels, drums and columns. | 4 | 1
MECH-T140 | MECH | Prepare mechanical datasheets for exchangers | Excel / Word | FEL3, DD | MEC-02 | Issues TEMA shell-and-tube and API 661 air-cooled exchanger datasheets from thermal designs. | 4 | 2
MECH-T150 | MECH | Prepare rotating equipment datasheets | Excel / Word | FEL3, DD | MEC-02 | Issues API datasheets for pumps, compressors, blowers and their drivers. | 7 | 2
MECH-T160 | MECH | Prepare package specifications and scope split | Excel / Word | FEL3, DD | MEC-02 | Defines scope of supply, battery limits, utility demands and interface requirements for packaged units. | 7 | 2
MECH-T170 | MECH | Select seal, flush and lube oil systems | Excel / Word | FEL3, DD | MEC-02 | Selects API 682 seal plans and API 614 lube/seal oil systems and defines their piping and instrumentation for P&IDs. | 6 | 1
MECH-T180 | MECH | Provide mechanical input to P&IDs and HAZOP | SPID | FEL3, DD | PRC-08 | Marks up P&IDs with equipment vents, drains, seal and lube systems and package boundaries, and closes mechanical HAZOP actions. | 6 | 2
MECH-T190 | MECH | Prepare nozzle orientations and allowable nozzle loads | Excel / Word | FEL3, DD | MEC-03 | Develops nozzle orientation drawings with layout and issues allowable nozzle loads for piping stress. | 5 | 3
MECH-T200 | MECH | Prepare equipment outline drawings, footprints and maintenance envelopes | Excel / Word | FEL2, FEL3, DD | MEC-03 | Produces equipment outline dimensions, footprints and maintenance and removal envelopes for layout and modelling. | 5 | 2
MECH-T210 | MECH | Compile equipment weights and foundation loads | Excel / Word | FEL3, DD | MEC-01 | Issues equipment weights and foundation loading data to civil and structural for foundations and structures. | 6 | 1
MECH-T220 | MECH | Prepare equipment lifting data | Excel / Word | DD, CON | MEC-01 | Defines lifting weights, centres of gravity and lifting lug/trunnion design for heavy and critical lifts. | 4 | 1
MECH-T230 | MECH | Issue motor and driver electrical data | Excel / Word | FEL3, DD | ELE-01 | Provides rated motor power, voltage, starting method and VFD requirements per driven machine to electrical. | 5 | 1
MECH-T240 | MECH | Prepare mechanical technical specifications | Excel / Word | FEL3, DD | MEC-02 | Writes project specifications for pressure vessels, exchangers, tanks, heaters, pumps, compressors and packages, including inspection and NDE requirements. | 4 | 1
MECH-T250 | MECH | Prepare requisition technical packages for bid | Excel / Word | FEL3, DD | PRO-01 | Assembles datasheets, specifications, VDRL and scope into requisitions for enquiry and records open holds. | 17 | 3
MECH-T260 | MECH | Issue technical queries and clarifications to bidders | Excel / Word | FEL3, DD | PRO-01 | Reviews bids for technical compliance and issues technical queries and resolves deviations with bidders. | 4 | 1
MECH-T270 | MECH | Prepare technical bid evaluations | Excel / Word | FEL3, DD | PRO-01 | Evaluates bids against the requisition and recommends technically acceptable bidders. | 7 | 1
MECH-T280 | MECH | Prepare requisitions for purchase | Excel / Word | FEL3, DD | PRO-01 | Conforms the requisition to the selected bidder's clarified offer for placement of the purchase order. | 4 | 1
MECH-T290 | MECH | Hold vendor kick-off meetings | Excel / Word | DD | VEN-01 | Confirms scope, data schedule, interfaces and open holds with the vendor after purchase order award. | 5 | 1
MECH-T300 | MECH | Review vendor drawings and data | Document Locator | DD, CON | VEN-01 | Reviews and coordinates interdisciplinary comments on vendor drawings, calculations and documents and returns coded comments. | 14 | 1
MECH-T310 | MECH | Release certified vendor data to other disciplines | Document Locator | DD | VEN-01 | Releases certified vendor data to piping, civil, electrical and I&C for final design once vendor documents are certified. | 4 | 4
MECH-T320 | MECH | Close requisition holds | Excel / Word | DD | PRO-01 | Tracks and closes holds on requisitions and vendor data as design data matures. | 4 | 1
MECH-T330 | MECH | Check piping loads against equipment nozzle allowables | Excel / Word | DD | PIP-05 | Checks calculated piping loads against vendor or code allowables and agrees acceptance or vendor confirmation. | 3 | 1
MECH-T340 | MECH | Review rotordynamic, torsional and pulsation studies | Excel / Word | DD | MEC-01 | Reviews vendor lateral, torsional and acoustic/pulsation studies for compressors and critical pumps. | 3 | 1
MECH-T350 | MECH | Review and approve inspection and test plans | Document Locator | DD | VEN-01 | Reviews vendor ITPs and sets witness and hold points and test requirements. | 2 | 1
MECH-T360 | MECH | Witness shop tests and factory acceptance tests | Excel / Word | DD | VEN-01 | Witnesses performance tests, mechanical run tests, hydrotests and FATs and releases equipment for shipment. | 4 | 1
MECH-T370 | MECH | Review spare parts recommendations | Excel / Word | DD | VEN-01 | Reviews vendor spare parts interchangeability records for commissioning, start-up and operating spares. | 2 | 1
MECH-T380 | MECH | Review manufacturer's data books | Document Locator | DD, CON | VEN-01 | Reviews final vendor data books, certificates, code stamps and manuals for completeness. | 4 | 1
MECH-T390 | MECH | Define equipment preservation and storage requirements | Excel / Word | DD, CON | MEC-02 | Specifies site storage and preservation requirements for mechanical equipment from receipt to commissioning. | 3 | 1
MECH-T400 | MECH | Review 3D model for equipment access and maintenance | S3D | FEL3, DD | LAY-03 | Checks equipment placement, nozzle connections, access and removal envelopes in 3D model reviews. | 4 | 1
MECH-T410 | MECH | Respond to field RFIs and equipment issues | Procore | CON, COM | CON-01 | Answers construction RFIs, non-conformances and field changes involving mechanical equipment. | 3 | 1
MECH-T420 | MECH | Coordinate vendor site representatives | Excel / Word | CON, COM | VEN-01 | Plans and coordinates vendor specialist attendance for installation, alignment, internals and start-up. | 6 | 1
MECH-T430 | MECH | Provide mechanical completion and pre-commissioning input | Smart Completions | CON, COM | CON-02 | Defines equipment check sheets, internals box-up, alignment and run-in requirements and supports MC walkdowns and punch. | 5 | 2
MECH-T440 | MECH | Issue as-built equipment data for handover | Excel / Word | COM | PRJ-04 | Updates equipment datasheets and the equipment register to as-built and certified data for owner handover. | 5 | 1
PIPE-T005 | PIPE | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 3 | 3
PIPE-T010 | PIPE | Prepare block plot plan options | Excel / Word | FEL1 | FEL-02 | Lays out alternative block plot arrangements for the unit, offsites and tankage on the candidate site for configuration screening. | 8 | 1
PIPE-T020 | PIPE | Estimate piping quantities for FEL1 estimate | Excel / Word | FEL1 | FEL-04 | Factors piping tonnage, bulk quantities and interconnecting run lengths per option for the Class 5 estimate. | 3 | 1
PIPE-T030 | PIPE | Write piping layout design basis | Excel / Word | FEL2, FEL3 | PRJ-01 | Sets the layout, spacing, access, maintenance, rack and model rules (elevations, clearances, valve access, naming) for the project. | 7 | 1
PIPE-T040 | PIPE | Develop plot plan and equipment layout | S3D | FEL2, FEL3, DD | LAY-01 | Develops the selected plot plan with equipment locations, rack corridors, roads and maintenance areas and issues it for review and HAZOP. | 14 | 2
PIPE-T050 | PIPE | Build 3D layout model | S3D | FEL2, FEL3 | LAY-02 | Builds the early S3D model with equipment envelopes, structures, rack and access space for layout reviews. | 5 | 1
PIPE-T060 | PIPE | Lay out pipe racks and assign tiers | S3D | FEL2, FEL3, DD | LAY-02 | Sizes main pipe rack widths and tiers, allocates lines and cable tray space, and estimates rack loads for civil. | 7 | 2
PIPE-T070 | PIPE | Study critical line routing | S3D | FEL3 | PIP-02 | Routes large-bore, alloy, two-phase, transfer and pump suction lines in the model to confirm layout and early stress feasibility. | 5 | 1
PIPE-T080 | PIPE | Request equipment nozzle orientations and elevations | S3D | FEL3, DD | LAY-01 | Defines required nozzle orientations, elevations, platform and davit positions from routing and returns them to mechanical and vendors. | 5 | 1
PIPE-T090 | PIPE | Develop piping material classes | Excel / Word | FEL2, FEL3, DD | PIP-01 | Writes piping classes by service with pressure-temperature ratings, components, branch tables and wall thickness calculations. | 6 | 1
PIPE-T100 | PIPE | Build S3D piping specification catalogue | S3D | FEL3, DD | PIP-01 | Loads piping classes, commodity codes and valve codes into the S3D catalogue for routing, isometrics and MTO. | 2 | 1
PIPE-T110 | PIPE | Prepare valve specifications and datasheets | Excel / Word | FEL3, DD | PIP-01 | Writes valve datasheets by valve code covering type, rating, materials, trim, end connection and testing. | 3 | 1
PIPE-T120 | PIPE | Prepare specialty item list and datasheets | Excel / Word | FEL3, DD | PIP-01 | Lists and specifies special piping items (strainers, spectacle blinds, hoses, sight glasses, expansion joints, steam traps). | 3 | 1
PIPE-T130 | PIPE | Prepare piping fabrication, erection and inspection specifications | Excel / Word | FEL3, DD | PIP-01 | Specifies fabrication, welding, NDE extent, PWHT, testing, cleaning and painting requirements for shop and field piping. | 4 | 1
PIPE-T140 | PIPE | Add piping data to the line list | Excel / Word | FEL3, DD | PRC-08 | Adds piping class, test pressure and medium, NDE category, PWHT, paint and insulation systems to each line in the line list. | 3 | 1
PIPE-T150 | PIPE | Prepare FEL3 piping MTO for the estimate | S3D | FEL2, FEL3 | CST-02 | Combines model-based quantities for routed areas with factored quantities for the rest into a bulk piping MTO for the estimate and early buys. | 6 | 1
PIPE-T160 | PIPE | Route piping in the 3D model | S3D | FEL3, DD | PIP-02 | Routes all lines to the P&IDs in S3D using the piping catalogue, placing valves, SP items and in-line instruments. | 14 | 1
PIPE-T170 | PIPE | Check model against P&IDs | SPF | DD | PIP-02 | Runs the SPID to S3D correlation through SPF and resolves differences in line numbers, sizes, specs and components. | 3 | 1
PIPE-T180 | PIPE | Position in-line instruments and instrument access | S3D | DD | ICS-09 | Places in-line and line-mounted instruments with straight runs, orientation and access, and issues positions to I&C. | 4 | 1
PIPE-T190 | PIPE | Issue as-routed line data for hydraulic checks | S3D | DD | PRC-03 | Extracts as-routed lengths, fittings and elevations for PSV inlet/outlet, pump suction and two-phase lines to process for hydraulic verification. | 3 | 1
PIPE-T200 | PIPE | Prepare stress-critical line list | Excel / Word | FEL3, DD | PIP-03 | Categorises lines for stress analysis by size, temperature, service and connected equipment. | 5 | 1
PIPE-T210 | PIPE | Perform screening stress analysis | CAESAR II | FEL3 | PIP-03 | Runs simplified and screening analyses on critical lines to confirm loops, layout and anchor concepts. | 3 | 1
PIPE-T220 | PIPE | Perform detailed stress analysis in CAESAR II | CAESAR II | DD | PIP-05 | Analyses stress-critical lines exported from S3D for sustained, thermal, occasional and test cases and sets supports. | 14 | 4
PIPE-T230 | PIPE | Resolve nozzle loads with mechanical and vendors | Excel / Word | DD | PIP-05 | Agrees exceeded nozzle loads with mechanical and vendors by re-routing, re-supporting or vendor acceptance. | 3 | 1
PIPE-T240 | PIPE | Specify and requisition spring and engineered supports | Excel / Word | DD | PRO-01 | Prepares the spring hanger and engineered support datasheet and requisition and reviews vendor data. | 4 | 1
PIPE-T250 | PIPE | Design pipe supports | S3D | DD | PIP-05 | Places standard and special supports in S3D and details special supports, trunnions and secondary steel requirements. | 5 | 2
PIPE-T260 | PIPE | Request civil and structural openings, platforms and foundations | S3D | FEL3, DD | LAY-02 | Issues piping requirements for platforms, access, sleepers, trenches, culverts, wall and floor penetrations to civil. | 3 | 1
PIPE-T270 | PIPE | Design underground piping | S3D | DD | PIP-02 | Lays out underground firewater, oily water and process drains and buried lines and coordinates with civil drainage and foundations. | 11 | 1
PIPE-T280 | PIPE | Run 30/60/90 model reviews | iConstruct | FEL3, DD | LAY-03 | Prepares model review packages and runs reviews with operations, safety, construction and all disciplines, tracking actions to close. | 13 | 2
PIPE-T290 | PIPE | Detect and resolve clashes | S3D | DD | LAY-03 | Runs interference checks across piping, structural, electrical and instrument models and resolves hard and soft clashes. | 6 | 1
PIPE-T300 | PIPE | Respond to HAZOP and safety layout actions | S3D | FEL3, DD | SAF-03 | Implements and closes HAZOP, siting and fire and gas actions that need layout or piping changes. | 6 | 1
PIPE-T310 | PIPE | Incorporate vendor data and manage piping holds | S3D | DD | VEN-01 | Updates the model with certified vendor nozzle and package data and maintains the piping hold list. | 5 | 2
PIPE-T320 | PIPE | Extract and check isometrics | S3D | DD | PIP-04 | Extracts isometrics from S3D, checks them and issues IFC isometrics with bill of materials and weld data. | 7 | 1
PIPE-T330 | PIPE | Prepare spool lists and fabrication packages | S3D | DD | PIP-04 | Splits isometrics into shop spools and field welds and issues spool lists and fabrication packages to the fabricator. | 3 | 1
PIPE-T340 | PIPE | Produce MTO by ident and bulk requisitions | S3D | FEL3, DD | PIP-04 | Exports MTO by commodity ident from S3D, applies surplus and reconciles against prior buys, and issues bulk requisitions. | 8 | 2
PIPE-T350 | PIPE | Evaluate piping bids | Excel / Word | DD | PRO-01 | Evaluates technical offers for bulk piping, valves and specialty items against requisitions. | 3 | 1
PIPE-T360 | PIPE | Review valve and specialty item vendor data | Document Locator | DD, CON | VEN-01 | Reviews vendor drawings, test certificates and data books for valves and specialty items. | 4 | 1
PIPE-T370 | PIPE | Produce piping GA and key plan drawings | S3D | DD | LAY-02 | Extracts piping general arrangement drawings, sections and key plans from S3D for construction and review. | 3 | 1
PIPE-T380 | PIPE | Identify tie-ins and issue tie-in packages | Excel / Word | FEL3, DD, CON | PIP-02 | Surveys existing connections, lists tie-ins with type and timing, and issues tie-in sketches and packages. | 5 | 2
PIPE-T390 | PIPE | Define hydrotest and test pack boundaries | Excel / Word | DD, CON | CON-02 | Defines test circuits by test pressure and medium aligned to systems and issues test pack boundaries. | 7 | 2
PIPE-T400 | PIPE | Issue model to AWP and construction model | iConstruct | DD, CON | CON-02 | Publishes the piping model through Navisworks to iConstruct with iso, spool and CWP attributes for work packaging. | 6 | 1
PIPE-T410 | PIPE | Review fabricator spool drawings | Document Locator | CON | PIP-04 | Reviews fabricator spool drawings and weld maps against IFC isometrics. | 2 | 1
PIPE-T420 | PIPE | Respond to piping RFIs and field changes | Procore | CON, COM | CON-01 | Answers site RFIs and issues field change isos and model updates for piping. | 5 | 2
PIPE-T430 | PIPE | Reconcile piping material shortages and surplus | Jovix | CON | PIP-04 | Reconciles MTO with received and issued materials and raises supplementary requisitions for shortages. | 5 | 1
PIPE-T440 | PIPE | Prepare as-built isometrics and model | S3D | CON, COM | PIP-04 | Incorporates field redlines into isometrics and the model and issues as-built records for handover. | 5 | 2
CIVL-T005 | CIVL | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 2 | 3
CIVL-T010 | CIVL | Assess candidate sites for civil constraints | Excel / Word | FEL1 | FEL-03 | Screens candidate sites for topography, flood risk, soil conditions, access, existing underground and earthworks cost drivers. | 6 | 1
CIVL-T020 | CIVL | Prepare civil and structural design basis | Excel / Word | FEL2, FEL3 | PRJ-01 | Sets the codes, site environmental loads, load combinations, materials and design criteria for all civil, structural, building and HVAC design. | 6 | 2
CIVL-T030 | CIVL | Specify and manage the topographic survey | Excel / Word | FEL2, FEL3 | CIV-01 | Scopes the topographic and existing-utilities survey, sets the plant coordinate grid and benchmarks and checks the survey contractor's deliverables. | 3 | 1
CIVL-T040 | CIVL | Specify the geotechnical investigation | Excel / Word | FEL2, FEL3 | CIV-01 | Defines borehole and CPT locations, depths, in-situ and laboratory tests and the geotechnical contractor scope. | 4 | 2
CIVL-T050 | CIVL | Set foundation design parameters from the geotechnical report | Excel / Word | FEL3, DD | CIV-01 | Reviews the geotechnical report and sets design soil parameters and foundation type by plant area. | 2 | 2
CIVL-T060 | CIVL | Prepare civil and structural quantities for estimates | Excel / Word | FEL1, FEL2, FEL3, DD | CST-02 | Builds factored and then take-off quantities for earthworks, piling, concrete, rebar, steel, paving and buildings for each estimate class and the control estimate. | 10 | 1
CIVL-T070 | CIVL | Review plot plan for civil constraints | Excel / Word | FEL1, FEL2, FEL3 | LAY-01 | Reviews plot plan revisions for grading falls, drainage, road access, crane access, foundation clashes and building locations and returns comments. | 6 | 1
CIVL-T080 | CIVL | Size pipe racks and process structures conceptually | Excel / Word | FEL2, FEL3 | CIV-01 | Sets rack widths, bent spacing, tier elevations and structure frames and estimates steel tonnage and load allowances. | 8 | 2
CIVL-T090 | CIVL | Design site preparation and earthworks | Excel / Word | FEL3, DD | CIV-01 | Designs clearing, demolition, cut and fill, soil improvement and temporary drainage for the site. | 5 | 1
CIVL-T100 | CIVL | Prepare grading plan and finished elevations | Excel / Word | FEL3, DD | CIV-01 | Sets high point of finished grade, paving areas, curbs and area falls and issues finished elevations to layout and piping. | 6 | 2
CIVL-T110 | CIVL | Design surface drainage and sewers | Excel / Word | FEL3, DD | CIV-01 | Classifies drainage areas and sizes storm, oily water and accidentally contaminated sewers, catch basins, seals and manholes. | 9 | 2
CIVL-T120 | CIVL | Design tank dikes and containment | Excel / Word | FEL3, DD | CIV-01 | Sizes bunds and dikes for tank and equipment containment, intermediate walls, impounding basins and dike drains. | 5 | 1
CIVL-T130 | CIVL | Design roads, access and fencing | Excel / Word | FEL3, DD | CIV-01 | Designs plant roads, emergency and maintenance access, crane pads, fencing and gates. | 8 | 1
CIVL-T140 | CIVL | Coordinate underground services and prepare composite | Excel / Word | DD, CON | CIV-01 | Combines sewers, firewater mains, underground piping, duct banks, grounding grid and foundations in one composite and resolves conflicts. | 9 | 2
CIVL-T150 | CIVL | Design static equipment foundations | Excel / Word | FEL3, DD | CIV-01 | Designs foundations for columns, vessels, exchangers, air cooler supports and heaters from vendor loads. | 8 | 1
CIVL-T160 | CIVL | Design rotating equipment foundations with dynamic analysis | Excel / Word | DD | CIV-01 | Designs pump, compressor and blower foundations and checks natural frequency and vibration amplitude. | 6 | 2
CIVL-T170 | CIVL | Design tank foundations | Excel / Word | FEL3, DD | CIV-01 | Designs ringwall or slab tank foundations and predicts settlement for hydrotest and operation. | 4 | 1
CIVL-T180 | CIVL | Design piles and prepare piling layout | Excel / Word | FEL3, DD | CIV-02 | Selects pile type, designs pile groups and issues the piling layout and test pile programme. | 8 | 2
CIVL-T190 | CIVL | Prepare foundation plans and anchor bolt layouts | Excel / Word | DD | CIV-02 | Issues foundation location plans, foundation details, anchor bolt setting plans and embedment details for construction. | 10 | 2
CIVL-T200 | CIVL | Analyse and design pipe racks | Excel / Word | FEL3, DD | CIV-01 | Analyses rack frames for pipe, cable, air cooler, wind and seismic loads and sizes members and bracing (in the structural analysis program). | 9 | 1
CIVL-T210 | CIVL | Analyse and design process structures and platforms | Excel / Word | FEL3, DD | CIV-01 | Designs equipment structures, shelters, platforms, stairs and ladders including vessel-mounted platforms coordination. | 10 | 1
CIVL-T220 | CIVL | Model structures in Tekla and share reference models | Tekla | FEL3, DD, CON | CIV-02 | Builds the steel and concrete model in Tekla and exports reference models to S3D and to iConstruct through Navisworks. | 6 | 3
CIVL-T230 | CIVL | Prepare steel GA drawings and connection design data | Tekla | DD | CIV-02 | Issues steel GA and erection drawings and connection design criteria for the fabricator. | 3 | 2
CIVL-T240 | CIVL | Prepare structural steel MTO | Tekla | FEL3, DD | CIV-02 | Extracts steel quantities by profile, grade and coating from Tekla for purchasing and fabrication packages. | 1 | 1
CIVL-T250 | CIVL | Coordinate embedments, sleeves and penetrations | Excel / Word | DD | CIV-02 | Collects and schedules embedded plates, sleeves, conduit stub-ups, floor openings and wall penetrations requested by other disciplines. | 9 | 1
CIVL-T260 | CIVL | Define structural fireproofing extent | Excel / Word | DD | CIV-02 | Identifies structural members and supports needing fireproofing within fire scenario envelopes and specifies rating and type. | 4 | 1
CIVL-T270 | CIVL | Develop building space programme and layouts | Excel / Word | FEL2, FEL3, DD | CIV-01 | Develops layouts for the control room, substations, rack rooms, analyzer shelters and other buildings with room sizes and openings. | 9 | 1
CIVL-T280 | CIVL | Design blast-resistant and other buildings structurally | Excel / Word | FEL3, DD | CIV-01 | Designs building structures for blast, wind and seismic loads and selects pre-engineered or blast-resistant module options. | 6 | 1
CIVL-T290 | CIVL | Prepare architectural drawings | Excel / Word | DD | CIV-01 | Issues building plans, elevations, sections, finishes, door and window schedules and fire ratings. | 6 | 1
CIVL-T300 | CIVL | Design building HVAC | Excel / Word | FEL3, DD | CIV-01 | Calculates heat loads and sizes HVAC, pressurisation and smoke/gas protection for control buildings and substations. | 9 | 4
CIVL-T310 | CIVL | Prepare civil and structural requisitions and bid evaluations | Purchasing DB | FEL3, DD | PRO-01 | Prepares technical scopes and evaluates bids for piling, civil works, steel fabrication, buildings and HVAC. | 10 | 1
CIVL-T320 | CIVL | Review vendor and fabricator drawings | Document Locator | DD, CON | VEN-01 | Reviews equipment vendor load and anchor data, steel shop drawings, building and HVAC vendor drawings and returns comments. | 5 | 1
CIVL-T330 | CIVL | Take part in 3D model reviews and clash resolution | iConstruct | FEL3, DD | LAY-03 | Reviews the combined S3D and Tekla model at 30/60/90 percent reviews and resolves structural clashes and access issues. | 5 | 1
CIVL-T340 | CIVL | Provide civil inputs to construction packaging | iConstruct | FEL3, DD | CON-02 | Defines civil and steel CWP boundaries, pour and erection sequence and early works priority with construction. | 6 | 1
CIVL-T350 | CIVL | Check, seal and issue civil and structural IFC packages | Document Locator | DD | PRJ-04 | Checks and PE-seals foundation, steel, underground, building and HVAC drawings and issues IFC packages. | 9 | 1
CIVL-T360 | CIVL | Answer RFIs and disposition field changes and NCRs | Procore | CON | CIV-02 | Answers civil and structural RFIs, approves field changes and dispositions concrete, piling and steel non-conformances. | 5 | 2
CIVL-T370 | CIVL | Evaluate settlement monitoring during hydrotest | Excel / Word | CON, COM | CIV-01 | Evaluates foundation and tank settlement readings during hydrotest and confirms acceptance. | 3 | 1
CIVL-T380 | CIVL | Incorporate as-built civil and structural changes | Tekla | CON, COM | CIV-02 | Updates civil drawings and the Tekla model from field redlines and survey for handover. | 4 | 1
INST-T005 | INST | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 2 | 3
INST-T010 | INST | Define preliminary control and safety concept | Excel / Word | FEL1, FEL2 | ICS-01 | Sets the early automation concept (DCS/SIS/F&G split, level of automation, control room location, remote operation) for screening and estimating. | 4 | 1
INST-T020 | INST | Prepare factored instrument count and I&C estimate input | Excel / Word | FEL1, FEL2, FEL3 | FEL-04 | Estimates instrument counts, I/O, control valves, analyzers and system cabinets from PFDs or P&IDs to feed the cost estimate. | 6 | 1
INST-T030 | INST | Develop ICS architecture and control/rack room requirements | Excel / Word | FEL2, FEL3, DD | ICS-07 | Develops the ICS network architecture and defines control room, rack room and field equipment room requirements including cabinet layouts and heat loads. | 7 | 2
INST-T040 | INST | Write I&C design basis and general instrument specifications | Excel / Word | FEL2, FEL3 | PRJ-01 | Writes the I&C design basis, instrument selection guide and general specifications for field instruments, installation and wiring. | 8 | 1
INST-T045 | INST | Review P&IDs for instrumentation and controls | SPID | FEL2, FEL3, DD | PRC-08 | Reviews and marks up P&IDs for instrument types, tagging, control and interlock representation, valve failure positions and instrument connections. | 6 | 1
INST-T050 | INST | Build and maintain the instrument index in SI | SI | FEL3, DD, CON | PRC-08 | Creates instrument tags and loops in SI from the P&IDs and keeps the index aligned with each P&ID revision. | 6 | 1
INST-T055 | INST | Close out HAZOP and LOPA actions on I&C design | PHA tool | FEL3, DD | SAF-03 | Responds to HAZOP and LOPA actions assigned to I&C (added transmitters, alarms, trips, SIF changes) and updates the design. | 4 | 1
INST-T060 | INST | Enter instrument process data | SI | FEL3, DD | PRC-08 | Enters process conditions for each instrument into SI process data sheets from process datasheets and the HYSYS stream summary. | 5 | 1
INST-T070 | INST | Size control valves | SI | FEL3, DD | ICS-04 | Sizes control valves for all cases, checks noise, cavitation and flashing, and selects body size, trim, rating and actuator. | 5 | 3
INST-T080 | INST | Size on/off and emergency shutdown valves and actuators | SI | FEL3, DD | ICS-04 | Sizes on/off, ESD and blowdown valves and specifies actuators, stroke times, failure positions and leak classes. | 6 | 1
INST-T090 | INST | Calculate flow elements and thermowells | SI | FEL3, DD | ICS-04 | Sizes orifice plates and other flow elements and checks thermowell wake frequency. | 3 | 2
INST-T100 | INST | Specify relief valves from the process sizing | SI | FEL3, DD | PRC-03 | Prepares PSV datasheets from the process relief cases and selects orifice, body size and rating. | 4 | 1
INST-T110 | INST | Prepare instrument datasheets | SI | FEL3, DD | PRO-01 | Prepares SI datasheets for transmitters, switches, gauges, flow meters, level instruments and valves ready for requisition. | 8 | 1
INST-T115 | INST | Define instrument connections on equipment and lines | Excel / Word | FEL3, DD | ICS-09 | Defines instrument nozzles and connections on vessels, columns, tanks and lines (level bridles, thermowells, pressure tappings). | 4 | 1
INST-T130 | INST | Prepare instrument material requisitions | Purchasing DB | FEL3, DD | PRO-01 | Compiles material requisitions for instrument packages (control valves, on/off valves, PSVs, transmitters, flow, analyzers, F&G devices, bulks). | 6 | 1
INST-T140 | INST | Evaluate instrument bids technically | Excel / Word | FEL3, DD | PRO-01 | Evaluates vendor technical offers against the requisition and issues the technical bid evaluation. | 5 | 1
INST-T145 | INST | Align final relief valve sizing with Process and vendor | SI | FEL3, DD | ICS-04 | Agree the vendor's final orifice, model and rating with Process before the relief valves are purchased. | 3 | 1
INST-T150 | INST | Review instrument vendor data | Document Locator | DD, CON | VEN-01 | Reviews vendor drawings and data for instruments and valves and loads certified data into SI. | 6 | 2
INST-T160 | INST | Specify analyzers and analyzer shelters | Excel / Word | FEL3, DD | ICS-01 | Specifies process and environmental analyzers, sample systems and analyzer shelters. | 5 | 2
INST-T170 | INST | Write control narratives and functional design specifications | Excel / Word | FEL3, DD | ICS-01 | Turns the process control philosophy into control narratives and functional logic for complex loops, sequences and permissives. | 7 | 1
INST-T180 | INST | Prepare DCS specification | Excel / Word | FEL3, DD | ICS-07 | Writes the DCS functional and hardware specification for the main automation contractor. | 3 | 1
INST-T190 | INST | Prepare SIS specification | Excel / Word | FEL3, DD | ICS-07 | Writes the SIS hardware and software specification consistent with the SRS. | 3 | 1
INST-T200 | INST | Specify fire and gas system and device list | SI | FEL3, DD | SAF-04 | Specifies the F&G system and builds the F&G detector and device list from the F&G mapping study. | 10 | 2
INST-T210 | INST | Define SIFs and input to SIL determination | PHA tool | FEL3, DD | ICS-02 | Defines SIF initiators, logic and final elements and provides instrument reliability input to the LOPA/SIL determination. | 2 | 1
INST-T220 | INST | Write safety requirements specification | Excel / Word | FEL3, DD | ICS-08 | Writes the SRS for each SIF covering safe state, response time, trip points, bypasses and proof test requirements. | 3 | 1
INST-T230 | INST | Verify SIL achievement | Excel / Word | DD | ICS-08 | Calculates PFDavg and architectural constraints for each SIF using selected device data and sets proof test intervals. | 4 | 2
INST-T240 | INST | Prepare cause and effect charts | Excel / Word | FEL3, DD | ICS-03 | Prepares the process shutdown and F&G cause and effect charts. | 6 | 2
INST-T250 | INST | Rationalize alarms and build master alarm database | Excel / Word | DD | ICS-01 | Runs alarm rationalization and records alarm set points, priorities and consequences. | 4 | 1
INST-T260 | INST | Develop I/O list and assign I/O | SI | FEL3, DD | ICS-05 | Builds the I/O list per system, assigns I/O to cabinets and cards and issues I/O counts to system vendors. | 4 | 2
INST-T270 | INST | Integrate vendor package controls | Excel / Word | DD, CON | VEN-01 | Defines package I&C requirements for mechanical requisitions and reviews package control data and interfaces. | 6 | 3
INST-T280 | INST | Compile instrument utility loads | Excel / Word | FEL3, DD | ELE-01 | Compiles instrument power, UPS, instrument air and heat tracing requirements. | 4 | 3
INST-T290 | INST | Prepare instrument location plans and JB locations | S3D | DD | ICS-09 | Places instruments and JBs in the 3D model, prepares location plans and comments in model reviews. | 6 | 3
INST-T300 | INST | Prepare hook-up drawings and assign typicals | Excel / Word | DD | ICS-09 | Prepares process, pneumatic and electrical installation hook-ups with bills of material and assigns each instrument tag to a hook-up typical. | 6 | 1
INST-T310 | INST | Design instrument wiring, marshalling and terminations | SI | DD | ICS-06 | Designs field JB wiring, marshalling and system cabinet terminations and cable block diagrams in SI. | 5 | 1
INST-T320 | INST | Prepare instrument cable schedule and tray loading | SI | DD | ELE-04 | Prepares the instrument cable schedule with lengths from the routed model and gives cable counts per route to electrical for tray sizing. | 3 | 2
INST-T330 | INST | Generate loop diagrams | SI | DD, CON | ICS-06 | Generates loop diagrams in SI from field device through JB and marshalling to system channel. | 4 | 1
INST-T340 | INST | Prepare instrument bulk MTO | Excel / Word | DD, CON | ICS-09 | Calculates bulk quantities (cable, tubing, fittings, JBs, glands, supports, cable tray branches) for purchase and site issue. | 4 | 1
INST-T350 | INST | Design telecom, CCTV and security systems | Excel / Word | FEL3, DD | ICS-07 | Designs PA/GA, CCTV, plant LAN/WAN, radio and access control systems and places devices. | 9 | 2
INST-T380 | INST | Prepare system configuration data for vendors | SI | DD | ICS-07 | Exports tag, range, alarm and I/O data from SI and the alarm database to the DCS/SIS/F&G vendors for configuration. | 8 | 1
INST-T390 | INST | Review configuration and witness system FAT | DCS / SIS config | DD, CON | ICS-07 | Reviews graphics and logic configuration and witnesses DCS, SIS and F&G factory acceptance tests. | 7 | 2
INST-T400 | INST | Answer construction RFIs and issue I&C field changes | Procore | CON | CON-01 | Answers I&C RFIs and technical queries from site and issues field change instructions. | 3 | 1
INST-T410 | INST | Prepare instrument tag register for completions | Excel / Word | CON, COM | CON-02 | Exports the instrument, cable and JB register with system/subsystem assignment for loading into Smart Completions. | 6 | 1
INST-T420 | INST | Support loop checks and resolve I&C punch | Smart Completions | CON, COM | CON-02 | Supports calibration and loop checks and gives engineering responses to I&C punch items. | 4 | 1
INST-T430 | INST | Support SAT, SIS validation and integrated testing | DCS / SIS config | COM | CON-02 | Supports site acceptance tests, SIS functional validation against the SRS and integrated C&E tests. | 4 | 1
INST-T440 | INST | Prepare as-built I&C database and drawings | SI | COM | PRJ-04 | Incorporates as-built redlines and final vendor data into SI and I&C drawings for handover. | 5 | 1
ELEC-T005 | ELEC | Plan, measure and report discipline deliverables | Excel / Word | FEL2, FEL3, DD | PRJ-03 | Keep the discipline deliverables list, measure progress by rules of credit, and report holds and change impacts to project controls. | 2 | 2
ELEC-T010 | ELEC | Prepare electrical design basis and philosophy | Excel / Word | FEL1, FEL2, FEL3 | PRJ-01 | Sets voltage levels, distribution configuration and redundancy, codes (NEC/NFPA 70, NFPA 70E, IEEE, API RP 500/505/540), motor voltage thresholds, emergency/essential power philosophy and owner electrical standards. | 5 | 3
ELEC-T020 | ELEC | Prepare preliminary electrical load estimate | Excel / Word | FEL1, FEL2 | ELE-01 | Estimates total connected and running load (MW/MVA) from the equipment list and factored allowances to size the plant supply and utility request. | 5 | 1
ELEC-T030 | ELEC | Coordinate utility interconnect and power supply | Excel / Word | FEL1, FEL2, FEL3, DD | SEL-03 | Prepares the interconnection request to the utility, obtains available fault levels and supply options, and agrees point of interconnection, metering and protection requirements. | 4 | 2
ELEC-T040 | ELEC | Develop configuration options and preliminary key one-line | Excel / Word | FEL2, FEL3 | FEL-02 | Screens supply and distribution options (on-site generation vs utility, substation count, voltage levels) and issues a key one-line for the selected option. | 5 | 1
ELEC-T050 | ELEC | Prepare electrical cost estimate inputs | Excel / Word | FEL1, FEL2, FEL3 | CST-01 | Produces factored then quantity-based electrical quantities and major equipment pricing for the Class 5/4/3 estimates. | 7 | 1
ELEC-T060 | ELEC | Prepare hazardous area release source list | Excel / Word | FEL2, FEL3, DD | ELE-02 | Identifies release sources, grades of release and ventilation per API RP 500/505 and NFPA 497 using process fluid data. | 6 | 1
ELEC-T070 | ELEC | Prepare hazardous area classification drawings | S3D | FEL3, DD, CON | ELE-02 | Draws classified area extents in plan and elevation on the plot plan background and issues them to all disciplines and vendors. | 7 | 2
ELEC-T080 | ELEC | Size substations and electrical buildings | Excel / Word | FEL2, FEL3, DD | ELE-06 | Develops substation and electrical room arrangements and passes sizes, loads, HVAC and civil requirements to civil/structural. | 7 | 3
ELEC-T090 | ELEC | Develop electrical load list in SPEL | SPEL | FEL3, DD, CON | ELE-01 | Keys every electrical consumer into SPEL with rating, voltage, duty, bus assignment and demand factors and maintains it through vendor data. | 13 | 2
ELEC-T100 | ELEC | Review P&IDs and assign electrical attributes | SPID | FEL3, DD | PRC-08 | Reviews P&IDs for motor tags, MOVs, heat tracing flags, electrical interlocks and local control stations and returns comments. | 2 | 1
ELEC-T110 | ELEC | Size major electrical equipment | Excel / Word | FEL3, DD | ELE-03 | Sizes transformers, switchgear, MCCs, emergency generator, UPS/batteries and capacitor/filter banks from the load list and study results. | 7 | 1
ELEC-T120 | ELEC | Develop one-line diagrams in SPEL | SPEL | FEL3, DD | ELE-03 | Draws main and MCC one-line diagrams from the SPEL load list and equipment ratings, with protection and metering. | 4 | 1
ELEC-T130 | ELEC | Specify MV switchgear | Excel / Word | FEL3, DD | PRO-01 | Writes the specification and datasheets and issues the technical part of the requisition. | 7 | 1
ELEC-T140 | ELEC | Specify power transformers | Excel / Word | FEL3, DD | PRO-01 | Writes the specification and datasheets and issues the technical part of the requisition. | 6 | 1
ELEC-T150 | ELEC | Specify LV switchgear, MCCs and E-houses | Excel / Word | FEL3, DD | PRO-01 | Writes the specification and datasheets and issues the technical part of the requisition. | 11 | 1
ELEC-T160 | ELEC | Specify VFDs and harmonic mitigation | Excel / Word | FEL3, DD | PRO-01 | Writes the specification and datasheets and issues the technical part of the requisition. | 9 | 1
ELEC-T170 | ELEC | Specify UPS, DC systems and emergency generator | Excel / Word | FEL3, DD | PRO-01 | Writes the specification and datasheets and issues the technical part of the requisition. | 9 | 1
ELEC-T180 | ELEC | Evaluate electrical bids technically | Excel / Word | FEL3, DD | PRO-01 | Evaluates vendor proposals against specifications, holds clarification meetings and issues technical recommendations. | 9 | 1
ELEC-T190 | ELEC | Review electrical vendor drawings and data | Document Locator | DD, CON | VEN-01 | Reviews vendor GA, schematics, datasheets and test procedures for electrical equipment and returns coded comments; loads certified data into SPEL/ETAP. | 4 | 2
ELEC-T200 | ELEC | Review motor and package electrical data | SPEL | DD | VEN-01 | Checks motor data sheets and package electrical scope from driven-equipment vendors against the electrical requirements and updates the load list. | 4 | 2
ELEC-T210 | ELEC | Build ETAP model and run load flow study | ETAP | FEL3, DD | ELE-05 | Builds the ETAP network from SPEL load list and one-lines, runs load flow for normal, contingency and maximum load cases and sets transformer taps. | 6 | 1
ELEC-T220 | ELEC | Run short-circuit study | ETAP | FEL3, DD | ELE-05 | Calculates maximum and minimum fault currents per IEEE/ANSI C37 to confirm equipment interrupting and withstand duties. | 3 | 1
ELEC-T230 | ELEC | Run motor-starting study | ETAP | FEL3, DD | ELE-05 | Simulates starting of large motors to check voltage dips and acceleration and sets the starting method. | 5 | 2
ELEC-T240 | ELEC | Run harmonic analysis | ETAP | DD | ELE-05 | Models VFD and non-linear loads and checks IEEE 519 compliance at the point of common coupling and buses. | 3 | 1
ELEC-T250 | ELEC | Perform protective relay coordination study | ETAP | DD, COM | ELE-05 | Develops time-current coordination and relay/breaker trip settings from utility interface to motors. | 5 | 2
ELEC-T260 | ELEC | Perform arc flash study | ETAP | DD, COM | ELE-05 | Calculates incident energy per IEEE 1584 and NFPA 70E, specifies PPE categories and produces equipment labels. | 4 | 1
ELEC-T270 | ELEC | Design grounding system | Excel / Word | FEL3, DD | ELE-06 | Performs ground grid study (IEEE 80) and designs plant, substation and equipment grounding. | 6 | 2
ELEC-T280 | ELEC | Design lightning protection | Excel / Word | DD | ELE-06 | Performs risk assessment (NFPA 780) and designs air terminals and down conductors for buildings and tall structures. | 4 | 1
ELEC-T290 | ELEC | Design lighting and small power | Excel / Word | DD | ELE-06 | Calculates illumination levels (IES) and lays out area, platform, building and emergency/egress lighting and receptacles. | 5 | 2
ELEC-T300 | ELEC | Design electric heat tracing | Excel / Word | DD | ELE-06 | Designs heat tracing circuits for freeze protection and process temperature maintenance using vendor design software outputs. | 5 | 3
ELEC-T310 | ELEC | Design cathodic protection | Excel / Word | DD, CON | ELE-06 | Designs impressed-current or galvanic cathodic protection for buried piping and tank bottoms per NACE/AMPP standards. | 5 | 1
ELEC-T320 | ELEC | Size cables and build cable schedule in SPEL | SPEL | DD, CON | ELE-04 | Sizes power and control cables for ampacity, voltage drop and short circuit per NEC and creates the cable schedule. | 5 | 2
ELEC-T330 | ELEC | Route raceway, cable tray and duct banks in S3D | S3D | FEL3, DD | ELE-06 | Models cable tray, conduit and underground duct banks in S3D and reserves space on racks and structures. | 9 | 3
ELEC-T340 | ELEC | Define MCC and switchgear interface signals with I&C | SPEL | DD | ICS-05 | Lists hardwired and serial signals between switchgear/MCC and DCS/SIS/ECMS and agrees marshalling and protocol. | 4 | 1
ELEC-T350 | ELEC | Prepare control and interlock schematics | SPEL | DD | ELE-03 | Prepares motor control typicals, elementary diagrams and interlock schematics, including SIS and MOV interfaces. | 4 | 1
ELEC-T360 | ELEC | Prepare electrical layouts and installation details | Excel / Word | DD | ELE-06 | Issues electrical equipment layouts, power plans and installation details for construction. | 6 | 2
ELEC-T370 | ELEC | Prepare electrical MTO and bulk requisitions | Excel / Word | DD, CON | PRO-01 | Takes off bulk materials (cable, tray, conduit, fittings, lighting, grounding, heat tracing) and issues MTO revisions to procurement. | 8 | 1
ELEC-T380 | ELEC | Design temporary construction power | Excel / Word | DD, CON | CON-01 | Sizes and lays out temporary construction power and early backfeed arrangements. | 4 | 1
ELEC-T390 | ELEC | Seal and issue electrical deliverables IFC | Document Locator | DD | PRJ-04 | Performs inter-discipline and PE check, seals and issues electrical deliverables IFC. | 5 | 1
ELEC-T400 | ELEC | Witness factory acceptance tests | Excel / Word | DD, CON | VEN-01 | Witnesses FAT of switchgear, MCCs, E-houses, transformers, VFDs and UPS, including integrated communication tests with the DCS. | 5 | 1
ELEC-T410 | ELEC | Answer RFIs and issue field changes | Procore | CON | CON-01 | Answers construction RFIs and issues field change notices and revised details. | 3 | 1
ELEC-T420 | ELEC | Define electrical systems and energization sequence | Smart Completions | DD, CON, COM | CON-02 | Defines electrical system/subsystem boundaries, energization sequence and supplies tag lists for completions. | 7 | 2
ELEC-T430 | ELEC | Support electrical testing, setting and energization | Smart Completions | COM | CON-02 | Supports field testing (NETA ATS), relay setting implementation, LOTO and first energization; reviews test records. | 5 | 1
ELEC-T440 | ELEC | Produce as-built electrical records | SPEL | CON, COM | CON-02 | Incorporates field redlines into SPEL, ETAP and drawings and issues as-built records. | 2 | 1
SCM-T010 | SCM | Prepare the procurement plan and long-lead list | Excel / Word | FEL2, FEL3 | PRO-01 | Plan each procurement package with sourcing route, durations and need dates, and identify long-lead items for early commitment. | 7 | 2
SCM-T020 | SCM | Prepare bidders lists and prequalify vendors | Purchasing DB | FEL3, DD | PRO-01 | Select qualified bidders per package from the approved vendor list and prequalify new vendors. | 4 | 2
SCM-T030 | SCM | Register material requisitions in the Purchasing DB | Purchasing DB | FEL3, DD | PRO-01 | Log each MR and revision received through Document Locator, key header and line data and set status. | 14 | 1
SCM-T040 | SCM | Load piping bulk MTO into the Purchasing DB | Purchasing DB | FEL3, DD | PIP-04 | Import the S3D MTO spreadsheet, map commodity codes and add surplus allowances to form bulk MR lines. | 4 | 1
SCM-T050 | SCM | Issue RFQ packages | Purchasing DB | FEL2, FEL3, DD | VEN-01 | Combine the technical MR with commercial terms and issue the request for quotation to the bidders list. | 8 | 1
SCM-T060 | SCM | Manage bid clarifications and bid bulletins | Excel / Word | FEL3, DD | VEN-01 | Collect bidder questions, get technical answers and issue bid bulletins to all bidders. | 4 | 1
SCM-T070 | SCM | Receive bids and distribute technical portions | Document Locator | FEL3, DD | PRO-01 | Open bids, separate priced and unpriced portions and send unpriced technical offers for technical bid evaluation. | 3 | 1
SCM-T080 | SCM | Prepare the commercial bid evaluation | Excel / Word | FEL3, DD | PRO-01 | Normalise prices, delivery and terms across bidders and score the commercial offers. | 5 | 1
SCM-T090 | SCM | Prepare the bid tabulation and award recommendation | Excel / Word | FEL3, DD | PRO-01 | Combine technical and commercial evaluations into the award recommendation for approval. | 7 | 1
SCM-T100 | SCM | Award the purchase order in the Purchasing DB | Purchasing DB | FEL3, DD | PRO-01 | Prepare the PO from the conformed MR and successful bid, enter PO header and lines and issue to the vendor. | 4 | 4
SCM-T110 | SCM | Process PO amendments | Purchasing DB | DD, CON | PRO-01 | Issue PO amendments for MR revisions, quantity changes and vendor change orders. | 4 | 1
SCM-T120 | SCM | Set up VDRL tracking | Purchasing DB | DD | VEN-01 | Load the vendor document requirements per PO with document numbers and due dates in the Purchasing DB. | 4 | 1
SCM-T130 | SCM | Expedite vendor documents and route them for review | Document Locator | DD, CON | VEN-01 | Receive vendor documents, transmit to engineering for review, return comments to the vendor and report print status. | 20 | 3
SCM-T140 | SCM | Expedite manufacturing and forecast deliveries | Purchasing DB | DD, CON | VEN-01 | Track sub-orders, manufacturing milestones and forecast ex-works dates per PO line and report exceptions. | 5 | 1
SCM-T150 | SCM | Coordinate inspection and test plans | Excel / Word | DD, CON | VEN-01 | Review vendor ITPs, set hold and witness points with engineering and owner and assign inspectors. | 5 | 1
SCM-T160 | SCM | Carry out shop inspection and release | Excel / Word | DD, CON | VEN-01 | Witness tests, review certificates and issue inspection reports and release notes for shipment. | 9 | 2
SCM-T170 | SCM | Prepare the logistics plan | Excel / Word | FEL3, DD | VEN-01 | Plan freight routes, heavy-haul and oversize moves, customs and port handling. | 4 | 1
SCM-T180 | SCM | Manage shipping and traffic | Excel / Word | DD, CON | VEN-01 | Book freight, clear customs and issue shipping notices to site. | 3 | 1
SCM-T190 | SCM | Pass PO data to Jovix for receiving | Jovix | DD, CON | VEN-01 | Transfer PO header and line data to Jovix as expected receipts. | 3 | 1
SCM-T200 | SCM | Receive materials at site in Jovix | Jovix | CON | CON-02 | Check received items against PO lines and packing lists, record heat numbers and tag them to location. | 4 | 1
SCM-T210 | SCM | Raise OS&D reports | Jovix | CON | CON-02 | Report overage, shortage and damage on receipt and follow up with vendor and carrier. | 2 | 1
SCM-T220 | SCM | Manage the warehouse, laydown and preservation | Jovix | CON, COM | CON-02 | Store materials by location, perform periodic preservation and record it. | 3 | 1
SCM-T230 | SCM | Report material availability to AWP | Jovix | CON | CON-02 | Match received materials against CWP/IWP bills of material and publish availability for constraint checks. | 3 | 2
SCM-T240 | SCM | Issue materials to construction | Jovix | CON | CON-02 | Reserve and issue materials against IWPs with pick tickets and record heat number traceability. | 2 | 1
SCM-T250 | SCM | Reconcile materials and dispose of surplus | Jovix | CON, COM | CON-02 | Reconcile ordered, received, issued and installed quantities and dispose of surplus. | 3 | 1
SCM-T260 | SCM | Call off vendor site services | Purchasing DB | CON, COM | VEN-01 | Request vendor representatives for installation supervision and commissioning against PO service rates. | 3 | 1
SCM-T270 | SCM | Procure commissioning and operating spares | Purchasing DB | DD, CON, COM | VEN-01 | Process vendor spare parts lists, get owner selection and place spares orders. | 4 | 1
SCM-T280 | SCM | Close out purchase orders | Purchasing DB | CON, COM | VEN-01 | Confirm final documentation, MDR and deliveries complete and close POs. | 5 | 1
VEND-T010 | VEND | Prepare budget quotations | Excel / Word | FEL1, FEL2 | VEN-01 | Quote budget price, delivery and outline scope for major equipment against preliminary data. | 1 | 1
VEND-T020 | VEND | Prepare firm technical and commercial quotations | Excel / Word | FEL3, DD | VEN-01 | Design to the RFQ and submit the technical offer, deviations and priced commercial offer. | 16 | 5
VEND-T030 | VEND | Answer bid clarifications | Excel / Word | FEL3, DD | VEN-01 | Respond to technical and commercial clarification questions during evaluation. | 2 | 2
VEND-T040 | VEND | Issue the vendor document schedule | Document Locator | DD | VEN-01 | After PO, list each vendor document with project number, type and planned submission date. | 2 | 1
VEND-T050 | VEND | Prepare GA and outline drawings for review | Excel / Word | DD | MEC-03 | Produce GA drawings with nozzles, orientations, weights, loads and anchor bolts for review. | 5 | 2
VEND-T060 | VEND | Prepare vendor design calculations | Mechanical calc tool | DD | MEC-01 | Mechanical design calculations (thickness, nozzles, wind/seismic, rotordynamics) to code. | 4 | 1
VEND-T070 | VEND | Prepare package P&IDs, I/O and control narrative | Excel / Word | DD | VEN-01 | Produce package P&IDs, instrument list, I/O list and control narrative for interface with the plant DCS/SIS. | 6 | 3
VEND-T080 | VEND | Prepare package electrical data | Excel / Word | DD | VEN-01 | Provide motor datasheets, electrical loads, local control panel data and heat tracing needs. | 5 | 1
VEND-T090 | VEND | Incorporate comments and issue certified final data | Document Locator | DD, CON | VEN-01 | Resolve review comments and issue certified drawings and data as final. | 2 | 2
VEND-T100 | VEND | Prepare the ITP and manufacturing schedule | Excel / Word | DD | VEN-01 | Issue the inspection and test plan and manufacturing schedule with milestones. | 3 | 2
VEND-T110 | VEND | Procure raw materials and issue MTRs | Excel / Word | DD | VEN-01 | Buy plates, forgings, pipe and components and collect material test reports with heat numbers. | 2 | 1
VEND-T120 | VEND | Fabricate and test the equipment | Excel / Word | DD, CON | VEN-01 | Fabricate, weld, NDE, pressure test and run performance or FAT tests, issuing inspection notices and certificates. | 3 | 3
VEND-T130 | VEND | Fabricate pipe spools | Excel / Word | DD, CON | PIP-04 | Fabricate spools from IFC isometrics, weld and test, and report spool status with heat traceability. | 5 | 2
VEND-T140 | VEND | Detail and fabricate structural steel | Tekla | DD, CON | CIV-02 | Produce shop drawings from the Tekla model, fabricate, coat and mark steel members. | 5 | 1
VEND-T150 | VEND | Report manufacturing progress | Excel / Word | DD, CON | VEN-01 | Issue periodic progress reports against milestones with forecast dates. | 2 | 1
VEND-T160 | VEND | Pack, preserve and ship | Excel / Word | DD, CON | VEN-01 | Prepare packing lists, preservation and shipping documents for released items. | 2 | 3
VEND-T170 | VEND | Prepare nameplate and as-built data | Excel / Word | DD, CON | VEN-01 | Issue nameplate data and as-built dimensions, weights and serial numbers. | 1 | 1
VEND-T180 | VEND | Compile the MDR / data book | Document Locator | CON, COM | VEN-01 | Assemble certified drawings, calculations, MTRs, weld and NDE records, test certificates into the data book. | 6 | 1
VEND-T190 | VEND | Prepare IOM manuals and spare parts lists | Document Locator | DD, CON | VEN-01 | Issue installation, operation and maintenance manuals and spare parts interchangeability records. | 2 | 2
VEND-T200 | VEND | Configure and test the DCS/SIS | DCS / SIS config | DD, CON | ICS-07 | Configure control and safety logic, graphics and alarms and run FAT with the project team. | 11 | 1
VEND-T210 | VEND | Provide site services | Excel / Word | CON, COM | VEN-01 | Supervise installation, assist pre-commissioning and commissioning and report findings. | 3 | 1
CONS-T010 | CONS | Compile constructability input and lessons learned | Excel / Word | FEL2, FEL3 | CON-01 | Collects site, contractor and lessons-learned constructability requirements and issues them as design input for layout and engineering. | 5 | 1
CONS-T020 | CONS | Prepare site logistics, laydown and temporary facilities plan | Excel / Word | FEL2, FEL3, DD | CON-01 | Lays out laydown, fabrication yards, temporary buildings, haul roads and construction access around the plot. | 9 | 2
CONS-T030 | CONS | Evaluate modularisation and prefabrication strategy | Excel / Word | FEL2, FEL3 | CON-01 | Compares stick-built, pre-assembled rack and skid/module options on cost, schedule, transport limits and site labour. | 6 | 1
CONS-T040 | CONS | Prepare heavy lift and crane study | Excel / Word | FEL3, DD | CON-01 | Selects cranes, crane pads and lift sequences for heavy and critical lifts and states the space and lifting-lug requirements back to design. | 7 | 2
CONS-T050 | CONS | Define path of construction | P6 | FEL3 | CON-01 | Sets the area-by-area construction sequence from underground through steel, equipment setting, piping, E&I and completions, driven by the commissioning sequence. | 4 | 1
CONS-T060 | CONS | Define construction work areas (CWAs) | iConstruct | FEL3 | CON-02 | Divides the plot into CWAs with boundaries and IDs aligned to the path of construction and plot plan areas. | 2 | 1
CONS-T070 | CONS | Define CWPs, boundaries and sequence | P6 | FEL3, DD | CON-02 | Breaks each CWA into discipline CWPs with scope boundaries, sequence and the dates by which engineering and materials are needed. | 13 | 3
CONS-T080 | CONS | Review 3D model for constructability (30/60/90 % reviews) | iConstruct | FEL3, DD | LAY-03 | Reviews the federated model for erection access, rigging, scaffolding, weld access, spool breaks and construction sequence. | 4 | 1
CONS-T090 | CONS | Review IFR drawings for constructability | Document Locator | DD | LAY-03 | Comments on IFR drawings and specifications for field installability, tolerances, tie-in access and construction sequence. | 11 | 1
CONS-T100 | CONS | Prepare construction execution plan and estimate input | Excel / Word | FEL3, DD | CST-02 | Writes the construction execution strategy and provides direct and indirect field hours, crew sizes and construction equipment for the estimate. | 10 | 2
CONS-T110 | CONS | Develop construction schedule by CWP | P6 | DD, CON | CON-01 | Builds the level 3 construction schedule with resource-loaded CWP activities tied to EWP and material delivery dates. | 6 | 1
CONS-T120 | CONS | Align EWPs and procurement packages to CWPs | P6 | DD | CON-02 | Maps EWPs and purchase orders to CWPs and flags where engineering or material release dates miss the CWP need dates. | 6 | 1
CONS-T130 | CONS | Build construction model and attach CWP/IWP attributes | iConstruct | DD, CON | CON-02 | Federates S3D and Tekla models in iConstruct, assigns objects to CWAs, CWPs and IWPs and links Jovix material status. | 6 | 1
CONS-T140 | CONS | Develop installation work packages (IWPs) | iConstruct | CON | CON-02 | Creates IWPs in iConstruct for one crew and one to two weeks of work, with scope, drawings, model views, materials and quantities. | 15 | 1
CONS-T150 | CONS | Check IWP material availability against Jovix | iConstruct | CON | CON-02 | Checks every IWP bill of materials against Jovix warehouse and laydown status and reports shortages before release. | 5 | 1
CONS-T160 | CONS | Manage IWP constraints and release IWPs | iConstruct | CON | CON-02 | Logs and chases IWP constraints (engineering holds, RFIs, materials, scaffolding, permits) and releases constraint-free IWPs to the field backlog. | 6 | 2
CONS-T170 | CONS | Raise and manage RFIs | Procore | CON | CON-01 | Raises requests for information against drawings and documents in Procore and tracks responses to closure. | 6 | 1
CONS-T180 | CONS | Raise field change requests | Procore | CON | CON-01 | Proposes field changes where IFC design cannot be built or a better field solution exists, with cost and schedule impact. | 5 | 2
CONS-T190 | CONS | Survey, set out and verify foundations | Excel / Word | CON | CIV-02 | Sets out grid and foundations, checks anchor bolt and embedded item positions and records as-built elevations before steel and equipment setting. | 4 | 3
CONS-T200 | CONS | Request and receive materials from the warehouse | Jovix | CON | CON-02 | Raises material issue requests for released IWPs and reports shortages, damage and surplus found in the field. | 3 | 2
CONS-T210 | CONS | Track installed quantities and progress | iConstruct | CON | CON-02 | Records installed quantities and IWP completion daily and rolls progress up to CWP and schedule. | 2 | 3
CONS-T220 | CONS | Track welds and NDE | Excel / Word | CON | PIP-04 | Maintains the weld log with welder IDs, NDE selection and results and repair rates by line and iso. | 4 | 1
CONS-T230 | CONS | Prepare and execute pressure test packs | Excel / Word | CON | PIP-04 | Assembles test packs (marked-up P&IDs and isos, test limits, blinds, test pressures) and runs and records hydro/pneumatic tests and reinstatement. | 8 | 2
CONS-T240 | CONS | Complete construction ITRs (A sheets) | Smart Completions | CON | CON-02 | Completes and signs construction check sheets by tag in Smart Completions as installation is inspected. | 6 | 1
CONS-T250 | CONS | Clear construction punch items | Smart Completions | CON, COM | CON-02 | Works off punch items assigned to construction and records clearance in Smart Completions. | 1 | 1
CONS-T260 | CONS | Prepare as-built redlines | Procore | CON, COM | CON-01 | Marks field deviations on IFC drawings (P&IDs, isometrics, cable routes, foundations) and transmits redlines for as-built drafting. | 5 | 1
CONS-T270 | CONS | Walk down and certify mechanical completion by subsystem | Smart Completions | CON | CON-02 | Walks down each subsystem with commissioning and owner, confirms A-ITRs complete and A punch cleared, and issues the MC certificate. | 6 | 1
CONS-T280 | CONS | Compile construction quality dossier | Document Locator | CON, COM | CON-02 | Collects weld, NDE, test, material traceability, calibration and inspection records per subsystem for the turnover package. | 4 | 1
COMM-T010 | COMM | Prepare completions and commissioning execution plan | Excel / Word | FEL3 | PRJ-05 | Sets the completions philosophy: MC, RFC, RFSU and handover definitions, ITR scheme, punch categories, certificate flow and systems used. | 3 | 1
COMM-T020 | COMM | Develop preliminary system list and start-up sequence | Excel / Word | FEL3 | CON-02 | Defines commissioning systems from PFDs and utility diagrams and sets the high-level start-up order (utilities first). | 4 | 1
COMM-T030 | COMM | Mark system and subsystem boundaries on P&IDs | SPID | FEL3, DD | CON-02 | Marks colour-coded system and subsystem limits on P&IDs and single-lines, including isolation points. | 8 | 2
COMM-T040 | COMM | Set commissioning sequence and required subsystem turnover dates | P6 | DD | CON-02 | Builds the commissioning schedule by system and gives construction the required MC/turnover date per subsystem. | 4 | 1
COMM-T050 | COMM | Define ITR library and ITR matrix by tag type | Smart Completions | DD | CON-02 | Defines A (construction), B (pre-commissioning) and C (commissioning) check sheets and maps them to discipline tag types. | 4 | 1
COMM-T060 | COMM | Build tag-to-subsystem register | Excel / Word | DD, CON | CON-02 | Assigns every tag (lines, equipment, instruments, cables, electrical equipment) to a subsystem from the engineering lists. | 8 | 1
COMM-T070 | COMM | Load tags and assign ITRs in Smart Completions | Smart Completions | DD, CON | CON-02 | Loads the tag register into Smart Completions by spreadsheet and generates the ITR set per tag from the ITR matrix. | 3 | 1
COMM-T080 | COMM | Write pre-commissioning procedures | Excel / Word | DD, CON | CON-02 | Writes flushing, blowing, chemical cleaning, drying, leak test and inerting procedures by system. | 9 | 1
COMM-T090 | COMM | Write commissioning and function test procedures | Excel / Word | DD, CON | CON-02 | Writes system commissioning, run-in and function test procedures, including SIS and C&E testing. | 9 | 1
COMM-T100 | COMM | Define commissioning spares, consumables and first fills | Excel / Word | DD | CON-02 | Lists commissioning spares, lubricants, chemicals, catalysts, filters and gases needed by system and date. | 4 | 1
COMM-T110 | COMM | Define vendor commissioning support requirements | Excel / Word | DD | CON-02 | States vendor representative scope, man-days and timing per package for pre-commissioning and start-up. | 3 | 1
COMM-T120 | COMM | Plan temporary commissioning facilities | Excel / Word | DD, CON | CON-02 | Defines temporary spools, strainers, blinds, flushing pumps, nitrogen and steam supply needed for pre-commissioning. | 4 | 1
COMM-T130 | COMM | Track test pack status by subsystem | Smart Completions | CON | CON-02 | Tracks test pack status (prepared, tested, reinstated) against subsystems to forecast MC. | 2 | 1
COMM-T140 | COMM | Raise and manage punch lists | Smart Completions | CON, COM | CON-02 | Records punch items from walkdowns by subsystem with A/B/C category and action-by party and tracks them to closure. | 3 | 1
COMM-T150 | COMM | Accept subsystem turnover from construction | Smart Completions | CON | CON-02 | Accepts MC subsystems from construction after checking A-ITRs and A punch and takes custody for pre-commissioning. | 4 | 1
COMM-T160 | COMM | Execute pre-commissioning (B-ITRs) | Smart Completions | CON, COM | CON-02 | Carries out flushing, cleaning, insulation tests, motor solo runs and other B-ITRs and records them per tag. | 3 | 1
COMM-T170 | COMM | Execute loop checks | Smart Completions | CON, COM | ICS-06 | Checks each loop from field device to DCS/SIS graphic and records loop status and defects. | 5 | 2
COMM-T180 | COMM | Execute C&E and SIF function tests | DCS / SIS config | COM | ICS-08 | Tests every cause and effect line and SIF end to end and records results against the SRS. | 4 | 1
COMM-T190 | COMM | Energise electrical systems | Smart Completions | CON, COM | CON-02 | Energises substations, switchboards and feeders under permit after protection testing and records energisation. | 5 | 1
COMM-T200 | COMM | Commission systems and confirm ready for start-up | Smart Completions | COM | CON-02 | Runs C-ITRs and system run-in tests, closes punch required for start-up and issues RFSU. | 7 | 2
COMM-T210 | COMM | Raise commissioning technical queries | Procore | COM | CON-02 | Raises queries and modification requests to engineering for design problems found during commissioning. | 4 | 1
COMM-T220 | COMM | Compile system turnover packages | Document Locator | COM | CON-02 | Assembles the turnover dossier per system: certificates, ITRs, test records, punch, vendor data and as-built list. | 4 | 1
COMM-T230 | COMM | Hand over systems to the owner | Smart Completions | COM | CON-02 | Hands over each system with the agreed punch list and turnover package and gets the owner handover certificate signed. | 3 | 1
COMM-T240 | COMM | Report completions progress | Smart Completions | CON, COM | CON-02 | Reports ITR, punch and certificate progress by system against the commissioning schedule. | 3 | 1
COMM-T250 | COMM | Support performance test run | Excel / Word | COM | CON-02 | Supports the owner's performance test run and compiles the test data against guarantees. | 3 | 1

## Items
ID | Discipline | Information | System | Form | Owner task | Content | Used by
OWNR-I010 | OWNR | Business case | Excel / Word | decision | OWNR-T010 | Project objective, nameplate capacity, economic hurdle rate, target start-up date and budget envelope. | 9
OWNR-I020 | OWNR | Product slate and specifications | Excel / Word | data | OWNR-T010 | Products with rates, quality specifications (sulfur, flash, distillation end points) and destinations. | 7
OWNR-I030 | OWNR | Crude assays and feed cases | Excel / Word | data | OWNR-T020 | Assay data (TBP, API, sulfur, metals, TAN) and design, check and turndown crude cases with rates. | 2
OWNR-I040 | OWNR | Site conditions data | Excel / Word | document | OWNR-T030 | Survey control and benchmarks, climatic design data, seismic zone, historic soil data and site access rules. | 13
OWNR-I050 | OWNR | Existing facility and utility data | Excel / Word | document | OWNR-T030 | As-built drawings and available capacity of existing utilities, flare, tankage, interconnecting piping and electrical supply. | 20
OWNR-I060 | OWNR | Owner standards and approved vendor list | Document Locator | document | OWNR-T040 | Owner engineering standards, order of precedence, allowed deviations, and approved vendor list by commodity. | 31
OWNR-I070 | OWNR | Owner design basis requirements | Excel / Word | document | OWNR-T050 | Design life, on-stream factor, turndown, sparing, design margins, utility conditions, environmental limits and winterisation. | 8
OWNR-I080 | OWNR | Risk tolerance criteria | Excel / Word | decision | OWNR-T060 | Risk matrix, individual and societal risk criteria and LOPA target frequencies. | 5
OWNR-I090 | OWNR | Gate decision | Excel / Word | decision | OWNR-T070 | Approval to proceed, selected option and conditions from each gate review. | 3
OWNR-I100 | OWNR | Permit approvals and conditions | Excel / Word | document | OWNR-T080 | Issued permits with limits and conditions (emissions, discharges, noise, construction hours). | 2
OWNR-I110 | OWNR | Owner comments on deliverables | Document Locator | document | OWNR-T090 | Owner comment sheets on IFR deliverables with code (approved, approved with comments, rejected). | 5
OWNR-I120 | OWNR | Operations and maintenance requirements | Excel / Word | document | OWNR-T100 | Sampling, isolation and blinding, drains, access, lifting, bundle pull, cleaning and maintenance-free intervals. | 5
OWNR-I130 | OWNR | Control and alarm management requirements | Excel / Word | document | OWNR-T110 | DCS/SIS platform, operator interface standards, alarm philosophy and integration with existing control room. | 7
OWNR-I140 | OWNR | Owner model review comments | iConstruct | data | OWNR-T120 | Model review comments by object/area on access, valve reach, maintenance clearance and escape, with action-by discipline. | 2
OWNR-I150 | OWNR | HAZOP action acceptance | PHA tool | decision | OWNR-T130 | Owner approval of HAZOP/LOPA action responses and residual risk. | 1
OWNR-I160 | OWNR | Tie-in and outage windows | P6 | data | OWNR-T140 | Turnaround and outage dates, tie-ins allowed in each window, and live-plant work constraints. | 4
OWNR-I170 | OWNR | Owner change approval | Excel / Word | decision | OWNR-T150 | Approve/reject decision on change requests and field changes, with conditions. | 3
OWNR-I180 | OWNR | Spares philosophy | Excel / Word | document | OWNR-T160 | Commissioning, capital and two-year operating spares policy, criticality rules and interchangeability targets. | 3
OWNR-I190 | OWNR | Approved operating spares list | Excel / Word | data | OWNR-T160 | Approved operating and capital spares by tag and part number with quantities, for procurement. | 2
OWNR-I200 | OWNR | CMMS asset data requirements | Excel / Word | document | OWNR-T170 | Asset hierarchy, equipment classes, required attributes per class, criticality and document link rules. | 4
OWNR-I210 | OWNR | Permit to work and isolation authorisation | Excel / Word | decision | OWNR-T180 | Issued permits to work, isolation certificates and site access for a work scope and date. | 2
OWNR-I220 | OWNR | Operating procedures | Excel / Word | document | OWNR-T190 | Normal, start-up, shutdown and emergency operating procedures by system. | 5
OWNR-I230 | OWNR | Owner test witness acceptance | Smart Completions | decision | OWNR-T200 | Owner signatures on witnessed walkdowns, loop checks, C&E tests and run-in. | 3
OWNR-I240 | OWNR | Handover acceptance | Smart Completions | decision | OWNR-T210 | Owner acceptance of a system with the agreed retained punch list and open-item dates. | 2
OWNR-I250 | OWNR | CMMS master data | Excel / Word | data | OWNR-T220 | Asset register loaded: functional locations, equipment records, attributes, BOMs and maintenance plans. | 1
OWNR-I260 | OWNR | CMMS data gap list | Excel / Word | data | OWNR-T220 | Missing or inconsistent asset data by tag and attribute, returned to the project for correction. | 1
OWNR-I270 | OWNR | Final documentation acceptance and deficiency list | Document Locator | decision | OWNR-T230 | Acceptance of as-built documents and data books, or deficiency list by document. | 1
OWNR-I280 | OWNR | Building programme and occupancy | Excel / Word | document | OWNR-T100 | Rooms required per building, staffing, occupancy hours and personnel counts (permanent and portable). | 2
OWNR-I281 | OWNR | Handover requirements and acceptance criteria | Excel / Word | document | OWNR-T210 | Owner handover requirements, operating organisation and system acceptance criteria. | 1
OWNR-I282 | OWNR | Contract performance guarantees | Excel / Word | document | OWNR-T050 | Guaranteed capacity, yields, utilities and the acceptance criteria for the performance test. | 1
OWNR-I283 | OWNR | Plant historian start-up data | Excel / Word | data | OWNR-T200 | Operating data from the DCS historian during start-up and the performance test. | 1
OWNR-I284 | OWNR | Owner cost structure and AFE codes | Excel / Word | data | OWNR-T010 | Owner cost reporting structure, AFE and capital codes and mapping to the project code of accounts. | 1
OWNR-I285 | OWNR | Invoices paid and back-charges | Excel / Word | data | OWNR-T240 | Invoices paid by PO and cost code, final invoice and back-charge status per PO. | 2
OWNR-I286 | OWNR | Incident history and previous PHAs | Excel / Word | document | OWNR-T130 | Site and corporate incident history, five-year accident history, previous PHAs of similar units, HAZID guidewords and nominated attendees. | 3
OWNR-I287 | OWNR | Surroundings, population and receptors | Excel / Word | data | OWNR-T030 | Neighbouring facilities, land boundaries, onsite and offsite population, ignition sources and public and environmental receptors. | 3
OWNR-I288 | OWNR | Emergency response organisation | Excel / Word | document | OWNR-T100 | Site emergency organisation, fire department and mutual aid capability, responder resources and insurer requirements. | 3
OWNR-I289 | OWNR | Permit strategy approval | Excel / Word | decision | OWNR-T080 | Approved permit strategy, responsible official signatory and agency pre-application outcomes. | 1
OWNR-I290 | OWNR | Operator training and emergency readiness record | Excel / Word | document | OWNR-T190 | Operator training records and emergency response readiness confirmation for the PSSR. | 1
OWNR-I291 | OWNR | Owner award approval | Excel / Word | decision | OWNR-T070 | Approval of purchase awards above delegated authority. | 1
OWNR-I292 | OWNR | Owner witness point selection | Excel / Word | decision | OWNR-T090 | Owner witness and hold points selected per PO and ITP. | 1
PROJ-I010 | PROJ | Project execution plan | Excel / Word | document | PROJ-T010 | Scope, organisation, phase plan, work split, gate criteria, key procedures, reporting requirements. | 11
PROJ-I020 | PROJ | Contracting and procurement strategy | Excel / Word | decision | PROJ-T020 | Contract packages, procurement packages, owner/contractor-furnished split, long-lead items to commit early, approved commercial terms. | 4
PROJ-I030 | PROJ | WBS, area codes and cost codes | P6 | data | PROJ-T030 | WBS levels, area and unit codes, cost codes, P6 activity codes and calendars. | 8
PROJ-I040 | PROJ | Document numbering procedure and codes | Document Locator | document | PROJ-T040 | Numbering format, discipline, document type and area codes, revision and issue-purpose conventions, required metadata. | 6
PROJ-I050 | PROJ | Document Locator structure and distribution matrix | Document Locator | data | PROJ-T040 | Folder structure, review workflows, distribution matrix by document type and recipient (owner, vendor, construction). | 2
PROJ-I060 | PROJ | Deliverables register | Document Locator | data | PROJ-T050 | Document number, title, discipline, type, planned and actual IFR/IFD/IFC dates, current revision and status. | 12
PROJ-I070 | PROJ | Assigned document numbers | Document Locator | data | PROJ-T050 | Document numbers reserved for each discipline's new deliverables, including vendor document numbers per PO. | 4
PROJ-I080 | PROJ | Estimate quantity request | Excel / Word | document | PROJ-T070 | Quantity take-off template per discipline, estimate class, basis, code of accounts and due date. | 7
PROJ-I090 | PROJ | Class 5 estimate | Excel / Word | document | PROJ-T060 | Order-of-magnitude capital cost by unit, accuracy range, basis and exclusions. | 2
PROJ-I100 | PROJ | Class 4 estimate | Excel / Word | document | PROJ-T080 | Equipment-factored cost by area and code of accounts, contingency, basis of estimate. | 3
PROJ-I110 | PROJ | Class 3 estimate | Excel / Word | document | PROJ-T090 | Detailed cost by WBS and commodity, unit rates, labour hours, indirects, contingency, basis of estimate. | 4
PROJ-I120 | PROJ | Control budget | Excel / Word | data | PROJ-T100 | Budget by WBS and cost code, contingency and management reserve. | 1
PROJ-I130 | PROJ | Baseline integrated schedule | P6 | data | PROJ-T110 | Level 2/3 activities, logic, durations and baseline dates for engineering, procurement, construction and commissioning. | 10
PROJ-I140 | PROJ | Deliverable schedule dates | P6 | data | PROJ-T110 | Planned IFR/IFD/IFC dates per deliverable sent to each discipline lead. | 10
PROJ-I150 | PROJ | Required-on-site and need dates per MR | P6 | data | PROJ-T110 | Required-on-site (ROS) date per MR and equipment tag, MR issue need date, PO award need date. | 4
PROJ-I160 | PROJ | Procurement and vendor dates in P6 | P6 | data | PROJ-T120 | PO award, vendor data return and forecast delivery dates linked to engineering and construction activities. | 1
PROJ-I170 | PROJ | Engineering progress and earned value | P6 | data | PROJ-T130 | Percent complete per deliverable and discipline, earned hours, SPI/CPI. | 1
PROJ-I180 | PROJ | Schedule update and critical path report | P6 | document | PROJ-T140 | Updated dates, critical and near-critical paths, float, look-ahead and recovery actions. | 1
PROJ-I190 | PROJ | Cost report and forecast | Excel / Word | document | PROJ-T150 | Budget, commitments, actuals, estimate to complete and forecast at completion by WBS. | 1
PROJ-I200 | PROJ | Trend register | Excel / Word | data | PROJ-T160 | Trend number, description, originator, rough cost and schedule impact, status. | 6
PROJ-I210 | PROJ | Approved change notice | Excel / Word | decision | PROJ-T160 | Change number, scope description, affected deliverables and POs, approved cost and schedule adjustment. | 4
PROJ-I220 | PROJ | Gate review package | Document Locator | document | PROJ-T170 | Deliverables, estimate, schedule, risk and readiness checklist for the gate. | 1
PROJ-I230 | PROJ | Gate decision | Document Locator | decision | PROJ-T170 | Owner decision to proceed, recycle or stop, with conditions and actions. | 1
PROJ-I240 | PROJ | Risk register | Excel / Word | data | PROJ-T180 | Risk ID, description, owner, probability, impact, mitigation and status. | 2
PROJ-I250 | PROJ | Contingency analysis result | Excel / Word | document | PROJ-T180 | P50/P90 cost and schedule results, recommended contingency and drivers. | 2
PROJ-I260 | PROJ | Interface register | Excel / Word | data | PROJ-T190 | Interface ID, parties, description, required date, status and agreement reference. | 2
PROJ-I270 | PROJ | Interface query and agreement | Excel / Word | decision | PROJ-T190 | Request for interface data and the agreed response (terminal point, design values, responsibility). | 2
PROJ-I280 | PROJ | Transmittal | Document Locator | document | PROJ-T200 | Transmittal number, recipient, documents and revisions, issue purpose, review due date. | 3
PROJ-I290 | PROJ | Consolidated comment sheet | Document Locator | document | PROJ-T210 | Comments from all reviewers per document with commenter, reply and close-out. | 1
PROJ-I300 | PROJ | Document review status | Document Locator | data | PROJ-T210 | Review code per document revision (approved, approved with comments, rejected) and return date. | 1
PROJ-I310 | PROJ | Hold list | Excel / Word | data | PROJ-T220 | Hold number, document, cause, responsible party, required information and target release date. | 2
PROJ-I320 | PROJ | IFC release and seal record | Document Locator | data | PROJ-T230 | Document, revision, checker, approver, seal holder and IFC release date. | 4
PROJ-I330 | PROJ | Monthly progress report | Excel / Word | document | PROJ-T240 | Progress, cost, schedule, changes, risks, procurement and HSE status for the owner. | 1
PROJ-I340 | PROJ | Construction progress in P6 | P6 | data | PROJ-T250 | Installed quantities and percent complete per CWP/IWP, earned hours. | 2
PROJ-I350 | PROJ | Final records index | Document Locator | data | PROJ-T260 | Final as-built document list, vendor data books and turnover records with locations for owner handover. | 3
PROJ-I360 | PROJ | Project close-out report | Excel / Word | document | PROJ-T260 | Final cost, schedule, lessons learned and open items at close. | 1
PROJ-I370 | PROJ | VDRL template by requisition type | Excel / Word | document | PROJ-T020 | Standard vendor document requirements per requisition type. | 1
PROJ-I371 | PROJ | Project specification and code list | Document Locator | document | PROJ-T010 | Project specifications, code editions, order of precedence and requested deviations from owner standards. | 2
PROJ-I372 | PROJ | Engineering data handover specification | Excel / Word | document | PROJ-T040 | SPF tag classes and attributes available from engineering systems for handover. | 1
PROJ-I373 | PROJ | Bulk surplus and allowance policy | Excel / Word | document | PROJ-T020 | Surplus allowance percent by commodity and size. | 1
PROC-I010 | PROC | Process design basis | Excel / Word | document | PROC-T010 | Capacity, turndown, on-stream factor, feed and product specifications, design margins, ambient design conditions, sparing philosophy, design cases. | 9
PROC-I015 | PROC | Battery-limit conditions | Excel / Word | data | PROC-T010 | Per battery-limit stream: pressure, temperature, flow range, composition at import/export points (feeds, products, utilities, flare, effluents). | 1
PROC-I020 | PROC | Feed characterisation basis | HYSYS | model | PROC-T020 | Pseudo-component set, assay cuts and properties, blend cases, property package selection, contaminant distribution basis. | 3
PROC-I030 | PROC | Screening case results | HYSYS | data | PROC-T030 | Per option: product yields and qualities, major heater/exchanger duties, column count, power and fuel demand, CO2 estimate. | 4
PROC-I040 | PROC | Block flow diagrams | Excel / Word | drawing | PROC-T030 | Unit blocks, main feed/product/intermediate streams, overall material balance and capacities per option. | 9
PROC-I050 | PROC | Screening equipment list | Excel / Word | data | PROC-T030 | Equipment type, count, key size parameter (duty, diameter, flow, power), material class per option for Class 5 estimate. | 4
PROC-I060 | PROC | Alternative case balances | HYSYS | data | PROC-T060 | Per alternative: overall H&MB, product yields, heat integration (pinch/target), utility demand, major equipment duties. | 5
PROC-I070 | PROC | Technology evaluation (process) | Excel / Word | document | PROC-T070 | Normalised licensor comparison: yields, utilities, catalyst life, guarantee basis, maturity and process risks, recommendation. | 2
PROC-I080 | PROC | Selected process configuration | Excel / Word | decision | PROC-T080 | Agreed configuration, unit capacities, technology choice, key design cases and reasons for selection. | 3
PROC-I090 | PROC | Utility and offsite basis | Excel / Word | document | PROC-T090 | Utility supply/return conditions (P, T, quality) per system, availability, tankage days, interconnecting lines, flare system basis. | 5
PROC-I095 | PROC | Process layout requirements | Excel / Word | document | PROC-T095 | Minimum elevations (NPSHa, thermosiphon, gravity drain), close-coupling, slope/no-pocket lines, equipment adjacency and operating access needs. | 5
PROC-I100 | PROC | Calibrated simulation model | HYSYS | model | PROC-T100 | Rigorous HYSYS case per design case (summer/winter, max/min throughput, start-of-run/end-of-run), calibration notes. | 3
PROC-I110 | PROC | Stream data | HYSYS | data | PROC-T110 | Per stream and case: flow (mass, molar, std vol), P, T, vapour fraction, composition, density, viscosity, MW, Cp, thermal conductivity, surface tension. | 17
PROC-I111 | PROC | Design and operating case list | Excel / Word | data | PROC-T110 | Design, check, turndown, start-up and upset cases with defining conditions and which equipment each governs. | 5
PROC-I112 | PROC | Corrosion-relevant process data | Excel / Word | data | PROC-T110 | Per circuit: H2S, CO2, chlorides, ammonia, free water, naphthenic acid, sulfur species, oxygen, operating T/P for corrosion and material selection. | 5
PROC-I120 | PROC | Process flow diagrams | Excel / Word | drawing | PROC-T120 | Major equipment with tags and duties, main lines with stream numbers, main control loops, stream table extract, utility interfaces. | 8
PROC-I130 | PROC | Design pressure and temperature basis | Excel / Word | data | PROC-T130 | Per system/equipment: max/min operating and design pressure, design and minimum design metal temperature, steam-out and vacuum conditions, settle-out pressure. | 11
PROC-I136 | PROC | Process agreement of materials selection | Excel / Word | decision | PROC-T135 | Process sign-off on materials and corrosion allowances per service, with the corrosion cases they cover. | 2
PROC-I140 | PROC | Vessel and column process sizing | Excel / Word | data | PROC-T140 | ID, T/T, liquid levels (LL/LLL/NLL/HLL/HHLL), residence times, nozzle duties, internals type and count, tray loading and flood margin. | 6
PROC-I150 | PROC | Rotating equipment process duties | Excel / Word | data | PROC-T150 | Per pump/compressor: rated/normal/min flow, suction/discharge P, differential head, NPSHa, fluid properties, sparing, driver preference, operating cases. | 4
PROC-I155 | PROC | Preliminary exchanger sizing | HYSYS | model | PROC-T155 | Duty, LMTD, preliminary area and allowable pressure drop per exchanger for screening and as the starting point for HTRI design. | 4
PROC-I160 | PROC | Equipment process duties | Excel / Word | data | PROC-T160 | Per equipment tag: service, type, duty/capacity, operating and design P/T, size, MoC recommendation, insulation, sparing. | 8
PROC-I170 | PROC | Vessel and column process datasheets | Excel / Word | document | PROC-T170 | Sketch, ID/T-T, levels, nozzle schedule with duties, internals, design/operating conditions, corrosion allowance basis, fluid data. | 5
PROC-I171 | PROC | Tank process datasheets | Excel / Word | document | PROC-T170 | Working/gross capacity, fill/draw rates, vapour pressure, breathing/emission data, blanketing, heating, mixer duty, levels. | 3
PROC-I175 | PROC | Shell-and-tube and plate exchanger process datasheets | Excel / Word | document | PROC-T175 | TEMA datasheet process part: duty, fluid allocation, flows, in/out T, properties, fouling, allowable dP, design P/T. | 3
PROC-I176 | PROC | Air cooler process datasheets | Excel / Word | document | PROC-T175 | Duty, process flows and properties, design air temperature, fan control requirement, winterisation, allowable dP. | 2
PROC-I177 | PROC | Fired heater process datasheet | Excel / Word | document | PROC-T175 | Absorbed duty per case, coil inlet/outlet conditions, vaporisation, allowable flux and film temperature, fuel composition, emission limits, turndown. | 4
PROC-I180 | PROC | Pump process datasheets | Excel / Word | document | PROC-T180 | Rated/normal/min flow, suction/discharge P, head, NPSHa, fluid properties, solids, operating cases, sealing considerations. | 4
PROC-I181 | PROC | Compressor process datasheets | Excel / Word | document | PROC-T180 | Gas composition per case, inlet/outlet P/T, flows, MW, k, Z, surge/turndown, settle-out pressure, control method. | 3
PROC-I185 | PROC | Package process specifications | Excel / Word | document | PROC-T185 | Per package: duty, feed and product specs, battery-limit P/T/flows, utility availability, turndown, process guarantees required. | 3
PROC-I190 | PROC | Line sizing results | Excel / Word | data | PROC-T190 | Per line: size, velocity, dP/100 m, rho-v2, two-phase flow regime, governing case, critical-line flags (slope, no pocket, two-phase). | 8
PROC-I200 | PROC | P&IDs issued for review | SPID | drawing | PROC-T200 | IFR P&IDs: equipment, lines with sizes/spec breaks, valves, instruments, control and trip loops, notes and holds. | 16
PROC-I201 | PROC | HAZOP-ready P&IDs | SPID | drawing | PROC-T200 | P&IDs issued for HAZOP with all relief, interlocks, set points, design P/T and holds listed, frozen revision for workshop. | 9
PROC-I210 | PROC | Line process data | SPID | data | PROC-T210 | Per line: from/to, fluid code, phase, flow, operating/design P/T, test pressure basis, insulation and tracing requirement, critical-line flags. | 13
PROC-I220 | PROC | Instrument process data | Excel / Word | data | PROC-T220 | Per tag: fluid, phase, min/normal/max flow, P, T, density, viscosity, MW, vapour pressure, CV allowable dP and shut-off dP, level ranges, set points. | 3
PROC-I230 | PROC | Control philosophy | Excel / Word | document | PROC-T230 | Control strategy for throughput, quality, pressure and inventory; manual vs automatic; APC scope; alarm philosophy input. | 7
PROC-I231 | PROC | Control narratives | Excel / Word | document | PROC-T230 | Per loop group: measured/controlled variables, cascades, overrides, split-range, ratio and sequence logic, set points. | 6
PROC-I235 | PROC | Trip and interlock schedule | Excel / Word | data | PROC-T235 | Per trip: initiator tag, set point, voting preference, final elements and action, reset type, process safety time, bypass needs. | 9
PROC-I240 | PROC | Operating philosophy | Excel / Word | document | PROC-T230 | Operating modes, turndown, sparing, run length, start-up/shutdown approach, isolation and blinding philosophy, sampling. | 13
PROC-I250 | PROC | Relief load summary | Flare / relief tool | data | PROC-T250 | Per device: governing scenario, relief load, fluid composition, MW, T, Z, k, set and back pressure, coincident loads by scenario. | 10
PROC-I251 | PROC | PSV process datasheets | Excel / Word | document | PROC-T250 | Per PSV: set pressure, relieving rate, relieving conditions, fluid properties, required area and orifice letter, back pressure, discharge destination. | 4
PROC-I255 | PROC | Process review of vendor relief valve sizing | Excel / Word | decision | PROC-T255 | Per PSV: governing case, required versus rated capacity, inlet loss and back pressure check, accept or resize. | 1
PROC-I260 | PROC | Flare network hydraulic results | Flare / relief tool | data | PROC-T260 | Header and sub-header sizes, back pressure at each device, Mach and rho-v2, KO drum and flare tip loads per scenario. | 2
PROC-I261 | PROC | Depressuring study results | Flare / relief tool | document | PROC-T260 | Per segment: inventory, restriction orifice size, peak rate, minimum metal temperature, time to target pressure. | 3
PROC-I270 | PROC | Utility consumption list | Excel / Word | data | PROC-T270 | Per consumer: steam by level, cooling water, instrument/plant air, nitrogen, fuel gas, BFW, condensate return, power estimate; normal/peak/intermittent. | 1
PROC-I271 | PROC | Utility system balances | Excel / Word | document | PROC-T270 | Steam/condensate, CW, air, N2 and fuel gas balances per case with generator/user sizing requirements. | 2
PROC-I275 | PROC | Chemical and catalyst consumption list | Excel / Word | data | PROC-T270 | Per chemical/catalyst: service, dosing point, normal/max rate, first fill quantity, storage days, hazard class, replacement frequency. | 4
PROC-I280 | PROC | Effluent and emissions data | Excel / Word | data | PROC-T280 | Per source: flow, composition, temperature, frequency; CO2/NOx/SOx/VOC per point source and fugitive basis; solid/liquid waste quantities. | 4
PROC-I285 | PROC | Release source and fluid data | Excel / Word | data | PROC-T280 | Per isolatable section or release source: composition, P, T, phase, inventory, flash point, MW, toxic content (H2S), fluid category for HAC. | 9
PROC-I290 | PROC | Process description and design report | Excel / Word | document | PROC-T290 | Process description by section, design cases, key design decisions, deviations from basis, open items and assumptions. | 2
PROC-I300 | PROC | HAZOP action responses (process) | PHA tool | decision | PROC-T300 | Per action: response, design change made, P&ID reference, closure evidence, status. | 1
PROC-I301 | PROC | P&ID markups from HAZOP | SPID | drawing | PROC-T300 | Clouded P&ID changes agreed in HAZOP/LOPA (new instruments, valves, relief, trips) for incorporation. | 4
PROC-I305 | PROC | Process technical bid evaluation input | Excel / Word | document | PROC-T305 | Per bidder: compliance with process duties, deviations, clarification questions, utility and performance comparison, acceptability. | 1
PROC-I310 | PROC | Process comments on vendor data | Document Locator | document | PROC-T310 | Commented vendor documents with process review code, deviations, required changes and holds. | 1
PROC-I315 | PROC | As-designed H&MB (vendor reconciled) | HYSYS | data | PROC-T315 | Final stream data and duties reflecting certified equipment, list of changed values affecting line list, instruments and relief. | 1
PROC-I320 | PROC | Process TQ responses and hold releases | Excel / Word | decision | PROC-T320 | Per query/hold: answer, data value confirmed or revised, affected documents, release date. | 2
PROC-I325 | PROC | Process comments on instrument datasheets | Document Locator | document | PROC-T325 | Comments on CV/FE/PSV/level instrument datasheets: data mismatches, rangeability, fail position, shut-off class. | 1
PROC-I330 | PROC | Process 3D model review comments | S3D | document | PROC-T330 | Model review comments: slope/pocket violations, NPSH elevations, two-phase symmetry, PSV location, sample/drain access. | 1
PROC-I335 | PROC | Tie-in process conditions | Excel / Word | data | PROC-T210 | Per tie-in: fluid, operating/design P/T, flow, hot-tap feasibility from process view, isolation and purging requirement, shutdown dependency. | 1
PROC-I340 | PROC | P&IDs issued for design | SPID | drawing | PROC-T340 | IFD P&IDs with HAZOP changes incorporated and remaining holds listed. | 15
PROC-I341 | PROC | P&IDs issued for construction | SPID | drawing | PROC-T340 | IFC P&IDs, holds cleared, vendor data incorporated, approved for construction. | 8
PROC-I345 | PROC | Process change impact assessment | Excel / Word | document | PROC-T320 | Per change: affected streams, equipment, lines, relief and safety, rework estimate, need for HAZOP re-review. | 3
PROC-I350 | PROC | Operating manual process input | Excel / Word | document | PROC-T350 | Process description, operating limits and integrity operating windows, control and trip descriptions, sampling plan, troubleshooting guidance. | 4
PROC-I355 | PROC | Process system boundary markups | SPID | drawing | PROC-T360 | P&IDs coloured by process system/subsystem with boundaries, isolation points and commissioning sequence preference. | 1
PROC-I360 | PROC | Process commissioning requirements | Excel / Word | document | PROC-T360 | Per system: cleaning/flushing method, drying and dew point, inerting and oxygen limits, run-in fluids, catalyst/chemical loading, first-fill list. | 2
PROC-I365 | PROC | Start-up and shutdown procedures | Excel / Word | document | PROC-T365 | Step-by-step initial and normal start-up, normal and emergency shutdown, with checkpoints, set points and hold points. | 3
PROC-I370 | PROC | Process RFI responses and field change dispositions | Procore | decision | PROC-T370 | Per RFI/field change: process answer, accept/reject, P&ID impact, need for MOC/HAZOP review. | 2
PROC-I375 | PROC | Commissioning process punch and troubleshooting log | Excel / Word | data | PROC-T375 | Process deficiencies found at commissioning, root cause, recommended change, set point adjustments, status. | 1
PROC-I380 | PROC | Performance test procedure and report | Excel / Word | document | PROC-T375 | Test conditions, measurements, sampling plan, correction methods, results vs guarantees, acceptance recommendation. | 1
PROC-I385 | PROC | As-built P&IDs | SPID | drawing | PROC-T385 | As-built P&IDs and line process data reflecting field changes and commissioning modifications for handover. | 3
PROC-I390 | PROC | Analyzer requirements | Excel / Word | data | PROC-T220 | Analyzer stream, components to measure, ranges and response time. | 1
PROC-I391 | PROC | Assay data gaps and requested cuts | Excel / Word | data | PROC-T020 | Missing assay data and additional cuts requested (TBP, sulfur, metals, acidity). | 1
PROC-I392 | PROC | Flare stack basis | Flare / relief tool | data | PROC-T260 | Flare stack height, tip type and diameter, and location basis. | 1
PROC-I901 | PROC | Process deliverables list | Excel / Word | data | PROC-T005 | Process deliverables with type, sheet count and planned IFR/IFD/IFC dates. | 1
PROC-I902 | PROC | Process progress measurement | Excel / Word | data | PROC-T005 | Percent complete per process deliverable by rules of credit. | 1
SAFE-I010 | SAFE | Environmental constraints register | Excel / Word | document | SAFE-T010 | Attainment status and PSD/NSR applicability triggers, receiving water limits, wetland and habitat constraints, nearby receptors and fence-line distances, noise limits at property line, permit lead times. | 9
SAFE-I015 | SAFE | Option SHE screening ranking | Excel / Word | decision | SAFE-T015 | Per option: inherent safety score, toxic/flammable inventory, worst-case offsite distance, emissions estimate and permitting pathway (minor vs major source), recommended option and risks. | 4
SAFE-I020 | SAFE | HAZID / ENVID register | PHA tool | document | SAFE-T020 | Hazards by area and node, causes, consequences, existing safeguards, risk ranking against owner matrix, environmental aspects. | 4
SAFE-I022 | SAFE | HAZID actions list | PHA tool | data | SAFE-T020 | Action number, description, responsible discipline, due phase, priority; used to steer layout, philosophy and design basis. | 3
SAFE-I030 | SAFE | Site selection SHE assessment | Excel / Word | document | SAFE-T030 | Per site: distance to public receptors, preliminary worst-case hazard zones, flood/wind exposure, permit complexity score, emergency services access; recommended site. | 2
SAFE-I035 | SAFE | Hazardous materials inventory and properties | Excel / Word | data | SAFE-T035 | Material, area, inventory (kg), flash point, LFL/UFL, autoignition temperature, gas group/T-class, IDLH/ERPG/AEGL, RMP threshold quantity check, OSHA PSM threshold check. | 8
SAFE-I040 | SAFE | SHE design basis | Excel / Word | document | SAFE-T040 | Codes and regulations, risk tolerance criteria, design blast and fire loads method, toxic thresholds, F&G performance targets, fire water design basis, noise limits, emission targets and study schedule. | 8
SAFE-I050 | SAFE | Preliminary hazard distances and spacing comments | Excel / Word | document | SAFE-T050 | Jet/pool fire radiation distances, flash fire extents, overpressure contours, toxic distances, recommended equipment spacing changes, building locations and sterile areas; marked-up plot plan. | 13
SAFE-I060 | SAFE | Emissions inventory | Excel / Word | data | SAFE-T060 | Per source: tag, pollutant (NOx, CO, VOC, SO2, PM, HAPs, GHG CO2e), emission factor basis, hourly and annual PTE, stack parameters (height, diameter, temperature, velocity, location). | 3
SAFE-I062 | SAFE | Emission control requirements | Excel / Word | document | SAFE-T060 | BACT/LAER and NSPS/NESHAP requirements by source: low-NOx burner or SCR, CEMS, tank seal type and vapour control, LDAR program, flare monitoring (40 CFR 63 CC) requirements to PROC, MECH and INST. | 12
SAFE-I070 | SAFE | Air permit application package | Excel / Word | document | SAFE-T070 | Application forms, emission calculations, dispersion modelling results, BACT analysis, regulatory applicability review, submitted to the agency. | 1
SAFE-I072 | SAFE | Permit conditions register | Excel / Word | data | SAFE-T070 | Each permit condition: source, limit, monitoring/recordkeeping requirement, design impact, construction/startup notification deadline, responsible party. | 4
SAFE-I080 | SAFE | Wastewater and stormwater permit data | Excel / Word | document | SAFE-T080 | Effluent characterization, outfall data, NOI and SWPPP basis, pretreatment limits, monitoring points. | 3
SAFE-I082 | SAFE | Secondary containment and spill control requirements | Excel / Word | document | SAFE-T080 | SPCC-covered containers, required containment volumes (110% plus rainfall), dike and curb locations, contaminated firewater runoff containment, oil/water separator basis; to CIVL. | 3
SAFE-I090 | SAFE | Preliminary HAZOP actions | Excel / Word | data | SAFE-T090 | Actions requiring design change (overpressure scenarios, isolation, materials, layout), responsible discipline, priority. | 2
SAFE-I100 | SAFE | Building blast loads | Excel / Word | data | SAFE-T100 | Per building: side-on peak overpressure, impulse, duration and reflected loads by wall, design frequency basis; to CIVL for blast-resistant design. | 5
SAFE-I102 | SAFE | Building siting decisions and occupancy restrictions | Excel / Word | decision | SAFE-T100 | Building acceptability per API 752, relocation or hardening required, occupancy limits, control room and lab location agreement. | 9
SAFE-I104 | SAFE | Portable building siting restrictions | Excel / Word | document | SAFE-T100 | Exclusion zones for trailers per API 753 for construction, turnaround and commissioning; allowed locations and construction requirements. | 1
SAFE-I110 | SAFE | Building toxic ingress and HVAC shutdown requirements | Excel / Word | document | SAFE-T110 | Required H2S/flammable detectors at HVAC intakes, damper closure times, building tightness, shelter-in-place capability, CO2/SCBA provisions; to CIVL (HVAC) and INST. | 2
SAFE-I120 | SAFE | QRA results | Excel / Word | document | SAFE-T120 | Individual risk contours, location-specific risk, F-N curve, PLL, risk ranking of contributors, comparison to criteria. | 2
SAFE-I122 | SAFE | QRA risk reduction recommendations | Excel / Word | data | SAFE-T120 | Recommended measures (isolation valves, detection, spacing, inventory reduction) with risk benefit, owner discipline and status. | 2
SAFE-I130 | SAFE | Flare radiation and sterile zone results | Excel / Word | document | SAFE-T130 | Radiation contours at grade (1.58, 4.73, 6.31, 9.46 kW/m2), sterile zone radius, dispersion of unignited release and H2S, noise at boundary; required stack height changes. | 2
SAFE-I140 | SAFE | Relief study review comments | Document Locator | document | SAFE-T140 | Comments on missing scenarios, fire-case wetted areas versus fire zones, depressuring target times (API 521), and credited safeguards. | 1
SAFE-I150 | SAFE | HAZOP worksheets and report | PHA tool | document | SAFE-T150 | Nodes, design intent, deviations, causes, consequences, safeguards, severity/likelihood ranking, attendance and P&ID revision basis. | 5
SAFE-I152 | SAFE | HAZOP recommendations register | PHA tool | data | SAFE-T150 | Recommendation number, P&ID and node, description, responsible discipline and person, priority, due date, LOPA referral flag. | 9
SAFE-I160 | SAFE | LOPA scenarios and SIL targets | PHA tool | data | SAFE-T160 | Per scenario: initiating event and frequency, enabling conditions, IPLs credited with PFD, mitigated frequency, gap; per SIF: tag, required SIL/RRF, process safety time, safe state; to INST for SRS. | 10
SAFE-I162 | SAFE | Non-SIF IPL and safeguard requirements | PHA tool | data | SAFE-T160 | Credited BPCS loops, alarms with operator response time, PSVs, check valves and mechanical IPLs requiring independence, testing and management as safety-critical. | 2
SAFE-I170 | SAFE | Action close-out records | PHA tool | data | SAFE-T170 | Per action: response, evidence document number and revision, verification by SAFE, owner acceptance, closure date; open items carried to PSSR. | 6
SAFE-I180 | SAFE | F&G detector layout and coverage | Excel / Word | drawing | SAFE-T180 | Detector tag, type, location coordinates, elevation, orientation, coverage maps and achieved coverage per zone; to INST for F&G system design and PIPE/INST for installation. | 2
SAFE-I182 | SAFE | F&G zones and executive action requirements | Excel / Word | data | SAFE-T180 | F&G zone list, detector voting per zone, alarm and executive actions (ESD, deluge release, HVAC trip, beacons), to INST for F&G C&E. | 6
SAFE-I210 | SAFE | Emergency isolation valve requirements | Excel / Word | data | SAFE-T210 | EIV/ROEIV location, initiating causes, closure time, fire-safe test (API 607), fireproofing of actuator and cable, operation point outside fire zone; to PROC and INST. | 1
SAFE-I230 | SAFE | Safety equipment and escape route layout | Excel / Word | drawing | SAFE-T230 | Locations of safety showers/eyewashes (with utility needs), escape routes, muster points, windsocks, alarm beacons and horns; to PIPE, CIVL and ELEC. | 8
SAFE-I240 | SAFE | Equipment noise limits | Excel / Word | data | SAFE-T240 | Maximum sound pressure level at 1 m per equipment type and tag for datasheets and requisitions; to MECH and INST. | 4
SAFE-I242 | SAFE | Noise study results and mitigation | Excel / Word | document | SAFE-T240 | Noise contours, fence-line levels, hearing protection zones, required mitigation (silencers, enclosures, acoustic insulation). | 1
SAFE-I250 | SAFE | Safety model review comments | S3D | document | SAFE-T250 | Model review comments on spacing (API 2510/NFPA 30), escape and access, firefighting access, valve operability in fire zones; tracked to closure. | 1
SAFE-I255 | SAFE | Hazardous area classification review comments | Document Locator | document | SAFE-T255 | Comments on missing sources, classification extents, gas group/T-class. | 2
SAFE-I260 | SAFE | C&E and SIL verification review comments | Document Locator | document | SAFE-T260 | Comments where achieved SIL is below target, missing trips or executive actions, proof test intervals inconsistent with LOPA. | 1
SAFE-I270 | SAFE | Vendor SHE review comments | Document Locator | document | SAFE-T270 | Technical bid and vendor document comments: noise exceedances, emission guarantee gaps, missing safety devices, package HAZOP requirements. | 1
SAFE-I280 | SAFE | Package and revalidation HAZOP actions | PHA tool | data | SAFE-T280 | Recommendations from package HAZOPs and change revalidation sessions with responsible discipline and priority. | 1
SAFE-I290 | SAFE | PSM process safety information package | Document Locator | document | SAFE-T290 | PSI index: chemical hazards, technology information, equipment information, PHA reports and close-out, safe operating limits; to OWNR. | 1
SAFE-I300 | SAFE | RMP offsite consequence and registration data | Excel / Word | document | SAFE-T300 | Worst-case and alternative release scenarios, endpoint distances, residential population and environmental receptors affected, program level, registration data for EPA submission by OWNR. | 1
SAFE-I310 | SAFE | Emergency response planning data | Excel / Word | document | SAFE-T310 | Credible emergency scenarios, hazard zones, alarm tones, muster and evacuation routes, firefighting resources and pre-fire plan data. | 1
SAFE-I320 | SAFE | Construction environmental compliance requirements | Excel / Word | document | SAFE-T320 | SWPPP BMPs, inspection frequencies, dust and waste controls, construction start notifications, temporary facility siting per API 753; to CONS. | 1
SAFE-I330 | SAFE | MOC safety review decisions | Procore | decision | SAFE-T330 | Per change: safety impact classification, required reviews (HAZOP, LOPA, siting, F&G), PSI documents to update, approval or rejection. | 2
SAFE-I340 | SAFE | PSSR checklist and findings | Smart Completions | data | SAFE-T340 | Per system: checklist items, findings, pre-startup and post-startup actions, responsible party, status. | 1
SAFE-I342 | SAFE | PSSR sign-off | Smart Completions | decision | SAFE-T340 | Approval to introduce hydrocarbons per system, with conditions and authorizing signatures. | 1
SAFE-I350 | SAFE | Startup environmental compliance records | Excel / Word | document | SAFE-T350 | Agency notifications, stack test protocols, CEMS certification plan, LDAR component inventory and monitoring schedule; to OWNR. | 1
SAFE-I360 | SAFE | As-built safety studies | Excel / Word | document | SAFE-T360 | Final revisions of siting study, F&G mapping, QRA, fire water and fireproofing studies; to OWNR via handover. | 1
SAFE-I370 | SAFE | Security vulnerability assessment | Excel / Word | document | SAFE-T040 | Security risks, required CCTV coverage and access control. | 1
FIRE-I045 | FIRE | Fire protection and F&G philosophy | Excel / Word | document | FIRE-T045 | Fire water source and redundancy, fixed system types per hazard, fireproofing criteria (API 2218), detector types, coverage targets, voting (2ooN), executive actions, alarm and beacon philosophy. | 9
FIRE-I190 | FIRE | Fire water demand and pump duty | Excel / Word | data | FIRE-T190 | Design scenario, deluge/monitor/hydrant/foam flows, total demand, required residual pressure, duration and storage volume; for the fire pump datasheets and PROC utility balance. | 4
FIRE-I192 | FIRE | Fire water network, hydrant and monitor layout requirements | Excel / Word | drawing | FIRE-T190 | Ring main sizing basis, hydrant and monitor locations and spacing, isolation valve sectioning, hose reel and foam connection locations; to PIPE/CIVL. | 5
FIRE-I200 | FIRE | Fire zones and fireproofing envelopes | Excel / Word | drawing | FIRE-T200 | Fire-scenario envelope boundaries in plan and elevation, fire zone numbers for relief fire case and deluge. | 6
FIRE-I202 | FIRE | Fireproofing requirements list | Excel / Word | data | FIRE-T200 | Steel members, skirts, vessel supports, cable trays and actuators needing fireproofing, rating (hours), test standard (UL 1709), extent; to CIVL, ELEC, INST. | 2
FIRE-I220 | FIRE | Fixed fire protection system requirements | Excel / Word | document | FIRE-T220 | System type and coverage per area (NFPA 11/13/15/2001), design density, deluge valve locations and activation logic, extinguisher schedule; to MECH (package requisition) and INST. | 8
FIRE-I230 | FIRE | Fire pump and fire protection equipment datasheets | Excel / Word | document | FIRE-T230 | Fire pump rated flow and head, driver type and rating, jockey pump, deluge and foam skid data, monitors, hydrants, NFPA 20 / 15 / 11 requirements. | 4
FIRE-I231 | FIRE | Fire protection material requisitions | Purchasing DB | document | FIRE-T230 | Requisitions for fire pumps, skids and fire equipment with datasheets and vendor document requirements. | 1
FIRE-I240 | FIRE | Fire protection vendor data comments | Document Locator | document | FIRE-T240 | Review codes and comments on fire pump and fire equipment vendor documents; certified data acceptance. | 1
MECH-I010 | MECH | FEL 1 equipment type and size list (mechanical attributes) | Excel / Word | data | MECH-T010 | Equipment tag/service, type, approximate size and duty class, base material, rough empty weight per option. | 2
MECH-I020 | MECH | FEL 1 equipment cost factors | Excel / Word | data | MECH-T010 | Factored equipment costs and weight factors per equipment type for the Class 5 estimate and screening. | 2
MECH-I030 | MECH | Mechanical design basis | Excel / Word | document | MECH-T020 | Applicable codes (ASME VIII, TEMA, API 650/610/617/661/560), design margins on P/T, corrosion allowance rules, sparing philosophy, driver preferences, wind/seismic criteria, units and standard sizes. | 6
MECH-I040 | MECH | Materials selection and corrosion allowances (Process and Mechanical) | Excel / Word | document | MECH-T030 | Per equipment/component: base material, cladding/lining, corrosion allowance, PWHT, NACE/sour service, impact test (MDMT) requirements. | 7
MECH-I050 | MECH | Rotating equipment sparing and driver selection list | Excel / Word | data | MECH-T040 | Per machine: number running/spare, driver type, fixed or variable speed (VFD), estimated absorbed and rated power, voltage class. | 5
MECH-I060 | MECH | Budget enquiry package | Document Locator | document | MECH-T050 | Short-form datasheets and scope for budget pricing of major equipment and packages. | 1
MECH-I070 | MECH | Equipment cost, weight and delivery data for estimate | Excel / Word | data | MECH-T050 | Per tag: budget price or factored cost, weight, delivery lead time, long-lead flag, source (quote or factored). | 6
MECH-I080 | MECH | Mechanical equipment list | Excel / Word | data | MECH-T060 | Per tag: service, type, size/rating, design P/T, material, empty/operating weight, driver power, PO number, vendor, status. | 14
MECH-I090 | MECH | Shell-and-tube exchanger thermal design | HTRI | model | MECH-T070 | TEMA type, shells in series/parallel, shell diameter, tube length/count/layout, area, overdesign, allowable vs calculated pressure drops, vibration check. | 3
MECH-I100 | MECH | Air-cooled exchanger thermal design | HTRI | model | MECH-T080 | Bays, bundles per bay, tube rows/length, fins, plot area, fans per bay, fan power, louvres, winterisation, noise per fan. | 4
MECH-I110 | MECH | Fired heater datasheet and specification | Excel / Word | document | MECH-T090 | Duty, coil passes and material, flux rates, burner type/number, fuel gas/oil conditions, stack height, efficiency, NOx, air preheat, draft. | 3
MECH-I120 | MECH | Fired heater burner management and combustion control requirements | Excel / Word | document | MECH-T090 | BMS functions, flame scanners, pilot/main fuel trips, draft and O2 control points, purge sequence and instrument requirements for I&C. | 1
MECH-I130 | MECH | Vessel and column mechanical design calculations | Mechanical calc tool | model | MECH-T100 | Shell/head thickness, nozzle reinforcement, skirt/saddle design, wind and seismic moments, empty/operating/test weights, MAWP, hydrotest pressure. | 10
MECH-I140 | MECH | Column and vessel internals datasheets | Excel / Word | document | MECH-T110 | Tray type/spacing/passes, packing type and bed heights, distributors, demisters, vortex breakers, support rings and clips, manway sizes, materials. | 3
MECH-I150 | MECH | Storage tank datasheets and calculations | Mechanical calc tool | document | MECH-T120 | Diameter/height, shell course thicknesses, roof type (fixed/floating), seals, annular plate, venting capacity, nozzles, appurtenances, heating coils. | 8
MECH-I160 | MECH | Tank foundation loads and settlement criteria | Excel / Word | data | MECH-T120 | Shell and bottom loads (empty/operating/hydrotest), wind/seismic overturning, anchorage, allowable differential and edge settlement, ringwall requirements. | 2
MECH-I170 | MECH | Vessel and column mechanical datasheets | Excel / Word | document | MECH-T130 | Sketch, nozzle schedule with size/rating/facing, design P/T, MAWP, materials, CA, PWHT, insulation, internals reference, weights, NDE extent. | 17
MECH-I180 | MECH | Shell-and-tube exchanger datasheets (TEMA) | Excel / Word | document | MECH-T140 | TEMA type, thermal results, design P/T both sides, materials, CA, nozzle sizes/ratings, weights empty/full/bundle, setting plan. | 3
MECH-I190 | MECH | Air-cooled exchanger datasheets (API 661) | Excel / Word | document | MECH-T140 | Thermal results, header type, tube/fin materials, fans and drivers, louvres, structure, walkways, weights, noise. | 6
MECH-I200 | MECH | Pump datasheets (API 610 / ASME) | Excel / Word | document | MECH-T150 | Rated flow/head, NPSHA, fluid properties, pump type (OH/BB/VS), seal and flush plan, materials class, driver, baseplate, nozzle sizes/ratings. | 6
MECH-I210 | MECH | Compressor and blower datasheets (API 617/618/672/673) | Excel / Word | document | MECH-T150 | Operating cases, gas composition, suction/discharge conditions, type, driver, lube/seal oil system, control (anti-surge/capacity), materials. | 8
MECH-I220 | MECH | Package specifications and scope-of-supply split | Excel / Word | document | MECH-T160 | Package function, scope of supply, terminal points, design data, controls philosophy (vendor PLC vs DCS), skid limits, required documentation. | 8
MECH-I230 | MECH | Equipment and package utility consumption data | Excel / Word | data | MECH-T160 | Cooling water, steam, instrument/plant air, nitrogen, seal flush, lube oil, fuel gas demands per tag (normal/peak). | 1
MECH-I240 | MECH | Seal plans and auxiliary system requirements | Excel / Word | document | MECH-T170 | Per machine: API 682 seal arrangement and plan, barrier/buffer fluid, seal pot instruments, lube oil console scope, coolers, alarms/trips for P&ID development. | 2
MECH-I250 | MECH | Mechanical P&ID markups | Document Locator | drawing | MECH-T180 | Seal plans, auxiliary piping, vent/drain nozzles, package battery limits, minimum flow/warm-up lines, equipment trim details. | 1
MECH-I260 | MECH | Mechanical HAZOP action responses | Excel / Word | decision | MECH-T180 | Responses and closure evidence for HAZOP/LOPA actions assigned to mechanical (design pressure changes, seal upgrades, trips). | 1
MECH-I270 | MECH | Nozzle orientation drawings (engineering) | Document Locator | drawing | MECH-T190 | Nozzle angles, elevations, projections, platform clips, davits, ladder and manway positions for vessels and columns. | 4
MECH-I280 | MECH | Allowable nozzle loads | Excel / Word | data | MECH-T190 | Per nozzle: allowable forces and moments (API 610/617/661, NEMA SM23, WRC 107/297 basis) for stress analysis. | 4
MECH-I290 | MECH | Equipment outline drawings (preliminary GA) | Document Locator | drawing | MECH-T200 | Overall dimensions, nozzle positions, support type and location, skirt/saddle details for model placement. | 5
MECH-I300 | MECH | Equipment footprints and maintenance envelopes | Excel / Word | data | MECH-T200 | Footprint, height, bundle pull length, rotor/internals removal space, crane access, laydown and handling areas per tag. | 6
MECH-I310 | MECH | Equipment weights and foundation load data | Excel / Word | data | MECH-T210 | Per tag: empty, operating and test weights, wind and seismic shear and moment, bundle pull force, dynamic loads (unbalanced forces, frequencies), anchor bolt circle and number. | 5
MECH-I320 | MECH | Equipment lifting data | Excel / Word | data | MECH-T220 | Lift weight, CoG, lifting lug/trunnion locations and capacities, tailing lug, dressed vs undressed lift, shipping dimensions. | 2
MECH-I330 | MECH | Motor and driver electrical data | Excel / Word | data | MECH-T230 | Per tag: absorbed and rated power, motor rating, voltage, speed, starting method and starting limitations, VFD, space heater, duty (continuous/intermittent), load factor. | 3
MECH-I340 | MECH | Mechanical technical specifications | Excel / Word | document | MECH-T240 | Project supplements to ASME/TEMA/API codes, fabrication, NDE, PWHT, painting/insulation interface, testing, documentation and nameplate requirements. | 4
MECH-I350 | MECH | Requisition technical package for bid | Document Locator | document | MECH-T250 | Requisition with scope, datasheets, specifications, VDRL, spare parts and inspection requirements, list of attachments. | 6
MECH-I360 | MECH | Requisition hold list | Excel / Word | data | MECH-T250 | Per requisition: open holds (design data pending, source discipline, expected date) at issue for bid and purchase. | 3
MECH-I370 | MECH | Bidder technical query log and clarifications | Excel / Word | document | MECH-T260 | Per bidder: technical queries, deviations/exceptions, responses and agreed clarifications. | 6
MECH-I380 | MECH | Technical bid evaluation and recommendation | Excel / Word | decision | MECH-T270 | Compliance matrix per bidder, efficiency/power and utility evaluation, deviations accepted, technically acceptable bidders, preferred bidder. | 6
MECH-I390 | MECH | Requisition for purchase (conformed technical package) | Document Locator | document | MECH-T280 | Updated datasheets and scope incorporating agreed clarifications, selected options, VDRL and remaining holds. | 5
MECH-I400 | MECH | Vendor kick-off meeting minutes | Document Locator | document | MECH-T290 | Agreed VDRL and data due dates, scope clarifications, interface data needed from vendor and project, hold resolution plan. | 2
MECH-I410 | MECH | Vendor document comment sheets (coded returns) | Document Locator | document | MECH-T300 | Consolidated comments from all disciplines with review code (approved, approved with comments, rejected) per vendor document revision. | 5
MECH-I420 | MECH | Certified equipment GA and nozzle data | Document Locator | drawing | MECH-T310 | Certified dimensions, nozzle locations/sizes/ratings, support details for model update and piping final design. | 4
MECH-I430 | MECH | Certified foundation loads and anchor bolt data | Document Locator | document | MECH-T310 | Certified loads, anchor bolt sizes and pattern, baseplate/skid details, dynamic data. | 3
MECH-I440 | MECH | Certified vendor electrical data | Document Locator | document | MECH-T310 | Certified motor datasheets, vendor panel power loads, heater/tracing loads, vendor wiring and cable entry details. | 2
MECH-I450 | MECH | Vendor instrument lists and package I/O | Document Locator | data | MECH-T310 | Vendor instrument index, package I/O list, serial link maps, cause and effect for package, control narratives. | 2
MECH-I460 | MECH | Hold list status update | Excel / Word | data | MECH-T320 | Hold status per requisition and vendor document, closure date, data received from source discipline. | 2
MECH-I470 | MECH | Nozzle load acceptance and exceedance resolutions | Excel / Word | decision | MECH-T330 | Per nozzle: calculated vs allowable loads, acceptance, vendor-confirmed exceedances, required piping changes. | 1
MECH-I480 | MECH | Rotordynamic and pulsation study acceptance | Excel / Word | decision | MECH-T340 | Accepted separation margins, required pulsation dampers/orifices, piping support requirements resulting from studies. | 1
MECH-I490 | MECH | Approved inspection and test plans | Document Locator | document | MECH-T350 | Inspection activities, acceptance criteria, witness/hold/review points, performance and mechanical run tests, hydrotest pressures. | 3
MECH-I500 | MECH | Shop test witness reports and release notes | Document Locator | document | MECH-T360 | Test results vs guarantees, punch items from FAT, release for shipment recommendation. | 1
MECH-I510 | MECH | Reviewed spare parts list | Excel / Word | data | MECH-T370 | Commissioning/start-up, two-year operating and capital spares per tag with quantities and interchangeability. | 2
MECH-I520 | MECH | Manufacturer's data book acceptance | Document Locator | decision | MECH-T380 | Accepted MDR with material certificates, NDE, PWHT, hydrotest records, U-stamp/nameplate, IOM manuals. | 2
MECH-I530 | MECH | Equipment preservation requirements | Excel / Word | document | MECH-T390 | Per tag: storage class (indoor/outdoor), nitrogen blanketing, shaft rotation intervals, desiccants, inspection frequency. | 2
MECH-I540 | MECH | Equipment model review comments | Excel / Word | document | MECH-T400 | Comments on equipment access, bundle/rotor removal clearances, platforms, lifting access, nozzle connection discrepancies. | 1
MECH-I550 | MECH | Mechanical RFI responses and field change dispositions | Procore | decision | MECH-T410 | Technical disposition of RFIs, damage, NCRs and field modifications on equipment, with markups where needed. | 1
MECH-I560 | MECH | Vendor site service schedule and reports | Excel / Word | data | MECH-T420 | Vendor attendance needed per tag and activity (installation, alignment, first fill, start-up), dates, service reports. | 2
MECH-I570 | MECH | Mechanical equipment ITR and check requirements | Excel / Word | data | MECH-T430 | Per equipment type: installation checks, alignment tolerances, internals inspection/box-up, lube flush, solo/run-in test criteria for ITR forms. | 3
MECH-I580 | MECH | Mechanical punch items and MC acceptance | Smart Completions | decision | MECH-T430 | Mechanical punch items raised in walkdowns, category, and engineering acceptance of mechanical completion. | 1
MECH-I590 | MECH | As-built equipment datasheets and equipment register | Excel / Word | data | MECH-T440 | Final certified attributes per tag (vendor, model, serial, design data, materials, weights) for asset register and maintenance system. | 3
MECH-I600 | MECH | Equipment thermal growth and nozzle flexibility | Excel / Word | data | MECH-T190 | Thermal growth and nozzle displacements per equipment nozzle and nozzle flexibility data for stress analysis. | 1
MECH-I601 | MECH | Technically acceptable bidders | Excel / Word | data | MECH-T250 | Technical acceptability of proposed bidders per equipment type. | 1
MECH-I901 | MECH | Mechanical deliverables list | Excel / Word | data | MECH-T005 | Datasheets, calculations and requisitions per equipment item with planned dates. | 1
MECH-I902 | MECH | Mechanical progress measurement | Excel / Word | data | MECH-T005 | Datasheet and requisition percent complete by rules of credit. | 1
MECH-I904 | MECH | Mechanical change impact | Excel / Word | data | MECH-T005 | Equipment affected by a trend or change, with vendor price and schedule impact. | 1
PIPE-I010 | PIPE | Block plot plan options | Excel / Word | drawing | PIPE-T010 | Block-level arrangement per option: block footprints, main rack corridor, tank farm, flare location, roads, approximate areas and interconnecting run lengths. | 7
PIPE-I020 | PIPE | FEL1 factored piping quantities | Excel / Word | data | PIPE-T020 | Per option: piping weight factors per equipment, interconnecting pipe length by size range, rack length, alloy fraction. | 3
PIPE-I030 | PIPE | Piping layout design basis | Excel / Word | document | PIPE-T030 | Spacing tables, clearances and headroom, rack elevations and tier allocation rules, valve and instrument access rules, platform rules, S3D modelling and naming conventions. | 2
PIPE-I040 | PIPE | Plot plan | S3D | drawing | PIPE-T040 | Equipment locations to grid, rack corridors, roads, buildings, lay-down and maintenance areas, north arrow, battery limits, area numbering. | 36
PIPE-I050 | PIPE | Equipment location list | Excel / Word | data | PIPE-T040 | Per equipment tag: coordinates (E/N), foundation top/grade elevation, orientation, support type (grade, structure, rack); used by civil foundations and mechanical. | 7
PIPE-I060 | PIPE | 3D layout model | S3D | model | PIPE-T050 | Equipment envelopes, structures and rack placeholders, access and maintenance volumes, main line corridors for layout review. | 5
PIPE-I070 | PIPE | Pipe rack layout and widths | S3D | drawing | PIPE-T060 | Rack routes, widths, bay spacing, tier elevations, line allocation by tier, cable tray levels, future space allowance, road crossing clearances. | 5
PIPE-I080 | PIPE | Pipe rack preliminary loads | Excel / Word | data | PIPE-T060 | Per rack bay and tier: uniform pipe load (operating, hydrotest), concentrated anchor/guide loads, friction allowance, future load allowance. | 2
PIPE-I090 | PIPE | Critical line routing studies | S3D | model | PIPE-T070 | Routing of critical lines with stress loop concepts, elevations and space claims; flags equipment relocation needs. | 4
PIPE-I100 | PIPE | Nozzle orientation and elevation requests | Excel / Word | drawing | PIPE-T080 | Per equipment: nozzle orientation angles, elevations, projections, platform, ladder and davit locations, clip locations for pipe supports. | 4
PIPE-I110 | PIPE | Piping material class specification | Excel / Word | document | PIPE-T090 | Per class: rating, P-T limits, materials, corrosion allowance, wall thickness by size, components by size range, gaskets and bolting, branch table, valve codes. | 15
PIPE-I120 | PIPE | S3D piping spec and commodity catalogue | S3D | data | PIPE-T100 | Spec rules, short codes, commodity codes (idents), dimensional tables, valve operators, branch rules used by routing and isometric extraction. | 2
PIPE-I130 | PIPE | Valve datasheets | Excel / Word | document | PIPE-T110 | Per valve code: type, rating, body/trim/seat materials, ends, operator, fire-safe and fugitive emission tests, NDE and inspection. | 1
PIPE-I140 | PIPE | Specialty piping item list and datasheets | Excel / Word | data | PIPE-T120 | Per SP tag: type, size, rating, materials, P&ID and line number, process data, quantity, datasheet reference. | 3
PIPE-I150 | PIPE | Piping fabrication, erection and inspection specification | Excel / Word | document | PIPE-T130 | Welding and WPS requirements, NDE class by line category, PWHT rules, hydrotest and pneumatic test rules, flushing and cleaning, painting and insulation reference. | 5
PIPE-I160 | PIPE | Line list piping attributes | Excel / Word | data | PIPE-T140 | Per line: piping class, test pressure, test medium, NDE category, PWHT, paint system, insulation type and thickness, stress category. | 12
PIPE-I170 | PIPE | Estimate piping bulk MTO | Excel / Word | data | PIPE-T150 | Pipe length, fittings, flanges, valves and SP items by class, size and material; field and shop weld counts; growth allowances by area. | 3
PIPE-I180 | PIPE | Routed piping model | S3D | model | PIPE-T160 | Lines by number with class, size, components, valves, SP items, in-line instruments, supports placeholders and insulation; source for isos, MTO, reviews and clash checks. | 27
PIPE-I190 | PIPE | P&ID to model consistency report | SPF | data | PIPE-T170 | Mismatches between P&ID and model: missing or extra lines, size, spec and component differences, tag mismatches, with resolution status. | 1
PIPE-I200 | PIPE | In-line instrument positions | S3D | data | PIPE-T180 | Per instrument tag: line number, coordinates, elevation, orientation, upstream/downstream straight run, access platform, tapping orientation; used for instrument hook-ups and cable routing. | 1
PIPE-I210 | PIPE | As-routed line hydraulic data | Excel / Word | data | PIPE-T190 | Per line: equivalent length, fittings count, elevation changes, pockets, PSV inlet/outlet routing and tailpipe geometry. | 4
PIPE-I220 | PIPE | Stress-critical line list | Excel / Word | data | PIPE-T200 | Per line: stress category (visual, simplified, CAESAR II), load cases, governing temperatures, connected sensitive equipment, analysis owner and status. | 2
PIPE-I230 | PIPE | Screening stress results and layout markups | Excel / Word | drawing | PIPE-T210 | Expansion loop and anchor concepts, routing changes, equipment location requests, spring support needs for critical lines. | 1
PIPE-I240 | PIPE | Stress calculation report | CAESAR II | model | PIPE-T220 | CAESAR II models and report per stress system: load cases, code compliance, displacements, flange leakage checks, support types and locations. | 3
PIPE-I250 | PIPE | Nozzle loads for equipment | Excel / Word | data | PIPE-T220 | Per equipment nozzle: forces and moments by load case compared to allowables; sent to mechanical and vendors for acceptance. | 4
PIPE-I260 | PIPE | Support loads for civil and structural | Excel / Word | data | PIPE-T220 | Per support tag: location, support type, operating, sustained, hydrotest, wind and seismic loads, friction loads, for steel and foundation design. | 4
PIPE-I270 | PIPE | Stress markups to the model | Excel / Word | drawing | PIPE-T220 | Routing changes, support type changes, gaps, guides, anchors and spring locations to be applied in S3D by layout designers. | 1
PIPE-I280 | PIPE | Nozzle load acceptance | Document Locator | decision | PIPE-T230 | Per nozzle: accepted, rerouted or reinforced; vendor and mechanical sign-off reference. | 1
PIPE-I290 | PIPE | Spring and engineered support requisition | Purchasing DB | document | PIPE-T240 | Per support tag: hot/cold load, travel, type, size, materials, coating, quantities; technical requisition and TBE. | 1
PIPE-I300 | PIPE | Pipe support model and special support drawings | S3D | model | PIPE-T250 | Supports in S3D by tag and standard type; special support details; support MTO for steel and attachments. | 5
PIPE-I310 | PIPE | Secondary steel and support steel requests | Excel / Word | data | PIPE-T250 | Required secondary steel, stub columns, extra beams, sleeper locations and support attachment points with loads; sent to civil/structural. | 2
PIPE-I320 | PIPE | Platform, access and penetration requests | Excel / Word | drawing | PIPE-T260 | Platform and ladder locations for valve and instrument access, sleeper and pipe-track positions, trench and culvert crossings, sleeves and wall openings with sizes. | 3
PIPE-I330 | PIPE | Underground piping layout | S3D | drawing | PIPE-T270 | Underground line routes, inverts, cover depths, crossings, manholes, catch basins and tie points; coordinated with civil drainage. | 3
PIPE-I340 | PIPE | Model review package | iConstruct | model | PIPE-T280 | Navisworks review model with checklists by area, review scope, attendee list, previous action status. | 6
PIPE-I350 | PIPE | Model review action list | Excel / Word | data | PIPE-T280 | Per action: area, location, description, responsible discipline, due date, close-out evidence. | 3
PIPE-I360 | PIPE | Clash report | S3D | data | PIPE-T290 | Per clash: objects, disciplines, location, type (hard/soft/clearance), owner, resolution and status. | 3
PIPE-I370 | PIPE | Piping safety action responses | Excel / Word | decision | PIPE-T300 | Per action: response, model/drawing changes made, evidence, close-out status. | 1
PIPE-I380 | PIPE | Piping vendor data review comments | Document Locator | document | PIPE-T310 | Piping comments on vendor GAs and interface drawings: nozzle orientation, connection type, support clips, access. | 2
PIPE-I390 | PIPE | Piping hold list | Excel / Word | data | PIPE-T310 | Per hold: line or iso, reason (vendor data, P&ID, stress), owner, due date, released status. | 5
PIPE-I400 | PIPE | IFC isometrics | S3D | drawing | PIPE-T320 | Per line/sheet: geometry, coordinates, BOM by ident, weld numbers, shop/field welds, supports, NDE, PWHT, test data, revision clouds. | 14
PIPE-I410 | PIPE | Spool list and fabrication package | Excel / Word | data | PIPE-T330 | Per spool: spool ID, iso, size, class, weight, welds, NDE, PWHT, paint, bill of materials; fabrication package release. | 3
PIPE-I420 | PIPE | Piping MTO by ident | Excel / Word | data | PIPE-T340 | Per commodity ident: description, class, size, schedule, material, quantity by area and iso, surplus, delta to previous MTO; exported to Purchasing DB. | 5
PIPE-I430 | PIPE | Piping bulk material requisitions | Purchasing DB | document | PIPE-T340 | Requisitions for pipe, fittings, flanges, gaskets, bolting, valves and SP items with technical specs, quantities and delivery split. | 3
PIPE-I440 | PIPE | Piping technical bid evaluation | Document Locator | document | PIPE-T350 | Per bidder and line item: compliance, deviations, clarifications, technical recommendation. | 1
PIPE-I450 | PIPE | Valve and SP item vendor data review | Document Locator | document | PIPE-T360 | Return codes and comments; certified dimensions to be updated in the S3D catalogue. | 1
PIPE-I460 | PIPE | Piping GA drawings and key plans | S3D | drawing | PIPE-T370 | Plans and sections by area with line numbers, elevations, equipment and structural references, match lines, area key plan. | 3
PIPE-I470 | PIPE | Tie-in list | Excel / Word | data | PIPE-T380 | Per tie-in: number, P&ID, existing and new line numbers, size, class, type (hot tap, cold cut, flanged), shutdown requirement, status. | 5
PIPE-I480 | PIPE | Tie-in packages | Document Locator | drawing | PIPE-T380 | Per tie-in: sketch, isometric, survey photos, materials, isolation and method, NDE and test requirements. | 2
PIPE-I490 | PIPE | Test pack boundaries | Excel / Word | drawing | PIPE-T390 | Marked-up P&IDs and isos for each test circuit: limits, blinds, vents and drains, test pressure and medium, gauge location. | 3
PIPE-I500 | PIPE | Test pack register | Smart Completions | data | PIPE-T390 | Per test pack: number, system/subsystem, lines and isos included, test pressure and medium; loaded to Smart Completions for ITR tracking. | 1
PIPE-I510 | PIPE | Piping construction model export | iConstruct | model | PIPE-T400 | Navisworks piping model with line, iso, spool, test pack and CWP attributes for AWP and material availability. | 1
PIPE-I520 | PIPE | Spool drawing review comments | Document Locator | document | PIPE-T410 | Return codes and comments per spool drawing against IFC iso. | 1
PIPE-I530 | PIPE | Piping RFI responses | Procore | document | PIPE-T420 | Per RFI: answer, sketch or markup, affected isos and lines, cost/schedule impact flag. | 2
PIPE-I540 | PIPE | Field change isometrics | S3D | drawing | PIPE-T420 | Revised isometrics and model updates issued for field changes with revision clouds and material changes. | 2
PIPE-I550 | PIPE | Piping material shortage and surplus list | Excel / Word | data | PIPE-T430 | Per ident: required, received, issued, shortage, surplus, supplementary requisition reference. | 1
PIPE-I560 | PIPE | As-built isometrics | Document Locator | drawing | PIPE-T440 | As-built isometrics with final routing, welds and supports, issued for handover. | 1
PIPE-I570 | PIPE | As-built piping model | S3D | model | PIPE-T440 | S3D model updated to as-built for operations handover. | 1
PIPE-I901 | PIPE | Piping deliverables list | Excel / Word | data | PIPE-T005 | Drawing types and isometric counts by area with planned dates. | 1
PIPE-I902 | PIPE | Piping progress measurement | Excel / Word | data | PIPE-T005 | Model completion and isometrics issued against plan by area. | 1
PIPE-I904 | PIPE | Piping change impact | Excel / Word | data | PIPE-T005 | Isometric and model rework estimate (hours, quantities) per trend or change. | 1
CIVL-I010 | CIVL | Site civil screening assessment | Document Locator | document | CIVL-T010 | Per candidate site: topography, flood elevation, likely soil type and foundation type (shallow or piled), access routes, demolition and relocation needs, relative earthworks and foundation cost. | 3
CIVL-I020 | CIVL | Structural design criteria | Document Locator | document | CIVL-T020 | Design codes, load cases and combinations, deflection and drift limits, steel and concrete grades, pipe rack load allowances, vibration criteria, fireproofing and corrosion protection rules. | 8
CIVL-I030 | CIVL | Site environmental design data | Document Locator | data | CIVL-T020 | Basic wind speed and exposure, seismic parameters, snow and ice, rainfall intensity-duration-frequency, frost depth, ambient design temperatures for HVAC, flood level. | 16
CIVL-I040 | CIVL | Topographic survey and plant grid | Document Locator | drawing | CIVL-T030 | Existing ground levels, plant coordinate system and benchmarks, existing roads, buildings, overhead lines and located underground services. | 9
CIVL-I050 | CIVL | Geotechnical investigation scope and borehole plan | Document Locator | document | CIVL-T040 | Borehole/CPT locations and depths, test schedule, groundwater monitoring, contractor technical scope for the requisition. | 3
CIVL-I060 | CIVL | Foundation design parameters | Document Locator | data | CIVL-T050 | Allowable bearing pressure, subgrade modulus, pile axial and lateral capacities, dynamic soil properties, predicted settlement, groundwater level, concrete exposure class. | 8
CIVL-I065 | CIVL | Foundation type recommendation by area | Document Locator | decision | CIVL-T050 | Shallow, piled or improved-ground foundation choice per area and per heavy item, with pile type and soil improvement needs. | 1
CIVL-I070 | CIVL | Civil and structural estimate quantities | Excel / Word | data | CIVL-T060 | By area and WBS: earthworks m3, piles no./m, concrete m3, rebar t, structural steel t by weight class, paving m2, roads m2, sewers m, building areas m2, with growth allowance. | 4
CIVL-I080 | CIVL | Civil comments on plot plan | Document Locator | document | CIVL-T070 | Marked-up plot plan: required road widths and turning radii, drainage fall directions, dike footprints, building positions, foundation interference and crane access. | 1
CIVL-I090 | CIVL | Site preparation and earthworks drawings | Document Locator | drawing | CIVL-T090 | Clearing and demolition limits, cut/fill volumes and limits, soil improvement extent, compaction specification, temporary drainage. | 1
CIVL-I100 | CIVL | Grading plan and finished grade elevations | Document Locator | drawing | CIVL-T100 | High point finished grade per area, paving and curb elevations, slopes, top-of-concrete reference elevation used by piping for equipment and support elevations. | 4
CIVL-I105 | CIVL | Paving and curbing layout | Document Locator | drawing | CIVL-T100 | Paved areas, curbed areas, curb heights, slab types and joints, unpaved gravel areas. | 1
CIVL-I110 | CIVL | Drainage area plan and sewer layout | Document Locator | drawing | CIVL-T110 | Drainage area classification, storm and oily water sewer routes, pipe sizes, invert elevations, catch basins, manholes, vapour seals and sumps. | 3
CIVL-I115 | CIVL | Stormwater runoff and discharge data | Excel / Word | data | CIVL-T110 | Runoff volumes and peak flows per catchment, first-flush volumes, contaminated water volumes to treatment, discharge points, for permitting and effluent treatment sizing. | 1
CIVL-I120 | CIVL | Dike and containment design | Document Locator | drawing | CIVL-T120 | Dike heights, capacities, wall types, intermediate walls, penetrations, drain valves and impounding basin sizes. | 1
CIVL-I130 | CIVL | Preliminary pipe rack and structure configuration | Document Locator | drawing | CIVL-T080 | Rack widths, bent spacing, tier elevations, bracing bays, structure frame sizes and steel tonnage per area. | 4
CIVL-I135 | CIVL | Pipe rack design load allowances | Document Locator | data | CIVL-T080 | Uniform piping load per tier (kN/m2), cable tray loads, concentrated anchor and guide load limits, future-space allowance, air cooler loads assumed; basis for PIPE stress to respect. | 2
CIVL-I140 | CIVL | Roads, access and fencing layout | Document Locator | drawing | CIVL-T130 | Road widths, pavement build-up, turning radii, crane pads and bearing capacity, gates, fencing lines, kerb and road crossings over underground. | 4
CIVL-I150 | CIVL | Underground composite drawing | Document Locator | drawing | CIVL-T140 | All underground services with depths and crossings: sewers, firewater, underground piping, duct banks, grounding, foundations and piles. | 4
CIVL-I155 | CIVL | Underground conflict list | Excel / Word | data | CIVL-T140 | Each crossing or clash, disciplines involved, required depth or route change and resolution status. | 2
CIVL-I160 | CIVL | Static equipment foundation calculations | Document Locator | document | CIVL-T150 | Per foundation: load cases, footing/pile cap size, pedestal size, anchor bolt check, bearing and stability checks, reinforcement. | 2
CIVL-I165 | CIVL | Rotating equipment foundation calculations | Document Locator | document | CIVL-T160 | Block size, mass ratio, natural frequencies, predicted amplitudes, anchor bolt and grout details. | 2
CIVL-I166 | CIVL | Dynamic analysis results for vendor review | Document Locator | document | CIVL-T160 | Foundation stiffness and frequency results sent to the machine vendor and mechanical for acceptance. | 1
CIVL-I170 | CIVL | Tank foundation design | Document Locator | drawing | CIVL-T170 | Ringwall dimensions, pad build-up, leak detection, predicted and allowable settlement, settlement monitoring points. | 2
CIVL-I190 | CIVL | Foundation plans and details | Document Locator | drawing | CIVL-T190 | Foundation coordinates, top of concrete and grout elevations, dimensions, reinforcement, concrete grade, construction joints. | 11
CIVL-I195 | CIVL | Anchor bolt layouts and schedule | Document Locator | drawing | CIVL-T190 | Anchor bolt coordinates, size, length, projection, material, sleeve and template details per foundation for procurement and setting. | 3
CIVL-I200 | CIVL | Pile layout and schedule | Document Locator | drawing | CIVL-T180 | Pile coordinates, cut-off levels, pile type, lengths, design capacities per pile group; early piling package for procurement. | 3
CIVL-I205 | CIVL | Test pile programme | Document Locator | document | CIVL-T180 | Test pile locations, load test types and acceptance criteria. | 1
CIVL-I210 | CIVL | Pipe rack design calculations and reactions | Document Locator | document | CIVL-T200 | Member sizes, connection forces, column base reactions per bent for foundation design, utilisation and deflection checks. | 3
CIVL-I220 | CIVL | Process structure design calculations and reactions | Document Locator | document | CIVL-T210 | Member sizes, platform loads, connection forces and base reactions for foundation design. | 3
CIVL-I230 | CIVL | Tekla structural model | Tekla | model | CIVL-T220 | Steel members, connections, plates, grating, stairs, ladders and concrete foundations with fabrication attributes. | 5
CIVL-I235 | CIVL | Structural reference model for S3D | Tekla | model | CIVL-T220 | Periodic export of steel and concrete geometry to S3D as a reference model for piping and layout clash checks. | 7
CIVL-I236 | CIVL | Structural model for iConstruct | iConstruct | model | CIVL-T220 | Tekla model published to Navisworks/iConstruct with CWP and erection sequence attributes for AWP. | 4
CIVL-I240 | CIVL | Steel GA and erection drawings | Document Locator | drawing | CIVL-T230 | Plans, elevations, member marks and sizes, platform layouts, erection marks and sequence notes. | 7
CIVL-I245 | CIVL | Connection design forces and criteria | Document Locator | document | CIVL-T230 | Connection forces per member end, connection types and bolting criteria for fabricator-designed connections. | 1
CIVL-I248 | CIVL | Structural steel MTO | Excel / Word | data | CIVL-T240 | Tonnage and lengths by profile, grade, coating and fireproofing, grating m2, bolts, per area and CWP; exported from Tekla for re-keying into Purchasing DB. | 1
CIVL-I250 | CIVL | Embedment and sleeve schedule | Excel / Word | data | CIVL-T250 | Each embedded item and penetration: requesting discipline, location, size, elevation, type and drawing reference. | 1
CIVL-I260 | CIVL | Structural fireproofing schedule | Document Locator | drawing | CIVL-T260 | Members, skirts, supports and rack levels to be fireproofed, rating, type (concrete, cementitious, intumescent), quantities. | 1
CIVL-I270 | CIVL | Building layouts for electrical and I&C | Document Locator | drawing | CIVL-T270 | Room layouts and dimensions, equipment areas, false floor and cable cellar, cable entry walls, door sizes, floor openings and trench locations. | 9
CIVL-I280 | CIVL | Building structural design | Document Locator | document | CIVL-T280 | Blast design response, wall/roof construction, blast doors, foundation reactions, floor load capacities. | 1
CIVL-I290 | CIVL | Architectural drawings | Document Locator | drawing | CIVL-T290 | Plans, elevations, finishes, door and window schedules, fire ratings, ceilings, plumbing fixtures. | 5
CIVL-I300 | CIVL | HVAC heat load calculations and equipment sizing | Document Locator | document | CIVL-T300 | Room heat loads, design conditions, air changes, pressurisation, AHU/package unit capacities and redundancy. | 3
CIVL-I305 | CIVL | HVAC electrical loads | Excel / Word | data | CIVL-T300 | Each HVAC consumer: tag, kW, voltage, duty/standby, essential/UPS supply need, for the electrical load list. | 1
CIVL-I306 | CIVL | HVAC control and shutdown interface | Document Locator | document | CIVL-T300 | Gas detector at air intakes, damper closure, HVAC trip and alarm signals to F&G/DCS, HVAC control panel I/O. | 2
CIVL-I307 | CIVL | HVAC datasheets and requisition scope | Document Locator | document | CIVL-T300 | HVAC unit datasheets, duct and damper specifications, scope for HVAC package requisition. | 2
CIVL-I310 | CIVL | Civil and structural requisitions and TBEs | Document Locator | document | CIVL-T310 | Material requisitions and technical scopes, technical bid evaluations and acceptability recommendations. | 1
CIVL-I320 | CIVL | Civil vendor data review comments | Document Locator | document | CIVL-T320 | Commented vendor documents with status codes: anchor bolt confirmation, load acceptance, shop drawing corrections. | 2
CIVL-I330 | CIVL | Civil model review responses and clash resolutions | Excel / Word | data | CIVL-T330 | Each structural or civil clash or comment, resolution and model change status. | 1
CIVL-I340 | CIVL | Civil and structural CWP scope and sequence | Excel / Word | data | CIVL-T340 | Civil/steel CWP list, deliverables per CWP, foundation pour sequence, steel erection sequence and release dates. | 3
CIVL-I350 | CIVL | Sealed IFC civil and structural package | Document Locator | decision | CIVL-T350 | IFC issue of civil, structural, architectural and HVAC drawings with PE seal and transmittal. | 2
CIVL-I360 | CIVL | Civil RFI responses and field change dispositions | Procore | decision | CIVL-T360 | Answer, sketch and any drawing revision for each RFI and field change. | 2
CIVL-I365 | CIVL | Civil non-conformance dispositions | Procore | decision | CIVL-T360 | Accept, repair or reject disposition for concrete strength, anchor bolt misplacement, pile capacity and steel fit-up NCRs. | 1
CIVL-I370 | CIVL | Settlement evaluation and acceptance | Document Locator | decision | CIVL-T370 | Measured vs predicted settlement, acceptance or hold on filling, remedial actions. | 1
CIVL-I380 | CIVL | As-built civil and structural drawings and model | Document Locator | drawing | CIVL-T380 | As-built foundation, underground, steel and building drawings and updated Tekla model for owner handover. | 2
CIVL-I390 | CIVL | Geotechnical and soil corrosivity report | Document Locator | document | CIVL-T040 | Geotechnical contractor's factual and interpretive report: soil profiles, bearing and pile capacities, settlement, groundwater, soil resistivity (Wenner) and chemistry (pH, chlorides). | 3
CIVL-I901 | CIVL | Civil deliverables list | Excel / Word | data | CIVL-T005 | Foundation, steel, building and site drawings with planned dates. | 1
CIVL-I902 | CIVL | Civil progress measurement | Excel / Word | data | CIVL-T005 | Foundation and steel drawing completion counts against plan. | 1
CIVL-I903 | CIVL | Civil holds | Excel / Word | data | CIVL-T005 | Foundation drawings on hold awaiting certified vendor loads, with cause. | 1
INST-I010 | INST | Preliminary control and safety system concept | Excel / Word | decision | INST-T010 | DCS/SIS/F&G split, level of automation, central vs local control room, fieldbus or conventional I/O, packaged unit control approach, basis for estimate. | 9
INST-I020 | INST | I&C quantities and estimate input | Excel / Word | data | INST-T020 | Instrument counts by type, I/O counts by system, control valve and on/off valve counts by size class, analyzer count, cabinet count, bulk factors (cable m per I/O, JBs), allowances. | 3
INST-I030 | INST | ICS architecture diagram | Excel / Word | drawing | INST-T030 | DCS, SIS, F&G, PLCs, historian, engineering stations, network switches, firewalls, serial/Ethernet links to packages, redundancy, time sync, remote I/O locations. | 7
INST-I031 | INST | Control and rack room space, cabinet layout and heat loads | Excel / Word | document | INST-T030 | Cabinet count and footprint, consoles, cable entry, cabinet heat dissipation (kW) for HVAC, floor loading, clean power needs per room. | 5
INST-I040 | INST | I&C design basis and general instrument specifications | Excel / Word | document | INST-T040 | Instrument selection rules, signal standards (4-20 mA/HART, fieldbus), Ex protection, enclosure ratings, process connection standards, tubing/cable specs, color coding, approved vendor list. | 5
INST-I045 | INST | I&C P&ID markups | SPID | document | INST-T045 | Instrument tag numbers, instrument types and symbols, signal lines, interlock and SIS boundaries, fail positions, instrument connection sizes, comments for PROC to incorporate. | 3
INST-I050 | INST | Instrument index | SI | data | INST-T050 | Tag, instrument type, service, loop, P&ID, line/equipment number, I/O type, system (DCS/SIS/F&G/package), supply scope, status and revision. | 13
INST-I055 | INST | I&C HAZOP/LOPA action responses | PHA tool | document | INST-T055 | Action number, response, design change made (tags added/changed, alarm/trip settings), evidence and closure request. | 1
INST-I060 | INST | Instrument process data in SI | SI | data | INST-T060 | Per tag: fluid, phase, operating and design P/T, flow cases, density, viscosity, MW, range, alarm and trip points, line size and class. | 7
INST-I070 | INST | Control valve sizing calculations | SI | document | INST-T070 | Cv per case, % opening, noise dB(A), cavitation/flashing check, trim type, actuator sizing, shut-off class. | 3
INST-I071 | INST | Control valve sizes and ratings for P&ID | SI | data | INST-T070 | Body size, ANSI rating, reducer sizes, Cv selected, fail action and leak class for PROC to show on P&IDs and in hydraulics. | 1
INST-I072 | INST | Preliminary in-line valve dimensions and weights | SI | data | INST-T070 | Face-to-face, end connection, estimated weight, actuator height and orientation envelope for control and on/off valves for piping layout. | 1
INST-I080 | INST | On/off and ESD valve sizing and actuator data | SI | data | INST-T080 | Valve type, size, rating, shut-off class, stroke time, failure position, actuator torque/thrust, air supply, fire-proofing, partial stroke testing. | 4
INST-I090 | INST | Flow element and thermowell calculations | SI | document | INST-T090 | Beta ratio, bore, differential, permanent pressure loss, uncertainty; thermowell wake frequency results and lengths. | 1
INST-I091 | INST | Flow element sizes and straight-run requirements | SI | data | INST-T090 | Flow element type, size, rating, flange taps, required upstream/downstream straight lengths and permanent pressure loss for PIPE layout and PROC hydraulics. | 2
INST-I100 | INST | Relief valve datasheets | SI | document | INST-T100 | Tag, set pressure, relieving rate, required/selected orifice, inlet/outlet size and rating, body/trim material, bellows/pilot, back pressure. | 2
INST-I110 | INST | Instrument datasheets for requisition | SI | document | INST-T110 | Per tag specification: process data, range, materials, process connection, Ex rating, enclosure, signal, accessories. | 5
INST-I115 | INST | Instrument connection requirements on equipment and piping | Excel / Word | data | INST-T115 | Per instrument: connection type, size, rating, orientation, elevation/level range, bridle arrangement; for MECH nozzle schedule and PIPE branch tables. | 4
INST-I130 | INST | Instrument material requisitions | Purchasing DB | document | INST-T130 | MR per instrument package: technical scope, datasheets, quantities, spares, VDRL, inspection and test requirements. | 1
INST-I140 | INST | Instrument technical bid evaluations | Excel / Word | document | INST-T140 | Compliance table, technical clarifications, deviations accepted, technically acceptable bidders, recommended vendor. | 3
INST-I145 | INST | Agreed final relief valve sizing for purchase | SI | decision | INST-T145 | Per PSV: final orifice, model, set pressure, rated capacity, inlet and outlet sizes and ratings, agreed by I&C, Process and vendor. | 4
INST-I150 | INST | Instrument vendor data comments | Document Locator | document | INST-T150 | Return code (1-4) and comments on vendor drawings, sizing, materials, certificates. | 2
INST-I151 | INST | Certified in-line instrument dimensions and weights | SI | data | INST-T150 | Certified face-to-face, end connections, weights, actuator envelopes, centre of gravity for control valves, on/off valves, flow meters and PSVs for PIPE model and stress. | 2
INST-I160 | INST | Analyzer datasheets and system specification | Excel / Word | document | INST-T160 | Analyzer type, components, ranges, sample conditioning, calibration gases, shelter scope. | 3
INST-I161 | INST | Analyzer shelter utility and space requirements | Excel / Word | data | INST-T160 | Shelter size, weight, location, power and UPS, HVAC, instrument air, sample return and vent connections, calibration gas storage. | 2
INST-I170 | INST | Control narratives and functional logic | Excel / Word | document | INST-T170 | Loop-by-loop control descriptions, cascade/ratio/split-range logic, sequences, permissives, overrides for DCS configuration. | 5
INST-I180 | INST | DCS specification | Excel / Word | document | INST-T180 | Hardware, software, redundancy, I/O counts with spare, graphics, historian, cyber security, FAT/SAT requirements. | 1
INST-I190 | INST | SIS specification | Excel / Word | document | INST-T190 | Certified logic solver, SIL capability, redundancy, I/O counts, bypass/override management, sequence of events, interface to DCS. | 2
INST-I200 | INST | F&G system specification | Excel / Word | document | INST-T200 | F&G logic solver, voting, alarm annunciation, interfaces to fire water, HVAC shutdown, PA/GA. | 2
INST-I201 | INST | F&G device list and locations | SI | data | INST-T200 | Detector tag, type, fire zone, coordinates/elevation, voting group, Ex rating, I/O type. | 1
INST-I210 | INST | SIF list with initiators and final elements | PHA tool | data | INST-T210 | SIF number, initiator tags, voting, logic, final element tags, safe state, response time, target SIL. | 5
INST-I220 | INST | Safety requirements specification | Excel / Word | document | INST-T220 | Per SIF: description, safe state, SIL, response time, trip set points, demand mode, bypass rules, reset, proof test interval, spurious trip rate target. | 10
INST-I230 | INST | SIL verification report | Excel / Word | document | INST-T230 | PFDavg, RRF, HFT and SFF per SIF, assumptions, compliance with target SIL. | 2
INST-I231 | INST | Proof test intervals and procedures | Excel / Word | document | INST-T230 | Proof test interval, coverage and test steps per SIF for operations and commissioning. | 2
INST-I240 | INST | Process shutdown cause and effect | Excel / Word | document | INST-T240 | Causes (tags, set points) versus effects (valves, motors, alarms) with shutdown levels and SIF references. | 13
INST-I241 | INST | F&G cause and effect | Excel / Word | document | INST-T240 | Detector voting by fire zone versus executive actions (ESD, deluge, HVAC, PA/GA, isolation). | 6
INST-I250 | INST | Master alarm database | Excel / Word | data | INST-T250 | Tag, alarm type, set point, priority, cause, consequence, operator action, response time. | 5
INST-I260 | INST | I/O list | SI | data | INST-T260 | Tag, signal type, system, cabinet, card, channel, IS/non-IS, SIL, spare. | 4
INST-I261 | INST | I/O counts and typicals for system vendors | SI | data | INST-T260 | I/O count per system and type, redundancy, spare percentage, typical circuits for DCS/SIS/F&G vendors. | 3
INST-I270 | INST | Package instrumentation and control requirements | Excel / Word | document | INST-T270 | I&C scope for packages: instrument standards, PLC requirements, interface signals, communications, F&G and SIS interfaces. | 4
INST-I271 | INST | Package control vendor data comments | Document Locator | document | INST-T270 | Comments on package P&IDs, instrument lists, panel drawings and communication maps. | 3
INST-I272 | INST | Package interface signal list | Excel / Word | data | INST-T270 | Hardwired and serial signals between packages and DCS/SIS/F&G: tag, register, type, direction. | 2
INST-I280 | INST | Instrument power and UPS load list | Excel / Word | data | INST-T280 | Consumer, voltage, kW/kVA, UPS or normal supply, redundancy, location for ELEC load list and UPS sizing (keyed into SPEL by hand). | 3
INST-I281 | INST | Instrument winterization and heat tracing requirements | Excel / Word | data | INST-T280 | Instrument tags, impulse lines and analyzer sample lines needing tracing, maintain temperature, enclosure heating. | 2
INST-I282 | INST | Instrument air consumers | Excel / Word | data | INST-T280 | Instrument air users and steady/peak consumption for PROC utility balance and MECH air package sizing. | 1
INST-I290 | INST | Instrument location plans | S3D | drawing | INST-T290 | Plan views with instrument and JB locations and elevations, tray routing. | 7
INST-I291 | INST | Junction box locations and sizes | S3D | data | INST-T290 | JB tag, coordinates, size, IS/non-IS, cables served. | 7
INST-I292 | INST | 3D model review comments for I&C | S3D | document | INST-T290 | Instrument access, valve orientation, clearance and maintainability comments. | 1
INST-I300 | INST | Hook-up drawings and tag assignments | Excel / Word | drawing | INST-T300 | Process, pneumatic and electrical hook-up typicals with bill of materials (tubing, fittings, manifolds, supports) and tag-to-hook-up assignment list. | 4
INST-I310 | INST | Wiring, marshalling and termination diagrams | SI | drawing | INST-T310 | JB and marshalling cabinet termination diagrams, multicore/single-pair allocation, cable block diagrams, IS/non-IS segregation. | 3
INST-I320 | INST | Instrument cable schedule | SI | data | INST-T320 | Cable tag, type, cores/pairs, size, from/to (device, JB, cabinet), route segments, length, gland type; for construction pulling and MTO. | 4
INST-I321 | INST | Instrument cable routing and tray loading requirements | Excel / Word | data | INST-T320 | Instrument cable count, overall diameter and weight per tray segment, IS/signal segregation, for ELEC raceway sizing. | 6
INST-I330 | INST | Loop diagrams | SI | drawing | INST-T330 | Loop from field device to system channel: terminals, cables, JBs, power, IS parameters, ranges, set points; used for loop checks. | 4
INST-I340 | INST | Instrument bulk MTO | Excel / Word | data | INST-T340 | Quantities and specs of cable by type, tubing, fittings, manifolds, JBs, glands, supports, with surplus, for requisition and Jovix material control. | 1
INST-I350 | INST | Telecom system design | Excel / Word | document | INST-T350 | PA/GA, CCTV, LAN/WAN, radio and access control specifications, block diagrams and requisition data. | 2
INST-I351 | INST | Telecom device list, locations and power | Excel / Word | data | INST-T350 | Speaker, beacon, camera, access point and reader tags with locations, mounting, power/UPS load and cabling needs. | 1
INST-I380 | INST | System configuration database | SI | data | INST-T380 | Tag, description, range, units, alarm limits and priorities, I/O assignment, control module typical, for DCS/SIS/F&G configuration (spreadsheet export to vendor tools). | 2
INST-I390 | INST | FAT report and punch list | DCS / SIS config | document | INST-T390 | FAT test record, punch items by category, configuration changes required, release for shipment. | 1
INST-I400 | INST | I&C RFI responses and field changes | Procore | document | INST-T400 | RFI answers, field change instructions with revised hook-up, routing or termination details. | 2
INST-I410 | INST | Instrument tag register for completions | Excel / Word | data | INST-T410 | Instrument, cable, JB and loop tags with type, system, subsystem, ITR form type, for spreadsheet load into Smart Completions. | 2
INST-I420 | INST | I&C punch and loop check resolutions | Smart Completions | document | INST-T420 | Engineering responses to loop check failures and punch items, range/set point corrections. | 2
INST-I430 | INST | SAT and SIS validation records and as-configured database | DCS / SIS config | document | INST-T430 | SAT results, SIF validation records, final as-configured database backup and change log. | 1
INST-I440 | INST | As-built I&C database and drawings | SI | data | INST-T440 | As-built instrument index, datasheets, loops, wiring and location drawings for owner handover. | 3
INST-I450 | INST | Electrical communication FAT setup | Excel / Word | document | INST-T390 | DCS/ECMS emulator or test rig and communication map for the integrated switchgear/MCC communication test. | 1
INST-I901 | INST | Instrumentation deliverables list | Excel / Word | data | INST-T005 | Index, datasheets, loops, C&E and layouts with planned dates. | 1
INST-I902 | INST | Instrumentation progress measurement | Excel / Word | data | INST-T005 | Datasheet and loop diagram completion counts against plan. | 1
INST-I903 | INST | Instrumentation holds | Excel / Word | data | INST-T005 | Loops and datasheets on hold awaiting vendor or other discipline data, with cause. | 1
ELEC-I010 | ELEC | Electrical design basis and philosophy | Document Locator | document | ELEC-T010 | System voltages (utility, 13.8 kV/4.16 kV/480 V/120-208 V), short-circuit design limits, redundancy (main-tie-main), motor voltage by kW range, motor efficiency (NEMA Premium), enclosure, starting philosophy, essential/UPS loads, grounding method (resistance-grounded MV), codes and standards list. | 12
ELEC-I012 | ELEC | Motor and electrical requirements for mechanical/vendor specs | Document Locator | document | ELEC-T010 | Electrical requirements section for driven-equipment and package specs: motor voltage by size, frequency, enclosure (TEFC/explosion-proof), insulation class, service factor, space heaters, winding RTDs, IEEE 841, VFD-duty requirements, package MCC/panel supply rules, local control station requirements. | 7
ELEC-I020 | ELEC | Preliminary power demand estimate | Excel / Word | data | ELEC-T020 | Connected kW, running kW, peak demand MW/MVA, power factor, essential load MW, largest motor size, growth margin; by unit/area. | 3
ELEC-I030 | ELEC | Utility interconnect requirements | Excel / Word | decision | ELEC-T030 | Point of interconnection, service voltage, available three-phase and SLG fault MVA and X/R (max/min), utility protection and metering requirements, revenue metering, power quality limits (IEEE 519), backfeed date, utility-owned vs owner-owned equipment boundary. | 8
ELEC-I032 | ELEC | Utility interconnection application and load forecast | Document Locator | document | ELEC-T030 | Formal application to utility: forecast demand by year, largest motor, harmonic sources, single-line at POI; supports owner commercial agreement and schedule. | 1
ELEC-I040 | ELEC | Preliminary key one-line diagram | Excel / Word | drawing | ELEC-T040 | Main substation, transformers (MVA, voltages), MV/LV distribution, number of substations, emergency generator and UPS, selected configuration with rationale. | 3
ELEC-I050 | ELEC | Electrical estimate quantities and pricing | Excel / Word | data | ELEC-T050 | Major equipment list with budget prices, bulk quantities (cable by size, tray, conduit, grounding, lighting fixtures, heat tracing), installation hours basis, by WBS/area. | 4
ELEC-I060 | ELEC | Hazardous area release source list | Excel / Word | data | ELEC-T060 | Per source: equipment/tag, fluid, NFPA 497 group, AIT, temperature class, grade of release, ventilation, Class/Division (or Zone), extent per API RP 500/505 figure reference. | 3
ELEC-I070 | ELEC | Hazardous area classification drawings | S3D | drawing | ELEC-T070 | Plan and elevation drawings with Class I Div 1/Div 2 (or Zone 0/1/2) boundaries, gas group, temperature class, unclassified buildings, pressurized rooms; issued to all disciplines, vendors and construction. | 8
ELEC-I072 | ELEC | Equipment certification requirements by area | Excel / Word | data | ELEC-T070 | Per area/equipment tag: Class/Division or Zone, gas group, T-code; used by MECH (motors, packages), INST (instruments, junction boxes), CIVL (HVAC), vendors. | 15
ELEC-I080 | ELEC | Substation and electrical building requirements to civil | Excel / Word | document | ELEC-T080 | Building footprint, ceiling height, equipment arrangement, floor loads and equipment weights, cable vault/raised floor/cable entry, doors and maintenance clearances (NEC 110.26), transformer pads, oil containment volumes, fire separation, battery room ventilation, blast rating. | 4
ELEC-I082 | ELEC | Electrical building HVAC and pressurization requirements | Excel / Word | data | ELEC-T080 | Heat dissipation per room (kW) for switchgear, MCC, VFD, UPS, transformers; design temperatures/humidity; battery hydrogen ventilation; positive pressurization and purge per NFPA 496; HVAC power supply needs back to ELEC. | 2
ELEC-I084 | ELEC | Prefabricated E-house scope definition | Excel / Word | decision | ELEC-T080 | Decision on stick-built vs E-house, modules, shipping splits, equipment included, skid foundation interface. | 2
ELEC-I090 | ELEC | Electrical load list | SPEL | data | ELEC-T090 | Per load: tag, description, P&ID, area, kW/HP, voltage, phases, efficiency, PF, duty, demand factor, bus/MCC assignment, essential/UPS flag, starter type (DOL/RVSS/VFD); summary by bus and switchboard. | 8
ELEC-I092 | ELEC | Plant power demand summary to process and owner | Excel / Word | data | ELEC-T090 | Total electrical demand (normal, peak, essential), per-unit kWh/yr for utility balance and opex; issued to PROC utility balance and OWNR. | 1
ELEC-I100 | ELEC | Electrical P&ID review comments | Document Locator | document | ELEC-T100 | Markups: missing motor tags, MOV/EOV electrical data, heat tracing notes, start/stop and interlock representation, ESD trip of motors, VFD symbols. | 1
ELEC-I110 | ELEC | Electrical equipment ratings | Excel / Word | data | ELEC-T110 | Transformer MVA, voltage, %Z, cooling; switchgear bus and interrupting ratings; MCC sizes and bucket counts; generator kW/kVA; UPS kVA and battery Ah/autonomy; spare capacity. | 10
ELEC-I120 | ELEC | Single-line diagrams | SPEL | drawing | ELEC-T120 | Main, MV, LV and MCC one-lines: buses, breakers, transformers, feeders, cable references, protection relays (ANSI devices), CTs/PTs, metering, interlocks, normal/tie/standby schemes. | 9
ELEC-I130 | ELEC | MV switchgear requisition package | Document Locator | document | ELEC-T130 | Specification and datasheets: voltage, continuous/interrupting ratings, arc-resistant construction (IEEE C37.20.7), relays, communication protocol, I/O to DCS/ECMS, testing and documentation requirements. | 2
ELEC-I140 | ELEC | Power transformer requisition package | Document Locator | document | ELEC-T140 | Specification and datasheets: MVA, voltages, %Z, vector group, OLTC/NLTC, cooling, neutral grounding resistor, oil containment data, losses evaluation basis, testing. | 2
ELEC-I150 | ELEC | LV switchgear, MCC and E-house requisition package | Document Locator | document | ELEC-T150 | Specification and datasheets: buses, starter schedule (bucket list), intelligent MCC protocol, E-house structure, HVAC, fire detection, internal lighting and shipping splits. | 2
ELEC-I160 | ELEC | VFD requisition package | Document Locator | document | ELEC-T160 | Specification and datasheets: motor list on VFD, ratings, pulse number/active front end, IEEE 519 limits, bypass, motor compatibility (inverter-duty), DCS interface. | 2
ELEC-I170 | ELEC | UPS, DC and generator requisition package | Document Locator | document | ELEC-T170 | Specification and datasheets: UPS kVA, autonomy, battery type, DC charger rating, generator kW, fuel and tank autonomy, ATS, NFPA 110 level, emissions tier. | 2
ELEC-I180 | ELEC | Electrical technical bid evaluations | Document Locator | document | ELEC-T180 | Technical compliance tables, accepted deviations, clarifications, recommended vendor per requisition, technical conditions for PO. | 2
ELEC-I190 | ELEC | Electrical vendor document comments | Document Locator | document | ELEC-T190 | Coded returns (approved, approved with comments, rejected) with markups on GA, schematics and datasheets. | 2
ELEC-I192 | ELEC | Certified electrical equipment data | SPEL | data | ELEC-T190 | Certified transformer %Z/X/R, losses, switchgear dimensions/weights, breaker and relay models, CT ratios, heat loss; keyed into SPEL and ETAP and passed to CIVL for foundations. | 5
ELEC-I200 | ELEC | Motor data review comments | Document Locator | document | ELEC-T200 | Comments to MECH and vendors on motor voltage, enclosure, area certification, starting capability, space heaters, RTDs, VFD compatibility. | 3
ELEC-I202 | ELEC | Certified motor data | SPEL | data | ELEC-T200 | Per motor: rated kW, FLA, LRC, PF and efficiency at load, inertia (motor and load), starting torque, accelerating time; used in SPEL, ETAP motor starting, cable sizing and relay settings. | 3
ELEC-I210 | ELEC | Load flow study results | ETAP | document | ELEC-T210 | Bus voltages, branch loading, transformer loading and tap settings, power factor and capacitor needs, losses, for normal and N-1 cases. | 5
ELEC-I220 | ELEC | Short-circuit study results | ETAP | document | ELEC-T220 | Momentary and interrupting duties per bus, X/R, SLG fault values, equipment duty check pass/fail; feeds specs, cable sizing (short-circuit withstand) and grounding. | 11
ELEC-I230 | ELEC | Motor-starting study results | ETAP | document | ELEC-T230 | Voltage dip at motor and buses, acceleration time, pass/fail per motor, restart/re-acceleration scheme. | 1
ELEC-I232 | ELEC | Motor starting method requirements | Excel / Word | decision | ELEC-T230 | Maximum DOL motor size per bus, motors requiring soft starter/VFD/autotransformer, minimum starting torque requirements; returned to MECH and driven-equipment vendors. | 1
ELEC-I240 | ELEC | Harmonic study results and filter requirements | ETAP | document | ELEC-T240 | THD/TDD per bus, resonance check, filter or capacitor bank requirements, VFD front-end requirements. | 1
ELEC-I250 | ELEC | Protective device coordination study | ETAP | document | ELEC-T250 | TCC curves, coordination per zone, selectivity exceptions, arc-flash reduction (maintenance switch) settings. | 1
ELEC-I252 | ELEC | Relay and breaker setting files | ETAP | data | ELEC-T250 | Setting sheets/files per relay and trip unit for loading by the commissioning testing contractor. | 4
ELEC-I260 | ELEC | Arc flash study and labels | ETAP | document | ELEC-T260 | Incident energy and arc flash boundary per bus, PPE category, label data file for printing and installation, mitigation recommendations. | 1
ELEC-I270 | ELEC | Ground grid study | Excel / Word | document | ELEC-T270 | Grid resistance, step and touch potentials vs IEEE 80 limits, conductor size, rod quantity. | 1
ELEC-I272 | ELEC | Grounding layouts and details | Excel / Word | drawing | ELEC-T270 | Ground grid routing, ground wells, equipment/tank/vessel/structure bonding points, embeds in foundations (to CIVL), static grounding details. | 6
ELEC-I280 | ELEC | Lightning protection design | Excel / Word | drawing | ELEC-T280 | Risk assessment, protected zones, air terminal and down-conductor layouts, bonding to ground grid. | 1
ELEC-I290 | ELEC | Lighting and small power layouts | Excel / Word | drawing | ELEC-T290 | Fixture types and locations, lux levels, circuiting, lighting panels, photocell/contactor control, convenience/welding receptacles. | 2
ELEC-I292 | ELEC | Lighting panel schedules and loads | SPEL | data | ELEC-T290 | Panel schedules: circuits, kW per panel, feeder supply; keyed into load list. | 1
ELEC-I300 | ELEC | Heat tracing circuit list and loads | SPEL | data | ELEC-T300 | Per circuit: line number, cable type, W/m, circuit length, breaker, panel, controller, maintain/max temperature; panel loads to load list. | 1
ELEC-I302 | ELEC | Heat tracing isometrics and requirements to piping | Excel / Word | drawing | ELEC-T300 | Heat tracing isometrics, power connection and end-seal locations, RTD locations, requirements back to piping/insulation (insulation oversize, aluminium tape). | 1
ELEC-I304 | ELEC | Heat tracing control and alarm interface to I&C | Excel / Word | data | ELEC-T300 | Heat trace panel common alarms and monitoring points, communication to DCS. | 1
ELEC-I310 | ELEC | Cathodic protection design | Excel / Word | drawing | ELEC-T310 | Current requirement calculations, anode beds, rectifiers (AC supply load to load list), test stations, insulating flange locations (to PIPE), cable routing. | 2
ELEC-I320 | ELEC | Cable schedule | SPEL | data | ELEC-T320 | Per cable: tag, from/to, voltage, conductors, size, type (MC/TC-ER), length, route/raceway segments, gland size. | 6
ELEC-I322 | ELEC | Cable pull cards and terminations | SPEL | data | ELEC-T320 | Pull cards with route segments, terminations and drum assignment for construction and Smart Completions tag load. | 2
ELEC-I330 | ELEC | Cable tray routing model | S3D | model | ELEC-T330 | Tray and conduit routes, sizes, elevations, rack levels reserved, fill; reference for piping clash checks and model reviews. | 12
ELEC-I332 | ELEC | Cable tray support loads to civil/structural | Excel / Word | data | ELEC-T330 | Tray loads per rack level and structure (kg/m), support locations and attachments. | 2
ELEC-I334 | ELEC | Underground duct bank and trench layout | S3D | drawing | ELEC-T330 | Duct bank routes, sections, manholes, depths and crossings; to CIVL for excavation and drainage coordination. | 3
ELEC-I340 | ELEC | MCC and switchgear interface signal list | SPEL | data | ELEC-T340 | Per motor/breaker: run status, trip, available, remote start/stop, SIS trip, VFD speed ref/feedback, kW/current via network; hardwired vs serial; marshalling terminal; for INST I/O list. | 4
ELEC-I350 | ELEC | Control and interlock schematics | SPEL | drawing | ELEC-T350 | Motor control typicals, elementary/interlock diagrams, transfer schemes, ESD interfaces with terminal numbers. | 2
ELEC-I360 | ELEC | Electrical layouts and power plans | Excel / Word | drawing | ELEC-T360 | Substation/room layouts, outdoor equipment locations, power plans with conduit/tray drops, local control station and motor locations. | 5
ELEC-I362 | ELEC | Electrical equipment foundation and embed requirements | Excel / Word | data | ELEC-T360 | Equipment weights, anchorage, base dimensions, conduit stub-ups and embeds for transformers, switchgear, E-houses, generators; to CIVL. | 2
ELEC-I370 | ELEC | Electrical bulk MTO | Purchasing DB | data | ELEC-T370 | Line items with commodity code, size, quantity, contingency, delta vs previous MTO; loaded by hand into Purchasing DB. | 1
ELEC-I380 | ELEC | Temporary construction power design | Excel / Word | drawing | ELEC-T380 | Temporary service, generators, distribution panels and routing for construction. | 1
ELEC-I390 | ELEC | IFC electrical deliverable package | Document Locator | document | ELEC-T390 | Sealed IFC one-lines, layouts, schedules, schematics, area classification and details. | 2
ELEC-I400 | ELEC | Electrical FAT reports and punch | Excel / Word | document | ELEC-T400 | FAT acceptance, punch items, open deviations, release for shipment recommendation. | 2
ELEC-I410 | ELEC | Electrical RFI responses and field changes | Procore | decision | ELEC-T410 | RFI answers, field change notices, revised sketches, impact on cable schedule and SPEL. | 1
ELEC-I420 | ELEC | Electrical energization sequence and system boundaries | Smart Completions | decision | ELEC-T420 | Electrical systems/subsystems marked on one-lines, energization order, permanent power backfeed date. | 3
ELEC-I422 | ELEC | Electrical tag and cable lists for completions | Smart Completions | data | ELEC-T420 | Equipment, cable and circuit tag lists with system assignment, loaded by spreadsheet into Smart Completions for ITRs. | 2
ELEC-I430 | ELEC | Energization readiness sign-off | Smart Completions | decision | ELEC-T430 | Engineering sign-off that settings are applied, labels installed, tests accepted, ready to energize. | 2
ELEC-I440 | ELEC | As-built electrical records | Document Locator | document | ELEC-T440 | As-built SPEL database, ETAP model, one-lines, cable schedule and layouts for handover to owner. | 2
ELEC-I450 | ELEC | Electrical acceptable manufacturers | Excel / Word | data | ELEC-T010 | Acceptable manufacturers per electrical equipment type. | 1
ELEC-I901 | ELEC | Electrical deliverables list | Excel / Word | data | ELEC-T005 | SLDs, studies, cable schedule and layouts with planned dates. | 1
ELEC-I902 | ELEC | Electrical progress measurement | Excel / Word | data | ELEC-T005 | Electrical deliverable completion counts against plan. | 1
SCM-I010 | SCM | Procurement plan | Excel / Word | document | SCM-T010 | Packages, sourcing route, procurement durations, RFQ/award dates and ROS per MR. | 3
SCM-I020 | SCM | Long-lead items list | Excel / Word | data | SCM-T010 | Tag, description, lead time, ROS and required commitment date for long-lead items. | 2
SCM-I030 | SCM | Bidders list | Purchasing DB | data | SCM-T020 | Approved bidders per MR with contact and qualification status. | 7
SCM-I040 | SCM | Vendor prequalification record | Purchasing DB | document | SCM-T020 | Capability, capacity, quality system and financial assessment of new vendors. | 1
SCM-I050 | SCM | MR register entry | Purchasing DB | data | SCM-T030 | MR number, revision, title, originator, tag list, status and need date. | 3
SCM-I060 | SCM | Bulk material MR lines | Purchasing DB | data | SCM-T040 | Commodity code, description, size, material, quantity with surplus allowance, area. | 3
SCM-I070 | SCM | RFQ package | Document Locator | document | SCM-T050 | MR, commercial terms, instructions to bidders, VDRL, bid due date. | 2
SCM-I080 | SCM | Bid bulletin | Excel / Word | document | SCM-T060 | Questions and answers and MR changes issued to all bidders. | 3
SCM-I090 | SCM | Unpriced technical offers for TBE | Document Locator | document | SCM-T070 | Technical portions of each bid sent to the technical evaluator with TBE due date. | 6
SCM-I100 | SCM | Commercial bid evaluation | Excel / Word | document | SCM-T080 | Normalised price, delivery, terms and commercial ranking per bidder. | 4
SCM-I110 | SCM | Award recommendation | Excel / Word | decision | SCM-T090 | Recommended vendor, evaluated price, delivery and justification, with approvals. | 3
SCM-I120 | SCM | Purchase order | Document Locator | document | SCM-T100 | Issued PO document: scope, conformed MR, price, delivery, terms, VDRL. | 6
SCM-I130 | SCM | PO header data | Purchasing DB | data | SCM-T100 | PO number, vendor, award date, value, delivery terms, buyer, expeditor. | 6
SCM-I140 | SCM | PO line items | Purchasing DB | data | SCM-T100 | Line number, tag or commodity code, description, quantity, unit price, contract delivery date, cost code. | 5
SCM-I150 | SCM | PO amendment | Purchasing DB | document | SCM-T110 | Amendment number, changed lines, quantities, price and delivery changes. | 2
SCM-I160 | SCM | VDRL tracking records | Purchasing DB | data | SCM-T120 | Per PO: vendor document number, project number, type, review/information, due date. | 1
SCM-I170 | SCM | Vendor print status report | Purchasing DB | data | SCM-T130 | Per vendor document: due, received, sent for review, returned, review code, overdue days. | 4
SCM-I180 | SCM | Vendor documents routed for review | Document Locator | document | SCM-T130 | Vendor drawings and data transmitted to reviewing disciplines with return date. | 6
SCM-I190 | SCM | Review comments returned to vendor | Document Locator | document | SCM-T130 | Consolidated comments and review code returned to the vendor by transmittal. | 2
SCM-I200 | SCM | Expediting forecast | Purchasing DB | data | SCM-T140 | Per PO line: milestone status, forecast ex-works and site delivery dates, exceptions. | 6
SCM-I210 | SCM | Inspection assignment and agreed ITP | Excel / Word | data | SCM-T150 | Inspection level, hold/witness points agreed, inspector assigned per PO. | 4
SCM-I220 | SCM | Inspection report | Excel / Word | document | SCM-T160 | Tests witnessed, results, non-conformances and open points. | 1
SCM-I230 | SCM | Inspection release note | Excel / Word | decision | SCM-T160 | Release for shipment per PO line with outstanding items listed. | 4
SCM-I240 | SCM | Logistics plan | Excel / Word | document | SCM-T170 | Routes, heavy-haul and oversize moves, port and customs plan, transport schedule. | 4
SCM-I250 | SCM | Shipping notice | Excel / Word | document | SCM-T180 | PO, shipping pieces, weights, dimensions, carrier and expected arrival date at site. | 1
SCM-I260 | SCM | Expected receipts in Jovix | Jovix | data | SCM-T190 | PO number and lines, quantities and descriptions passed from the Purchasing DB for receiving. | 1
SCM-I270 | SCM | Material receipt record | Jovix | data | SCM-T200 | PO line received, quantity, date, location, heat numbers and MTR reference, tag. | 6
SCM-I280 | SCM | OS&D report | Jovix | document | SCM-T210 | Overage, shortage and damage details, photos, PO line and disposition. | 1
SCM-I290 | SCM | Storage location and preservation records | Jovix | data | SCM-T220 | Item location and preservation activity dates and findings. | 3
SCM-I300 | SCM | Material availability status | Jovix | data | SCM-T230 | Material availability per IWP fed to iConstruct for constraint checks. | 4
SCM-I310 | SCM | Material issue record | Jovix | data | SCM-T240 | Pick ticket, IWP, items and quantities issued with heat numbers. | 2
SCM-I320 | SCM | Material shortage report | Jovix | data | SCM-T230 | Shortages per IWP with expected receipt dates. | 1
SCM-I330 | SCM | Material reconciliation and surplus report | Jovix | document | SCM-T250 | Ordered vs received vs issued vs installed by commodity, surplus disposal. | 2
SCM-I340 | SCM | Vendor site service request | Purchasing DB | document | SCM-T260 | Service type, dates, location and PO reference for vendor representatives. | 2
SCM-I350 | SCM | Spares purchase order and register | Purchasing DB | data | SCM-T270 | Spare parts ordered by tag and part number, quantities, delivery. | 1
SCM-I360 | SCM | PO close-out record | Purchasing DB | data | SCM-T280 | Final documentation, deliveries and claims complete, PO closed date. | 1
SCM-I370 | SCM | Committed cost data | Purchasing DB | data | SCM-T100 | PO and amendment values by cost code and WBS for cost reporting. | 2
VEND-I010 | VEND | Budget quotation | Excel / Word | document | VEND-T010 | Budget price, delivery, outline scope, weight and main dimensions. | 3
VEND-I020 | VEND | Technical quotation | Excel / Word | document | VEND-T020 | Compliance statement, completed datasheets, outline drawings, weights, utilities, performance guarantees. | 18
VEND-I030 | VEND | Commercial quotation | Excel / Word | document | VEND-T020 | Price breakdown, options, spares prices, delivery, payment and validity. | 2
VEND-I040 | VEND | Deviations and exceptions list | Excel / Word | data | VEND-T020 | Technical and commercial exceptions to the RFQ with justification. | 6
VEND-I050 | VEND | Clarification responses | Excel / Word | document | VEND-T030 | Answers to TBE and commercial queries, revised offers. | 7
VEND-I060 | VEND | Vendor document schedule | Document Locator | data | VEND-T040 | Vendor document numbers, project numbers, titles, types and planned submission dates. | 2
VEND-I070 | VEND | Vendor GA drawings for review | Document Locator | drawing | VEND-T050 | Dimensions, nozzle sizes and orientations, weights, lifting points, access, terminal points. | 9
VEND-I080 | VEND | Vendor foundation and load data | Document Locator | drawing | VEND-T050 | Anchor bolt layout, static and dynamic loads, operating and test weights. | 6
VEND-I090 | VEND | Vendor design calculations | Mechanical calc tool | document | VEND-T060 | Thicknesses, MAWP, nozzle reinforcement, wind/seismic, allowable nozzle loads. | 6
VEND-I100 | VEND | Package P&IDs | Document Locator | drawing | VEND-T070 | Package process and instrument scheme with vendor tags and battery-limit points. | 9
VEND-I110 | VEND | Package I/O list and control narrative | Excel / Word | data | VEND-T070 | Signals to and from DCS/SIS, communication protocol, control and shutdown description. | 6
VEND-I120 | VEND | Package electrical data | Excel / Word | data | VEND-T080 | Motor ratings, starting data, electrical loads, panel requirements, heat tracing. | 5
VEND-I130 | VEND | Package instrument list and datasheets | Excel / Word | data | VEND-T070 | Vendor-supplied instrument tags, types, ranges and datasheets. | 5
VEND-I140 | VEND | Certified vendor drawings and data | Document Locator | document | VEND-T090 | Final certified GA, foundation, P&ID, electrical and instrument data. | 27
VEND-I150 | VEND | Inspection and test plan | Excel / Word | document | VEND-T100 | Inspection activities, acceptance criteria, hold and witness points. | 6
VEND-I160 | VEND | Manufacturing schedule | Excel / Word | data | VEND-T100 | Baseline milestones: drawings, material order, fabrication, tests, ex-works date. | 3
VEND-I170 | VEND | Material test reports | Excel / Word | document | VEND-T110 | MTRs per component with heat numbers, chemistry and mechanical properties. | 6
VEND-I180 | VEND | Test certificates | Excel / Word | document | VEND-T120 | Hydrotest, NDE, PMI, performance and FAT certificates. | 7
VEND-I190 | VEND | Inspection notification | Excel / Word | data | VEND-T120 | Test or inspection due, date and location, notice period. | 2
VEND-I200 | VEND | Spool fabrication status | Excel / Word | data | VEND-T130 | Spool number, isometric, status (cut, welded, NDE, painted, shipped), heat numbers per spool. | 2
VEND-I210 | VEND | Steel shop drawings and fabrication status | Tekla | drawing | VEND-T140 | Shop drawings, piece marks, erection drawings and fabrication/shipping status. | 1
VEND-I220 | VEND | Packing list and shipping documents | Excel / Word | document | VEND-T160 | Shipping pieces, item marks, tags, weights, dimensions, heat numbers, certificates of origin. | 2
VEND-I230 | VEND | Nameplate and as-built data | Excel / Word | data | VEND-T170 | Serial number, nameplate rating, MAWP, test pressure, as-built weights and dimensions. | 3
VEND-I240 | VEND | MDR / data book | Document Locator | document | VEND-T180 | Certified drawings, calculations, MTRs, weld maps, NDE and test records, certificates. | 6
VEND-I250 | VEND | IOM manuals | Document Locator | document | VEND-T190 | Installation, operation and maintenance instructions. | 8
VEND-I260 | VEND | Spare parts interchangeability records | Excel / Word | data | VEND-T190 | Part numbers, recommended quantities, prices and lead times per tag. | 5
VEND-I270 | VEND | Site service reports | Excel / Word | document | VEND-T210 | Installation checks, alignment, commissioning findings and sign-offs. | 5
VEND-I280 | VEND | DCS/SIS configuration and FAT records | DCS / SIS config | data | VEND-T200 | Configured database, logic, graphics, FAT punch list and FAT certificate. | 3
VEND-I290 | VEND | Preservation and storage instructions | Excel / Word | document | VEND-T160 | Storage conditions and preservation activities and frequencies per item. | 4
VEND-I300 | VEND | Weld maps and NDE records | Excel / Word | document | VEND-T120 | Weld map, WPS/PQR references, welder IDs and NDE results. | 3
VEND-I310 | VEND | Manufacturing progress report | Excel / Word | data | VEND-T150 | Milestone actuals, sub-order status, percent complete, forecast ex-works date and delays. | 1
VEND-I320 | VEND | Fabricator spool shop drawings | Document Locator | drawing | VEND-T130 | Spool shop drawings for review against IFC isometrics. | 1
VEND-I321 | VEND | Licensor process proposal | Excel / Word | document | VEND-T020 | Licensor yields, utilities, catalyst and chemical consumption, and guarantees. | 2
VEND-I322 | VEND | Licensor process design package | Document Locator | document | VEND-T090 | Licensor H&MB, operating conditions, dosing rates and catalyst volumes, performance test procedure and correction curves. | 3
VEND-I323 | VEND | Bidder questions | Excel / Word | data | VEND-T030 | Technical and commercial questions raised by bidders during the bid period. | 1
VEND-I324 | VEND | Change-order quotation | Excel / Word | document | VEND-T020 | Price and delivery impact of a post-award change. | 1
VEND-I325 | VEND | OS&D response | Excel / Word | document | VEND-T160 | Vendor replacement, repair or credit proposal for an OS&D report. | 1
CONS-I010 | CONS | Constructability input register | Excel / Word | document | CONS-T010 | Constructability requirements and lessons learned: access widths, crane corridors, preferred spool sizes, shop vs field work, sequence constraints, site labour limits. | 4
CONS-I020 | CONS | Site logistics and laydown plan | Excel / Word | drawing | CONS-T020 | Laydown and fabrication areas, temporary buildings, haul roads, construction gates, parking, temporary utility connection points. | 6
CONS-I025 | CONS | Temporary facility and utility requirements | Excel / Word | data | CONS-T020 | Temporary power demand, construction water, temporary building locations and loads, needed from civil, electrical and owner. | 4
CONS-I030 | CONS | Modularisation and prefabrication decision | Excel / Word | decision | CONS-T030 | Selected module/skid/pre-assembled rack scope, module boundaries, maximum module dimensions and weights, shop vs field fabrication split. | 5
CONS-I040 | CONS | Heavy lift and crane plan | Excel / Word | document | CONS-T040 | Heavy lift list (item, weight, radius), crane selection, crane pad locations and loads, lift sequence and dates. | 7
CONS-I045 | CONS | Lift and setting requirements to design | Excel / Word | data | CONS-T040 | Requirements returned to design: lifting and tailing lug type and position, crane pad bearing, keep-clear zones, late-set equipment, leave-outs in steel and piping. | 2
CONS-I050 | CONS | Path of construction | P6 | document | CONS-T050 | Area sequence and logic from underground to commissioning, with target dates by area and system, used to set engineering and procurement priorities. | 12
CONS-I060 | CONS | CWA boundaries | iConstruct | drawing | CONS-T060 | CWA IDs, boundaries on the plot plan grid and area descriptions. | 4
CONS-I070 | CONS | CWP breakdown and boundaries | P6 | data | CONS-T070 | CWP IDs, discipline, CWA, scope boundaries and budget quantities. | 5
CONS-I080 | CONS | CWP sequence and EWP need dates | P6 | data | CONS-T070 | CWP start dates and the date each supporting EWP (IFC drawings and data) must be issued; sent to engineering and project controls. | 5
CONS-I090 | CONS | CWP material required-on-site dates | P6 | data | CONS-T070 | Required-on-site (ROS) dates by CWP for equipment, bulks and fabricated spools and steel; sent to procurement. | 4
CONS-I100 | CONS | Model review constructability comments | iConstruct | data | CONS-T080 | Model review comments by object and area: access, rigging, scaffolding, spool breaks, weld access, clashes with temporary works, with action-by discipline. | 2
CONS-I110 | CONS | Drawing constructability comments | Document Locator | document | CONS-T090 | Comment sheets on IFR drawings and specifications: installability, tolerances, sequence, field welds, tie-in access. | 1
CONS-I120 | CONS | Construction execution plan | Excel / Word | document | CONS-T100 | Construction strategy, contracting split, organisation, work hours, temporary facilities, sequence and AWP approach. | 3
CONS-I130 | CONS | Construction hours and indirects estimate input | Excel / Word | data | CONS-T100 | Direct field hours by discipline and CWA, crew sizes, construction equipment, scaffolding and indirect costs for the estimate. | 2
CONS-I140 | CONS | Construction schedule by CWP | P6 | data | CONS-T110 | Resource-loaded level 3 CWP and IWP activities with logic links to EWP, material and subsystem turnover dates. | 5
CONS-I150 | CONS | EWP-CWP alignment and gap report | P6 | data | CONS-T120 | Mapping of EWPs and POs to CWPs with forecast vs need dates and gaps flagged for engineering and procurement. | 1
CONS-I160 | CONS | Construction model with CWP/IWP attributes | iConstruct | model | CONS-T130 | Federated model with every object tagged with CWA, CWP, IWP and Jovix material status. | 1
CONS-I170 | CONS | Installation work package (IWP) | iConstruct | document | CONS-T140 | IWP scope, model views, drawing list and revisions, bill of materials, quantities, hours, safety and quality requirements. | 5
CONS-I180 | CONS | IWP material shortage report | iConstruct | data | CONS-T150 | IWP bill of materials vs Jovix availability: short items by item code, PO line and expected date. | 1
CONS-I190 | CONS | IWP constraint log | iConstruct | data | CONS-T160 | Open constraints by IWP: engineering hold, RFI, material, scaffolding, permit, predecessor; with owner and need date. | 2
CONS-I200 | CONS | Released IWP backlog | iConstruct | data | CONS-T160 | IWPs released to the field with planned start and crew, and backlog weeks by discipline. | 3
CONS-I210 | CONS | Request for information (RFI) | Procore | document | CONS-T170 | Question against a drawing or document revision with location, marked-up extract, required response date and response. | 11
CONS-I220 | CONS | Field change request | Procore | document | CONS-T180 | Proposed field change with reason, markups, affected drawings and tags, needing engineering disposition and owner approval. | 11
CONS-I230 | CONS | Field change cost and schedule impact | Procore | data | CONS-T180 | Hours, material and schedule impact of each field change, for change control. | 2
CONS-I240 | CONS | Foundation and setting-out survey record | Excel / Word | data | CONS-T190 | As-built foundation elevations, anchor bolt positions and deviations against IFC, accepted or non-conforming. | 4
CONS-I250 | CONS | Material issue request | Jovix | data | CONS-T200 | Pick list by IWP: item code, quantity, heat number, required date. | 1
CONS-I260 | CONS | Field shortage, overage and damage report | Jovix | data | CONS-T200 | Shortages, damaged items and surplus found at the work face, by item code and PO line. | 1
CONS-I270 | CONS | Installed quantities and progress | iConstruct | data | CONS-T210 | Installed quantities and percent complete by IWP, CWP and CWA, daily and weekly. | 4
CONS-I280 | CONS | Weld log and NDE register | Excel / Word | data | CONS-T220 | Weld numbers by iso, welder ID, NDE type and result, repairs and PWHT records. | 3
CONS-I290 | CONS | Pressure test pack | Excel / Word | document | CONS-T230 | Test limits on P&IDs and isos, line list, test pressure and medium, blinds and vents, punch before test. | 1
CONS-I300 | CONS | Pressure test and reinstatement record | Excel / Word | document | CONS-T230 | Signed test record, gauge calibration, reinstatement checklist and test pack status (tested, reinstated). | 3
CONS-I310 | CONS | Completed construction ITRs (A sheets) | Smart Completions | data | CONS-T240 | Signed A-ITR records by tag with status in Smart Completions. | 3
CONS-I320 | CONS | Construction punch clearance status | Smart Completions | data | CONS-T250 | Punch items cleared by construction with date and evidence. | 1
CONS-I330 | CONS | As-built redline markups | Procore | drawing | CONS-T260 | Redlined P&IDs, isometrics, cable routes, foundation and layout drawings with field deviations, for as-built drafting by engineering. | 9
CONS-I340 | CONS | Mechanical completion certificate | Smart Completions | decision | CONS-T270 | Subsystem MC certificate signed by construction, commissioning and owner, with outstanding B punch attached. | 1
CONS-I350 | CONS | Construction quality dossier | Document Locator | document | CONS-T280 | Per subsystem: weld and NDE records, test records, material traceability, calibration and inspection reports. | 3
CONS-I360 | CONS | Settlement monitoring readings | Excel / Word | data | CONS-T190 | Survey readings at tank and foundation monitoring points during hydrotest filling and holding. | 1
CONS-I361 | CONS | Tie-in field verification survey | Excel / Word | data | CONS-T190 | Measured dimensions, wall thickness, condition and photos of existing tie-in points. | 1
CONS-I362 | CONS | Field labour hours and subcontractor claims | Excel / Word | data | CONS-T210 | Direct hours spent and subcontractor progress claims by cost code. | 1
CONS-I363 | CONS | Construction HSE statistics | Excel / Word | data | CONS-T210 | Hours worked, incidents and rates for the period. | 1
COMM-I010 | COMM | Completions and commissioning execution plan | Excel / Word | document | COMM-T010 | Definitions of MC, RFC, RFSU and handover, ITR scheme, punch categories, certificate flow, roles and systems used. | 1
COMM-I020 | COMM | Preliminary system list and start-up sequence | Excel / Word | data | COMM-T020 | System numbers and descriptions, start-up order and preliminary ready-for-commissioning dates. | 5
COMM-I030 | COMM | System boundary P&IDs | SPID | drawing | COMM-T030 | P&IDs and single-lines colour-marked with system and subsystem limits and isolation points. | 5
COMM-I040 | COMM | System and subsystem register | Excel / Word | data | COMM-T030 | System and subsystem numbers, descriptions, discipline, priority and boundary descriptions. | 9
COMM-I050 | COMM | Commissioning sequence and required turnover dates | P6 | data | COMM-T040 | Subsystem sequence and required MC/turnover date per subsystem; sent to construction and project controls. | 9
COMM-I060 | COMM | ITR library and ITR matrix | Smart Completions | data | COMM-T050 | A/B/C check sheet forms and the mapping of discipline tag types to ITRs. | 2
COMM-I070 | COMM | Tag-to-subsystem register | Excel / Word | data | COMM-T060 | Every tag with discipline, tag type, P&ID and subsystem, ready for spreadsheet load into Smart Completions. | 2
COMM-I080 | COMM | ITR assignment register | Smart Completions | data | COMM-T070 | Tag, ITR, subsystem and status in Smart Completions; the ITR set construction and commissioning must complete. | 5
COMM-I090 | COMM | Pre-commissioning procedures | Excel / Word | document | COMM-T080 | Flushing, blowing, chemical cleaning, drying, leak test and inerting procedures by system. | 2
COMM-I100 | COMM | Commissioning and function test procedures | Excel / Word | document | COMM-T090 | System commissioning, run-in, C&E and SIF test procedures. | 3
COMM-I110 | COMM | Commissioning spares and first-fill list | Excel / Word | data | COMM-T100 | Commissioning spares, lubricants, chemicals, catalysts, filters and gases by system, quantity and need date; sent to procurement and owner. | 1
COMM-I120 | COMM | Vendor commissioning support requirements | Excel / Word | data | COMM-T110 | Vendor representative scope, man-days and call-off dates per package; sent to procurement and vendors. | 2
COMM-I130 | COMM | Temporary commissioning facility requirements | Excel / Word | data | COMM-T120 | Temporary spools, strainers, blinds, pumps and N2/steam/water needs with locations; sent to piping and construction. | 1
COMM-I140 | COMM | Test pack status by subsystem | Smart Completions | data | COMM-T130 | Test packs per subsystem with status (prepared, tested, reinstated). | 1
COMM-I150 | COMM | Punch list | Smart Completions | data | COMM-T140 | Punch items by tag and subsystem: description, category A/B/C, action-by discipline, due date and status. | 9
COMM-I160 | COMM | Subsystem turnover certificate (construction to commissioning) | Smart Completions | decision | COMM-T150 | Signed acceptance of MC subsystem custody transfer with exceptions. | 2
COMM-I170 | COMM | Completed pre-commissioning ITRs (B sheets) | Smart Completions | data | COMM-T160 | Signed B-ITR records by tag: flushing, cleaning, insulation tests, solo runs. | 1
COMM-I180 | COMM | Loop check records | Smart Completions | data | COMM-T170 | Loop status, test results and sign-off by loop. | 2
COMM-I190 | COMM | Loop and configuration defect list | Smart Completions | data | COMM-T170 | Defects found in loops: wrong ranges, wiring, tag or graphic errors, with action-by INST or DCS vendor. | 2
COMM-I200 | COMM | C&E and SIF function test records | DCS / SIS config | document | COMM-T180 | Test results for every C&E line and SIF with response times and sign-off. | 2
COMM-I210 | COMM | Energisation certificates | Smart Completions | decision | COMM-T190 | Signed energisation certificates per switchboard and feeder. | 1
COMM-I220 | COMM | Commissioning ITR records (C sheets) | Smart Completions | data | COMM-T200 | Signed C-ITRs and run-in test results by system. | 1
COMM-I230 | COMM | Ready-for-start-up certificate | Smart Completions | decision | COMM-T200 | RFSU certificate per system with outstanding punch and pre-start-up safety review closure. | 1
COMM-I240 | COMM | Commissioning technical query | Procore | document | COMM-T210 | Query or modification request to engineering with tags, markups and impact on start-up. | 3
COMM-I250 | COMM | System turnover package | Document Locator | document | COMM-T220 | Per system: certificates, ITRs, test records, punch, vendor data and as-built list. | 3
COMM-I260 | COMM | System handover certificate | Smart Completions | decision | COMM-T230 | Owner-signed handover certificate per system with retained punch. | 1
COMM-I270 | COMM | Completions progress report | Smart Completions | data | COMM-T240 | ITR, punch and certificate progress by system against plan. | 2
COMM-I280 | COMM | Performance test report | Excel / Word | document | COMM-T250 | Measured yields, product quality and utilities against guarantees. | 1

## Discipline matrix
From \ To | OWNR | PROJ | PROC | SAFE | FIRE | MECH | PIPE | CIVL | INST | ELEC | SCM | VEND | CONS | COMM
OWNR | 4 | 18 | 26 | 34 | 4 | 9 | 13 | 13 | 13 | 11 | 5 | 3 | 8 | 11
PROJ | 14 | 29 | 10 | 3 |  | 6 | 9 | 8 | 8 | 8 | 14 | 1 | 19 | 6
PROC | 16 | 17 | 92 | 50 |  | 34 | 41 | 5 | 40 | 12 |  | 12 | 1 | 17
SAFE | 13 | 12 | 21 | 48 | 3 | 14 | 13 | 18 | 17 | 9 |  | 1 | 2 | 3
FIRE |  | 1 | 2 | 4 | 6 | 2 | 2 | 11 | 6 | 4 | 2
MECH | 5 | 13 | 25 | 11 | 4 | 56 | 27 | 26 | 12 | 11 | 22 | 13 | 6 | 6
PIPE | 4 | 12 | 15 | 17 | 3 | 19 | 52 | 36 | 17 | 20 | 14 | 5 | 30 | 8
CIVL | 2 | 9 | 1 | 12 | 4 | 8 | 23 | 63 | 8 | 20 | 3 | 5 | 23 | 1
INST | 5 | 8 | 19 | 24 | 3 | 11 | 16 | 8 | 55 | 19 | 14 | 13 | 15 | 16
ELEC | 2 | 8 | 5 | 4 | 1 | 12 | 7 | 21 | 17 | 102 | 13 | 7 | 13 | 12
SCM | 3 | 20 | 3 |  | 2 | 16 | 11 | 6 | 8 | 7 | 14 | 12 | 12 | 1
VEND | 6 | 4 | 20 | 7 | 1 | 34 | 14 | 10 | 19 | 16 | 33 | 12 | 4 | 7
CONS | 6 | 28 | 3 | 7 |  | 9 | 16 | 19 | 4 | 8 | 10 | 2 | 24 | 10
COMM | 7 | 6 | 9 | 4 |  | 4 | 5 |  | 9 | 4 | 2 | 2 | 12 | 15
Exchanges from the row discipline to the column discipline.

## System matrix
From \ To | HYSYS | HTRI | Flare / relief tool | SPID | SI | SPEL | S3D | SPF | CAESAR II | Tekla | ETAP | Mechanical calc tool | PHA tool | Document Locator | Purchasing DB | Jovix | P6 | iConstruct | Procore | Smart Completions | DCS / SIS config | Excel / Word
HYSYS | 7 | 2 (2 manual) | 1 | 2 (2 manual) | 1 (1 manual) | [7 empty] | 2 | [8 empty] | 22 (17 manual)
HTRI | [21 empty] | 7 (5 manual)
Flare / relief tool |  |  | 4 (1 manual) |  | 3 (3 manual) |  |  |  | 1 (1 manual) |  |  |  |  | 1 | [7 empty] | 7 (5 manual)
SPID |  |  | 1 | 13 (2 manual) | 6 (4 manual) | 1 (1 manual) | 10 (3 manual) | 2 |  |  |  |  | 8 | 7 | [7 empty] | 29 (15 manual)
SI |  |  | 1 (1 manual) | 3 (2 manual) | 19 |  | 6 (6 manual) | [6 empty] | 4 (1 manual) | 2 |  | 1 (1 manual) | 3 (3 manual) |  | 4 (3 manual) | 2 | 24 (17 manual)
SPEL |  |  |  | 1 | 3 (3 manual) | 7 (2 manual) |  |  |  |  | 9 (5 manual) | [6 empty] | 2 (2 manual) |  | 5 |  | 14 (7 manual)
S3D | 1 | 2 | 1 |  | 6 (5 manual) | 1 (1 manual) | 37 (1 manual) | 1 | 2 | 2 |  |  |  | 8 | 1 (1 manual) |  | 2 | 19 (2 manual) | 1 (1 manual) |  |  | 67 (12 manual)
SPF |  |  |  | 1
CAESAR II | [6 empty] | 1 | [14 empty] | 2 (1 manual)
Tekla | [6 empty] | 7 |  |  | 3 |  |  |  | 1 | [7 empty] | 2
ETAP | [5 empty] | 2 (2 manual) |  |  |  |  | 7 | [8 empty] | 3 (1 manual) |  | 12 (9 manual)
Mechanical calc tool |  |  | 1 (1 manual) | [5 empty] | 1 (1 manual) |  |  |  |  | 2 | [7 empty] | 20 (16 manual)
PHA tool |  |  |  | 6 (3 manual) |  | 1 | 3 | [5 empty] | 16 (5 manual) | 6 (3 manual) |  |  | 1 (1 manual) |  |  | 1 (1 manual) | 1 | 13 (8 manual)
Document Locator | 4 (3 manual) | 1 (1 manual) | 1 (1 manual) | 6 (2 manual) | 6 (2 manual) | 4 (1 manual) | 29 (16 manual) |  | 4 (4 manual) | 7 (5 manual) | 4 (3 manual) | 5 (5 manual) | 2 | 94 (11 manual) | 24 (21 manual) |  | 9 (4 manual) | 4 (4 manual) | 5 (4 manual) | 8 (4 manual) | 1 | 216 (101 manual)
Purchasing DB | [6 empty] | 2 | [6 empty] | 5 (2 manual) | 11 (6 manual) | 3 | 7 (5 manual) | 1 (1 manual) |  |  |  | 22 (14 manual)
Jovix | [13 empty] | 1 (1 manual) | 2 | 9 (1 manual) | 1 | 3 | 2 (2 manual) |  |  | 4 (3 manual)
P6 |  |  |  | 1 |  |  | 1 (1 manual) |  |  | 1 (1 manual) |  |  |  | 4 (1 manual) | 5 (4 manual) |  | 23 (18 manual) | 8 (2 manual) |  | 4 | 1 | 34 (17 manual)
iConstruct | [6 empty] | 3 | [7 empty] | 1 (1 manual) | 5 (1 manual) | 5 (3 manual) | 18 |  |  |  | 3 (3 manual)
Procore |  |  |  | 2 (2 manual) | 2 (1 manual) | 1 (1 manual) | 1 (1 manual) |  |  | 3 (3 manual) |  |  |  | 1 |  |  |  | 1 | 27 (17 manual) | 2 (1 manual) |  | 9 (6 manual)
Smart Completions |  |  |  | 2 (1 manual) | 1 |  | 2 (2 manual) | [6 empty] | 2 |  |  | 1 (1 manual) |  | 1 (1 manual) | 37 (6 manual) |  | 7 (3 manual)
DCS / SIS config |  |  |  |  | 1 (1 manual) | [14 empty] | 4 | 1 | 1
Excel / Word | 20 (10 manual) | 5 (4 manual) | 8 (4 manual) | 20 (11 manual) | 35 (20 manual) | 19 (13 manual) | 60 (36 manual) |  | 9 (9 manual) | 3 (3 manual) | 6 (4 manual) | 9 (9 manual) | 29 (1 manual) | 75 (24 manual) | 29 (17 manual) | 11 (8 manual) | 18 (15 manual) | 14 (8 manual) | 10 (3 manual) | 26 (9 manual) | 20 (9 manual) | 836 (456 manual)

## Manual hand-offs
From system | To system | Item | Information | From task | To task | What is re-entered
CAESAR II | Excel / Word | PIPE-I240 | Stress calculation report | PIPE-T220 Perform detailed stress analysis in CAESAR II | PIPE-T240 Specify and requisition spring and engineered supports | spring loads, travel and support type
DCS / SIS config | SI | VEND-I280 | DCS/SIS configuration and FAT records | VEND-T200 Configure and test the DCS/SIS | INST-T330 Generate loop diagrams | final I/O assignment and terminal numbers after FAT
Document Locator | CAESAR II | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | PIPE-T220 Perform detailed stress analysis in CAESAR II | structure deflection limits and rack load allowance assumptions
Document Locator | CAESAR II | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | PIPE-T220 Perform detailed stress analysis in CAESAR II | wind speed and exposure, seismic parameters
Document Locator | CAESAR II | MECH-I420 | Certified equipment GA and nozzle data | MECH-T310 Release certified vendor data to other disciplines | PIPE-T220 Perform detailed stress analysis in CAESAR II | certified nozzle locations for anchor points
Document Locator | CAESAR II | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | PIPE-T220 Perform detailed stress analysis in CAESAR II | certified nozzle data for rotating equipment and packages
Document Locator | ETAP | MECH-I440 | Certified vendor electrical data | MECH-T310 Release certified vendor data to other disciplines | ELEC-T230 Run motor-starting study | load torque curve and load inertia from certified motor/driven-equipment data
Document Locator | ETAP | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | ELEC-T240 Run harmonic analysis | certified VFD harmonic spectra and front-end type
Document Locator | ETAP | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | ELEC-T250 Perform protective relay coordination study | certified relay models, CT ratios, breaker trip units, fuse curves
Document Locator | Excel / Word | CIVL-I010 | Site civil screening assessment | CIVL-T010 Assess candidate sites for civil constraints | PIPE-T010 Prepare block plot plan options | topography, flood elevation and access routes per candidate site
Document Locator | Excel / Word | CIVL-I010 | Site civil screening assessment | CIVL-T010 Assess candidate sites for civil constraints | SAFE-T010 Compile environmental baseline and site constraints | per site topography, flood elevation and relocation needs; wetland/floodplain screening
Document Locator | Excel / Word | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | CIVL-T080 Size pipe racks and process structures conceptually | rack load allowances, deflection limits and load combinations
Document Locator | Excel / Word | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | CIVL-T150 Design static equipment foundations | load combinations and stability criteria
Document Locator | Excel / Word | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | CIVL-T200 Analyse and design pipe racks | load combinations and deflection limits
Document Locator | Excel / Word | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | CIVL-T210 Analyse and design process structures and platforms | load combinations and drift limits
Document Locator | Excel / Word | CIVL-I020 | Structural design criteria | CIVL-T020 Prepare civil and structural design basis | CIVL-T280 Design blast-resistant and other buildings structurally | design criteria
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | CIVL-T070 Review plot plan for civil constraints | flood level and rainfall for drainage fall comments
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | CIVL-T100 Prepare grading plan and finished elevations | rainfall intensity and flood level for falls and HPFG
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | CIVL-T110 Design surface drainage and sewers | rainfall intensity-duration-frequency
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | CIVL-T300 Design building HVAC | HVAC ambient design temperatures
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | ELEC-T010 Prepare electrical design basis and philosophy | ambient max/min temperatures, wind, seismic parameters, snow/ice for equipment ratings and derating
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | MECH-T020 Develop mechanical design basis | basic wind speed, seismic parameters, ambient min/max design temperatures
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | PROC-T010 Prepare process design basis | design ambient dry/wet bulb temperatures, rainfall, frost data
Document Locator | Excel / Word | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | SAFE-T050 Run preliminary consequence modelling for layout spacing | wind speed and ambient design data
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | CIVL-T040 Specify the geotechnical investigation | plant grid and ground levels for borehole coordinates
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | CIVL-T070 Review plot plan for civil constraints | existing ground levels and existing features
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | CIVL-T090 Design site preparation and earthworks | existing ground levels for cut/fill
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | CIVL-T100 Prepare grading plan and finished elevations | existing ground levels
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | PIPE-T010 Prepare block plot plan options | existing ground levels, plant grid, existing roads and underground services
Document Locator | Excel / Word | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | SAFE-T010 Compile environmental baseline and site constraints | existing ground levels, outfalls, existing roads and buildings
Document Locator | Excel / Word | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T090 Design site preparation and earthworks | soil parameters for compaction and soil improvement
Document Locator | Excel / Word | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T150 Design static equipment foundations | bearing pressure, subgrade modulus and pile capacities
Document Locator | Excel / Word | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T160 Design rotating equipment foundations with dynamic analysis | dynamic soil properties
Document Locator | Excel / Word | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T170 Design tank foundations | settlement predictions and bearing capacity
Document Locator | Excel / Word | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T180 Design piles and prepare piling layout | pile axial and lateral capacities
Document Locator | Excel / Word | CIVL-I065 | Foundation type recommendation by area | CIVL-T050 Set foundation design parameters from the geotechnical report | CIVL-T060 Prepare civil and structural quantities for estimates | foundation type (shallow/piled) by area
Document Locator | Excel / Word | CIVL-I100 | Grading plan and finished grade elevations | CIVL-T100 Prepare grading plan and finished elevations | CIVL-T110 Design surface drainage and sewers | finished grades and area falls
Document Locator | Excel / Word | CIVL-I100 | Grading plan and finished grade elevations | CIVL-T100 Prepare grading plan and finished elevations | CIVL-T190 Prepare foundation plans and anchor bolt layouts | finished grade and top-of-concrete reference
Document Locator | Excel / Word | CIVL-I110 | Drainage area plan and sewer layout | CIVL-T110 Design surface drainage and sewers | CIVL-T140 Coordinate underground services and prepare composite | sewer routes and inverts
Document Locator | Excel / Word | CIVL-I110 | Drainage area plan and sewer layout | CIVL-T110 Design surface drainage and sewers | SAFE-T080 Prepare water, stormwater and spill permit data | drainage areas and sewer outfalls
Document Locator | Excel / Word | CIVL-I120 | Dike and containment design | CIVL-T120 Design tank dikes and containment | SAFE-T300 Prepare RMP hazard assessment and registration data | dike capacities as passive mitigation
Document Locator | Excel / Word | CIVL-I130 | Preliminary pipe rack and structure configuration | CIVL-T080 Size pipe racks and process structures conceptually | CIVL-T060 Prepare civil and structural quantities for estimates | rack and structure steel tonnage per area
Document Locator | Excel / Word | CIVL-I130 | Preliminary pipe rack and structure configuration | CIVL-T080 Size pipe racks and process structures conceptually | CIVL-T200 Analyse and design pipe racks | rack configuration
Document Locator | Excel / Word | CIVL-I135 | Pipe rack design load allowances | CIVL-T080 Size pipe racks and process structures conceptually | CIVL-T200 Analyse and design pipe racks | load allowances
Document Locator | Excel / Word | CIVL-I160 | Static equipment foundation calculations | CIVL-T150 Design static equipment foundations | CIVL-T180 Design piles and prepare piling layout | static equipment foundation loads
Document Locator | Excel / Word | CIVL-I160 | Static equipment foundation calculations | CIVL-T150 Design static equipment foundations | CIVL-T190 Prepare foundation plans and anchor bolt layouts | footing and pedestal sizes, reinforcement
Document Locator | Excel / Word | CIVL-I165 | Rotating equipment foundation calculations | CIVL-T160 Design rotating equipment foundations with dynamic analysis | CIVL-T180 Design piles and prepare piling layout | rotating equipment foundation loads
Document Locator | Excel / Word | CIVL-I165 | Rotating equipment foundation calculations | CIVL-T160 Design rotating equipment foundations with dynamic analysis | CIVL-T190 Prepare foundation plans and anchor bolt layouts | block sizes and anchor bolt details
Document Locator | Excel / Word | CIVL-I170 | Tank foundation design | CIVL-T170 Design tank foundations | CIVL-T180 Design piles and prepare piling layout | tank foundation loads
Document Locator | Excel / Word | CIVL-I170 | Tank foundation design | CIVL-T170 Design tank foundations | CIVL-T190 Prepare foundation plans and anchor bolt layouts | ringwall dimensions
Document Locator | Excel / Word | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | CIVL-T140 Coordinate underground services and prepare composite | foundation outlines and depths
Document Locator | Excel / Word | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | CONS-T190 Survey, set out and verify foundations | foundation coordinates and top-of-concrete elevations
Document Locator | Excel / Word | CIVL-I195 | Anchor bolt layouts and schedule | CIVL-T190 Prepare foundation plans and anchor bolt layouts | CONS-T190 Survey, set out and verify foundations | anchor bolt coordinates, size and projection
Document Locator | Excel / Word | CIVL-I200 | Pile layout and schedule | CIVL-T180 Design piles and prepare piling layout | CIVL-T140 Coordinate underground services and prepare composite | pile locations
Document Locator | Excel / Word | CIVL-I210 | Pipe rack design calculations and reactions | CIVL-T200 Analyse and design pipe racks | CIVL-T180 Design piles and prepare piling layout | rack column base reactions
Document Locator | Excel / Word | CIVL-I220 | Process structure design calculations and reactions | CIVL-T210 Analyse and design process structures and platforms | CIVL-T180 Design piles and prepare piling layout | structure base reactions
Document Locator | Excel / Word | CIVL-I270 | Building layouts for electrical and I&C | CIVL-T270 Develop building space programme and layouts | CIVL-T280 Design blast-resistant and other buildings structurally | building layouts
Document Locator | Excel / Word | CIVL-I270 | Building layouts for electrical and I&C | CIVL-T270 Develop building space programme and layouts | CIVL-T290 Prepare architectural drawings | room layouts
Document Locator | Excel / Word | CIVL-I270 | Building layouts for electrical and I&C | CIVL-T270 Develop building space programme and layouts | CIVL-T300 Design building HVAC | room layouts and volumes
Document Locator | Excel / Word | CIVL-I280 | Building structural design | CIVL-T280 Design blast-resistant and other buildings structurally | CIVL-T290 Prepare architectural drawings | wall/roof construction and blast doors
Document Locator | Excel / Word | CIVL-I290 | Architectural drawings | CIVL-T290 Prepare architectural drawings | SAFE-T100 Perform facility siting study (API RP 752/753) | building plans, construction type and dimensions
Document Locator | Excel / Word | CIVL-I390 | Geotechnical and soil corrosivity report | CIVL-T040 Specify the geotechnical investigation | CIVL-T050 Set foundation design parameters from the geotechnical report | Geotechnical factual and interpretive report (soil profiles, bearing and pile capacities, settlement, groundwater, soil chemistry) from the geotechnical contractor; no VEND item exists
Document Locator | Excel / Word | CIVL-I390 | Geotechnical and soil corrosivity report | CIVL-T040 Specify the geotechnical investigation | ELEC-T270 Design grounding system | Soil resistivity survey (Wenner four-pin) and soil chemistry for grounding design
Document Locator | Excel / Word | CIVL-I390 | Geotechnical and soil corrosivity report | CIVL-T040 Specify the geotechnical investigation | ELEC-T310 Design cathodic protection | Soil resistivity and soil chemistry (pH, chlorides) survey along buried routes and tank pads for CP design
Document Locator | Excel / Word | ELEC-I010 | Electrical design basis and philosophy | ELEC-T010 Prepare electrical design basis and philosophy | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | voltage levels and power supply for electric fire pump drivers
Document Locator | Excel / Word | ELEC-I010 | Electrical design basis and philosophy | ELEC-T010 Prepare electrical design basis and philosophy | MECH-T230 Issue motor and driver electrical data | motor voltage by kW range
Document Locator | Excel / Word | ELEC-I010 | Electrical design basis and philosophy | ELEC-T010 Prepare electrical design basis and philosophy | VEND-T080 Prepare package electrical data | system voltages and frequency
Document Locator | Excel / Word | ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | ELEC-T010 Prepare electrical design basis and philosophy | MECH-T150 Prepare rotating equipment datasheets | motor voltage by size, enclosure, efficiency and electrical requirements for driven equipment
Document Locator | Excel / Word | ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | ELEC-T010 Prepare electrical design basis and philosophy | MECH-T250 Prepare requisition technical packages for bid | motor and electrical requirements for vendor scope
Document Locator | Excel / Word | ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | ELEC-T010 Prepare electrical design basis and philosophy | VEND-T020 Prepare firm technical and commercial quotations | motor and package electrical requirements
Document Locator | Excel / Word | ELEC-I012 | Motor and electrical requirements for mechanical/vendor specs | ELEC-T010 Prepare electrical design basis and philosophy | VEND-T080 Prepare package electrical data | motor specification requirements
Document Locator | Excel / Word | ELEC-I180 | Electrical technical bid evaluations | ELEC-T180 Evaluate electrical bids technically | SCM-T060 Manage bid clarifications and bid bulletins | clarifications for electrical packages
Document Locator | Excel / Word | MECH-I060 | Budget enquiry package | MECH-T050 Obtain budget quotations and equipment cost data | VEND-T010 Prepare budget quotations | short-form datasheets and scope for budget pricing; enquiry due date; enquiry scope and due date
Document Locator | Excel / Word | MECH-I270 | Nozzle orientation drawings (engineering) | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | CIVL-T210 Analyse and design process structures and platforms | platform clip, davit and ladder positions on vessels
Document Locator | Excel / Word | MECH-I270 | Nozzle orientation drawings (engineering) | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | VEND-T050 Prepare GA and outline drawings for review | required nozzle orientations, platform clips and davits
Document Locator | Excel / Word | MECH-I350 | Requisition technical package for bid | MECH-T250 Prepare requisition technical packages for bid | SCM-T150 Coordinate inspection and test plans | inspection level and testing requirements in the requisition
Document Locator | Excel / Word | MECH-I350 | Requisition technical package for bid | MECH-T250 Prepare requisition technical packages for bid | VEND-T020 Prepare firm technical and commercial quotations | requisition scope, datasheets, spares and inspection requirements
Document Locator | Excel / Word | MECH-I350 | Requisition technical package for bid | MECH-T250 Prepare requisition technical packages for bid | VEND-T100 Prepare the ITP and manufacturing schedule | inspection level and required tests
Document Locator | Excel / Word | MECH-I390 | Requisition for purchase (conformed technical package) | MECH-T280 Prepare requisitions for purchase | VEND-T050 Prepare GA and outline drawings for review | conformed datasheets and nozzle schedule
Document Locator | Excel / Word | MECH-I430 | Certified foundation loads and anchor bolt data | MECH-T310 Release certified vendor data to other disciplines | CIVL-T150 Design static equipment foundations | certified foundation loads and anchor bolt sizes and pattern
Document Locator | Excel / Word | MECH-I430 | Certified foundation loads and anchor bolt data | MECH-T310 Release certified vendor data to other disciplines | CIVL-T160 Design rotating equipment foundations with dynamic analysis | certified dynamic data and grouting requirements
Document Locator | Excel / Word | MECH-I430 | Certified foundation loads and anchor bolt data | MECH-T310 Release certified vendor data to other disciplines | CIVL-T190 Prepare foundation plans and anchor bolt layouts | certified anchor bolt sizes and pattern
Document Locator | Excel / Word | MECH-I490 | Approved inspection and test plans | MECH-T350 Review and approve inspection and test plans | SCM-T150 Coordinate inspection and test plans | approved ITP with witness/hold points
Document Locator | Excel / Word | OWNR-I060 | Owner standards and approved vendor list | OWNR-T040 Issue owner standards and specifications | CIVL-T020 Prepare civil and structural design basis | owner civil/structural standards and order of precedence
Document Locator | Excel / Word | OWNR-I060 | Owner standards and approved vendor list | OWNR-T040 Issue owner standards and specifications | PIPE-T010 Prepare block plot plan options | owner layout and spacing standards
Document Locator | Excel / Word | OWNR-I060 | Owner standards and approved vendor list | OWNR-T040 Issue owner standards and specifications | PROJ-T010 Prepare the project execution plan | owner standards, order of precedence and procedures the execution plan must reference
Document Locator | Excel / Word | PIPE-I440 | Piping technical bid evaluation | PIPE-T350 Evaluate piping bids | SCM-T090 Prepare the bid tabulation and award recommendation | piping technical acceptability per bidder
Document Locator | Excel / Word | PROJ-I230 | Gate decision | PROJ-T170 Prepare gate review packages and record gate decisions | PROJ-T100 Prepare the control estimate and budget | gate approval and conditions on the sanctioned estimate
Document Locator | Excel / Word | PROJ-I371 | Project specification and code list | PROJ-T010 Prepare the project execution plan | PIPE-T090 Develop piping material classes | Project specification and code list (ASME B31.3 edition, referenced standards, order of precedence for piping)
Document Locator | Excel / Word | SAFE-I270 | Vendor SHE review comments | SAFE-T270 Review vendor packages and bids for SHE compliance | MECH-T270 Prepare technical bid evaluations | SHE compliance of each package offer
Document Locator | Excel / Word | SCM-I070 | RFQ package | SCM-T050 Issue RFQ packages | VEND-T020 Prepare firm technical and commercial quotations | MR, commercial terms, instructions to bidders, VDRL, bid due date
Document Locator | Excel / Word | SCM-I120 | Purchase order | SCM-T100 Award the purchase order in the Purchasing DB | VEND-T100 Prepare the ITP and manufacturing schedule | PO inspection requirements and delivery dates
Document Locator | Excel / Word | SCM-I120 | Purchase order | SCM-T100 Award the purchase order in the Purchasing DB | VEND-T150 Report manufacturing progress | PO progress reporting requirements
Document Locator | Excel / Word | VEND-I070 | Vendor GA drawings for review | VEND-T050 Prepare GA and outline drawings for review | SCM-T170 Prepare the logistics plan | weights, dimensions and lifting points
Document Locator | Excel / Word | VEND-I080 | Vendor foundation and load data | VEND-T050 Prepare GA and outline drawings for review | CIVL-T150 Design static equipment foundations | anchor bolt layout, base ring/saddle dimensions, static loads
Document Locator | Excel / Word | VEND-I080 | Vendor foundation and load data | VEND-T050 Prepare GA and outline drawings for review | CIVL-T160 Design rotating equipment foundations with dynamic analysis | machine and rotor weights, unbalanced forces, baseplate and anchor bolt layout
Document Locator | Excel / Word | VEND-I080 | Vendor foundation and load data | VEND-T050 Prepare GA and outline drawings for review | CIVL-T170 Design tank foundations | tank vendor anchor and shell loads
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | CIVL-T190 Prepare foundation plans and anchor bolt layouts | certified anchor bolt templates and baseplate drawings
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | CONS-T040 Prepare heavy lift and crane study | certified GA with shipping and lift weights and lift points
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | CONS-T190 Survey, set out and verify foundations | certified base plate and anchor bolt pattern
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | MECH-T220 Prepare equipment lifting data | certified weights and centre of gravity
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | MECH-T440 Issue as-built equipment data for handover | final certified data
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | PROC-T130 Set design pressures and temperatures | certified shut-off pressure from certified performance data
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | VEND-T110 Procure raw materials and issue MTRs | certified bill of materials
Document Locator | Excel / Word | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | VEND-T120 Fabricate and test the equipment | certified drawings for fabrication
Document Locator | Excel / Word | VEND-I240 | MDR / data book | VEND-T180 Compile the MDR / data book | OWNR-T220 Load asset register and CMMS | data books
Document Locator | Excel / Word | VEND-I250 | IOM manuals | VEND-T190 Prepare IOM manuals and spare parts lists | COMM-T080 Write pre-commissioning procedures | IOM pre-commissioning instructions
Document Locator | Excel / Word | VEND-I250 | IOM manuals | VEND-T190 Prepare IOM manuals and spare parts lists | OWNR-T190 Write operating procedures and train operators | package operating instructions
Document Locator | Excel / Word | VEND-I250 | IOM manuals | VEND-T190 Prepare IOM manuals and spare parts lists | OWNR-T220 Load asset register and CMMS | IOM manuals
Document Locator | Excel / Word | VEND-I322 | Licensor process design package | VEND-T090 Incorporate comments and issue certified final data | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | Licensor/chemical vendor dosing rates and catalyst volumes
Document Locator | Flare / relief tool | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | PROC-T250 Calculate relief loads and size relief valves | certified exchanger design pressures, pump/compressor shut-off data
Document Locator | HTRI | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | MECH-T080 Perform air-cooled exchanger thermal design | summer and winter design dry-bulb temperature, elevation
Document Locator | HYSYS | MECH-I500 | Shop test witness reports and release notes | MECH-T360 Witness shop tests and factory acceptance tests | PROC-T315 Reconcile simulation with certified vendor data | shop test performance results vs guarantees
Document Locator | HYSYS | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | PROC-T315 Reconcile simulation with certified vendor data | certified pump performance curves and NPSHr; certified exchanger rating sheets and fired heater performance; certified compressor performance maps and settle-out data
Document Locator | HYSYS | VEND-I322 | Licensor process design package | VEND-T090 Incorporate comments and issue certified final data | PROC-T100 Build and calibrate rigorous simulation | Licensor process design package: H&MB and operating conditions
Document Locator | Mechanical calc tool | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | MECH-T100 Perform vessel and column mechanical design calculations | basic wind speed and exposure, seismic parameters
Document Locator | Mechanical calc tool | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | MECH-T120 Design storage tanks | wind and seismic parameters
Document Locator | Mechanical calc tool | CIVL-I030 | Site environmental design data | CIVL-T020 Prepare civil and structural design basis | VEND-T060 Prepare vendor design calculations | wind speed, exposure and seismic parameters
Document Locator | Mechanical calc tool | CIVL-I060 | Foundation design parameters | CIVL-T050 Set foundation design parameters from the geotechnical report | MECH-T120 Design storage tanks | allowable bearing pressure, predicted settlement
Document Locator | Mechanical calc tool | MECH-I390 | Requisition for purchase (conformed technical package) | MECH-T280 Prepare requisitions for purchase | VEND-T060 Prepare vendor design calculations | design P/T, code and nozzle schedule
Document Locator | P6 | CIVL-I205 | Test pile programme | CIVL-T180 Design piles and prepare piling layout | CONS-T110 Develop construction schedule by CWP | test pile scope, locations and durations for the construction schedule
Document Locator | P6 | PROJ-I060 | Deliverables register | PROJ-T050 Compile and maintain the deliverables register | CONS-T070 Define CWPs, boundaries and sequence | deliverables by discipline and area to group into EWPs
Document Locator | P6 | PROJ-I060 | Deliverables register | PROJ-T050 Compile and maintain the deliverables register | CONS-T120 Align EWPs and procurement packages to CWPs | deliverables with EWP assignment and current status
Document Locator | P6 | PROJ-I060 | Deliverables register | PROJ-T050 Compile and maintain the deliverables register | PROJ-T110 Build and baseline the integrated schedule in P6 | document numbers, types and planned issue dates
Document Locator | Procore | CONS-I350 | Construction quality dossier | CONS-T280 Compile construction quality dossier | CIVL-T360 Answer RFIs and disposition field changes and NCRs | pile records and concrete test results in the quality dossier
Document Locator | Procore | PROJ-I280 | Transmittal | PROJ-T200 Issue documents by transmittal | CONS-T260 Prepare as-built redlines | IFC transmittals with documents and revisions
Document Locator | Procore | PROJ-I320 | IFC release and seal record | PROJ-T230 Track IFC issue and PE seal status | CONS-T170 Raise and manage RFIs | current IFC revision per document
Document Locator | Procore | PROJ-I320 | IFC release and seal record | PROJ-T230 Track IFC issue and PE seal status | CONS-T260 Prepare as-built redlines | IFC document list and revisions
Document Locator | Purchasing DB | CIVL-I050 | Geotechnical investigation scope and borehole plan | CIVL-T040 Specify the geotechnical investigation | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | geotechnical contractor scope
Document Locator | Purchasing DB | CIVL-I200 | Pile layout and schedule | CIVL-T180 Design piles and prepare piling layout | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | pile quantities and types
Document Locator | Purchasing DB | CIVL-I307 | HVAC datasheets and requisition scope | CIVL-T300 Design building HVAC | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | HVAC datasheets
Document Locator | Purchasing DB | CIVL-I307 | HVAC datasheets and requisition scope | CIVL-T300 Design building HVAC | SCM-T030 Register material requisitions in the Purchasing DB | HVAC requisition scope and datasheets
Document Locator | Purchasing DB | CIVL-I310 | Civil and structural requisitions and TBEs | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | SCM-T030 Register material requisitions in the Purchasing DB | civil and structural MRs and scopes
Document Locator | Purchasing DB | ELEC-I130 | MV switchgear requisition package | ELEC-T130 Specify MV switchgear | SCM-T030 Register material requisitions in the Purchasing DB | MV switchgear MR scope and datasheets
Document Locator | Purchasing DB | ELEC-I140 | Power transformer requisition package | ELEC-T140 Specify power transformers | SCM-T030 Register material requisitions in the Purchasing DB | power transformer MR scope and datasheets
Document Locator | Purchasing DB | ELEC-I150 | LV switchgear, MCC and E-house requisition package | ELEC-T150 Specify LV switchgear, MCCs and E-houses | SCM-T030 Register material requisitions in the Purchasing DB | LV switchgear/MCC/E-house MR scope
Document Locator | Purchasing DB | ELEC-I160 | VFD requisition package | ELEC-T160 Specify VFDs and harmonic mitigation | SCM-T030 Register material requisitions in the Purchasing DB | VFD MR scope
Document Locator | Purchasing DB | ELEC-I170 | UPS, DC and generator requisition package | ELEC-T170 Specify UPS, DC systems and emergency generator | SCM-T030 Register material requisitions in the Purchasing DB | UPS, DC and generator MR scope
Document Locator | Purchasing DB | MECH-I350 | Requisition technical package for bid | MECH-T250 Prepare requisition technical packages for bid | SCM-T030 Register material requisitions in the Purchasing DB | MR number, revision, scope, tags, datasheets, VDRL, inspection requirements
Document Locator | Purchasing DB | MECH-I390 | Requisition for purchase (conformed technical package) | MECH-T280 Prepare requisitions for purchase | SCM-T100 Award the purchase order in the Purchasing DB | conformed datasheets, scope, VDRL and remaining holds
Document Locator | Purchasing DB | MECH-I390 | Requisition for purchase (conformed technical package) | MECH-T280 Prepare requisitions for purchase | SCM-T110 Process PO amendments | revised conformed requisition scope and data
Document Locator | Purchasing DB | MECH-I390 | Requisition for purchase (conformed technical package) | MECH-T280 Prepare requisitions for purchase | SCM-T120 Set up VDRL tracking | VDRL document types, review/information and due weeks after PO
Document Locator | Purchasing DB | MECH-I400 | Vendor kick-off meeting minutes | MECH-T290 Hold vendor kick-off meetings | SCM-T120 Set up VDRL tracking | agreed VDRL dates from kick-off
Document Locator | Purchasing DB | OWNR-I060 | Owner standards and approved vendor list | OWNR-T040 Issue owner standards and specifications | SCM-T020 Prepare bidders lists and prequalify vendors | approved vendor list by commodity and excluded vendors
Document Locator | Purchasing DB | PROJ-I040 | Document numbering procedure and codes | PROJ-T040 Set up document numbering and the Document Locator project | SCM-T050 Issue RFQ packages | vendor document numbering and metadata rules
Document Locator | Purchasing DB | PROJ-I050 | Document Locator structure and distribution matrix | PROJ-T040 Set up document numbering and the Document Locator project | SCM-T050 Issue RFQ packages | Document Locator submission workflow
Document Locator | Purchasing DB | PROJ-I070 | Assigned document numbers | PROJ-T050 Compile and maintain the deliverables register | SCM-T120 Set up VDRL tracking | project document numbers for vendor documents
Document Locator | Purchasing DB | SCM-I070 | RFQ package | SCM-T050 Issue RFQ packages | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | commercial terms, instructions to bidders, VDRL
Document Locator | Purchasing DB | VEND-I060 | Vendor document schedule | VEND-T040 Issue the vendor document schedule | SCM-T120 Set up VDRL tracking | vendor document numbers and planned submission dates
Document Locator | S3D | CIVL-I040 | Topographic survey and plant grid | CIVL-T030 Specify and manage the topographic survey | PIPE-T370 Produce piping GA and key plan drawings | plant grid references
Document Locator | S3D | CIVL-I100 | Grading plan and finished grade elevations | CIVL-T100 Prepare grading plan and finished elevations | PIPE-T270 Design underground piping | finished grade elevations
Document Locator | S3D | CIVL-I110 | Drainage area plan and sewer layout | CIVL-T110 Design surface drainage and sewers | PIPE-T270 Design underground piping | sewer routes, inverts, catch basins and manholes
Document Locator | S3D | CIVL-I130 | Preliminary pipe rack and structure configuration | CIVL-T080 Size pipe racks and process structures conceptually | PIPE-T050 Build 3D layout model | rack widths, bent spacing, tier elevations and structure frame sizes
Document Locator | S3D | CIVL-I135 | Pipe rack design load allowances | CIVL-T080 Size pipe racks and process structures conceptually | PIPE-T060 Lay out pipe racks and assign tiers | uniform tier load and anchor/guide load limits assumed by civil
Document Locator | S3D | CIVL-I140 | Roads, access and fencing layout | CIVL-T130 Design roads, access and fencing | PIPE-T270 Design underground piping | road crossings
Document Locator | S3D | CIVL-I150 | Underground composite drawing | CIVL-T140 Coordinate underground services and prepare composite | PIPE-T270 Design underground piping | underground composite: crossings and depths
Document Locator | S3D | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | PIPE-T260 Request civil and structural openings, platforms and foundations | foundation locations and top of concrete
Document Locator | S3D | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | PIPE-T270 Design underground piping | foundation outlines and depths
Document Locator | S3D | MECH-I290 | Equipment outline drawings (preliminary GA) | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | PIPE-T040 Develop plot plan and equipment layout | overall dimensions, support type and location
Document Locator | S3D | MECH-I290 | Equipment outline drawings (preliminary GA) | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | PIPE-T050 Build 3D layout model | outline dimensions, skirt/saddle heights and nozzle positions
Document Locator | S3D | MECH-I290 | Equipment outline drawings (preliminary GA) | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | PIPE-T070 Study critical line routing | preliminary nozzle positions on heaters, pumps and exchangers
Document Locator | S3D | MECH-I420 | Certified equipment GA and nozzle data | MECH-T310 Release certified vendor data to other disciplines | PIPE-T160 Route piping in the 3D model | certified nozzle locations, sizes and ratings for final routing
Document Locator | S3D | OWNR-I060 | Owner standards and approved vendor list | OWNR-T040 Issue owner standards and specifications | PIPE-T250 Design pipe supports | owner standard pipe support catalogue and standards
Document Locator | S3D | PROJ-I040 | Document numbering procedure and codes | PROJ-T040 Set up document numbering and the Document Locator project | PIPE-T320 Extract and check isometrics | document numbering, revision and issue-purpose conventions
Document Locator | S3D | PROJ-I070 | Assigned document numbers | PROJ-T050 Compile and maintain the deliverables register | PIPE-T320 Extract and check isometrics | reserved isometric document numbers
Document Locator | SI | MECH-I450 | Vendor instrument lists and package I/O | MECH-T310 Release certified vendor data to other disciplines | INST-T260 Develop I/O list and assign I/O | package I/O list and serial link maps
Document Locator | SI | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | INST-T310 Design instrument wiring, marshalling and terminations | system cabinet arrangement, marshalling terminal numbering, barrier types
Document Locator | SPEL | MECH-I440 | Certified vendor electrical data | MECH-T310 Release certified vendor data to other disciplines | ELEC-T200 Review motor and package electrical data | certified motor datasheets: kW, FLA, LRC, PF, efficiency, inertia, speed-torque, accessories
Document Locator | SPID | MECH-I250 | Mechanical P&ID markups | MECH-T180 Provide mechanical input to P&IDs and HAZOP | PROC-T340 Update P&IDs to IFD and IFC | mechanical P&ID markups (seal plans, vents, drains)
Document Locator | SPID | VEND-I140 | Certified vendor drawings and data | VEND-T090 Incorporate comments and issue certified final data | PROC-T340 Update P&IDs to IFD and IFC | certified package P&IDs and nozzle data
Document Locator | Smart Completions | COMM-I250 | System turnover package | COMM-T220 Compile system turnover packages | COMM-T230 Hand over systems to the owner | complete turnover package
Document Locator | Smart Completions | CONS-I350 | Construction quality dossier | CONS-T280 Compile construction quality dossier | COMM-T150 Accept subsystem turnover from construction | quality dossier per subsystem
Document Locator | Smart Completions | PROJ-I320 | IFC release and seal record | PROJ-T230 Track IFC issue and PE seal status | COMM-T070 Load tags and assign ITRs in Smart Completions | IFC re-issues triggering engineering list deltas
Document Locator | Smart Completions | VEND-I250 | IOM manuals | VEND-T190 Prepare IOM manuals and spare parts lists | MECH-T430 Provide mechanical completion and pre-commissioning input | installation and run-in instructions
Document Locator | Tekla | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | CIVL-T220 Model structures in Tekla and share reference models | foundation geometry for concrete modelling
Document Locator | Tekla | CIVL-I210 | Pipe rack design calculations and reactions | CIVL-T200 Analyse and design pipe racks | CIVL-T220 Model structures in Tekla and share reference models | rack member sizes and geometry
Document Locator | Tekla | CIVL-I210 | Pipe rack design calculations and reactions | CIVL-T200 Analyse and design pipe racks | CIVL-T230 Prepare steel GA drawings and connection design data | rack connection forces
Document Locator | Tekla | CIVL-I220 | Process structure design calculations and reactions | CIVL-T210 Analyse and design process structures and platforms | CIVL-T220 Model structures in Tekla and share reference models | structure member sizes and geometry
Document Locator | Tekla | CIVL-I220 | Process structure design calculations and reactions | CIVL-T210 Analyse and design process structures and platforms | CIVL-T230 Prepare steel GA drawings and connection design data | structure connection forces
Document Locator | iConstruct | CIVL-I190 | Foundation plans and details | CIVL-T190 Prepare foundation plans and anchor bolt layouts | CONS-T140 Develop installation work packages (IWPs) | IFC foundation drawings
Document Locator | iConstruct | CIVL-I240 | Steel GA and erection drawings | CIVL-T230 Prepare steel GA drawings and connection design data | CONS-T140 Develop installation work packages (IWPs) | IFC steel erection drawings
Document Locator | iConstruct | PIPE-I480 | Tie-in packages | PIPE-T380 Identify tie-ins and issue tie-in packages | CONS-T140 Develop installation work packages (IWPs) | tie-in sketches, isolation and method
Document Locator | iConstruct | PROJ-I320 | IFC release and seal record | PROJ-T230 Track IFC issue and PE seal status | CONS-T140 Develop installation work packages (IWPs) | current IFC revision and release date per document
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T130 Specify MV switchgear | short-circuit interrupting and withstand duties at the bus
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T140 Specify power transformers | short-circuit interrupting and withstand duties at the bus
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T150 Specify LV switchgear, MCCs and E-houses | short-circuit interrupting and withstand duties at the bus
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T160 Specify VFDs and harmonic mitigation | short-circuit interrupting and withstand duties at the bus
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T170 Specify UPS, DC systems and emergency generator | short-circuit interrupting and withstand duties at the bus
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T270 Design grounding system | SLG fault current and clearing times
ETAP | Excel / Word | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | VEND-T080 Prepare package electrical data | fault level at the supply bus
ETAP | Excel / Word | ELEC-I230 | Motor-starting study results | ELEC-T230 Run motor-starting study | MECH-T150 Prepare rotating equipment datasheets | starting method and voltage dip limits for driver selection
ETAP | Excel / Word | ELEC-I240 | Harmonic study results and filter requirements | ELEC-T240 Run harmonic analysis | VEND-T080 Prepare package electrical data | harmonic limits and filter requirements for package VFDs
ETAP | SPEL | ELEC-I220 | Short-circuit study results | ELEC-T220 Run short-circuit study | ELEC-T320 Size cables and build cable schedule in SPEL | short-circuit duties and clearing times for withstand check
ETAP | SPEL | ELEC-I252 | Relay and breaker setting files | ELEC-T250 Perform protective relay coordination study | ELEC-T440 Produce as-built electrical records | as-left relay settings recorded against setting files
ETAP | Smart Completions | ELEC-I252 | Relay and breaker setting files | ELEC-T250 Perform protective relay coordination study | COMM-T190 Energise electrical systems | relay and trip unit settings
Excel / Word | CAESAR II | MECH-I280 | Allowable nozzle loads | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | PIPE-T210 Perform screening stress analysis | preliminary allowable forces and moments per nozzle
Excel / Word | CAESAR II | MECH-I280 | Allowable nozzle loads | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | PIPE-T220 Perform detailed stress analysis in CAESAR II | allowable nozzle forces and moments
Excel / Word | CAESAR II | MECH-I480 | Rotordynamic and pulsation study acceptance | MECH-T340 Review rotordynamic, torsional and pulsation studies | PIPE-T220 Perform detailed stress analysis in CAESAR II | pulsation study results (orifices, dampeners, support spacing) for stress
Excel / Word | CAESAR II | MECH-I600 | Equipment thermal growth and nozzle flexibility | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | PIPE-T220 Perform detailed stress analysis in CAESAR II | Equipment thermal growth and nozzle displacements (columns, heaters, exchangers) and nozzle flexibility data for CAESAR II
Excel / Word | CAESAR II | PIPE-I220 | Stress-critical line list | PIPE-T200 Prepare stress-critical line list | PIPE-T210 Perform screening stress analysis | lines and load cases to screen
Excel / Word | CAESAR II | PIPE-I220 | Stress-critical line list | PIPE-T200 Prepare stress-critical line list | PIPE-T220 Perform detailed stress analysis in CAESAR II | stress category, load cases and temperatures
Excel / Word | CAESAR II | PROC-I111 | Design and operating case list | PROC-T110 Prepare heat and material balance | PIPE-T220 Perform detailed stress analysis in CAESAR II | operating cases for load case definition
Excel / Word | CAESAR II | PROC-I130 | Design pressure and temperature basis | PROC-T130 Set design pressures and temperatures | PIPE-T220 Perform detailed stress analysis in CAESAR II | design and upset temperatures and pressures
Excel / Word | CAESAR II | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PIPE-T220 Perform detailed stress analysis in CAESAR II | two-phase flow regime and slug flags
Excel / Word | DCS / SIS config | INST-I170 | Control narratives and functional logic | INST-T170 Write control narratives and functional design specifications | VEND-T200 Configure and test the DCS/SIS | control narratives and functional logic
Excel / Word | DCS / SIS config | INST-I220 | Safety requirements specification | INST-T220 Write safety requirements specification | COMM-T180 Execute C&E and SIF function tests | SIF safe state, response time, trip set points
Excel / Word | DCS / SIS config | INST-I220 | Safety requirements specification | INST-T220 Write safety requirements specification | VEND-T200 Configure and test the DCS/SIS | SRS per SIF
Excel / Word | DCS / SIS config | INST-I240 | Process shutdown cause and effect | INST-T240 Prepare cause and effect charts | COMM-T180 Execute C&E and SIF function tests | C&E causes, set points and effects
Excel / Word | DCS / SIS config | INST-I240 | Process shutdown cause and effect | INST-T240 Prepare cause and effect charts | VEND-T200 Configure and test the DCS/SIS | process shutdown C&E
Excel / Word | DCS / SIS config | INST-I241 | F&G cause and effect | INST-T240 Prepare cause and effect charts | COMM-T180 Execute C&E and SIF function tests | F&G C&E
Excel / Word | DCS / SIS config | INST-I241 | F&G cause and effect | INST-T240 Prepare cause and effect charts | VEND-T200 Configure and test the DCS/SIS | F&G C&E
Excel / Word | DCS / SIS config | PROC-I235 | Trip and interlock schedule | PROC-T235 Define trips, interlocks and process input to SIF | VEND-T200 Configure and test the DCS/SIS | trip initiators, set points and actions
Excel / Word | DCS / SIS config | PROC-I240 | Operating philosophy | PROC-T230 Prepare control and operating philosophy and control narratives | VEND-T200 Configure and test the DCS/SIS | operating modes and philosophy
Excel / Word | Document Locator | CIVL-I340 | Civil and structural CWP scope and sequence | CIVL-T340 Provide civil inputs to construction packaging | PROJ-T050 Compile and maintain the deliverables register | deliverables per civil/steel CWP and their release dates
Excel / Word | Document Locator | CIVL-I901 | Civil deliverables list | CIVL-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | civil deliverables with planned dates
Excel / Word | Document Locator | CONS-I280 | Weld log and NDE register | CONS-T220 Track welds and NDE | CONS-T280 Compile construction quality dossier | weld and NDE records
Excel / Word | Document Locator | CONS-I300 | Pressure test and reinstatement record | CONS-T230 Prepare and execute pressure test packs | CONS-T280 Compile construction quality dossier | test records
Excel / Word | Document Locator | ELEC-I901 | Electrical deliverables list | ELEC-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | Electrical deliverables list: SLDs, studies, cable schedule, layouts with planned dates
Excel / Word | Document Locator | INST-I901 | Instrumentation deliverables list | INST-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | Instrumentation deliverables list: index, datasheets, loops, C&E, layouts with planned dates
Excel / Word | Document Locator | MECH-I901 | Mechanical deliverables list | MECH-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | Mechanical deliverables list: datasheets, calculations and requisitions per equipment item with planned dates
Excel / Word | Document Locator | OWNR-I180 | Spares philosophy | OWNR-T160 Define spare parts philosophy and approve spares | VEND-T190 Prepare IOM manuals and spare parts lists | spares policy and interchangeability targets
Excel / Word | Document Locator | OWNR-I200 | CMMS asset data requirements | OWNR-T170 Define CMMS asset data requirements | PROJ-T040 Set up document numbering and the Document Locator project | required document metadata and document link rules per asset class for handover
Excel / Word | Document Locator | OWNR-I200 | CMMS asset data requirements | OWNR-T170 Define CMMS asset data requirements | VEND-T190 Prepare IOM manuals and spare parts lists | CMMS asset classes and required attributes
Excel / Word | Document Locator | PIPE-I901 | Piping deliverables list | PIPE-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | Piping deliverables list: drawing types and isometric counts by area with planned dates
Excel / Word | Document Locator | PROC-I901 | Process deliverables list | PROC-T005 Plan, measure and report discipline deliverables | PROJ-T050 Compile and maintain the deliverables register | Process deliverables list: titles, document types, sheet counts, planned IFR/IFD/IFC dates
Excel / Word | Document Locator | PROJ-I310 | Hold list | PROJ-T220 Maintain the hold list | PROJ-T230 Track IFC issue and PE seal status | holds cleared per document
Excel / Word | Document Locator | SAFE-I040 | SHE design basis | SAFE-T040 Prepare SHE design basis and risk criteria | PROJ-T050 Compile and maintain the deliverables register | study schedule in the SHE design basis: list of safety studies and planned workshop/report dates
Excel / Word | Document Locator | SAFE-I100 | Building blast loads | SAFE-T100 Perform facility siting study (API RP 752/753) | SAFE-T290 Compile process safety information for PSM | siting results
Excel / Word | Document Locator | SAFE-I120 | QRA results | SAFE-T120 Perform quantitative risk assessment | SAFE-T290 Compile process safety information for PSM | QRA
Excel / Word | Document Locator | VEND-I020 | Technical quotation | VEND-T020 Prepare firm technical and commercial quotations | SCM-T070 Receive bids and distribute technical portions | technical offer to forward unpriced for TBE
Excel / Word | Document Locator | VEND-I030 | Commercial quotation | VEND-T020 Prepare firm technical and commercial quotations | SCM-T070 Receive bids and distribute technical portions | priced offer held for commercial evaluation
Excel / Word | Document Locator | VEND-I040 | Deviations and exceptions list | VEND-T020 Prepare firm technical and commercial quotations | SCM-T070 Receive bids and distribute technical portions | technical exceptions to forward for TBE
Excel / Word | Document Locator | VEND-I170 | Material test reports | VEND-T110 Procure raw materials and issue MTRs | VEND-T180 Compile the MDR / data book | MTRs
Excel / Word | Document Locator | VEND-I180 | Test certificates | VEND-T120 Fabricate and test the equipment | VEND-T180 Compile the MDR / data book | test certificates
Excel / Word | Document Locator | VEND-I230 | Nameplate and as-built data | VEND-T170 Prepare nameplate and as-built data | VEND-T180 Compile the MDR / data book | nameplate data
Excel / Word | Document Locator | VEND-I270 | Site service reports | VEND-T210 Provide site services | CONS-T280 Compile construction quality dossier | vendor site installation and inspection reports
Excel / Word | Document Locator | VEND-I300 | Weld maps and NDE records | VEND-T120 Fabricate and test the equipment | VEND-T180 Compile the MDR / data book | weld maps and NDE records
Excel / Word | ETAP | ELEC-I030 | Utility interconnect requirements | ELEC-T030 Coordinate utility interconnect and power supply | ELEC-T210 Build ETAP model and run load flow study | utility fault MVA, X/R and voltage range
Excel / Word | ETAP | ELEC-I030 | Utility interconnect requirements | ELEC-T030 Coordinate utility interconnect and power supply | ELEC-T250 Perform protective relay coordination study | utility protection settings at interconnect
Excel / Word | ETAP | ELEC-I110 | Electrical equipment ratings | ELEC-T110 Size major electrical equipment | ELEC-T210 Build ETAP model and run load flow study | equipment ratings
Excel / Word | ETAP | MECH-I210 | Compressor and blower datasheets (API 617/618/672/673) | MECH-T150 Prepare rotating equipment datasheets | ELEC-T230 Run motor-starting study | compressor start conditions (unloaded/loaded, valve position)
Excel / Word | Flare / relief tool | FIRE-I200 | Fire zones and fireproofing envelopes | FIRE-T200 Define fire scenario envelopes and fireproofing zones | PROC-T250 Calculate relief loads and size relief valves | fire zone boundaries for fire-case grouping
Excel / Word | Flare / relief tool | MECH-I170 | Vessel and column mechanical datasheets | MECH-T130 Prepare mechanical datasheets for vessels and columns | PROC-T250 Calculate relief loads and size relief valves | vessel dimensions, liquid levels and insulation for wetted area
Excel / Word | Flare / relief tool | MECH-I170 | Vessel and column mechanical datasheets | MECH-T130 Prepare mechanical datasheets for vessels and columns | PROC-T260 Run flare and blowdown hydraulics | vessel volumes, materials and thickness
Excel / Word | Flare / relief tool | PIPE-I210 | As-routed line hydraulic data | PIPE-T190 Issue as-routed line data for hydraulic checks | PROC-T250 Calculate relief loads and size relief valves | PSV inlet/outlet routing and tailpipe lengths
Excel / Word | HTRI | MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | MECH-T030 Select equipment materials and corrosion allowances with Process | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | tube and shell materials and corrosion allowance
Excel / Word | HTRI | PROC-I175 | Shell-and-tube and plate exchanger process datasheets | PROC-T175 Prepare heat transfer equipment process datasheets | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | duty, fluid allocation, flows, in/out T, properties, fouling, allowable dP, design P/T
Excel / Word | HTRI | PROC-I176 | Air cooler process datasheets | PROC-T175 Prepare heat transfer equipment process datasheets | MECH-T080 Perform air-cooled exchanger thermal design | duty, flows, properties, design air temperature, fan control, winterisation, allowable dP
Excel / Word | HTRI | SAFE-I240 | Equipment noise limits | SAFE-T240 Perform noise study | MECH-T080 Perform air-cooled exchanger thermal design | noise limit per air-cooler fan
Excel / Word | HYSYS | MECH-I140 | Column and vessel internals datasheets | MECH-T110 Specify column and vessel internals | PROC-T140 Size vessels and columns | tray/packing type, spacing, passes and vendor hydraulic rating results
Excel / Word | HYSYS | MECH-I140 | Column and vessel internals datasheets | MECH-T110 Specify column and vessel internals | PROC-T315 Reconcile simulation with certified vendor data | final tray/packing type and hydraulic ratings
Excel / Word | HYSYS | MECH-I590 | As-built equipment datasheets and equipment register | MECH-T440 Issue as-built equipment data for handover | PROC-T315 Reconcile simulation with certified vendor data | final certified design data per tag
Excel / Word | HYSYS | OWNR-I030 | Crude assays and feed cases | OWNR-T020 Supply crude assays and feed cases | PROC-T020 Characterise feed and set up assay in simulation | TBP/distillation curves, API, sulfur, metals, TAN per assay; design, check and turndown crude cases with rates
Excel / Word | HYSYS | OWNR-I050 | Existing facility and utility data | OWNR-T030 Supply site and existing facility data | PROC-T100 Build and calibrate rigorous simulation | existing unit operating data for calibration (brownfield)
Excel / Word | HYSYS | PROC-I010 | Process design basis | PROC-T010 Prepare process design basis | PROC-T020 Characterise feed and set up assay in simulation | feed slate and design cases
Excel / Word | HYSYS | PROC-I010 | Process design basis | PROC-T010 Prepare process design basis | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | capacity and product specifications
Excel / Word | HYSYS | PROC-I010 | Process design basis | PROC-T010 Prepare process design basis | PROC-T155 Estimate exchanger duties and preliminary areas | fouling factors and allowable pressure drops
Excel / Word | HYSYS | PROC-I130 | Design pressure and temperature basis | PROC-T130 Set design pressures and temperatures | PROC-T140 Size vessels and columns | design P/T
Excel / Word | HYSYS | VEND-I321 | Licensor process proposal | VEND-T020 Prepare firm technical and commercial quotations | PROC-T060 Develop and simulate FEL2 alternatives | Licensor/technology yield and performance data for proprietary sections (no licensor process data item in catalog)
Excel / Word | Jovix | CONS-I020 | Site logistics and laydown plan | CONS-T020 Prepare site logistics, laydown and temporary facilities plan | SCM-T220 Manage the warehouse, laydown and preservation | laydown and storage areas
Excel / Word | Jovix | MECH-I530 | Equipment preservation requirements | MECH-T390 Define equipment preservation and storage requirements | SCM-T220 Manage the warehouse, laydown and preservation | storage class, N2 blanket, shaft rotation intervals
Excel / Word | Jovix | PIPE-I420 | Piping MTO by ident | PIPE-T340 Produce MTO by ident and bulk requisitions | PIPE-T430 Reconcile piping material shortages and surplus | required quantities by ident
Excel / Word | Jovix | SCM-I250 | Shipping notice | SCM-T180 Manage shipping and traffic | SCM-T200 Receive materials at site in Jovix | shipping pieces and expected arrival
Excel / Word | Jovix | VEND-I170 | Material test reports | VEND-T110 Procure raw materials and issue MTRs | SCM-T200 Receive materials at site in Jovix | MTR reference per heat number
Excel / Word | Jovix | VEND-I220 | Packing list and shipping documents | VEND-T160 Pack, preserve and ship | SCM-T200 Receive materials at site in Jovix | item marks, tags and heat numbers per piece
Excel / Word | Jovix | VEND-I290 | Preservation and storage instructions | VEND-T160 Pack, preserve and ship | SCM-T220 Manage the warehouse, laydown and preservation | storage conditions and preservation frequencies
Excel / Word | Jovix | VEND-I325 | OS&D response | VEND-T160 Pack, preserve and ship | SCM-T210 Raise OS&D reports | Vendor response to OS&D: replacement, repair or credit proposal
Excel / Word | Mechanical calc tool | FIRE-I220 | Fixed fire protection system requirements | FIRE-T220 Specify fixed fire protection systems | MECH-T120 Design storage tanks | foam and cooling ring requirements for tanks
Excel / Word | Mechanical calc tool | MECH-I030 | Mechanical design basis | MECH-T020 Develop mechanical design basis | MECH-T100 Perform vessel and column mechanical design calculations | codes and design margins
Excel / Word | Mechanical calc tool | MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | MECH-T030 Select equipment materials and corrosion allowances with Process | MECH-T100 Perform vessel and column mechanical design calculations | materials and corrosion allowance per component
Excel / Word | Mechanical calc tool | MECH-I040 | Materials selection and corrosion allowances (Process and Mechanical) | MECH-T030 Select equipment materials and corrosion allowances with Process | VEND-T060 Prepare vendor design calculations | materials, corrosion allowance, PWHT, impact test
Excel / Word | Mechanical calc tool | MECH-I280 | Allowable nozzle loads | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | VEND-T060 Prepare vendor design calculations | allowable nozzle load basis
Excel / Word | Mechanical calc tool | PROC-I130 | Design pressure and temperature basis | PROC-T130 Set design pressures and temperatures | MECH-T100 Perform vessel and column mechanical design calculations | design P/T, MDMT, vacuum and steam-out conditions
Excel / Word | Mechanical calc tool | PROC-I170 | Vessel and column process datasheets | PROC-T170 Prepare static equipment process datasheets | MECH-T100 Perform vessel and column mechanical design calculations | ID, T/T, liquid levels, nozzle schedule, internals type, design/operating conditions
Excel / Word | Mechanical calc tool | PROC-I171 | Tank process datasheets | PROC-T170 Prepare static equipment process datasheets | MECH-T120 Design storage tanks | working/gross capacity, fill/draw rates, vapour pressure, blanketing, heating
Excel / Word | Mechanical calc tool | SAFE-I062 | Emission control requirements | SAFE-T060 Develop emissions inventory | MECH-T120 Design storage tanks | tank seal type and vapour control requirements
Excel / Word | P6 | CIVL-I070 | Civil and structural estimate quantities | CIVL-T060 Prepare civil and structural quantities for estimates | CONS-T070 Define CWPs, boundaries and sequence | concrete, steel and pile quantities by area
Excel / Word | P6 | CIVL-I340 | Civil and structural CWP scope and sequence | CIVL-T340 Provide civil inputs to construction packaging | CONS-T070 Define CWPs, boundaries and sequence | civil/steel CWP list, pour and erection sequence
Excel / Word | P6 | CIVL-I902 | Civil progress measurement | CIVL-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Civil progress: foundation and steel drawing completion counts
Excel / Word | P6 | COMM-I020 | Preliminary system list and start-up sequence | COMM-T020 Develop preliminary system list and start-up sequence | CONS-T050 Define path of construction | preliminary system list and start-up sequence with required ready-for-commissioning dates by system
Excel / Word | P6 | COMM-I020 | Preliminary system list and start-up sequence | COMM-T020 Develop preliminary system list and start-up sequence | PROJ-T110 Build and baseline the integrated schedule in P6 | system list and start-up order with RFC dates
Excel / Word | P6 | COMM-I040 | System and subsystem register | COMM-T030 Mark system and subsystem boundaries on P&IDs | COMM-T040 Set commissioning sequence and required subsystem turnover dates | systems and subsystems with priority
Excel / Word | P6 | CONS-I040 | Heavy lift and crane plan | CONS-T040 Prepare heavy lift and crane study | CONS-T050 Define path of construction | lift sequence, dates and crane positions that constrain area sequence
Excel / Word | P6 | ELEC-I050 | Electrical estimate quantities and pricing | ELEC-T050 Prepare electrical cost estimate inputs | CONS-T070 Define CWPs, boundaries and sequence | cable, tray and conduit quantities by area
Excel / Word | P6 | ELEC-I902 | Electrical progress measurement | ELEC-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Electrical progress: deliverable completion counts
Excel / Word | P6 | INST-I902 | Instrumentation progress measurement | INST-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Instrumentation progress: datasheet and loop diagram completion counts
Excel / Word | P6 | MECH-I902 | Mechanical progress measurement | MECH-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Mechanical progress: datasheets and requisitions percent complete
Excel / Word | P6 | OWNR-I284 | Owner cost structure and AFE codes | OWNR-T010 Define business case, capacity and product slate | PROJ-T030 Set up the WBS, cost codes and P6 project structure | Owner cost reporting structure, AFE/capital codes and code of accounts mapping
Excel / Word | P6 | PIPE-I902 | Piping progress measurement | PIPE-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Piping progress: model completion and isometrics issued vs planned by area
Excel / Word | P6 | PROC-I902 | Process progress measurement | PROC-T005 Plan, measure and report discipline deliverables | PROJ-T130 Measure engineering progress | Process progress per deliverable (percent complete by rules of credit)
Excel / Word | P6 | SCM-I010 | Procurement plan | SCM-T010 Prepare the procurement plan and long-lead list | PROJ-T110 Build and baseline the integrated schedule in P6 | RFQ, bid, award, vendor data and delivery durations and ROS per MR
Excel / Word | PHA tool | PROC-I235 | Trip and interlock schedule | PROC-T235 Define trips, interlocks and process input to SIF | INST-T210 Define SIFs and input to SIL determination | initiator tags, set points, voting preference, final elements, process safety time
Excel / Word | Procore | CONS-I240 | Foundation and setting-out survey record | CONS-T190 Survey, set out and verify foundations | CIVL-T360 Answer RFIs and disposition field changes and NCRs | as-built foundation elevations and anchor bolt deviations
Excel / Word | Procore | CONS-I240 | Foundation and setting-out survey record | CONS-T190 Survey, set out and verify foundations | CONS-T260 Prepare as-built redlines | as-built foundation elevations and anchor bolt positions
Excel / Word | Procore | PROC-I375 | Commissioning process punch and troubleshooting log | PROC-T375 Support commissioning, start-up and performance test | COMM-T210 Raise commissioning technical queries | commissioning troubleshooting and set point changes
Excel / Word | Purchasing DB | CIVL-I248 | Structural steel MTO | CIVL-T240 Prepare structural steel MTO | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | steel tonnage by profile and grade for fabrication requisition
Excel / Word | Purchasing DB | COMM-I110 | Commissioning spares and first-fill list | COMM-T100 Define commissioning spares, consumables and first fills | SCM-T270 Procure commissioning and operating spares | commissioning spares and first fill by system and need date
Excel / Word | Purchasing DB | COMM-I120 | Vendor commissioning support requirements | COMM-T110 Define vendor commissioning support requirements | SCM-T260 Call off vendor site services | vendor representative scope, man-days and call-off dates
Excel / Word | Purchasing DB | INST-I340 | Instrument bulk MTO | INST-T340 Prepare instrument bulk MTO | SCM-T030 Register material requisitions in the Purchasing DB | instrument bulk MR lines (tubing, fittings, cable, supports)
Excel / Word | Purchasing DB | MECH-I510 | Reviewed spare parts list | MECH-T370 Review spare parts recommendations | SCM-T270 Procure commissioning and operating spares | reviewed commissioning, operating and capital spares per tag
Excel / Word | Purchasing DB | MECH-I560 | Vendor site service schedule and reports | MECH-T420 Coordinate vendor site representatives | SCM-T260 Call off vendor site services | vendor site service dates to call off
Excel / Word | Purchasing DB | OWNR-I285 | Invoices paid and back-charges | OWNR-T240 Pay invoices and report actual cost | SCM-T280 Close out purchase orders | Final invoice and back-charge status per PO
Excel / Word | Purchasing DB | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | SCM-T040 Load piping bulk MTO into the Purchasing DB | class materials and component descriptions
Excel / Word | Purchasing DB | PROJ-I020 | Contracting and procurement strategy | PROJ-T020 Develop the contracting and procurement strategy | SCM-T050 Issue RFQ packages | approved commercial terms and delivery terms
Excel / Word | Purchasing DB | PROJ-I210 | Approved change notice | PROJ-T160 Run change control: trends and change notices | SCM-T110 Process PO amendments | approved change scope and affected POs
Excel / Word | Purchasing DB | SCM-I080 | Bid bulletin | SCM-T060 Manage bid clarifications and bid bulletins | CIVL-T310 Prepare civil and structural requisitions and bid evaluations | bid questions and answers issued
Excel / Word | Purchasing DB | SCM-I110 | Award recommendation | SCM-T090 Prepare the bid tabulation and award recommendation | SCM-T100 Award the purchase order in the Purchasing DB | approved vendor, price and delivery
Excel / Word | Purchasing DB | VEND-I160 | Manufacturing schedule | VEND-T100 Prepare the ITP and manufacturing schedule | SCM-T140 Expedite manufacturing and forecast deliveries | baseline milestone dates
Excel / Word | Purchasing DB | VEND-I200 | Spool fabrication status | VEND-T130 Fabricate pipe spools | SCM-T140 Expedite manufacturing and forecast deliveries | spool fabrication status for expediting
Excel / Word | Purchasing DB | VEND-I260 | Spare parts interchangeability records | VEND-T190 Prepare IOM manuals and spare parts lists | SCM-T270 Procure commissioning and operating spares | part numbers, recommended quantities, prices and lead times
Excel / Word | Purchasing DB | VEND-I310 | Manufacturing progress report | VEND-T150 Report manufacturing progress | SCM-T140 Expedite manufacturing and forecast deliveries | milestone actuals, percent complete and forecast ex-works date
Excel / Word | Purchasing DB | VEND-I324 | Change-order quotation | VEND-T020 Prepare firm technical and commercial quotations | SCM-T110 Process PO amendments | Vendor change-order quotation: price and delivery impact of post-award changes
Excel / Word | S3D | CIVL-I155 | Underground conflict list | CIVL-T140 Coordinate underground services and prepare composite | ELEC-T330 Route raceway, cable tray and duct banks in S3D | conflicts between duct banks and other underground services
Excel / Word | S3D | CIVL-I155 | Underground conflict list | CIVL-T140 Coordinate underground services and prepare composite | PIPE-T270 Design underground piping | conflicts between underground piping and other services
Excel / Word | S3D | CONS-I280 | Weld log and NDE register | CONS-T220 Track welds and NDE | PIPE-T440 Prepare as-built isometrics and model | final weld numbers and NDE/PWHT records
Excel / Word | S3D | ELEC-I060 | Hazardous area release source list | ELEC-T060 Prepare hazardous area release source list | ELEC-T070 Prepare hazardous area classification drawings | Class/Division, group, T-code and extent per source
Excel / Word | S3D | ELEC-I272 | Grounding layouts and details | ELEC-T270 Design grounding system | PIPE-T270 Design underground piping | ground grid routing
Excel / Word | S3D | FIRE-I192 | Fire water network, hydrant and monitor layout requirements | FIRE-T190 Calculate fire water demand | PIPE-T270 Design underground piping | ring main sizing basis, hydrant and monitor locations, isolation valve sectioning
Excel / Word | S3D | FIRE-I230 | Fire pump and fire protection equipment datasheets | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | PIPE-T160 Route piping in the 3D model | fire pump and skid nozzle connections for firewater piping
Excel / Word | S3D | INST-I115 | Instrument connection requirements on equipment and piping | INST-T115 Define instrument connections on equipment and lines | PIPE-T180 Position in-line instruments and instrument access | connection type, size, orientation and elevation
Excel / Word | S3D | MECH-I080 | Mechanical equipment list | MECH-T060 Maintain mechanical equipment list | PIPE-T040 Develop plot plan and equipment layout | equipment tag list with size and operating weight
Excel / Word | S3D | MECH-I170 | Vessel and column mechanical datasheets | MECH-T130 Prepare mechanical datasheets for vessels and columns | PIPE-T050 Build 3D layout model | preliminary nozzle schedule sizes and ratings
Excel / Word | S3D | MECH-I170 | Vessel and column mechanical datasheets | MECH-T130 Prepare mechanical datasheets for vessels and columns | PIPE-T070 Study critical line routing | nozzle schedule sizes, ratings and duties on columns and vessels
Excel / Word | S3D | MECH-I170 | Vessel and column mechanical datasheets | MECH-T130 Prepare mechanical datasheets for vessels and columns | PIPE-T160 Route piping in the 3D model | nozzle size, rating, facing and location
Excel / Word | S3D | MECH-I300 | Equipment footprints and maintenance envelopes | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | PIPE-T040 Develop plot plan and equipment layout | footprint, height, bundle pull, internals removal and crane access envelopes
Excel / Word | S3D | PIPE-I030 | Piping layout design basis | PIPE-T030 Write piping layout design basis | PIPE-T040 Develop plot plan and equipment layout | spacing tables, access and maintenance rules
Excel / Word | S3D | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | PIPE-T100 Build S3D piping specification catalogue | class rules, components by size, wall thickness, branch tables, valve codes
Excel / Word | S3D | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | PIPE-T150 Prepare FEL3 piping MTO for the estimate | class components and materials for pricing
Excel / Word | S3D | PIPE-I130 | Valve datasheets | PIPE-T110 Prepare valve specifications and datasheets | PIPE-T340 Produce MTO by ident and bulk requisitions | valve datasheets
Excel / Word | S3D | PIPE-I140 | Specialty piping item list and datasheets | PIPE-T120 Prepare specialty item list and datasheets | PIPE-T340 Produce MTO by ident and bulk requisitions | SP item list
Excel / Word | S3D | PIPE-I160 | Line list piping attributes | PIPE-T140 Add piping data to the line list | PIPE-T320 Extract and check isometrics | test pressure, NDE, PWHT, paint and insulation per line
Excel / Word | S3D | PIPE-I230 | Screening stress results and layout markups | PIPE-T210 Perform screening stress analysis | PIPE-T160 Route piping in the 3D model | screening stress markups (loops, supports, routing changes)
Excel / Word | S3D | PIPE-I260 | Support loads for civil and structural | PIPE-T220 Perform detailed stress analysis in CAESAR II | PIPE-T250 Design pipe supports | support loads for support selection
Excel / Word | S3D | PIPE-I270 | Stress markups to the model | PIPE-T220 Perform detailed stress analysis in CAESAR II | PIPE-T250 Design pipe supports | support type changes, guides, anchors and spring locations
Excel / Word | S3D | PIPE-I390 | Piping hold list | PIPE-T310 Incorporate vendor data and manage piping holds | PIPE-T320 Extract and check isometrics | released holds
Excel / Word | S3D | PROC-I095 | Process layout requirements | PROC-T095 Define process layout requirements | PIPE-T040 Develop plot plan and equipment layout | minimum elevations for NPSH, thermosiphon and gravity drain, close-coupling and adjacency
Excel / Word | S3D | PROC-I095 | Process layout requirements | PROC-T095 Define process layout requirements | PIPE-T070 Study critical line routing | slope, no-pocket, gravity, NPSH and symmetrical routing requirements
Excel / Word | S3D | PROC-I160 | Equipment process duties | PROC-T160 Prepare equipment list process data | PIPE-T040 Develop plot plan and equipment layout | equipment tag, type, size and operating/design P/T
Excel / Word | S3D | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PIPE-T060 Lay out pipe racks and assign tiers | line sizes for rack lines
Excel / Word | S3D | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PIPE-T070 Study critical line routing | critical-line flags, two-phase flow regime and line sizes
Excel / Word | S3D | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PIPE-T150 Prepare FEL3 piping MTO for the estimate | line sizes
Excel / Word | S3D | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PIPE-T190 Issue as-routed line data for hydraulic checks | critical lines requiring hydraulic verification (gravity, two-phase, pump suction)
Excel / Word | S3D | PROC-I251 | PSV process datasheets | PROC-T250 Calculate relief loads and size relief valves | PIPE-T190 Issue as-routed line data for hydraulic checks | PSV tags, inlet/outlet sizes and allowable back pressure for inlet loss and tailpipe checks
Excel / Word | S3D | PROC-I280 | Effluent and emissions data | PROC-T280 Prepare process input to environmental and safety studies | PIPE-T270 Design underground piping | effluent and drain flows and composition
Excel / Word | S3D | PROC-I320 | Process TQ responses and hold releases | PROC-T320 Respond to technical queries, holds and change requests | PIPE-T310 Incorporate vendor data and manage piping holds | P&ID hold answers and release dates
Excel / Word | S3D | PROJ-I080 | Estimate quantity request | PROJ-T070 Issue estimate quantity requests to disciplines | PIPE-T150 Prepare FEL3 piping MTO for the estimate | estimate class, basis, growth and allowance and code of accounts
Excel / Word | S3D | PROJ-I373 | Bulk surplus and allowance policy | PROJ-T020 Develop the contracting and procurement strategy | PIPE-T340 Produce MTO by ident and bulk requisitions | Bulk material surplus and allowance policy (percent by commodity and size)
Excel / Word | S3D | VEND-I020 | Technical quotation | VEND-T020 Prepare firm technical and commercial quotations | PIPE-T100 Build S3D piping specification catalogue | valve and component outline dimensions and weights from preferred vendor offers
Excel / Word | SI | ELEC-I072 | Equipment certification requirements by area | ELEC-T070 Prepare hazardous area classification drawings | INST-T110 Prepare instrument datasheets | Class/Division or Zone, gas group, T-code at instrument location
Excel / Word | SI | ELEC-I072 | Equipment certification requirements by area | ELEC-T070 Prepare hazardous area classification drawings | INST-T200 Specify fire and gas system and device list | Class/Division or Zone, gas group, T-code for detector Ex rating
Excel / Word | SI | ELEC-I304 | Heat tracing control and alarm interface to I&C | ELEC-T300 Design electric heat tracing | INST-T260 Develop I/O list and assign I/O | heat tracing panel alarms and signals to the DCS
Excel / Word | SI | FIRE-I230 | Fire pump and fire protection equipment datasheets | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | INST-T200 Specify fire and gas system and device list | fire pump controller and deluge skid signals to the F&G system
Excel / Word | SI | INST-I140 | Instrument technical bid evaluations | INST-T140 Evaluate instrument bids technically | INST-T145 Align final relief valve sizing with Process and vendor | technical evaluation of the relief valve offers
Excel / Word | SI | MECH-I080 | Mechanical equipment list | MECH-T060 Maintain mechanical equipment list | INST-T050 Build and maintain the instrument index in SI | equipment numbers and services for instruments on equipment
Excel / Word | SI | MECH-I220 | Package specifications and scope-of-supply split | MECH-T160 Prepare package specifications and scope split | INST-T050 Build and maintain the instrument index in SI | package scope of supply: which instruments are vendor supplied
Excel / Word | SI | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | INST-T060 Enter instrument process data | piping class per line; rating and materials of the class for instrument wetted parts and flange rating
Excel / Word | SI | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | INST-T090 Calculate flow elements and thermowells | line class and size; wall thickness/schedule by size for internal diameter
Excel / Word | SI | PIPE-I110 | Piping material class specification | PIPE-T090 Develop piping material classes | INST-T110 Prepare instrument datasheets | wetted part material, flange rating and facing per class
Excel / Word | SI | PIPE-I160 | Line list piping attributes | PIPE-T140 Add piping data to the line list | INST-T060 Enter instrument process data | piping class per line; rating and materials of the class for instrument wetted parts and flange rating
Excel / Word | SI | PIPE-I160 | Line list piping attributes | PIPE-T140 Add piping data to the line list | INST-T070 Size control valves | line size and piping class at the valve; reducer arrangement as routed
Excel / Word | SI | PIPE-I160 | Line list piping attributes | PIPE-T140 Add piping data to the line list | INST-T090 Calculate flow elements and thermowells | line class and size; wall thickness/schedule by size for internal diameter
Excel / Word | SI | PIPE-I160 | Line list piping attributes | PIPE-T140 Add piping data to the line list | INST-T100 Specify relief valves from the process sizing | inlet/outlet line class and rating
Excel / Word | SI | PROC-I220 | Instrument process data | PROC-T220 Prepare instrument process data | INST-T060 Enter instrument process data | per tag: min/normal/max flow, ranges, level ranges, set points, alarm/trip settings, CV allowable dP
Excel / Word | SI | PROC-I220 | Instrument process data | PROC-T220 Prepare instrument process data | INST-T070 Size control valves | CV allowable dP, shut-off dP and flow cases
Excel / Word | SI | PROC-I235 | Trip and interlock schedule | PROC-T235 Define trips, interlocks and process input to SIF | INST-T080 Size on/off and emergency shutdown valves and actuators | final element action, fail position, required closure time; blowdown restriction orifice size and depressuring time targets
Excel / Word | SI | PROC-I251 | PSV process datasheets | PROC-T250 Calculate relief loads and size relief valves | INST-T100 Specify relief valves from the process sizing | governing case, relieving rate, set and back pressure, fluid MW/T/Z/k, required area and orifice letter (copied by hand)
Excel / Word | SI | SAFE-I180 | F&G detector layout and coverage | SAFE-T180 Perform fire and gas detector mapping | INST-T200 Specify fire and gas system and device list | detector tag, type, coordinates, elevation, orientation, coverage per zone
Excel / Word | SI | VEND-I020 | Technical quotation | VEND-T020 Prepare firm technical and commercial quotations | INST-T145 Align final relief valve sizing with Process and vendor | vendor final sizing: orifice, model, rating, inlet/outlet sizes
Excel / Word | SPEL | CIVL-I305 | HVAC electrical loads | CIVL-T300 Design building HVAC | ELEC-T090 Develop electrical load list in SPEL | HVAC consumer tag, kW, voltage, duty/standby, essential/UPS need
Excel / Word | SPEL | ELEC-I030 | Utility interconnect requirements | ELEC-T030 Coordinate utility interconnect and power supply | ELEC-T120 Develop one-line diagrams in SPEL | point of interconnection, metering and utility protection requirements
Excel / Word | SPEL | ELEC-I110 | Electrical equipment ratings | ELEC-T110 Size major electrical equipment | ELEC-T120 Develop one-line diagrams in SPEL | transformer, switchgear, MCC, generator and UPS ratings
Excel / Word | SPEL | FIRE-I230 | Fire pump and fire protection equipment datasheets | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | ELEC-T090 Develop electrical load list in SPEL | fire pump motor rating and supply requirements
Excel / Word | SPEL | INST-I161 | Analyzer shelter utility and space requirements | INST-T160 Specify analyzers and analyzer shelters | ELEC-T090 Develop electrical load list in SPEL | analyzer shelter power and UPS
Excel / Word | SPEL | INST-I280 | Instrument power and UPS load list | INST-T280 Compile instrument utility loads | ELEC-T090 Develop electrical load list in SPEL | DCS/SIS/F&G cabinet and instrument power kW/kVA, UPS vs normal
Excel / Word | SPEL | INST-I350 | Telecom system design | INST-T350 Design telecom, CCTV and security systems | ELEC-T090 Develop electrical load list in SPEL | telecom and CCTV power loads
Excel / Word | SPEL | INST-I351 | Telecom device list, locations and power | INST-T350 Design telecom, CCTV and security systems | ELEC-T090 Develop electrical load list in SPEL | telecom device power and UPS load
Excel / Word | SPEL | MECH-I080 | Mechanical equipment list | MECH-T060 Maintain mechanical equipment list | ELEC-T090 Develop electrical load list in SPEL | tags, service, driver power, vendor/PO status
Excel / Word | SPEL | MECH-I330 | Motor and driver electrical data | MECH-T230 Issue motor and driver electrical data | ELEC-T090 Develop electrical load list in SPEL | absorbed and rated motor power, voltage, speed, starting method, VFD, duty, space heater
Excel / Word | SPEL | MECH-I330 | Motor and driver electrical data | MECH-T230 Issue motor and driver electrical data | ELEC-T200 Review motor and package electrical data | motor rating, voltage, starting method and limitations per tag
Excel / Word | SPEL | PROC-I240 | Operating philosophy | PROC-T230 Prepare control and operating philosophy and control narratives | ELEC-T090 Develop electrical load list in SPEL | operating modes and simultaneous operation for demand factors
Excel / Word | SPEL | VEND-I120 | Package electrical data | VEND-T080 Prepare package electrical data | ELEC-T090 Develop electrical load list in SPEL | package motor ratings, electrical loads and panel requirements
Excel / Word | SPID | COMM-I020 | Preliminary system list and start-up sequence | COMM-T020 Develop preliminary system list and start-up sequence | COMM-T030 Mark system and subsystem boundaries on P&IDs | system list
Excel / Word | SPID | MECH-I220 | Package specifications and scope-of-supply split | MECH-T160 Prepare package specifications and scope split | MECH-T180 Provide mechanical input to P&IDs and HAZOP | package battery limits and scope
Excel / Word | SPID | MECH-I240 | Seal plans and auxiliary system requirements | MECH-T170 Select seal, flush and lube oil systems | MECH-T180 Provide mechanical input to P&IDs and HAZOP | seal plans and auxiliary system scope to show on P&IDs
Excel / Word | SPID | PIPE-I470 | Tie-in list | PIPE-T380 Identify tie-ins and issue tie-in packages | PROC-T210 Prepare line list and tie-in process data | tie-in numbers, existing/new line numbers, size, class, type
Excel / Word | SPID | PROC-I120 | Process flow diagrams | PROC-T120 Prepare process flow diagrams | PROC-T200 Develop P&IDs (process content) | equipment, main lines and loops
Excel / Word | SPID | PROC-I130 | Design pressure and temperature basis | PROC-T130 Set design pressures and temperatures | PROC-T210 Prepare line list and tie-in process data | design P/T
Excel / Word | SPID | PROC-I160 | Equipment process duties | PROC-T160 Prepare equipment list process data | PROC-T200 Develop P&IDs (process content) | equipment tags and duties
Excel / Word | SPID | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PROC-T200 Develop P&IDs (process content) | line sizes
Excel / Word | SPID | PROC-I190 | Line sizing results | PROC-T190 Size lines and run hydraulics | PROC-T210 Prepare line list and tie-in process data | line size and critical-line flags
Excel / Word | SPID | PROC-I230 | Control philosophy | PROC-T230 Prepare control and operating philosophy and control narratives | PROC-T200 Develop P&IDs (process content) | control loops
Excel / Word | SPID | PROC-I235 | Trip and interlock schedule | PROC-T235 Define trips, interlocks and process input to SIF | PROC-T200 Develop P&IDs (process content) | trips and interlocks
Excel / Word | Smart Completions | COMM-I040 | System and subsystem register | COMM-T030 Mark system and subsystem boundaries on P&IDs | MECH-T430 Provide mechanical completion and pre-commissioning input | system and subsystem boundaries
Excel / Word | Smart Completions | CONS-I290 | Pressure test pack | CONS-T230 Prepare and execute pressure test packs | COMM-T130 Track test pack status by subsystem | test packs and lines included
Excel / Word | Smart Completions | CONS-I300 | Pressure test and reinstatement record | CONS-T230 Prepare and execute pressure test packs | COMM-T130 Track test pack status by subsystem | tested/reinstated status
Excel / Word | Smart Completions | CONS-I300 | Pressure test and reinstatement record | CONS-T230 Prepare and execute pressure test packs | CONS-T270 Walk down and certify mechanical completion by subsystem | test packs tested and reinstated
Excel / Word | Smart Completions | ELEC-I400 | Electrical FAT reports and punch | ELEC-T400 Witness factory acceptance tests | COMM-T140 Raise and manage punch lists | open electrical FAT punch items carried to site
Excel / Word | Smart Completions | INST-I410 | Instrument tag register for completions | INST-T410 Prepare instrument tag register for completions | COMM-T050 Define ITR library and ITR matrix by tag type | instrument, cable, JB and loop tag types and ITR form types
Excel / Word | Smart Completions | MECH-I570 | Mechanical equipment ITR and check requirements | MECH-T430 Provide mechanical completion and pre-commissioning input | COMM-T050 Define ITR library and ITR matrix by tag type | per equipment type: installation, box-up, flush and run-in test criteria
Excel / Word | Smart Completions | OWNR-I210 | Permit to work and isolation authorisation | OWNR-T180 Issue permits to work and isolations | COMM-T190 Energise electrical systems | permit to energise
Excel / Word | Smart Completions | VEND-I270 | Site service reports | VEND-T210 Provide site services | COMM-T160 Execute pre-commissioning (B-ITRs) | vendor site service reports and sign-offs
Excel / Word | Tekla | CIVL-I340 | Civil and structural CWP scope and sequence | CIVL-T340 Provide civil inputs to construction packaging | VEND-T140 Detail and fabricate structural steel | steel erection sequence and release dates
Excel / Word | Tekla | CONS-I240 | Foundation and setting-out survey record | CONS-T190 Survey, set out and verify foundations | CIVL-T380 Incorporate as-built civil and structural changes | as-built foundation elevations and anchor bolt positions
Excel / Word | Tekla | PIPE-I310 | Secondary steel and support steel requests | PIPE-T250 Design pipe supports | CIVL-T220 Model structures in Tekla and share reference models | secondary steel, stub columns, dummy legs and attachment points with loads
Excel / Word | iConstruct | COMM-I040 | System and subsystem register | COMM-T030 Mark system and subsystem boundaries on P&IDs | CONS-T160 Manage IWP constraints and release IWPs | subsystem priority
Excel / Word | iConstruct | ELEC-I360 | Electrical layouts and power plans | ELEC-T360 Prepare electrical layouts and installation details | CONS-T140 Develop installation work packages (IWPs) | power plans and tray/conduit drops
Excel / Word | iConstruct | INST-I300 | Hook-up drawings and tag assignments | INST-T300 Prepare hook-up drawings and assign typicals | CONS-T140 Develop installation work packages (IWPs) | hook-ups and tag assignments
Excel / Word | iConstruct | OWNR-I120 | Operations and maintenance requirements | OWNR-T100 Provide operations and maintenance input | OWNR-T120 Review the 3D model for operability and maintenance | O&M requirements as review checklist
Excel / Word | iConstruct | OWNR-I210 | Permit to work and isolation authorisation | OWNR-T180 Issue permits to work and isolations | CONS-T160 Manage IWP constraints and release IWPs | permits to work and isolations for brownfield IWPs
Excel / Word | iConstruct | PIPE-I390 | Piping hold list | PIPE-T310 Incorporate vendor data and manage piping holds | CONS-T160 Manage IWP constraints and release IWPs | holds per line/iso with reason and release date
Excel / Word | iConstruct | PIPE-I410 | Spool list and fabrication package | PIPE-T330 Prepare spool lists and fabrication packages | CONS-T140 Develop installation work packages (IWPs) | spool IDs and spool BOMs
Excel / Word | iConstruct | VEND-I200 | Spool fabrication status | VEND-T130 Fabricate pipe spools | CONS-T150 Check IWP material availability against Jovix | spool fabrication status for IWP material checks
Flare / relief tool | CAESAR II | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | PIPE-T220 Perform detailed stress analysis in CAESAR II | relief load, set pressure and fluid for PSV reaction forces
Flare / relief tool | Excel / Word | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | PROC-T130 Set design pressures and temperatures | PSV set pressures
Flare / relief tool | Excel / Word | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | PROC-T235 Define trips, interlocks and process input to SIF | PSV set pressures
Flare / relief tool | Excel / Word | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | PROC-T255 Review vendor relief valve sizing | relief cases and required capacities to check against
Flare / relief tool | Excel / Word | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | SAFE-T240 Perform noise study | PSV and flare noise source rates
Flare / relief tool | Excel / Word | PROC-I261 | Depressuring study results | PROC-T260 Run flare and blowdown hydraulics | SAFE-T120 Perform quantitative risk assessment | depressuring time to target pressure
Flare / relief tool | SI | PROC-I250 | Relief load summary | PROC-T250 Calculate relief loads and size relief valves | INST-T100 Specify relief valves from the process sizing | governing case, relieving rate, set and back pressure, fluid MW/T/Z/k, required area and orifice letter (copied by hand)
Flare / relief tool | SI | PROC-I260 | Flare network hydraulic results | PROC-T260 Run flare and blowdown hydraulics | INST-T100 Specify relief valves from the process sizing | built-up back pressure at each device
Flare / relief tool | SI | PROC-I261 | Depressuring study results | PROC-T260 Run flare and blowdown hydraulics | INST-T080 Size on/off and emergency shutdown valves and actuators | final element action, fail position, required closure time; blowdown restriction orifice size and depressuring time targets
HTRI | Excel / Word | MECH-I090 | Shell-and-tube exchanger thermal design | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | shell diameter, tube length, bundle pull length
HTRI | Excel / Word | MECH-I090 | Shell-and-tube exchanger thermal design | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | PROC-T160 Prepare equipment list process data | final area, pressure drop and configuration from the HTRI design
HTRI | Excel / Word | MECH-I100 | Air-cooled exchanger thermal design | MECH-T080 Perform air-cooled exchanger thermal design | CIVL-T080 Size pipe racks and process structures conceptually | air cooler bays, plot area and fans to place on rack
HTRI | Excel / Word | MECH-I100 | Air-cooled exchanger thermal design | MECH-T080 Perform air-cooled exchanger thermal design | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | bay dimensions and plot area
HTRI | Excel / Word | MECH-I100 | Air-cooled exchanger thermal design | MECH-T080 Perform air-cooled exchanger thermal design | PROC-T160 Prepare equipment list process data | final area, pressure drop and configuration from the HTRI design
HYSYS | Excel / Word | PROC-I030 | Screening case results | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | ELEC-T020 Prepare preliminary electrical load estimate | power demand per screening option
HYSYS | Excel / Word | PROC-I030 | Screening case results | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | MECH-T010 Prepare mechanical input to FEL 1 equipment list and configuration screening | major heater/exchanger duties, column count and power demand per option
HYSYS | Excel / Word | PROC-I030 | Screening case results | PROC-T030 Run screening simulations and prepare BFDs and screening equipment list | SAFE-T015 Screen configuration options for inherent safety and environmental impact | per option fuel, power demand and CO2 estimate
HYSYS | Excel / Word | PROC-I060 | Alternative case balances | PROC-T060 Develop and simulate FEL2 alternatives | PROC-T070 Evaluate technology and licensor process offers | alternative case balances for normalising licensor yields and utilities
HYSYS | Excel / Word | PROC-I060 | Alternative case balances | PROC-T060 Develop and simulate FEL2 alternatives | PROC-T090 Define utility and offsite basis | utility demand per alternative
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | INST-T160 Specify analyzers and analyzer shelters | stream composition, P and T at sample points for sample conditioning
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T120 Prepare process flow diagrams | stream numbers, flows, P and T for stream table
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T130 Set design pressures and temperatures | max/min operating P and T per case
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T150 Define rotating equipment process duties | flow, density, viscosity, vapour pressure
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T175 Prepare heat transfer equipment process datasheets | heater duty, coil conditions and fuel composition
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T190 Size lines and run hydraulics | flow, density, viscosity, phase per line
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T220 Prepare instrument process data | fluid properties at instrument location
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T270 Prepare utility, chemical and catalyst consumption lists and balances | stream duties; flows at dosing points
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T280 Prepare process input to environmental and safety studies | effluent and vent stream flows and compositions; composition, P, T
HYSYS | Excel / Word | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | SAFE-T035 Compile hazardous materials inventory and properties | stream composition, phase, P, T, H2S and benzene content
HYSYS | Excel / Word | PROC-I155 | Preliminary exchanger sizing | PROC-T155 Estimate exchanger duties and preliminary areas | PROC-T160 Prepare equipment list process data | exchanger area and duty
HYSYS | Excel / Word | PROC-I155 | Preliminary exchanger sizing | PROC-T155 Estimate exchanger duties and preliminary areas | PROC-T175 Prepare heat transfer equipment process datasheets | HTRI thermal results per exchanger and air cooler
HYSYS | HTRI | PROC-I155 | Preliminary exchanger sizing | PROC-T155 Estimate exchanger duties and preliminary areas | MECH-T070 Perform shell-and-tube exchanger thermal and hydraulic design | process preliminary sizing as the starting point: duty, area, allowable pressure drop, fouling
HYSYS | HTRI | PROC-I155 | Preliminary exchanger sizing | PROC-T155 Estimate exchanger duties and preliminary areas | MECH-T080 Perform air-cooled exchanger thermal design | process preliminary air cooler duty and area as the starting point
HYSYS | SI | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | INST-T060 Enter instrument process data | per stream and case: flow, P, T, density, viscosity, MW, Cp/Cv, Z, vapour fraction (HYSYS not linked to SI: copied by hand)
HYSYS | SPID | PROC-I110 | Stream data | PROC-T110 Prepare heat and material balance | PROC-T210 Prepare line list and tie-in process data | flow, phase and operating P/T per line
HYSYS | SPID | PROC-I315 | As-designed H&MB (vendor reconciled) | PROC-T315 Reconcile simulation with certified vendor data | PROC-T340 Update P&IDs to IFD and IFC | reconciled H&MB values
Jovix | Document Locator | SCM-I270 | Material receipt record | SCM-T200 Receive materials at site in Jovix | CONS-T280 Compile construction quality dossier | receiving records with heat numbers and MTR references
Jovix | Excel / Word | SCM-I270 | Material receipt record | SCM-T200 Receive materials at site in Jovix | CONS-T220 Track welds and NDE | heat numbers and MTR reference per received item
Jovix | Excel / Word | SCM-I310 | Material issue record | SCM-T240 Issue materials to construction | VEND-T130 Fabricate pipe spools | free-issue material issued with heat numbers
Jovix | Excel / Word | SCM-I330 | Material reconciliation and surplus report | SCM-T250 Reconcile materials and dispose of surplus | ELEC-T370 Prepare electrical MTO and bulk requisitions | surplus and reconciliation by commodity
Jovix | Procore | SCM-I300 | Material availability status | SCM-T230 Report material availability to AWP | PIPE-T420 Respond to piping RFIs and field changes | material availability per IWP
Jovix | Procore | SCM-I320 | Material shortage report | SCM-T230 Report material availability to AWP | PIPE-T420 Respond to piping RFIs and field changes | material shortages per IWP
Mechanical calc tool | CAESAR II | VEND-I090 | Vendor design calculations | VEND-T060 Prepare vendor design calculations | PIPE-T220 Perform detailed stress analysis in CAESAR II | vendor allowable nozzle loads
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | CIVL-T150 Design static equipment foundations | skirt/saddle design, wind and seismic moments, hydrotest weights
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T110 Specify column and vessel internals | shell ID and support ring elevations
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T130 Prepare mechanical datasheets for vessels and columns | thicknesses, MAWP and weights
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T190 Prepare nozzle orientations and allowable nozzle loads | shell thickness and nozzle reinforcement basis for allowable loads
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T200 Prepare equipment outline drawings, footprints and maintenance envelopes | vessel dimensions and support type
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T210 Compile equipment weights and foundation loads | empty/operating/test weights, wind and seismic moments
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | MECH-T220 Prepare equipment lifting data | calculated empty and dressed weights
Mechanical calc tool | Excel / Word | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | PIPE-T390 Define hydrotest and test pack boundaries | equipment hydrotest pressure and MAWP
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | CIVL-T120 Design tank dikes and containment | tank diameters, heights and capacities
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | CIVL-T170 Design tank foundations | tank diameter, height, roof type and annular plate
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | FIRE-T190 Calculate fire water demand | tank diameter and roof type
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | FIRE-T220 Specify fixed fire protection systems | tank roof type, rim seal and diameter
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | MECH-T250 Prepare requisition technical packages for bid | tank datasheets
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | SAFE-T060 Develop emissions inventory | tank roof type, seals, size
Mechanical calc tool | Excel / Word | MECH-I150 | Storage tank datasheets and calculations | MECH-T120 Design storage tanks | SAFE-T080 Prepare water, stormwater and spill permit data | tank capacities
Mechanical calc tool | Excel / Word | VEND-I090 | Vendor design calculations | VEND-T060 Prepare vendor design calculations | VEND-T110 Procure raw materials and issue MTRs | design thicknesses and materials
Mechanical calc tool | Flare / relief tool | MECH-I130 | Vessel and column mechanical design calculations | MECH-T100 Perform vessel and column mechanical design calculations | PROC-T260 Run flare and blowdown hydraulics | empty weights/metal masses
P6 | Document Locator | PROJ-I030 | WBS, area codes and cost codes | PROJ-T030 Set up the WBS, cost codes and P6 project structure | PROJ-T040 Set up document numbering and the Document Locator project | area and unit codes used in document numbers
P6 | Excel / Word | COMM-I050 | Commissioning sequence and required turnover dates | COMM-T040 Set commissioning sequence and required subsystem turnover dates | COMM-T110 Define vendor commissioning support requirements | commissioning sequence by subsystem
P6 | Excel / Word | CONS-I090 | CWP material required-on-site dates | CONS-T070 Define CWPs, boundaries and sequence | VEND-T130 Fabricate pipe spools | ROS dates for spools by CWP
P6 | Excel / Word | OWNR-I160 | Tie-in and outage windows | OWNR-T140 Provide tie-in and outage windows | PIPE-T380 Identify tie-ins and issue tie-in packages | outage windows and tie-ins allowed per window
P6 | Excel / Word | PROJ-I030 | WBS, area codes and cost codes | PROJ-T030 Set up the WBS, cost codes and P6 project structure | CONS-T100 Prepare construction execution plan and estimate input | WBS, area and cost codes
P6 | Excel / Word | PROJ-I030 | WBS, area codes and cost codes | PROJ-T030 Set up the WBS, cost codes and P6 project structure | PROJ-T070 Issue estimate quantity requests to disciplines | code of accounts and WBS for the quantity templates
P6 | Excel / Word | PROJ-I130 | Baseline integrated schedule | PROJ-T110 Build and baseline the integrated schedule in P6 | CONS-T030 Evaluate modularisation and prefabrication strategy | schedule targets and milestones
P6 | Excel / Word | PROJ-I130 | Baseline integrated schedule | PROJ-T110 Build and baseline the integrated schedule in P6 | PROJ-T180 Maintain the risk register and contingency analysis | schedule logic for schedule risk analysis
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | CIVL-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | ELEC-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | INST-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | MECH-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | PIPE-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I140 | Deliverable schedule dates | PROJ-T110 Build and baseline the integrated schedule in P6 | PROC-T005 Plan, measure and report discipline deliverables | planned IFR/IFD/IFC dates per deliverable
P6 | Excel / Word | PROJ-I150 | Required-on-site and need dates per MR | PROJ-T110 Build and baseline the integrated schedule in P6 | SCM-T010 Prepare the procurement plan and long-lead list | ROS and MR/PO need dates
P6 | Excel / Word | PROJ-I180 | Schedule update and critical path report | PROJ-T140 Update the schedule and analyse the critical path | PROJ-T240 Prepare monthly progress reports | schedule status and critical path
P6 | Excel / Word | PROJ-I340 | Construction progress in P6 | PROJ-T250 Load construction progress into P6 | PROJ-T150 Track cost and forecast at completion | installed progress for cost forecast
P6 | Excel / Word | PROJ-I340 | Construction progress in P6 | PROJ-T250 Load construction progress into P6 | PROJ-T240 Prepare monthly progress reports | construction progress for the monthly report
P6 | Purchasing DB | CONS-I140 | Construction schedule by CWP | CONS-T110 Develop construction schedule by CWP | SCM-T260 Call off vendor site services | installation dates by CWP/IWP needing vendor supervision
P6 | Purchasing DB | PROJ-I030 | WBS, area codes and cost codes | PROJ-T030 Set up the WBS, cost codes and P6 project structure | SCM-T100 Award the purchase order in the Purchasing DB | cost codes and WBS per PO line
P6 | Purchasing DB | PROJ-I150 | Required-on-site and need dates per MR | PROJ-T110 Build and baseline the integrated schedule in P6 | SCM-T030 Register material requisitions in the Purchasing DB | ROS and MR need date per MR
P6 | Purchasing DB | PROJ-I150 | Required-on-site and need dates per MR | PROJ-T110 Build and baseline the integrated schedule in P6 | SCM-T140 Expedite manufacturing and forecast deliveries | ROS per MR and tag to check against forecast
P6 | S3D | CONS-I090 | CWP material required-on-site dates | CONS-T070 Define CWPs, boundaries and sequence | PIPE-T340 Produce MTO by ident and bulk requisitions | ROS dates by CWP for delivery split
P6 | Tekla | CONS-I090 | CWP material required-on-site dates | CONS-T070 Define CWPs, boundaries and sequence | VEND-T140 Detail and fabricate structural steel | ROS dates for steel by CWP
P6 | iConstruct | COMM-I050 | Commissioning sequence and required turnover dates | COMM-T040 Set commissioning sequence and required subsystem turnover dates | CONS-T160 Manage IWP constraints and release IWPs | subsystem turnover dates
P6 | iConstruct | CONS-I050 | Path of construction | CONS-T050 Define path of construction | CONS-T060 Define construction work areas (CWAs) | area sequence
PHA tool | Document Locator | SAFE-I150 | HAZOP worksheets and report | SAFE-T150 Facilitate formal HAZOP | SAFE-T290 Compile process safety information for PSM | HAZOP report
PHA tool | Document Locator | SAFE-I160 | LOPA scenarios and SIL targets | SAFE-T160 Run LOPA and set SIL targets | SAFE-T290 Compile process safety information for PSM | LOPA
PHA tool | Document Locator | SAFE-I170 | Action close-out records | SAFE-T170 Track and close out PHA and study actions | SAFE-T290 Compile process safety information for PSM | close-out records
PHA tool | Excel / Word | INST-I210 | SIF list with initiators and final elements | INST-T210 Define SIFs and input to SIL determination | INST-T220 Write safety requirements specification | SIF initiators, logic and final elements
PHA tool | Excel / Word | INST-I210 | SIF list with initiators and final elements | INST-T210 Define SIFs and input to SIL determination | INST-T240 Prepare cause and effect charts | SIF references for C&E lines
PHA tool | Excel / Word | SAFE-I022 | HAZID actions list | SAFE-T020 Facilitate concept HAZID and ENVID | SAFE-T040 Prepare SHE design basis and risk criteria | HAZID actions affecting design basis
PHA tool | Excel / Word | SAFE-I152 | HAZOP recommendations register | SAFE-T150 Facilitate formal HAZOP | PROC-T235 Define trips, interlocks and process input to SIF | HAZOP recommendations for new trips/interlocks
PHA tool | Excel / Word | SAFE-I152 | HAZOP recommendations register | SAFE-T150 Facilitate formal HAZOP | SAFE-T140 Review relief and depressuring scenarios | overpressure HAZOP recommendations
PHA tool | Excel / Word | SAFE-I160 | LOPA scenarios and SIL targets | SAFE-T160 Run LOPA and set SIL targets | PROC-T235 Define trips, interlocks and process input to SIF | SIF requirements and target SIL per scenario
PHA tool | Excel / Word | SAFE-I160 | LOPA scenarios and SIL targets | SAFE-T160 Run LOPA and set SIL targets | SAFE-T260 Review cause and effect and SIL verification | SIL targets
PHA tool | Excel / Word | SAFE-I160 | LOPA scenarios and SIL targets | SAFE-T160 Run LOPA and set SIL targets | VEND-T070 Prepare package P&IDs, I/O and control narrative | SIF tags, SIL and safe state affecting the package
PHA tool | P6 | SAFE-I170 | Action close-out records | SAFE-T170 Track and close out PHA and study actions | PROJ-T130 Measure engineering progress | action close-out status and closure dates for safety progress
PHA tool | SPID | SAFE-I152 | HAZOP recommendations register | SAFE-T150 Facilitate formal HAZOP | MECH-T180 Provide mechanical input to P&IDs and HAZOP | HAZOP recommendations assigned to mechanical
PHA tool | SPID | SAFE-I162 | Non-SIF IPL and safeguard requirements | SAFE-T160 Run LOPA and set SIL targets | MECH-T180 Provide mechanical input to P&IDs and HAZOP | mechanical IPLs (check valves, PSVs) requiring independence and testing
PHA tool | SPID | SAFE-I280 | Package and revalidation HAZOP actions | SAFE-T280 Facilitate vendor package and design change HAZOPs | PROC-T340 Update P&IDs to IFD and IFC | package and revalidation HAZOP actions affecting P&IDs
PHA tool | Smart Completions | SAFE-I170 | Action close-out records | SAFE-T170 Track and close out PHA and study actions | SAFE-T340 Lead pre-startup safety review (PSSR) | open actions
Procore | Excel / Word | COMM-I240 | Commissioning technical query | COMM-T210 Raise commissioning technical queries | PROC-T375 Support commissioning, start-up and performance test | commissioning technical queries
Procore | Excel / Word | CONS-I210 | Request for information (RFI) | CONS-T170 Raise and manage RFIs | PROJ-T160 Run change control: trends and change notices | RFIs that lead to change
Procore | Excel / Word | CONS-I220 | Field change request | CONS-T180 Raise field change requests | PROJ-T160 Run change control: trends and change notices | proposed field change, reason, affected drawings
Procore | Excel / Word | CONS-I230 | Field change cost and schedule impact | CONS-T180 Raise field change requests | PROJ-T160 Run change control: trends and change notices | hours, material and schedule impact per field change
Procore | Excel / Word | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | MECH-T440 Issue as-built equipment data for handover | field deviations affecting equipment
Procore | Excel / Word | SAFE-I330 | MOC safety review decisions | SAFE-T330 Perform MOC safety reviews of field and design changes | SAFE-T360 Update safety studies to as-built and hand over | MOC decisions
Procore | S3D | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | PIPE-T440 Prepare as-built isometrics and model | redlined isometrics and layout drawings
Procore | SI | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | INST-T440 Prepare as-built I&C database and drawings | redlines on loop, wiring, location and hook-up drawings
Procore | SPEL | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | ELEC-T440 Produce as-built electrical records | redlined cable routes, terminations, layouts
Procore | SPID | COMM-I240 | Commissioning technical query | COMM-T210 Raise commissioning technical queries | PROC-T385 Incorporate as-built redlines into P&IDs | commissioning modifications
Procore | SPID | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | PROC-T385 Incorporate as-built redlines into P&IDs | as-built redline P&IDs
Procore | Smart Completions | SAFE-I330 | MOC safety review decisions | SAFE-T330 Perform MOC safety reviews of field and design changes | SAFE-T340 Lead pre-startup safety review (PSSR) | MOC decisions
Procore | Tekla | CIVL-I360 | Civil RFI responses and field change dispositions | CIVL-T360 Answer RFIs and disposition field changes and NCRs | CIVL-T380 Incorporate as-built civil and structural changes | approved RFI and field change revisions
Procore | Tekla | CIVL-I365 | Civil non-conformance dispositions | CIVL-T360 Answer RFIs and disposition field changes and NCRs | CIVL-T380 Incorporate as-built civil and structural changes | non-conformance repairs affecting as-built
Procore | Tekla | CONS-I330 | As-built redline markups | CONS-T260 Prepare as-built redlines | CIVL-T380 Incorporate as-built civil and structural changes | redlined foundation, underground and layout drawings
Purchasing DB | Document Locator | SCM-I350 | Spares purchase order and register | SCM-T270 Procure commissioning and operating spares | PROJ-T260 Compile the final records and close out | spares ordered and handed over
Purchasing DB | Document Locator | SCM-I360 | PO close-out record | SCM-T280 Close out purchase orders | PROJ-T260 Compile the final records and close out | PO close-out status
Purchasing DB | Excel / Word | PIPE-I430 | Piping bulk material requisitions | PIPE-T340 Produce MTO by ident and bulk requisitions | PIPE-T350 Evaluate piping bids | requisition technical requirements
Purchasing DB | Excel / Word | SCM-I030 | Bidders list | SCM-T020 Prepare bidders lists and prequalify vendors | FIRE-T230 Prepare fire pump and fire protection equipment datasheets and requisitions | bidders for fire protection equipment
Purchasing DB | Excel / Word | SCM-I030 | Bidders list | SCM-T020 Prepare bidders lists and prequalify vendors | PIPE-T240 Specify and requisition spring and engineered supports | approved bidders for spring supports
Purchasing DB | Excel / Word | SCM-I050 | MR register entry | SCM-T030 Register material requisitions in the Purchasing DB | PIPE-T240 Specify and requisition spring and engineered supports | MR number and need date
Purchasing DB | Excel / Word | SCM-I050 | MR register entry | SCM-T030 Register material requisitions in the Purchasing DB | PROJ-T240 Prepare monthly progress reports | MRs issued and status
Purchasing DB | Excel / Word | SCM-I060 | Bulk material MR lines | SCM-T040 Load piping bulk MTO into the Purchasing DB | ELEC-T370 Prepare electrical MTO and bulk requisitions | commodity codes and bulk MR lines
Purchasing DB | Excel / Word | SCM-I130 | PO header data | SCM-T100 Award the purchase order in the Purchasing DB | MECH-T060 Maintain mechanical equipment list | PO number, vendor, award date
Purchasing DB | Excel / Word | SCM-I130 | PO header data | SCM-T100 Award the purchase order in the Purchasing DB | OWNR-T240 Pay invoices and report actual cost | PO number, value and payment terms
Purchasing DB | Excel / Word | SCM-I130 | PO header data | SCM-T100 Award the purchase order in the Purchasing DB | PROJ-T240 Prepare monthly progress reports | POs placed and values
Purchasing DB | Excel / Word | SCM-I140 | PO line items | SCM-T100 Award the purchase order in the Purchasing DB | MECH-T060 Maintain mechanical equipment list | tag-to-PO line mapping
Purchasing DB | Excel / Word | SCM-I150 | PO amendment | SCM-T110 Process PO amendments | PROJ-T160 Run change control: trends and change notices | PO amendment price and delivery changes
Purchasing DB | Excel / Word | SCM-I170 | Vendor print status report | SCM-T130 Expedite vendor documents and route them for review | PROJ-T220 Maintain the hold list | overdue vendor documents and days late
Purchasing DB | Excel / Word | SCM-I200 | Expediting forecast | SCM-T140 Expedite manufacturing and forecast deliveries | PROJ-T240 Prepare monthly progress reports | expediting exceptions
Purchasing DB | Excel / Word | SCM-I340 | Vendor site service request | SCM-T260 Call off vendor site services | VEND-T210 Provide site services | service type, dates and location
Purchasing DB | P6 | SCM-I130 | PO header data | SCM-T100 Award the purchase order in the Purchasing DB | PROJ-T120 Integrate procurement and vendor dates into the schedule | PO number, vendor and award date
Purchasing DB | P6 | SCM-I140 | PO line items | SCM-T100 Award the purchase order in the Purchasing DB | PROJ-T120 Integrate procurement and vendor dates into the schedule | contract delivery date per PO line
Purchasing DB | P6 | SCM-I170 | Vendor print status report | SCM-T130 Expedite vendor documents and route them for review | PROJ-T120 Integrate procurement and vendor dates into the schedule | due, received and returned dates per vendor document
Purchasing DB | P6 | SCM-I200 | Expediting forecast | SCM-T140 Expedite manufacturing and forecast deliveries | CONS-T110 Develop construction schedule by CWP | forecast site delivery dates by PO line
Purchasing DB | P6 | SCM-I200 | Expediting forecast | SCM-T140 Expedite manufacturing and forecast deliveries | PROJ-T120 Integrate procurement and vendor dates into the schedule | forecast ex-works and site delivery dates per PO line, exceptions
Purchasing DB | iConstruct | SCM-I200 | Expediting forecast | SCM-T140 Expedite manufacturing and forecast deliveries | CONS-T150 Check IWP material availability against Jovix | forecast site delivery for outstanding PO lines
S3D | Excel / Word | INST-I290 | Instrument location plans | INST-T290 Prepare instrument location plans and JB locations | CIVL-T250 Coordinate embedments, sleeves and penetrations | instrument and JB locations needing conduit stub-ups
S3D | Excel / Word | PIPE-I040 | Plot plan | PIPE-T040 Develop plot plan and equipment layout | CIVL-T060 Prepare civil and structural quantities for estimates | equipment, rack, road and building areas for take-off
S3D | Excel / Word | PIPE-I040 | Plot plan | PIPE-T040 Develop plot plan and equipment layout | CIVL-T100 Prepare grading plan and finished elevations | equipment, paving and road layout
S3D | Excel / Word | PIPE-I040 | Plot plan | PIPE-T040 Develop plot plan and equipment layout | ELEC-T050 Prepare electrical cost estimate inputs | area dimensions and rack corridors for cable and tray lengths
S3D | Excel / Word | PIPE-I040 | Plot plan | PIPE-T040 Develop plot plan and equipment layout | FIRE-T190 Calculate fire water demand | fire zones, dikes and equipment positions
S3D | Excel / Word | PIPE-I040 | Plot plan | PIPE-T040 Develop plot plan and equipment layout | SAFE-T070 Prepare air permit application | building and stack locations for downwash
S3D | Excel / Word | PIPE-I060 | 3D layout model | PIPE-T050 Build 3D layout model | CIVL-T080 Size pipe racks and process structures conceptually | structure placeholders and platform levels in the layout model
S3D | Excel / Word | PIPE-I070 | Pipe rack layout and widths | PIPE-T060 Lay out pipe racks and assign tiers | CIVL-T060 Prepare civil and structural quantities for estimates | rack routes, widths, bay spacing and tiers for steel and foundation quantities
S3D | Excel / Word | PIPE-I070 | Pipe rack layout and widths | PIPE-T060 Lay out pipe racks and assign tiers | CIVL-T080 Size pipe racks and process structures conceptually | rack routes, widths, bay spacing, tier elevations, line allocation and future space
S3D | Excel / Word | PIPE-I400 | IFC isometrics | PIPE-T320 Extract and check isometrics | CONS-T220 Track welds and NDE | weld numbers and shop/field welds per iso
S3D | Excel / Word | PIPE-I400 | IFC isometrics | PIPE-T320 Extract and check isometrics | CONS-T230 Prepare and execute pressure test packs | IFC isos for marking test limits
S3D | Excel / Word | PIPE-I400 | IFC isometrics | PIPE-T320 Extract and check isometrics | PIPE-T390 Define hydrotest and test pack boundaries | isometrics for circuit definition
S3D | Procore | PIPE-I540 | Field change isometrics | PIPE-T420 Respond to piping RFIs and field changes | CONS-T180 Raise field change requests | revised field-change isometrics
S3D | Purchasing DB | PIPE-I120 | S3D piping spec and commodity catalogue | PIPE-T100 Build S3D piping specification catalogue | SCM-T040 Load piping bulk MTO into the Purchasing DB | short codes and commodity codes (idents)
S3D | SI | ELEC-I070 | Hazardous area classification drawings | ELEC-T070 Prepare hazardous area classification drawings | INST-T110 Prepare instrument datasheets | Class/Division or Zone, gas group, T-code at instrument location
S3D | SI | ELEC-I070 | Hazardous area classification drawings | ELEC-T070 Prepare hazardous area classification drawings | INST-T200 Specify fire and gas system and device list | Class/Division or Zone, gas group, T-code for detector Ex rating
S3D | SI | ELEC-I330 | Cable tray routing model | ELEC-T330 Route raceway, cable tray and duct banks in S3D | INST-T320 Prepare instrument cable schedule and tray loading | tray and trench route segments and segregation
S3D | SI | INST-I291 | Junction box locations and sizes | INST-T290 Prepare instrument location plans and JB locations | INST-T310 Design instrument wiring, marshalling and terminations | JB tags and sizes
S3D | SI | PIPE-I180 | Routed piping model | PIPE-T160 Route piping in the 3D model | INST-T070 Size control valves | line size and piping class at the valve; reducer arrangement as routed
S3D | SPEL | ELEC-I330 | Cable tray routing model | ELEC-T330 Route raceway, cable tray and duct banks in S3D | ELEC-T320 Size cables and build cable schedule in SPEL | route lengths per raceway segment
S3D | iConstruct | PIPE-I300 | Pipe support model and special support drawings | PIPE-T250 Design pipe supports | CONS-T140 Develop installation work packages (IWPs) | support tags and special support details
S3D | iConstruct | PIPE-I400 | IFC isometrics | PIPE-T320 Extract and check isometrics | CONS-T140 Develop installation work packages (IWPs) | IFC isos with BOM, welds, supports
SI | Document Locator | INST-I145 | Agreed final relief valve sizing for purchase | INST-T145 Align final relief valve sizing with Process and vendor | INST-T150 Review instrument vendor data | agreed sizing to check certified relief valve data against
SI | Excel / Word | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | INST-T250 Rationalize alarms and build master alarm database | tag list for the alarm database
SI | Excel / Word | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | INST-T280 Compile instrument utility loads | instrument consumers by type and location
SI | Excel / Word | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | INST-T300 Prepare hook-up drawings and assign typicals | tag list and instrument types
SI | Excel / Word | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | PIPE-T390 Define hydrotest and test pack boundaries | in-line instrument types to remove or isolate
SI | Excel / Word | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | PROC-T220 Prepare instrument process data | tag, type, service, loop and line/equipment number
SI | Excel / Word | INST-I060 | Instrument process data in SI | INST-T060 Enter instrument process data | PROC-T220 Prepare instrument process data | SI process data fields to be filled per tag
SI | Excel / Word | INST-I060 | Instrument process data in SI | INST-T060 Enter instrument process data | PROC-T320 Respond to technical queries, holds and change requests | instrument process data queries and set points
SI | Excel / Word | INST-I070 | Control valve sizing calculations | INST-T070 Size control valves | SAFE-T240 Perform noise study | control valve noise dB(A)
SI | Excel / Word | INST-I080 | On/off and ESD valve sizing and actuator data | INST-T080 Size on/off and emergency shutdown valves and actuators | FIRE-T200 Define fire scenario envelopes and fireproofing zones | ESD valve fire-proofing need and locations
SI | Excel / Word | INST-I080 | On/off and ESD valve sizing and actuator data | INST-T080 Size on/off and emergency shutdown valves and actuators | PIPE-T110 Prepare valve specifications and datasheets | actuated on/off valve type, size, rating, shut-off class and fire-proofing
SI | Excel / Word | INST-I080 | On/off and ESD valve sizing and actuator data | INST-T080 Size on/off and emergency shutdown valves and actuators | SAFE-T120 Perform quantitative risk assessment | ESD valve stroke time and failure position
SI | Excel / Word | INST-I110 | Instrument datasheets for requisition | INST-T110 Prepare instrument datasheets | INST-T300 Prepare hook-up drawings and assign typicals | process connection and mounting per tag
SI | Excel / Word | INST-I110 | Instrument datasheets for requisition | INST-T110 Prepare instrument datasheets | MECH-T250 Prepare requisition technical packages for bid | instrument datasheets for vendor-supplied instruments
SI | Excel / Word | INST-I145 | Agreed final relief valve sizing for purchase | INST-T145 Align final relief valve sizing with Process and vendor | SCM-T090 Prepare the bid tabulation and award recommendation | agreed relief valve sizing before award
SI | Excel / Word | INST-I261 | I/O counts and typicals for system vendors | INST-T260 Develop I/O list and assign I/O | INST-T030 Develop ICS architecture and control/rack room requirements | I/O counts per system for cabinet counts
SI | Excel / Word | INST-I261 | I/O counts and typicals for system vendors | INST-T260 Develop I/O list and assign I/O | INST-T180 Prepare DCS specification | I/O counts per type for DCS sizing
SI | Excel / Word | INST-I261 | I/O counts and typicals for system vendors | INST-T260 Develop I/O list and assign I/O | INST-T190 Prepare SIS specification | SIS I/O counts
SI | Flare / relief tool | INST-I145 | Agreed final relief valve sizing for purchase | INST-T145 Align final relief valve sizing with Process and vendor | PROC-T260 Run flare and blowdown hydraulics | rated capacities and outlet sizes for flare back-pressure checks
SI | P6 | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | CONS-T070 Define CWPs, boundaries and sequence | instrument count by type and area (via P&ID/unit)
SI | S3D | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | PIPE-T180 Position in-line instruments and instrument access | tag, type, line number and P&ID
SI | S3D | INST-I072 | Preliminary in-line valve dimensions and weights | INST-T070 Size control valves | PIPE-T160 Route piping in the 3D model | control and on/off valve face-to-face, weights and actuator envelopes
SI | S3D | INST-I091 | Flow element sizes and straight-run requirements | INST-T090 Calculate flow elements and thermowells | PIPE-T160 Route piping in the 3D model | flow element sizes and upstream/downstream straight runs
SI | S3D | INST-I091 | Flow element sizes and straight-run requirements | INST-T090 Calculate flow elements and thermowells | PIPE-T180 Position in-line instruments and instrument access | straight-run requirements
SI | S3D | INST-I145 | Agreed final relief valve sizing for purchase | INST-T145 Align final relief valve sizing with Process and vendor | PIPE-T160 Route piping in the 3D model | final PSV inlet and outlet sizes and ratings
SI | S3D | INST-I151 | Certified in-line instrument dimensions and weights | INST-T150 Review instrument vendor data | PIPE-T160 Route piping in the 3D model | certified face-to-face and weights for model update
SI | SPID | INST-I050 | Instrument index | INST-T050 Build and maintain the instrument index in SI | PROC-T340 Update P&IDs to IFD and IFC | instrument index
SI | SPID | INST-I071 | Control valve sizes and ratings for P&ID | INST-T070 Size control valves | PROC-T200 Develop P&IDs (process content) | control valve sizes, ratings and reducers
SI | Smart Completions | INST-I260 | I/O list | INST-T260 Develop I/O list and assign I/O | COMM-T170 Execute loop checks | I/O assignment
SI | Smart Completions | INST-I330 | Loop diagrams | INST-T330 Generate loop diagrams | COMM-T170 Execute loop checks | loop terminals, ranges, set points
SI | Smart Completions | INST-I380 | System configuration database | INST-T380 Prepare system configuration data for vendors | COMM-T170 Execute loop checks | ranges, units, alarm limits as configured
SI | iConstruct | INST-I310 | Wiring, marshalling and termination diagrams | INST-T310 Design instrument wiring, marshalling and terminations | CONS-T140 Develop installation work packages (IWPs) | termination diagrams
SI | iConstruct | INST-I320 | Instrument cable schedule | INST-T320 Prepare instrument cable schedule and tray loading | CONS-T140 Develop installation work packages (IWPs) | instrument cable from/to and lengths
SI | iConstruct | INST-I330 | Loop diagrams | INST-T330 Generate loop diagrams | CONS-T140 Develop installation work packages (IWPs) | loop diagrams
SPEL | ETAP | ELEC-I192 | Certified electrical equipment data | ELEC-T190 Review electrical vendor drawings and data | ELEC-T210 Build ETAP model and run load flow study | certified transformer %Z, X/R, losses and tap ranges
SPEL | ETAP | ELEC-I192 | Certified electrical equipment data | ELEC-T190 Review electrical vendor drawings and data | ELEC-T260 Perform arc flash study | enclosure type, gaps, electrode configuration
SPEL | ETAP | ELEC-I202 | Certified motor data | ELEC-T200 Review motor and package electrical data | ELEC-T220 Run short-circuit study | motor kW, LRC and X/R for motor contribution
SPEL | ETAP | ELEC-I202 | Certified motor data | ELEC-T200 Review motor and package electrical data | ELEC-T230 Run motor-starting study | LRC, inertia, speed-torque curves
SPEL | ETAP | ELEC-I202 | Certified motor data | ELEC-T200 Review motor and package electrical data | ELEC-T250 Perform protective relay coordination study | FLA, LRC, accelerating time, thermal limit curves
SPEL | Excel / Word | ELEC-I090 | Electrical load list | ELEC-T090 Develop electrical load list in SPEL | ELEC-T050 Prepare electrical cost estimate inputs | number and size of motors and loads by voltage
SPEL | Excel / Word | ELEC-I120 | Single-line diagrams | ELEC-T120 Develop one-line diagrams in SPEL | ELEC-T130 Specify MV switchgear | one-line configuration, feeders, protection and metering
SPEL | Excel / Word | ELEC-I120 | Single-line diagrams | ELEC-T120 Develop one-line diagrams in SPEL | ELEC-T140 Specify power transformers | one-line configuration, feeders, protection and metering
SPEL | Excel / Word | ELEC-I120 | Single-line diagrams | ELEC-T120 Develop one-line diagrams in SPEL | ELEC-T150 Specify LV switchgear, MCCs and E-houses | one-line configuration, feeders, protection and metering
SPEL | Excel / Word | ELEC-I120 | Single-line diagrams | ELEC-T120 Develop one-line diagrams in SPEL | ELEC-T160 Specify VFDs and harmonic mitigation | one-line configuration, feeders, protection and metering
SPEL | Excel / Word | ELEC-I120 | Single-line diagrams | ELEC-T120 Develop one-line diagrams in SPEL | ELEC-T170 Specify UPS, DC systems and emergency generator | one-line configuration, feeders, protection and metering
SPEL | Excel / Word | ELEC-I192 | Certified electrical equipment data | ELEC-T190 Review electrical vendor drawings and data | CIVL-T280 Design blast-resistant and other buildings structurally | certified switchgear and transformer weights
SPEL | SI | ELEC-I340 | MCC and switchgear interface signal list | ELEC-T340 Define MCC and switchgear interface signals with I&C | INST-T260 Develop I/O list and assign I/O | per motor: run/trip/start/stop/SIS trip signals, hardwired vs serial (SPEL not linked: keyed in by hand)
SPEL | SI | ELEC-I340 | MCC and switchgear interface signal list | ELEC-T340 Define MCC and switchgear interface signals with I&C | INST-T310 Design instrument wiring, marshalling and terminations | MCC interposing relay terminals and signal list (SPEL not linked)
SPEL | SI | ELEC-I350 | Control and interlock schematics | ELEC-T350 Prepare control and interlock schematics | INST-T310 Design instrument wiring, marshalling and terminations | MCC interposing relay terminals and signal list (SPEL not linked)
SPEL | iConstruct | ELEC-I320 | Cable schedule | ELEC-T320 Size cables and build cable schedule in SPEL | CONS-T140 Develop installation work packages (IWPs) | cables, from/to, route segments, length
SPEL | iConstruct | ELEC-I322 | Cable pull cards and terminations | ELEC-T320 Size cables and build cable schedule in SPEL | CONS-T140 Develop installation work packages (IWPs) | pull cards and terminations
SPID | Excel / Word | COMM-I030 | System boundary P&IDs | COMM-T030 Mark system and subsystem boundaries on P&IDs | COMM-T060 Build tag-to-subsystem register | subsystem limits on P&IDs
SPID | Excel / Word | COMM-I030 | System boundary P&IDs | COMM-T030 Mark system and subsystem boundaries on P&IDs | CONS-T230 Prepare and execute pressure test packs | subsystem limits on P&IDs
SPID | Excel / Word | COMM-I030 | System boundary P&IDs | COMM-T030 Mark system and subsystem boundaries on P&IDs | INST-T410 Prepare instrument tag register for completions | system/subsystem numbers and boundaries; tag-to-subsystem register format
SPID | Excel / Word | COMM-I030 | System boundary P&IDs | COMM-T030 Mark system and subsystem boundaries on P&IDs | OWNR-T180 Issue permits to work and isolations | isolation points on boundary P&IDs
SPID | Excel / Word | PROC-I200 | P&IDs issued for review | PROC-T200 Develop P&IDs (process content) | INST-T020 Prepare factored instrument count and I&C estimate input | equipment count, main control loops, streams needing analyzers; preliminary instrument counts from P&IDs where available
SPID | Excel / Word | PROC-I200 | P&IDs issued for review | PROC-T200 Develop P&IDs (process content) | MECH-T160 Prepare package specifications and scope split | package boundaries shown on IFR P&IDs
SPID | Excel / Word | PROC-I200 | P&IDs issued for review | PROC-T200 Develop P&IDs (process content) | PROC-T220 Prepare instrument process data | instrument tags and locations
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | ELEC-T300 Design electric heat tracing | lines requiring tracing, maintain temperature, design/steam-out temperature, fluid
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | INST-T300 Prepare hook-up drawings and assign typicals | service flags (steam, viscous, cryogenic) and sour/H2S, hydrogen content needing special hook-ups
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T090 Develop piping material classes | fluid code and design P/T per line group
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T120 Prepare specialty item list and datasheets | flow, operating/design P/T and fluid per SP item line
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T140 Add piping data to the line list | line number, fluid, operating/design P/T, test pressure basis, insulation and tracing requirement
SPID | Excel / Word | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T200 Prepare stress-critical line list | operating and design temperature per line
SPID | Excel / Word | PROC-I340 | P&IDs issued for design | PROC-T340 Update P&IDs to IFD and IFC | CIVL-T110 Design surface drainage and sewers | drain connections to oily water and closed drain systems on IFD P&IDs
SPID | Excel / Word | PROC-I341 | P&IDs issued for construction | PROC-T340 Update P&IDs to IFD and IFC | CONS-T230 Prepare and execute pressure test packs | IFC P&IDs for marking test boundaries
SPID | S3D | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T060 Lay out pipe racks and assign tiers | line number, from/to, fluid, design P/T and insulation for rack lines
SPID | S3D | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T150 Prepare FEL3 piping MTO for the estimate | line count per P&ID and fluid
SPID | S3D | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | PIPE-T160 Route piping in the 3D model | design P/T, fluid, insulation and critical-line flags
SPID | SI | PROC-I200 | P&IDs issued for review | PROC-T200 Develop P&IDs (process content) | INST-T050 Build and maintain the instrument index in SI | instrument tags, loop numbers, service, line/equipment, P&ID number; re-created by hand in SI (SPID and SI not linked)
SPID | SI | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | INST-T050 Build and maintain the instrument index in SI | line number, from/to and service for instrument line reference
SPID | SI | PROC-I210 | Line process data | PROC-T210 Prepare line list and tie-in process data | INST-T060 Enter instrument process data | per line: fluid code, phase, operating/design P/T
SPID | SI | PROC-I340 | P&IDs issued for design | PROC-T340 Update P&IDs to IFD and IFC | INST-T050 Build and maintain the instrument index in SI | instrument tags, loop numbers, service, line/equipment, P&ID number; re-created by hand in SI (SPID and SI not linked)
SPID | SPEL | PROC-I340 | P&IDs issued for design | PROC-T340 Update P&IDs to IFD and IFC | ELEC-T090 Develop electrical load list in SPEL | running vs spare equipment and motor tags on IFD P&IDs
Smart Completions | Excel / Word | COMM-I150 | Punch list | COMM-T140 Raise and manage punch lists | PROC-T375 Support commissioning, start-up and performance test | process punch items
Smart Completions | Excel / Word | COMM-I270 | Completions progress report | COMM-T240 Report completions progress | PROJ-T240 Prepare monthly progress reports | ITR, punch and certificate progress
Smart Completions | Excel / Word | PIPE-I500 | Test pack register | PIPE-T390 Define hydrotest and test pack boundaries | CONS-T230 Prepare and execute pressure test packs | test pack number, lines and isos included
Smart Completions | P6 | COMM-I270 | Completions progress report | COMM-T240 Report completions progress | PROJ-T140 Update the schedule and analyse the critical path | ITR, punch and certificate progress by system
Smart Completions | Procore | INST-I420 | I&C punch and loop check resolutions | INST-T420 Support loop checks and resolve I&C punch | COMM-T210 Raise commissioning technical queries | loop check and set point corrections
Smart Completions | S3D | COMM-I140 | Test pack status by subsystem | COMM-T130 Track test pack status by subsystem | PIPE-T440 Prepare as-built isometrics and model | test pack status
Smart Completions | S3D | COMM-I150 | Punch list | COMM-T140 Raise and manage punch lists | PIPE-T440 Prepare as-built isometrics and model | punch items affecting piping
Smart Completions | SPID | INST-I420 | I&C punch and loop check resolutions | INST-T420 Support loop checks and resolve I&C punch | PROC-T385 Incorporate as-built redlines into P&IDs | range/set point corrections
iConstruct | Excel / Word | CONS-I170 | Installation work package (IWP) | CONS-T140 Develop installation work packages (IWPs) | OWNR-T180 Issue permits to work and isolations | IWP scope, location and hazards
iConstruct | Excel / Word | CONS-I200 | Released IWP backlog | CONS-T160 Manage IWP constraints and release IWPs | OWNR-T180 Issue permits to work and isolations | planned IWP start dates
iConstruct | Excel / Word | CONS-I270 | Installed quantities and progress | CONS-T210 Track installed quantities and progress | PROJ-T240 Prepare monthly progress reports | construction installed quantities and percent complete
iConstruct | Jovix | CONS-I270 | Installed quantities and progress | CONS-T210 Track installed quantities and progress | SCM-T250 Reconcile materials and dispose of surplus | installed quantities by IWP/CWP
iConstruct | P6 | CONS-I060 | CWA boundaries | CONS-T060 Define construction work areas (CWAs) | CONS-T070 Define CWPs, boundaries and sequence | CWA IDs and boundaries
iConstruct | P6 | CONS-I190 | IWP constraint log | CONS-T160 Manage IWP constraints and release IWPs | PROJ-T140 Update the schedule and analyse the critical path | open IWP constraints driving the look-ahead
iConstruct | P6 | CONS-I270 | Installed quantities and progress | CONS-T210 Track installed quantities and progress | PROJ-T140 Update the schedule and analyse the critical path | installed quantities and percent complete by IWP/CWP
iConstruct | Purchasing DB | CONS-I190 | IWP constraint log | CONS-T160 Manage IWP constraints and release IWPs | SCM-T140 Expedite manufacturing and forecast deliveries | material constraints on IWPs to expedite

## Checks
Severity | Message